## Sheet1
Submission_Session | Submission_Session_Revision | Submitted_By | Department | Transmittal_Number | Project_Code | Facility_Code | Document_Type | Discipline | Document_Sequence_Number | Document_Revision | Document_ID | Submission_Date | Submission_Session_Subject | Review_Comments | Review_Return_Plan_Date | Review_Return_Actual_Date | Duration_of_Review | Review_Status | Resubmission_Required | Resubmission_Plan_Date | Submission_Closed | Resubmission_Overdue_Status | Delay_of_Resubmission | Resubmission_Forecast_Date | Notes | Document_Title | Consolidated_Submission_Session_Subject | First_Submission_Date | Latest_Submission_Date | Latest_Revision | All_Submission_Sessions | All_Submission_Dates | All_Submission_Session_Revisions | Count_of_Submissions | Review_Status_Code | Approval_Code | This_Submission_Approval_Code
000001 | 00 | Soe Myat | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 0 | 131242-WST00-PP-0001 | 2023-05-15 | Project Quality Plan | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-13 | 2023-12-05 | 122 | Approved with Comments | YES | 2023-12-26 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | AWC | AWC
000001 | 01 | Radha | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 1 | 131242-WST00-PP-0001 | 2024-05-13 | Project Quality Plan | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-03 | 2024-09-10 | 69 | Approved with Comments | YES | 2024-09-30 | NO | Overdue | 343 |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | AWC | AWC
000002 | 00 | Shena | PMT | NA | 131242 | WST00 | PP | PC | 0001 | 0 | 131242-WST00-PP-0001 | 2023-05-15 | Project Risk Management Plan | Rev 0: Approved with Comments. Refer to comment sheet and resubmit. | 2023-06-13 | 2023-06-14 | 1 | Approved with Comments | YES | 2023-07-05 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | AWC | AWC
000002 | 01 | Max/Edwin | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 1 | 131242-WSW41-PP-0001 | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-09-25 | 2023-09-13 |  | Approved with Comments | YES | 2023-10-03 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | #000002.0_ Reply_2023 08 31 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 08 31-NA-NA-NA | 2023-09-05 | Project Risk Management Plan | For Information | 2023-10-03 | 2023-09-13 |  | Approved with Comments | YES | 2023-10-03 | YES | Resubmitted |  |  |  | NA | "Project Risk Management Plan" | 2023-09-05 | 2023-09-05 | NA | 000000 | 2023-09-05 | 00 | 1 | PEN | AWC | AWC
000002 | 02 | Max | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 2 | 131242-WSW41-PP-0001 | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-20 | 2023-11-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025-NA-NA-NA | 2023-10-30 | Project Risk Management Plan | For Information | 2023-11-28 | 2023-11-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "Project Risk Management Plan" | 2023-10-30 | 2023-10-30 | NA | 000000 | 2023-10-30 | 00 | 1 | PEN | APP | APP
000003 | 00 | Heng Peng | BIM | NA | 131242 | WST00 | PP | IM | 0001 | 0 | 131242-WST00-PP-0001 | 2023-05-16 | BIM Execution Plan (BEP) | R0- Not Approved, please refer to comment sheet | 2023-06-14 | 2023-07-03 | 12 | Not Approved | YES | 2023-07-21 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | NAP | NAP
000003 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 1 | 131242-WSW41-PP-0001 | 2023-08-21 | BIM Execution Plan (BEP) | R1- Not Approved. Please refer to "Comment Sheet_Submittal-0003-1". | 2023-09-08 | 2023-10-20 | 30 | Not Approved | YES | 2023-11-09 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000003 | 02 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 2 | 131242-WSW41-PP-0001 | 2023-12-12 | BIM Execution Plan (BEP) | R2- Not Approved, revise and resubmit. Please refer to "Comment Sheet_Submittal-0003-2". | 2024-01-03 | 2024-03-14 | 50 | Not Approved | YES | 2024-04-04 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000003 | 03 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 3 | 131242-WSW41-PP-0001 | 2024-03-15 | BIM Execution Plan (BEP) | R3- Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet | 2024-04-05 | 2024-03-20 |  | Approved with Comments | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | AWC | AWC
000003 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 4 | 131242-WSW41-PP-0001 | 2024-06-28 | BIM Execution Plan (BEP) | Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet. | 2024-07-18 | 2024-08-07 | 14 | Approved with Comments | YES | 2024-08-28 | YES | Resubmitted |  |  | R3_AWC | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | AWC | AWC
000003 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 5 | 131242-WSW41-PP-0001 | 2024-09-18 | BIM Execution Plan (BEP) | Approved | 2024-10-08 | 2024-10-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | PEN | APP | APP
000004 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 0 | 131242-WST00-PP-0001 | 2023-05-16 | Project HSE Plan | Names are not as proposed. Signatory also not as proposed for HSEM. Review and resubmit. | 2023-06-14 | 2023-07-24 | 27 | Not Approved | YES | 2023-08-14 | YES | Resubmitted |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | NAP | NAP
000004 | 01 | Dharmen | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 1 | 131242-WST00-PP-0001 | 2023-09-27 | Project HSE Plan | Approved from HSE standpoint. | 2023-10-17 | 2023-10-04 |  | Approved | NO |  | YES |  |  |  |  | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | PEN | APP | APP
000005 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 0 | 131242-WST00-PG-0001 | 2023-05-17 | PROGRAMME OF THE WORKS | Rev. 0 - Not Approved, need to re-submit (see comments sheet) | 2023-06-15 | 2023-06-14 |  | Not Approved | YES | 2023-07-05 | YES | Resubmitted |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-05-17 | 2023-07-13 | 1 | 000005 | 2023-05-17, 2023-07-13 | 00, 01 | 2 | PEN | NAP | NAP
000005 | 01 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 1 | 131242-WST00-PG-0001 | 2023-07-13 | PROGRAMME OF THE WORKS | Rev. 1 - Not Approved, need to re-submit (see attached comments sheet R1) | 2023-08-02 | 2023-07-31 |  | Not Approved | YES | 2023-08-21 | YES | Resubmitted |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-05-17 | 2023-07-13 | 1 | 000005 | 2023-05-17, 2023-07-13 | 00, 01 | 2 | PEN | NAP | NAP
000005 | 02 | Thomas | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 2 | 131242-WSW41-PG-0001 | 2023-09-07 | PROGRAMME OF THE WORKS | Rev. 2 Approved with comments. Need to re-submit (see attached comment sheet) | 2023-09-27 | 2023-09-18 |  | Approved with Comments | YES | 2023-10-06 | YES | Resubmitted |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | PEN | AWC | AWC
000005 | 03 | Thomas | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-0003 | 2023-09-26 | PROGRAMME OF THE WORKS | For Information | 2023-10-16 | 2023-10-03 |  | For Information | YES | 2023-10-23 | YES | Resubmitted |  |  | 000040 | NA | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-07-06 | 2023-09-26 | 0 | 000005&&000040 | 2023-07-06, 2023-09-26 | 00, 03 | 2 | PEN | INF | INF
000005 | 04 | Krishanthy | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 3 | 131242-WSW41-PG-0001 | 2023-10-27 | PROGRAMME OF THE WORKS | Rev. 4 Approved with comments. | 2023-11-17 | 2023-11-14 |  | Approved with Comments | YES | 2023-12-04 | YES | Resubmitted |  |  | To be resubmitted when there is a major change in the program of works. Thomas checked with S.O. in the meeting on 18 Jan. | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | PEN | AWC | AWC
000005 | 05 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 4 | 131242-WSW41-PG-0001 | 2024-10-19 | PROGRAMME OF THE WORKS | Rev. 5. Not-Approved need to re-submit (see attached comment sheet) - new Rebaseline of the Programme Rev.1 need to re-submit with a new Prolog Submittal Number | 2024-11-08 | 2024-11-04 |  | Not Approved | YES | 2024-11-22 | YES | Resubmitted |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | PEN | NAP | NAP
000005 | 06 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5 | 131242-WSW41-PG-0001 | 2025-03-14 | PROGRAMME OF THE WORKS | Rev. 6 - Approved with comments (need to re-submit - see attached comments sheet rev.1) | 2025-04-03 | 2025-04-15 | 8 | Approved with Comments | YES | 2025-05-05 | YES | Resubmitted |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | PEN | AWC | AWC
000005 | 07 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5.1 | 131242-WSW41-PG-0001 | 2025-04-16 | PROGRAMME OF THE WORKS | Rev. 7 - Approved with comments (No resubmission needed - See attached comments sheet rev.7) | 2025-05-06 | 2025-04-27 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | PEN | AWC | AWC
000006 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 0 | 131242-WST00-VI-0001 | 2023-05-17 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-15 | 2023-06-12 |  | Approved with Comments | YES | 2023-07-03 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | AWC | AWC
000006 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 1 | 131242-WST00-VI-0001 | 2023-06-23 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Approved | 2023-07-14 | 2023-06-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | APP | APP
000007 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0002 | 0 | 131242-WST00-PG-0002 | 2023-05-18 | MOBILIZATION PROGRAMME | Rev. 0 - Not Approved need to re-submit Refer Comment sheet) | 2023-06-16 | 2023-06-13 |  | Not Approved | YES | 2023-07-04 | YES | Resubmitted |  |  | Reply to S.O. Comment Sheet Only | NA | "MOBILIZATION PROGRAMME " | 2023-05-18 | 2023-05-18 | 0 | 000007 | 2023-05-18 | 00 | 1 | PEN | NAP | NAP
000007 | 01 | Thomas | PCM | NA | Reply to Comment Sheet_#000007 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000007-NA-NA-NA | 2023-09-13 | MOBILIZATION PROGRAMME | Approved | 2023-10-03 | 2023-09-20 |  | Approved | NO |  | YES |  |  |  |  | NA | "MOBILIZATION PROGRAMME " | 2023-09-13 | 2023-09-13 | NA | 000007 | 2023-09-13 | 01 | 1 | PEN | APP | APP
000008 | 00 | Frank/ Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 0 | 131242-WST00-RG-0001 | 2023-05-18 | Engineering Deliverable Lists | Rev 0: Not approved - Revise and Resubmit | 2023-06-16 | 2023-11-21 | 109 | Not Approved | YES | 2023-12-11 | YES | Resubmitted |  |  |  | NA | "Engineering Deliverable Lists" | 2023-05-18 | 2024-01-15 | 1 | 000008 | 2023-05-18, 2024-01-15 | 00, 01 | 2 | PEN | NAP | NAP
000008 | 01 | Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 1 | 131242-WST00-RG-0001 | 2024-01-15 | Engineering Deliverable Lists | For Information To revise and resubmit. Refer to attached file for comments. | 2024-02-02 | 2024-08-29 | 142 | For Information | YES | 2024-09-18 | NO | Overdue | 351 |  | R1_Not APP | NA | "Engineering Deliverable Lists" | 2023-05-18 | 2024-01-15 | 1 | 000008 | 2023-05-18, 2024-01-15 | 00, 01 | 2 | PEN | INF | INF
000009 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 0 | 131242-WST00-VI-0002 | 2023-05-19 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-12 |  | Not Approved | YES | 2023-07-03 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-05-19 | 2023-07-03 | 1 | 000009 | 2023-05-19, 2023-07-03 | 00, 01 | 2 | PEN | NAP | NAP
000009 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 1 | 131242-WST00-VI-0002 | 2023-07-03 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Approved | 2023-07-21 | 2023-07-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-05-19 | 2023-07-03 | 1 | 000009 | 2023-05-19, 2023-07-03 | 00, 01 | 2 | PEN | APP | APP
000010 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | S | 0001 | 0 | 131242-WST00-VI-0001 | 2023-05-19 | Vendor Approval for CSA Consultant QP (Tenwit) | Approved | 2023-06-19 | 2023-06-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | APP | APP
000011 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | G | 0001 | 0 | 131242-WST00-VI-0001 | 2023-05-19 | Vendor Approval for Temp ERSS QPD,QPS (Tenwit ) | Approved | 2023-06-19 | 2023-06-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | APP | APP
000012 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 0 | 131242-WST00-VI-0001 | 2023-05-19 | Vendor Approval for QECP Consultant (Tenwit ) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-14 |  | Not Approved | YES | 2023-07-05 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | NAP | NAP
000012 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 1 | 131242-WST00-VI-0001 | 2023-06-23 | Vendor Approval for QECP Consultant (Tenwit ) | Approved | 2023-07-14 | 2023-07-24 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | APP | APP
000013 | 00 | Freedomer | EICA | NA | 131242 | WST00 | VI | B | 0001 | 0 | 131242-WST00-VI-0001 | 2023-05-21 | Vendor Approval for M&E QP (C2D Solutions Pte. LTD ) | Approved | 2023-06-19 | 2024-03-18 | 189 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | PEN | APP | APP
000014 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 0 | 131242-WST00-VI-0003 | 2023-05-22 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-20 | 2023-06-12 |  | Not Approved | YES | 2023-07-03 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | PEN | NAP | NAP
000014 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 1 | 131242-WST00-VI-0003 | 2023-06-23 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.1: Not Approved. Please refer to attached comment sheet for resubmission. | 2023-07-14 | 2023-07-12 |  | Not Approved | YES | 2023-08-01 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | PEN | NAP | NAP
000014 | 02 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 2 | 131242-WST00-VI-0003 | 2023-07-31 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Approved | 2023-08-21 | 2023-08-11 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | PEN | APP | APP
000015 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0001 | 0 | 131242-WST00-MI-0001 | 2023-05-23 | CSA Meeting Minutes 0001 | For Information | 2023-06-21 | 2023-06-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | PEN | INF | INF
000016 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 0001 | 0 | 131242-WST02-DS-0001 | 2023-05-26 | FRP TANK DATA SHEET | Not approved - Revise and Resubmit | 2023-06-26 | 2023-10-16 | 78 | Not Approved | YES | 2023-11-03 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for ACMV Equipment" && "Epoxy Coating System" && "FRP TANK DATA SHEET" | 2023-05-26 | 2025-10-13 | 0 | 000016&&001236&&001296&&001740 | 2023-05-26, 2025-04-18, 2025-05-15, 2025-10-13 | 00 | 4 | PEN | NAP | NAP
000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 0 | 131242-WST02-DS-5401 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | 2 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  | 2025-03-14 | In Progress | NA | "FRP TANK DATA SHEET" | 2024-09-20 | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5416 | NA | 131242-WST02-DS-5416 | 2024-09-20 | Project Risk Management Plan | For Information | 2024-10-10 | 2024-10-14 | 2 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Project Risk Management Plan" | 2024-09-20 | 2025-04-01 | NA | 000000 | 2024-09-20, 2025-04-01 | 00 | 2 | PEN | AWC | AWC
000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 1 | 131242-WST02-DS-5401 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "FRP TANK DATA SHEET" | 2024-09-20 | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5416 | NA | 131242-WST02-DS-5416 | 2025-04-01 | Project Risk Management Plan | For Information | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Project Risk Management Plan" | 2024-09-20 | 2025-04-01 | NA | 000000 | 2024-09-20, 2025-04-01 | 00 | 2 | PEN | APP | APP
000017 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 0 | 131242-WST00-LT-0001 | 2023-05-27 | CVs of Team Member | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-26 | 2023-06-27 | 1 | Approved with Comments | YES | 2023-07-18 | YES | Resubmitted |  |  |  | NA | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-05-27 | 2023-07-12 | 1 | 000017 | 2023-05-27, 2023-07-12 | 00, 01 | 2 | PEN | AWC | AWC
000017 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 1 | 131242-WST00-LT-0001 | 2023-07-12 | CVs of Team Member Part 1 (14 Members) | Rev.1: Approved with comments. Please refer to attached comment sheet. | 2023-08-01 | 2023-07-25 |  | Approved with Comments | YES | 2023-08-15 | YES | Resubmitted |  |  |  | NA | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-05-27 | 2023-07-12 | 1 | 000017 | 2023-05-27, 2023-07-12 | 00, 01 | 2 | PEN | AWC | AWC
000017 | 02 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000017 | 2 | 131242-WSW41-LT- Reply to Comment Sheet_#000017 | 2023-09-04 | CVs of Team Member Part 1 (14 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-22 | 2023-10-10 | 12 | Approved with Comments | YES | 2023-10-30 | NO | Overdue | 573 |  | To obtain S.O. evaluation & final approval based on the probation period. To check with S.O during CSA bi-weekly meeting | NA | "CVs of Team Member Part 1 (14 Members)" | 2023-09-04 | 2023-09-04 | 2 | 000017 | 2023-09-04 | 02 | 1 | PEN | AWC | AWC
000018 | 00 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-0001 | 2023-05-31 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-30 | 2023-06-06 |  | Not Approved | YES | 2023-06-26 | YES | Resubmitted |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | NAP | NAP
000018 | 01 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 1 | 131242-WST00-DR-0001 | 2023-06-06 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-26 | 2023-06-23 |  | Not Approved | YES | 2023-07-14 | YES | Resubmitted |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | NAP | NAP
000018 | 02 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 2 | 131242-WST00-DR-0001 | 2023-06-27 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-07-18 | 2023-07-03 |  | Not Approved | YES | 2023-07-21 | YES | Resubmitted |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | NAP | NAP
000018 | 03 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 3 | 131242-WST00-DR-0001 | 2023-07-04 | Title Block Template (CAD) | Approved | 2023-07-24 | 2023-07-03 |  | Approved | NO |  | YES |  |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | APP | APP
000019 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 0 | 131242-WST00-VI-0004 | 2023-05-31 | Vendor Approval for Cable Dectector (JLCD) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-30 | 2023-06-16 |  | Approved with Comments | YES | 2023-07-07 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Cable Dectector (JLCD)" | 2023-05-31 | 2023-06-23 | 1 | 000019 | 2023-05-31, 2023-06-23 | 00, 01 | 2 | PEN | AWC | AWC
000019 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 1 | 131242-WST00-VI-0004 | 2023-06-23 | Vendor Approval for Cable Dectector (JLCD) | Approved | 2023-07-14 | 2023-06-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Cable Dectector (JLCD)" | 2023-05-31 | 2023-06-23 | 1 | 000019 | 2023-05-31, 2023-06-23 | 00, 01 | 2 | PEN | APP | APP
000020 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | FM | HS | 0001 | 0 | 131242-WST00-FM-0001 | 2023-06-05 | HSE Stickers for Machineries and SIC Induction | Approved | 2023-07-04 | 2023-06-14 |  | Approved | NO |  | YES |  |  |  |  | NA | "HSE Stickers for Machineries and SIC Induction" | 2023-06-05 | 2023-06-05 | 0 | 000020 | 2023-06-05 | 00 | 1 | PEN | APP | APP
000021 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0001 | 0 | 131242-WST00-MI-0001 | 2023-06-11 | Process & MEICA Meeting Minutes 0001 | For Information | 2023-07-10 | 2023-10-18 | 71 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | PEN | INF | INF
000022 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0002 | 0 | 131242-WST00-MI-0002 | 2023-06-11 | Process & MEICA Meeting Minutes 0002 | For Information | 2023-07-10 | 2024-03-18 | 175 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0002" && "Process & MEICA Meeting Minutes 0002" | 2023-06-11 | 2023-06-16 | 0 | 000022&&000029 | 2023-06-11, 2023-06-16 | 00 | 2 | PEN | INF | INF
000023 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0003 | 0 | 131242-WST00-MI-0003 | 2023-06-11 | Process & MEICA Meeting Minutes 0003 | For Information | 2023-07-10 | 2024-03-18 | 175 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0003" && "Process & MEICA Meeting Minutes 0003" | 2023-06-11 | 2023-06-16 | 0 | 000023&&000030 | 2023-06-11, 2023-06-16 | 00 | 2 | PEN | INF | INF
000024 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0004 | 0 | 131242-WST00-MI-0004 | 2023-06-11 | Process & MEICA Meeting Minutes 0004 | For Information | 2023-07-10 | 2024-03-18 | 175 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Process & MEICA Meeting Minutes 0004" | 2023-06-11 | 2023-06-28 | 0 | 000024&&000036 | 2023-06-11, 2023-06-28 | 00 | 2 | PEN | INF | INF
000025 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 0 | 131242-WST00-LT-0002 | 2023-06-12 | CVs of Team Member | Approved with comments. Please refer to comment sheet for resubmission. | 2023-07-11 | 2023-06-20 |  | Approved with Comments | YES | 2023-07-11 | YES | Resubmitted |  |  |  | NA | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-06-12 | 2023-07-12 | 1 | 000025 | 2023-06-12, 2023-07-12 | 00, 01 | 2 | PEN | AWC | AWC
000025 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 1 | 131242-WST00-LT-0002 | 2023-07-12 | CVs of Team Member Part 2 (7 Members) | Rev.1: Approved with comments. Please refer to S.O. comment sheet. | 2023-08-01 | 2023-07-25 |  | Approved with Comments | YES | 2023-08-15 | YES | Resubmitted |  |  | Reply to S.O. Comment Sheet Only | NA | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-06-12 | 2023-07-12 | 1 | 000025 | 2023-06-12, 2023-07-12 | 00, 01 | 2 | PEN | AWC | AWC
000025 | 02 | Shena/ Htet | PMT | NA | 131242 | NA | LT | PM | Reply to Comment Sheet_#000025 | NA | 131242-NA-LT-Reply to Comment Sheet_#000025 | 2023-09-11 | CVs of Team Member Part 2 (7 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-29 | 2024-09-10 | 237 | Approved with Comments | YES | 2024-09-30 | NO | Overdue | 343 |  |  | NA | "CVs of Team Member Part 2 (7 Members)" | 2023-09-11 | 2023-09-11 | NA | 000025 | 2023-09-11 | 02 | 1 | PEN | AWC | AWC
000026 | 00 | Bryan | HSE | NA | 131242 | WST00 | MS | C | 0001 | 0 | 131242-WST00-MS-0001 | 2023-06-13 | Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-29 |  | Not Approved | YES | 2023-07-19 | NO | Overdue | 645 | 2024-01-10 | In Progress | NA | "Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD)" | 2023-06-13 | 2023-06-13 | 0 | 000026 | 2023-06-13 | 00 | 1 | PEN | NAP | NAP
000027 | 00 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 0 | 131242-WST00-RT-0001 | 2023-06-13 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-16 |  | Not Approved | YES | 2023-07-07 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | PEN | NAP | NAP
000027 | 01 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 1 | 131242-WST00-RT-0001 | 2023-07-04 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-24 | 2023-07-13 |  | Not Approved | YES | 2023-08-02 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | PEN | NAP | NAP
000027 | 02 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 2 | 131242-WST00-RT-0001 | 2023-07-14 | C4B Monthly Progress Report Number No.01 (05/23) | Approved | 2023-08-03 | 2023-10-18 | 53 | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | PEN | APP | APP
000028 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 0 | 131242-WSD11-VI-0001 | 2023-06-14 | Vendor Approval for THP Package | Rev 0: Not approved - Revise and Resubmit | 2023-07-13 | 2023-07-14 | 1 | Not Approved | YES | 2023-08-03 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | NAP | NAP
000028 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 1 | 131242-WSD11-VI-0001 | 2023-07-28 | Vendor Approval for THP Package | Rev 1: Rejected as per contractor requested email dated on 31-Jul-2023 as there has few changes and will resubmit to include the comment sheet in next revision. | 2023-08-18 | 2023-08-01 |  | Not Approved | YES | 2023-08-22 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | NAP | NAP
000028 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 2 | 131242-WSD11-VI-0001 | 2023-08-02 | Preliminary design and Vendor Approval | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-08-23 | 2023-08-31 | 6 | Approved with Comments | YES | 2023-09-20 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | AWC | AWC
000028 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 3 | 131242-WSD11-VI-0001 | 2023-11-10 | Preliminary design and Vendor Approval - THP Package | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-01 | 2023-12-20 | 13 | Approved with Comments | YES | 2024-01-11 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | AWC | AWC
000028 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 4 | 131242-WSD11-VI-0001 | 2024-03-01 | Preliminary design and Vendor Approval - THP Package | Rev 4: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-03-21 | 2024-04-26 | 24 | Approved with Comments | NO |  | YES |  |  |  | Rev3: AWC | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | AWC | AWC
000029 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0002 | 0 | 131242-WST00-MI-0002 | 2023-06-16 | CSA Meeting Minutes 0002 | For information | 2023-07-17 | 2023-06-28 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0002" && "Process & MEICA Meeting Minutes 0002" | 2023-06-11 | 2023-06-16 | 0 | 000022&&000029 | 2023-06-11, 2023-06-16 | 00 | 2 | PEN | INF | INF
000030 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0003 | 0 | 131242-WST00-MI-0003 | 2023-06-16 | CSA Meeting Minutes 0003 | For information | 2023-07-17 | 2023-06-28 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0003" && "Process & MEICA Meeting Minutes 0003" | 2023-06-11 | 2023-06-16 | 0 | 000023&&000030 | 2023-06-11, 2023-06-16 | 00 | 2 | PEN | INF | INF
000031 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | Z | 0001 | 0 | 131242-WST00-MI-0001 | 2023-06-19 | Engineering Kick Off Meeting Minutes 0001 | For Information | 2023-07-18 | 2024-03-18 | 169 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | PEN | INF | INF
000032 | 00 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 0 | 131242-WST00-MS-0002 | 2023-06-19 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-18 | 2023-06-29 |  | Not Approved | YES | 2023-07-19 | YES | Resubmitted |  | 2024-01-10 | In Progress | NA | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2023-06-19 | 2024-04-12 | 1 | 000032 | 2023-06-19, 2024-04-12 | 00, 01 | 2 | PEN | NAP | NAP
000032 | 01 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 1 | 131242-WST00-MS-0002 | 2024-04-12 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 23 | Approved | NO |  | YES |  |  |  |  | NA | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2023-06-19 | 2024-04-12 | 1 | 000032 | 2023-06-19, 2024-04-12 | 00, 01 | 2 | PEN | APP | APP
000033 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PS | HS | 0001 | 0 | 131242-WST00-PS-0001 | 2023-06-20 | C4B HSE Induction Course | Noted for information | 2023-07-19 | 2023-07-24 | 3 | For Information | NO |  | YES |  |  |  |  | NA | "C4B HSE Induction Course" | 2023-06-20 | 2023-06-20 | 0 | 000033 | 2023-06-20 | 00 | 1 | PEN | INF | INF
000034 | 00 | Kristnnan | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 0 | 131242-WSW41-PP-0003 | 2023-06-21 | Emergency Response Plan | Reporting timeline is not in sequence with what we have. Please use information in your KOM slides when preparing. Review and resubmit. | 2023-07-20 | 2023-08-02 | 9 | Not Approved | YES | 2023-08-23 | YES | Resubmitted |  |  |  | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | PEN | NAP | NAP
000034 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 1 | 131242-WSW41-PP-0003 | 2023-09-07 | Emergency Response Plan | Approved | 2023-09-27 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | PEN | APP | APP
000035 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0002 | 0 | 131242-WST00-PP-0002 | 2023-06-22 | Project Accident Statistic Board and BCA Board | Rev.0: Not Approved. Please find attached comment sheet for resubmission. | 2023-07-21 | 2023-08-18 | 19 | Not Approved | YES | 2023-09-07 | YES | Resubmitted |  |  |  | NA | "Project Accident Statistic Board and BCA Board" | 2023-06-22 | 2023-06-22 | 0 | 000035 | 2023-06-22 | 00 | 1 | PEN | NAP | NAP
000035 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0002 | 1 | 131242-WSW41-PP-0002 | 2023-10-13 | Project Accident Statistic Board and BCA Board | Approved | 2023-11-02 | 2023-10-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | PEN | APP | APP
000036 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0004 | 0 | 131242-WST00-MI-0004 | 2023-06-28 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-07-27 | 2023-07-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Process & MEICA Meeting Minutes 0004" | 2023-06-11 | 2023-06-28 | 0 | 000024&&000036 | 2023-06-11, 2023-06-28 | 00 | 2 | PEN | INF | INF
000037 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0001 | 0 | 131242-WSW41-MI-0001 | 2023-06-28 | BIM Bi-Weekly Meeting Minutes 0001_20230614 | For Information | 2023-07-27 | 2023-07-04 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | PEN | INF | INF
000038 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | B | 0001 | 0 | 131242-WSW41-CL-0001 | 2023-07-05 | Temporary Utilities for Contractor’s Site Office | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-02 | 2023-07-21 |  | Approved with Comments | YES | 2023-08-11 | NO | Overdue | 629 |  |  | NA | "ECM Plan and Calculation" && "Temporary Utilities for Contractor’s Site Office" | 2023-07-05 | 2023-08-31 | 0 | 000038&&000086 | 2023-07-05, 2023-08-31 | 00 | 2 | PEN | AWC | AWC
000039 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0001 | 0 | 131242-WSD11-MI-0001 | 2023-07-05 | MI-Process & MEICA Meeting Minutes with THP (CAMBI) | For Information | 2023-08-02 | 2024-03-18 | 158 | For Information | NO |  | YES |  |  |  |  | NA | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" && "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2023-07-05 | 2024-02-28 | 0 | 000039&&000330 | 2023-07-05, 2024-02-28 | 00 | 2 | PEN | INF | INF
000040 | 00 | Stanley | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | NA | 131242-WSW41-LT-0003 | 2023-07-06 | Request for time extension_Programme of works resubmission | The Prolog Submittals number 000040 (need to void) should not be created as new submission, this submission should under Prologs number 000005 because this extension request is referring from Rev. 0 to Rev. 1 - Programme of the Works | 2023-08-03 | 2023-09-22 | 35 | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-07-06 | 2023-09-26 | 0 | 000005&&000040 | 2023-07-06, 2023-09-26 | 00, 03 | 2 | PEN | PEN | PEN
000041 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0005 | 0 | 131242-WSW41-MI-0005 | 2023-07-06 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-08-03 | 2023-10-18 | 53 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-06 | 2023-11-20 | 0 | 000000&&000041&&000068&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | PEN | INF | INF
000042 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0004 | 0 | 131242-WSW41-LT-0004 | 2023-07-06 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-08-03 | 2023-08-21 | 11 | Approved with Comments | YES | 2023-09-08 | YES | Resubmitted |  |  |  | NA | "CVs of Team Members (Part 3)" | 2023-07-06 | 2023-07-06 | 0 | 000042 | 2023-07-06 | 00 | 1 | PEN | AWC | AWC
000042 | 01 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000042 | NA | 131242-WSW41-LT-Reply to Comment Sheet_#000042 | 2023-09-04 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-09-22 | 2024-02-01 | 91 | Approved with Comments | YES | 2024-02-22 | NO | Overdue | 494 |  |  | NA | "CVs of Team Members (Part 3)" | 2023-09-04 | 2023-09-04 | NA | 000042 | 2023-09-04 | 01 | 1 | PEN | AWC | AWC
000043 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0001 | 0 | 131242-WSW41-PS-0001 | 2023-07-07 | Presentation Slide for Monthly Progress Meeting No. 01(0523) | For information only | 2023-08-04 | 2023-07-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Presentation Slide for Monthly Progress Meeting No. 01(0523)" | 2023-07-07 | 2023-07-07 | 0 | 000043 | 2023-07-07 | 00 | 1 | PEN | INF | INF
000044 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0005 | 0 | 131242-WSW41-LT-0005 | 2023-07-07 | CVs of Team Members (Part 4) | Approved | 2023-08-04 | 2023-07-24 |  | Approved | NO |  | YES |  |  |  |  | NA | "CVs of Team Members (Part 4)" | 2023-07-07 | 2023-07-07 | 0 | 000044 | 2023-07-07 | 00 | 1 | PEN | APP | APP
000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0002 | 0 | 131242-WSW41-DR-0002 | 2023-07-10 | SITE UTILIZATION PLAN | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 |  | Approved with Comments | YES | 2023-08-11 | YES | Resubmitted |  |  |  | NA | "SITE UTILIZATION PLAN" | 2023-07-10 | 2023-07-10 | 0 | 000045 | 2023-07-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | Z | 0003 | NA | 131242-WSW41-DR-0003 | 2023-07-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-08-07 | 2023-07-21 |  | Approved with Comments | YES | 2023-08-11 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-10 | 2023-07-26 | 1 | 000000&&000045 | 2023-07-10, 2023-07-26 | 00, 01 | 2 | PEN | AWC | AWC
000045 | 01 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 1 | 131242-WSW41-DR-0003 | 2023-07-26 | SITE OFFICE LAYOUT (Rev2) | Approved | 2023-08-16 | 2023-08-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-10 | 2023-07-26 | 1 | 000000&&000045 | 2023-07-10, 2023-07-26 | 00, 01 | 2 | PEN | APP | APP
000046 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 0 | 131242-WSW41-RT-0002 | 2023-07-12 | C4B Monthly Progress Report Number No.02 (06/23) | Rejected as informed by contractor email dated 12-Jul-2023 there has few changes/ corrections in the attached file. | 2023-08-10 | 2023-07-14 |  | Rejected | YES | 2023-08-03 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | REJ | REJ
000046 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 1 | 131242-WSW41-RT-0002 | 2023-07-14 | C4B Monthly Progress Report Number No.02 (06/23) | Rev. 1 - Approved with comments (see the comment sheet) Resubmission required | 2023-08-03 | 2023-10-18 | 53 | Approved with Comments | YES | 2023-11-07 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | AWC | AWC
000046 | 02 | Thomas | PCM | NA | Comment Reply Sheet 08112023 | NA | NA | NA | NA | NA | Comment Reply Sheet 08112023-NA-NA-NA | 2023-11-09 | C4B Monthly Progress Report Number No.02 (06/23) | Approved | 2023-11-30 | 2023-11-15 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" | 2023-11-09 | 2023-11-09 | NA | 000046 | 2023-11-09 | 02 | 1 | PEN | APP | APP
000047 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0002 | 0 | 131242-WSW41-MI-0002 | 2023-07-13 | BIM Bi-Weekly Meeting Minutes 0002_20230628 | For Information | 2023-08-11 | 2023-07-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0002_20230628" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-13 | 2023-09-04 | 0 | 000000&&000047 | 2023-07-13, 2023-09-04 | 00 | 2 | PEN | INF | INF
000048 | 00 | Matthew | Piping/ BS | NA | 131242 | WSW41 | MI | B | 0001 | 0 | 131242-WSW41-MI-0001 | 2023-07-14 | BS Meeting Minutes 0001_20230706 | For Information | 2023-08-14 | 2024-02-15 | 129 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | PEN | INF | INF
000049 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PP | PM | 0002 | 0 | 131242-WSW41-PP-0002 | 2023-07-14 | C4B Manpower Deployment Plan | Approved as noted. Please note that acceptable of the manpower deployment plan shall not relieve the Contractor's responsibility to engage key personnel whenever is required or employ additional manpower to complete and successfully deliver the project timely and safely. | 2023-08-14 | 2023-07-24 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | PEN | APP | APP
000050 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0006 | 0 | 131242-WSW41-MI-0006 | 2023-07-14 | CSA Meeting Minutes 0004_20230705 | For Information | 2023-08-14 | 2023-07-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-14 | 2023-11-15 | 0 | 000000&&000050&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | PEN | INF | INF
000051 | 00 | REY | PMT | NA | 131242 | WSW41 | DR | C | 1000 | 0 | 131242-WSW41-DR-1000 | 2023-07-18 | Drawing of Pre-Con Topographical Survey | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-08-16 | 2023-08-11 |  | Approved with Comments | YES | 2023-08-31 | NO | Overdue | 615 |  | Heng Peng: To clear BIM comments | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | AWC | AWC
000052 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0003 | 0 | 131242-WSW41-MI-0003 | 2023-07-18 | BIM Bi-Weekly Meeting Minutes 0003_20230712 | For Information | 2023-08-16 | 2023-07-25 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0003_20230712" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-07-18 | 2023-10-25 | 0 | 000052&&000138 | 2023-07-18, 2023-10-25 | 00 | 2 | PEN | INF | INF
000053 | 00 | Heng Peng | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 0 | 131242-WSW41-LT-0006 | 2023-07-19 | CV of Team Member (BIM Authoring Lead) | R0- Proposed candidate doesn’t meet the requirement. Please refer to "Comment sheet - Submittal 000053.0" | 2023-08-17 | 2023-10-23 | 47 | Not Approved | YES | 2023-11-10 | YES | Resubmitted |  |  |  | NA | "CV of Team Member (BIM Authoring Lead)" | 2023-07-19 | 2023-12-11 | 1 | 000053 | 2023-07-19, 2023-12-11 | 00, 01 | 2 | PEN | NAP | NAP
000053 | 01 | Leon | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 1 | 131242-WSW41-LT-0006 | 2023-12-11 | CV of Team Member (BIM Authoring Lead) | R1- Subject to 6 months' probation period. Please refer to "Comment sheet - Submittal 000053.1" | 2024-01-02 | 2023-12-22 |  | Not Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (BIM Authoring Lead)" | 2023-07-19 | 2023-12-11 | 1 | 000053 | 2023-07-19, 2023-12-11 | 00, 01 | 2 | PEN | NAP | NAP
000054 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0007 | 0 | 131242-WSW41-MI-0007 | 2023-07-24 | CSA Meeting Minutes 0007_20230712 | For Information | 2023-08-22 | 2023-08-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | PEN | INF | INF
000055 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0001 | 0 | 131242-WSW41-PC-0001 | 2023-07-24 | PROGRESS CLAIM NO.1 | Accepted. Please refer to S.O. Correspondence no. 25 dated 25 July 2023. | 2023-08-22 | 2023-08-30 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "PROGRESS CLAIM NO.1" | 2023-07-24 | 2023-07-24 | 0 | 000055 | 2023-07-24 | 00 | 1 | PEN | APP | APP
000056 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0004 | 0 | 131242-WSW41-PP-0004 | 2023-07-27 | Signboard Sticker for TWRP Main Gate route 3 entrance | For information | 2023-08-25 | 2023-08-02 |  | For Information | NO |  | YES |  |  |  |  | NA | "Signboard Sticker for TWRP Main Gate route 3 entrance" | 2023-07-27 | 2023-07-27 | 0 | 000056 | 2023-07-27 | 00 | 1 | PEN | INF | INF
000057 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0002 | 0 | 131242-WSW41-PS-0002 | 2023-07-28 | Presentation Slide for Monthly Progress Meeting No. 02(0623) | For information | 2023-08-28 | 2023-08-01 |  | For Information | NO |  | YES |  |  |  |  | NA | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" && "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | 2023-07-28 | 2023-11-02 | 0 | 000057&&000157 | 2023-07-28, 2023-11-02 | 00 | 2 | PEN | INF | INF
000058 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 0 | 131242-WSW41-MS-0003 | 2023-07-28 | MSRA, SWP for General Civil Works | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-28 | 2023-08-14 |  | Approved with Comments | YES | 2023-09-01 | YES | Resubmitted |  |  |  | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000058 | 01 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 1 | 131242-WSW41-MS-0003 | 2024-01-22 | MSRA, SWP for General Civil Works | Rev.1: Approved with comments. Please refer to attached comment sheet for resubmission. | 2024-02-09 | 2024-02-21 | 7 | Approved with Comments | YES | 2024-03-12 | YES | Resubmitted |  |  |  | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000058 | 02 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 2 | 131242-WSW41-MS-0003 | 2024-04-12 | MSRA, SWP for General Civil Works | Rev.2: Approved | 2024-05-03 | 2024-06-06 | 23 | Approved | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | PEN | APP | APP
000058 | 03 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 3 | 131242-WSW41-MS-0003 | 2025-03-20 | MSRA, SWP for General Civil Works | R3: Approved | 2025-04-09 | 2025-05-07 | 18 | Approved | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | PEN | APP | APP
000059 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0005 | 0 | 131242-WSW41-VI-0005 | 2023-08-01 | Vendor Approval of Concrete Supplier-Alliance | Rev.0: Approved | 2023-08-30 | 2023-08-10 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | APP | APP
000060 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-0002 | 2023-08-01 | Adjustment of Stage Payment | Rejected as contractor would like to resubmit with the correct reference. | 2023-08-30 | 2023-08-02 |  | Rejected | YES | 2023-08-23 | YES | Resubmitted |  |  |  | NA | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-01 | 2023-08-25 | 0 | 000060&&000080 | 2023-08-01, 2023-08-25 | 00 | 2 | PEN | REJ | REJ
000060 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0008 | 0 | 131242-WSW41-LT-0008 | 2023-08-02 | Adjustment of Stage Payment | Rejected. Contractor to re-submit. Please refer to S.O. correspondence no. 55 dated 13 Sep 2023. | 2023-08-23 | 2023-09-15 | 17 | Rejected | YES | 2023-10-05 | YES | Resubmitted |  |  |  | NA | "Adjustment of Stage Payment" | 2023-08-02 | 2023-08-02 | 0 | 000060 | 2023-08-02 | 01 | 1 | PEN | REJ | REJ
000060 | 02 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0014 | 0 | 131242-WSW41-LT-0014 | 2023-10-18 | Adjustment of Stage Payment | For Information | 2023-11-07 | 2023-12-18 | 28 | For Information | NO |  | YES |  |  |  |  | NA | "Adjustment of Stage Payment" | 2023-10-18 | 2023-10-18 | 0 | 000060 | 2023-10-18 | 02 | 1 | PEN | INF | INF
000061 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0009 | 0 | 131242-WSW41-LT-0009 | 2023-08-03 | CV of Team Member (CM) | Approved | 2023-09-01 | 2023-08-11 |  | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (CM)" | 2023-08-03 | 2023-08-03 | 0 | 000061 | 2023-08-03 | 00 | 1 | PEN | APP | APP
000062 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0007 | 0 | 131242-WSW41-LT-0007 | 2023-08-03 | Request for Variable Site Management Team Payment | Rev(0) Accepted. Please refer to S.O. correspondence no. 84 dated 22 Nov 2023. | 2023-09-01 | 2024-01-30 | 104 | For Information | NO |  | YES |  |  |  |  | NA | "Request for Variable Site Management Team Payment" | 2023-08-03 | 2023-08-03 | 0 | 000062 | 2023-08-03 | 00 | 1 | PEN | INF | INF
000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0008 | 0 | 131242-WSW41-MI-0008 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0009 | NA | 131242-WSW41-MI-0009 | 2023-08-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-05 | 2023-08-11 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Meeting Minutes 0009_20240220" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-07 | 2024-03-01 | 0 | 000000&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | PEN | INF | INF
000064 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 0 | 131242-WSW41-VI-0006 | 2023-08-08 | Vendor Approval of Concrete Supplier-Pan United | Rev.0: Approved with comment. Please refer to attached comment sheet for resubmission. | 2023-09-06 | 2023-08-30 |  | Approved with Comments | YES | 2023-09-19 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | AWC | AWC
000064 | 01 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 1 | 131242-WSW41-VI-0006 | 2023-09-22 | Vendor Approval of Concrete Supplier-Pan United | Approved | 2023-10-12 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | APP | APP
000065 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CN | E | 0001 | 0 | 131242-WSW41-CN-0001 | 2023-08-08 | RFC For HV Routing (from C3B1) to SSN Transformer Room | Approved. Refer comment sheet for more details. | 2023-09-06 | 2024-02-15 | 112 | Approved | NO |  | YES |  |  |  |  | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | APP | APP
000066 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0001 | 0 | 131242-WSW41-CD-0001 | 2023-08-08 | Submission Of BIM Coordination VCM Model (July – 2023) | Approved with Comments. Please refer to "Comments Sheet_Sub-0066-0" | 2023-09-06 | 2023-08-24 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " && "Submission Of BIM Coordination VCM Model (July – 2023)" | 2023-08-08 | 2025-07-25 | 1 | 000066&&001350&&001467 | 2023-08-08, 2025-06-10, 2025-07-25 | 00, 01 | 3 | PEN | AWC | AWC
000067 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0007 | 0 | 131242-WSW41-VI-0007 | 2023-08-11 | Vendor Approval of Rebar Supplier-BRC ASIA LIMITED | Approved | 2023-09-08 | 2023-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | PEN | APP | APP
000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0005 | 0 | 131242-WSW41-MI-0005 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | 131 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-06 | 2023-11-20 | 0 | 000000&&000041&&000068&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | P | 0006 | NA | 131242-WSW41-MI-0006 | 2023-08-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-11 | 2024-03-18 | 131 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-14 | 2023-11-15 | 0 | 000000&&000050&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | PEN | INF | INF
000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0001 | 0 | 131242-WST02-MI-0001 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | 131 | For Information | NO |  | YES |  |  |  |  | NA | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | 2023-08-14 | 2023-08-14 | 0 | 000069 | 2023-08-14 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | MI | P | 0002 | NA | 131242-WST02-MI-0002 | 2023-08-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-11 | 2024-03-18 | 131 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-14 | 2023-08-14 | NA | 000000 | 2023-08-14 | 00 | 1 | PEN | INF | INF
000070 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 0 | 131242-WSW41-RT-0003 | 2023-08-14 | C4B Monthly Progress Report Number No.03 (07/23) | Rev. 0 - Approved with Comments . Refer to Comments sheet to re-submit. | 2023-09-11 | 2023-08-29 |  | Approved with Comments | YES | 2023-09-18 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-08-14 | 2023-09-25 | 1 | 000070 | 2023-08-14, 2023-09-25 | 00, 01 | 2 | PEN | AWC | AWC
000070 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 1 | 131242-WSW41-RT-0003 | 2023-09-25 | C4B Monthly Progress Report Number No.03 (07/23) | Approved | 2023-10-13 | 2023-09-27 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-08-14 | 2023-09-25 | 1 | 000070 | 2023-08-14, 2023-09-25 | 00, 01 | 2 | PEN | APP | APP
000071 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0009 | 0 | 131242-WSW41-VI-0009 | 2023-08-15 | Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " && "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | 2023-08-15 | 2024-10-26 | 0 | 000071&&000780 | 2023-08-15, 2024-10-26 | 00 | 2 | PEN | APP | APP
000072 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0010 | 0 | 131242-WSW41-VI-0010 | 2023-08-15 | Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | APP | APP
000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0004 | 0 | 131242-WSW41-MI-0004 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-15 | 2023-10-25 | 0 | 000000&&000073 | 2023-08-15, 2023-10-25 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0005 | NA | 131242-WSW41-MI-0005 | 2023-08-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-12 | 2023-08-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-06 | 2023-11-20 | 0 | 000000&&000041&&000068&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | PEN | INF | INF
000074 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0008 | 0 | 131242-WSW41-VI-0008 | 2023-08-16 | Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd | Approved | 2023-09-13 | 2023-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | PEN | APP | APP
000075 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0011 | 0 | 131242-WSW41-LT-0011 | 2023-08-22 | CV of Team Member (WSHC) | Approved | 2023-09-19 | 2023-09-25 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (WSHC)" | 2023-08-22 | 2023-08-22 | 0 | 000075 | 2023-08-22 | 00 | 1 | PEN | APP | APP
000076 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0010 | 0 | 131242-WSW41-LT-0010 | 2023-08-22 | Delegation of Signing Authorities | For Information | 2023-09-19 | 2023-09-25 | 4 | For Information | NO |  | YES |  |  |  |  | NA | "Delegation of Signing Authorities" | 2023-08-22 | 2023-08-22 | 0 | 000076 | 2023-08-22 | 00 | 1 | PEN | INF | INF
000077 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0003 | 0 | 131242-WSW41-PS-0003 | 2023-08-28 | Presentation Slide for Monthly Progress Meeting No. 03(0723) | For Information | 2023-09-25 | 2023-08-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" && "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | 2023-08-28 | 2024-02-03 | 0 | 000077&&000300 | 2023-08-28, 2024-02-03 | 00 | 2 | PEN | INF | INF
000078 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0001 | 0 | 131242-WSW41-RT-0001 | 2023-08-24 | Photographic Survey Report for C4B | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-09-21 | 2023-08-30 |  | Not Approved | YES | 2023-09-19 | NO | Overdue | 602 |  |  | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | PEN | NAP | NAP
000079 | 00 | Zora | CSA | NA | 1.0 Design Brief | NA | NA | NA | NA | NA | 1.0 Design Brief-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-08-31 |  | Not Approved | YES | 2023-09-20 | YES | Resubmitted |  |  |  | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-08-24 | NA | 000079 | 2023-08-24 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003 | NA | NA | NA | NA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003-NA-NA-NA | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-08-24 | NA | 000000 | 2023-08-24 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 3.0 Overall SSN area Loading Plan Marked up | NA | NA | NA | NA | NA | 3.0 Overall SSN area Loading Plan Marked up-NA-NA-NA | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-08-24 | NA | 000000 | 2023-08-24 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 4.0 SSN Overall Area Layout and Elevations | NA | NA | NA | NA | NA | 4.0 SSN Overall Area Layout and Elevations-NA-NA-NA | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-08-24 | NA | 000000 | 2023-08-24 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 5.0 Soil Report | NA | NA | NA | NA | NA | 5.0 Soil Report-NA-NA-NA | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-08-24 | NA | 000000 | 2023-08-24 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8000_ST604 | NA | 131242-WST00-DR-8000_ST604 | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-11-07 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 1000_ST604 | NA | 131242-WST00-DR-1000_ST604 | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-11-07 | A1 | 000000&&000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 02 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604 | NA | 131242-WST02-DR-1001_ST604 | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604 | NA | 131242-WST02-DR-5001_ST604 | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604 | NA | 131242-WST02-DR-7000_ST604 | 2023-08-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-09-21 | 2023-09-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | APP | APP
000079 | 01 | Zora | CSA | NA | 1. C4B SSN Overall Piling Design Brief | NA | NA | NA | NA | NA | 1. C4B SSN Overall Piling Design Brief-NA-NA-NA | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-16 | 2023-10-17 | 1 | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | 2023-09-26 | NA | 000079 | 2023-09-26 | 01 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | C | 0001_ST604 | NA | 131242-WST02-CL-0001_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-26 | 2023-09-26 | NA | 000000 | 2023-09-26 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604 | NA | 131242-WST02-DR-1001_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604 | NA | 131242-WST02-DR-5001_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604 | NA | 131242-WST02-DR-7000_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8000_ST604 | NA | 131242-WST00-DR-8000_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-11-07 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-1000_ST604 | 2023-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-24 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-11-07 | A1 | 000000&&000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 02 | 3 | PEN | NAP | NAP
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-1000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-21 |  | Approved with Comments | YES | 2023-12-11 | NO | Overdue | 544 | 2024-08-16 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-11-07 | A1 | 000000&&000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604 | NA | 131242-WST02-DR-1001_ST604 | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-21 |  | Approved with Comments | YES | 2023-12-11 | NO | Overdue | 544 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604 | NA | 131242-WST02-DR-5001_ST604 | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-21 |  | Approved with Comments | YES | 2023-12-11 | NO | Overdue | 544 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604 | NA | 131242-WST02-DR-7000_ST604 | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-21 |  | Approved with Comments | YES | 2023-12-11 | NO | Overdue | 544 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8000_ST604 | NA | 131242-WST00-DR-8000_ST604 | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-21 |  | Approved with Comments | YES | 2023-12-11 | NO | Overdue | 544 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2023-11-07 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000080 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-0002 | 2023-08-25 | PAYMENT CLAIM NO.2 | Accepted. Please refer to S.O. Correspondence no. 48 dated 29 August 2023. | 2023-09-22 | 2023-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-01 | 2023-08-25 | 0 | 000060&&000080 | 2023-08-01, 2023-08-25 | 00 | 2 | PEN | APP | APP
000081 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 0 | 131242-WSW41-SP-0001 | 2023-08-28 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-09-25 |  | Approved with Comments | YES | 2023-10-13 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-08-28 | 2023-10-05 | 1 | 000081 | 2023-08-28, 2023-10-05 | 00, 01 | 2 | PEN | AWC | AWC
000081 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 1 | 131242-WSW41-SP-0001 | 2023-10-05 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.1: Approved | 2023-10-25 | 2023-10-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-08-28 | 2023-10-05 | 1 | 000081 | 2023-08-28, 2023-10-05 | 00, 01 | 2 | PEN | APP | APP
000082 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0006 | 0 | 131242-WSW41-MI-0006 | 2023-08-28 | BIM Bi-Weekly Meeting Minutes 0006_20230823 | For Information | 2023-09-25 | 2023-09-06 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-14 | 2023-11-15 | 0 | 000000&&000050&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | PEN | INF | INF
000083 | 00 | Zora | CSA | NA | 131242 | WSW41 | SK | S | 0001 | 0 | 131242-WSW41-SK-0001 | 2023-08-28 | Sidewide Pipe Rack GA and Reactions | Not Approved. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-10-06 | 9 | Not Approved | YES | 2023-10-26 | YES | Resubmitted |  |  |  | NA | "Sidewide Pipe Rack GA and Reactions" && "Time Lapse Camera Location" | 2023-08-28 | 2023-10-23 | 0 | 000083&&000136 | 2023-08-28, 2023-10-23 | 00 | 2 | PEN | NAP | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A | 131242-WSW41-DR-1000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-01 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-06-08 | A.1 | 000000&&000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1004_ST603 | NA | 131242-WSW41-DR-1004_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1007_ST603 | NA | 131242-WSW41-DR-1007_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1008_ST603 | NA | 131242-WSW41-DR-1008_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1009_ST603 | NA | 131242-WSW41-DR-1009_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1010_ST603 | NA | 131242-WSW41-DR-1010_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2000_ST603 | NA | 131242-WSW41-DR-2000_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2001_ST603 | NA | 131242-WSW41-DR-2001_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2002_ST603 | NA | 131242-WSW41-DR-2002_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3000_ST603 | NA | 131242-WSW41-DR-3000_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3001_ST603 | NA | 131242-WSW41-DR-3001_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5000_ST603 | NA | 131242-WSW41-DR-5000_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5001_ST603 | NA | 131242-WSW41-DR-5001_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5002_ST603 | NA | 131242-WSW41-DR-5002_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 8001_ST603 | NA | 131242-WSW41-DR-8001_ST603 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | Site wide PR Reactions for information | NA | NA | NA | NA | NA | Site wide PR Reactions for information-NA-NA-NA | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-01-25 |  | Not Approved | YES | 2024-02-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-01-13 | NA | 000000 | 2024-01-13 | 00 | 1 | PEN | NAP | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.1 | 131242-WSW41-DR-1000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-01 | 2024-05-02 | 21 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  | Rev 1 : Not Approved. | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-06-08 | A.1 | 000000&&000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1004_ST603 | NA | 131242-WSW41-DR-1004_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1007_ST603 | NA | 131242-WSW41-DR-1007_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1008_ST603 | NA | 131242-WSW41-DR-1008_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1009_ST603 | NA | 131242-WSW41-DR-1009_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1010_ST603 | NA | 131242-WSW41-DR-1010_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2000_ST603 | NA | 131242-WSW41-DR-2000_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2001_ST603 | NA | 131242-WSW41-DR-2001_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2002_ST603 | NA | 131242-WSW41-DR-2002_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3000_ST603 | NA | 131242-WSW41-DR-3000_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3001_ST603 | NA | 131242-WSW41-DR-3001_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5000_ST603 | NA | 131242-WSW41-DR-5000_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5001_ST603 | NA | 131242-WSW41-DR-5001_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5002_ST603 | NA | 131242-WSW41-DR-5002_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5003_ST603 | NA | 131242-WSW41-DR-5003_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5004_ST603 | NA | 131242-WSW41-DR-5004_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 8001_ST603 | NA | 131242-WSW41-DR-8001_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 0300_ST603 | NA | 131242-WSW41-DR-0300_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 0301_ST603 | NA | 131242-WSW41-DR-0301_ST603 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | CL | S | 1000_ST603 | 2 | 131242-WSW41-CL-1000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  | To clear technical comments first and Heng Peng to clear BIM comments. | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-06-08 | 2 | 000083 | 2024-06-08 | 03 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1000_ST603 | NA | 131242-WSW41-DR-1000_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-06-08 | A.1 | 000000&&000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1004_ST603 | NA | 131242-WSW41-DR-1004_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1007_ST603 | NA | 131242-WSW41-DR-1007_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1008_ST603 | NA | 131242-WSW41-DR-1008_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1009_ST603 | NA | 131242-WSW41-DR-1009_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1010_ST603 | NA | 131242-WSW41-DR-1010_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2000_ST603 | NA | 131242-WSW41-DR-2000_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2001_ST603 | NA | 131242-WSW41-DR-2001_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2002_ST603 | NA | 131242-WSW41-DR-2002_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3000_ST603 | NA | 131242-WSW41-DR-3000_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 3001_ST603 | NA | 131242-WSW41-DR-3001_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5000_ST603 | NA | 131242-WSW41-DR-5000_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5001_ST603 | NA | 131242-WSW41-DR-5001_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5002_ST603 | NA | 131242-WSW41-DR-5002_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5003_ST603 | NA | 131242-WSW41-DR-5003_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 5004_ST603 | NA | 131242-WSW41-DR-5004_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 8001_ST603 | NA | 131242-WSW41-DR-8001_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-06-08 | NA | 000000 | 2024-01-13, 2024-03-11, 2024-06-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 0300_ST603 | NA | 131242-WSW41-DR-0300_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 0301_ST603 | NA | 131242-WSW41-DR-0301_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-11 | 2024-06-08 | NA | 000000 | 2024-03-11, 2024-06-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 0302_ST603 | NA | 131242-WSW41-DR-0302_ST603 | 2024-06-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-08 | 2024-06-08 | NA | 000000 | 2024-06-08 | 00 | 1 | PEN | NAP | NAP
000084 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | S | 0002 | 0 | 131242-WSW41-VI-0002 | 2023-08-28 | Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd. | Approved | 2023-09-25 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | APP | APP
000085 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0002 | 0 | 131242-WSW41-SP-0002 | 2023-08-31 | Concrete Design Mix for ULT Test Pile C50/60 (Alliance) | Approved | 2023-09-28 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for ULT Test Pile C50/60 (Alliance) " | 2023-08-31 | 2023-08-31 | 0 | 000085 | 2023-08-31 | 00 | 1 | PEN | APP | APP
000086 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | Z | 0001 | 0 | 131242-WSW41-CL-0001 | 2023-08-31 | ECM Plan and Calculation | Approved | 2023-09-28 | 2023-10-04 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "ECM Plan and Calculation" && "Temporary Utilities for Contractor’s Site Office" | 2023-07-05 | 2023-08-31 | 0 | 000038&&000086 | 2023-07-05, 2023-08-31 | 00 | 2 | PEN | APP | APP
000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0001 | 0 | 131242-WSW41-MI-0001 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | PM | 0002 | NA | 131242-WSW41-MI-0002 | 2023-09-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-02 | 2023-09-06 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0002_20230628" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-13 | 2023-09-04 | 0 | 000000&&000047 | 2023-07-13, 2023-09-04 | 00 | 2 | PEN | INF | INF
000088 | 00 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 0 | 131242-WST02-VI-0001 | 2023-09-05 | Preliminary design and Vendor Approval for SSN Package | Rev 0: Not approved - Revise and Resubmit | 2023-10-03 | 2023-09-25 |  | Not Approved | YES | 2023-10-13 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
000088 | 01 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 1 | 131242-WST02-VI-0001 | 2023-10-05 | Preliminary design and Vendor Approval for SSN Package | Rev 1: Not approved - Revise and Resubmit Document not approved as requested by Contractor. | 2023-10-25 | 2023-10-23 |  | Not Approved | YES | 2023-11-10 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
000088 | 02 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 2 | 131242-WST02-VI-0001 | 2023-10-31 | Preliminary design and Vendor Approval for SSN Package | Rev 2: Approved with Comments, subject to clarification of comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-21 | 2023-11-08 |  | Approved with Comments | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | AWC | AWC
000088 | 03 | Joo kwan | Process | NA | 131242 | WST02 | VI | M | 0001 | 3 | 131242-WST02-VI-0001 | 2024-02-03 | Preliminary design and Vendor Approval for SSN Package | Rev 3: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-02-23 | 2024-04-29 | 44 | Approved with Comments | NO |  | YES |  |  |  | Rev 2: AWC | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | AWC | AWC
000089 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0007 | 0 | 131242-WSW41-MI-0007 | 2023-09-05 | Process & MEICA Meeting Minutes 0007_20230718 | For Information | 2023-10-03 | 2024-03-18 | 115 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | PEN | INF | INF
000090 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | D | 0001 | 0 | 131242-WSW41-VI-0001 | 2023-09-07 | Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq) | Approved | 2023-10-05 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | PEN | APP | APP
000091 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0002 | 0 | 131242-WSW41-RT-0002 | 2023-09-07 | Cable Detection Report | Approved with comments. Please refer to comment sheet for resubmission. | 2023-10-05 | 2023-09-25 |  | Approved with Comments | YES | 2023-10-13 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | AWC | AWC
000091 | 01 | Eng Bee | PMT | NA | Reply to Comment Sheet_#000091 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000091-NA-NA-NA | 2023-10-06 | Cable Detection Report | Approved | 2023-10-26 | 2023-10-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "Cable Detection Report" | 2023-10-06 | 2023-10-06 | NA | 000091 | 2023-10-06 | 01 | 1 | PEN | APP | APP
000092 | 00 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 0 | 131242-WSW41-SP-8001 | 2023-09-08 | Piping Material Specification | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-10-06 | 2023-09-25 |  | Approved with Comments | YES | 2023-10-13 | YES | Resubmitted |  |  |  | NA | "Piping Material Specification" | 2023-09-08 | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000092 | 01 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 1 | 131242-WSW41-SP-8001 | 2024-02-22 | Piping Material Specification | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-13 | 2024-04-17 | 23 | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  |  | Rev 0: AWC | NA | "Piping Material Specification" | 2023-09-08 | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000092 | 02 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 2 | 131242-WSW41-SP-8001 | 2024-08-07 | Piping Material Specification | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Piping Material Specification" | 2023-09-08 | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | PEN | APP | APP
000092 | 03 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 3 | 131242-WSW41-SP-8001 | 2024-12-13 | Piping Material Specification | Rev 3: Approved | 2025-01-03 | 2025-01-20 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "Piping Material Specification" | 2023-09-08 | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | PEN | APP | APP
000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | 0 | 131242-WSW41-DR-6000 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 35 | Approved with Comments | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2023-09-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-06 | 2023-11-27 | 35 | Approved with Comments | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | Pipeline - All_Data Report | NA | NA | NA | NA | NA | Pipeline - All_Data Report-NA-NA-NA | 2023-09-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-06 | 2023-11-27 | 35 | Approved with Comments | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2023-09-08 | NA | 000000 | 2023-09-08 | 00 | 1 | PEN | AWC | AWC
000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6000 | B | 131242-WSW41-DR-6000 | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | 21 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  | 2024-07-31 | Rev 0: AWC | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2024-03-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-04-25 | 21 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | C | 131242-WSW41-DR-6000 | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2024-08-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | D | 131242-WSW41-DR-6000 | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | 13 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | 2025-02-28 | comments received on 14 Feb | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2024-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-27 | 2025-01-16 | 13 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-6000 | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | 18 | Approved with Comments | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2025-03-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-03 | 2025-04-30 | 18 | Approved with Comments | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-6000 | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 |  | Awaiting S.O.'s response | [7 empty] | NA | "Piperack P&IDs" | 2023-09-08 | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | P | 6001 | NA | 131242-WSW41-DR-6001 | 2026-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-03-16 | 2025-04-30 |  | Awaiting S.O.'s response | [7 empty] | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-08 | 2026-02-24 | NA | 000000 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00 | 6 | PEN | PEN | PEN
000094 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0002 | 0 | 131242-WSW41-CD-0002 | 2023-09-08 | Submission Of BIM Coordination VCM Model (Aug – 2023) | For Information | 2023-10-06 | 2023-09-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Aug – 2023)" | 2023-09-08 | 2023-09-08 | 0 | 000094 | 2023-09-08 | 00 | 1 | PEN | INF | INF
000095 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0007 | 0 | 131242-WSW41-MI-0007 | 2023-09-11 | BIM Bi-Weekly Meeting Minutes 0007_20230906 | For Information | 2023-10-09 | 2023-10-03 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | PEN | INF | INF
000096 | 00 | Darren | Piping/ BS | NA | 131242 | WST02 | CL | B | 0002 | 0 | 131242-WST02-CL-0002 | 2023-09-12 | Engineering Calculation Report For Fire Hydrant Pipe | Rev 0: Rejected as requested by contractor. | 2023-10-10 | 2023-11-10 | 23 | Rejected | NO |  | YES |  |  |  | Kindly refer to Submittal 000193 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | PEN | REJ | REJ
000097 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0003 | 0 | 131242-WST02-CL-0003 | 2023-09-12 | Engineering Calculation Report For Potable Water Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-10-10 | 2023-11-10 | 23 | Not Approved | YES | 2023-12-01 | YES | Resubmitted |  |  |  | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | PEN | NAP | NAP
000097 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 1 | 131242-WST02-CL-8000 | 2024-05-30 | Engineering Calculation Report For Potable Water Pipe | Rev 1: Not approved - Revise and Resubmit | 2024-06-20 | 2024-07-09 | 13 | Not Approved | YES | 2024-07-29 | YES | Resubmitted |  | 2024-08-09 | To check with C2D for resubmission | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000097 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 2 | 131242-WST02-CL-8000 | 2024-10-17 | Engineering Calculation Report For Potable Water Pipe | Rev 2: Not approved - Revise and Resubmit | 2024-11-07 | 2024-11-25 | 12 | Not Approved | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000097 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 3 | 131242-WST02-CL-8000 | 2025-02-18 | Engineering Calculation Report For Potable Water Pipe | Rev3: Approved | 2025-03-10 | 2025-03-25 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | APP | APP
000098 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 0 | 131242-WSW41-RT-0004 | 2023-09-13 | C4B Monthly Progress Report Number No.04 (08/23) | Rev. 0 - Not Approved need to re-submit (see attached comment sheet) | 2023-10-11 | 2023-09-20 |  | Not Approved | YES | 2023-10-10 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-09-13 | 2023-10-04 | 1 | 000098 | 2023-09-13, 2023-10-04 | 00, 01 | 2 | PEN | NAP | NAP
000098 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 1 | 131242-WSW41-RT-0004 | 2023-10-04 | C4B Monthly Progress Report Number No.04 (08/23) | Approved | 2023-10-24 | 2023-10-06 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-09-13 | 2023-10-04 | 1 | 000098 | 2023-09-13, 2023-10-04 | 00, 01 | 2 | PEN | APP | APP
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | 0 | 131242-WSW41-DR-5002 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "C4B Sitewide Piping GA Drawing" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2026-01-19 | 0 | 000000&&000099 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5003 | NA | 131242-WSW41-DR-5003 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2026-01-19 | NA | 000000 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5004 | NA | 131242-WSW41-DR-5004 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5005 | NA | 131242-WSW41-DR-5005 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5006 | NA | 131242-WSW41-DR-5006 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5007 | NA | 131242-WSW41-DR-5007 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5008 | NA | 131242-WSW41-DR-5008 | 2023-09-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-11 | 2023-11-27 | 32 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | NAP | NAP
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5001 | A1 | 131242-WSW41-DR-5001 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-01 | 2024-05-02 | 21 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 | Submitted | Under M2 submission (Shall be Submitted After M3 WT) | NA | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2026-01-19 | A1 | 000000&&000099 | 2024-03-11, 2026-01-19 | 01, NA | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5002 | NA | 131242-WSW41-DR-5002 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "C4B Sitewide Piping GA Drawing" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2026-01-19 | 0 | 000000&&000099 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5003 | NA | 131242-WSW41-DR-5003 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2026-01-19 | NA | 000000 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5004 | NA | 131242-WSW41-DR-5004 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5005 | NA | 131242-WSW41-DR-5005 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5006 | NA | 131242-WSW41-DR-5006 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5007 | NA | 131242-WSW41-DR-5007 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5008 | NA | 131242-WSW41-DR-5008 | 2024-03-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-05-02 | 15 | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-13 | 2024-03-11 | NA | 000000 | 2023-09-13, 2024-03-11 | 00 | 2 | PEN | AWC | AWC
000100 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0001 | 0 | 131242-WSD11-PO-0001 | 2023-09-14 | Unpriced PO for THP Package (Cambi) | For Information | 2023-10-12 | 2023-11-27 | 31 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | PEN | INF | INF
000101 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0005 | 0 | 131242-WSW41-PP-0005 | 2023-09-14 | Heat Stress Prevention Program | Approved | 2023-10-12 | 2023-09-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Heat Stress Prevention Program" | 2023-09-14 | 2023-09-14 | 0 | 000101 | 2023-09-14 | 00 | 1 | PEN | APP | APP
000102 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 0 | 131242-WSW41-VI-0011 | 2023-09-18 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 25 | Approved with Comments | YES | 2023-12-11 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | PEN | AWC | AWC
000102 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 1 | 131242-WSW41-VI-0011 | 2024-01-04 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-24 | 2024-02-15 | 15 | Approved with Comments | YES | 2024-03-06 | YES | Resubmitted |  |  | Drawings are ready to re-submit. Pending update data sheet from INGERSOLL-RAND. | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | PEN | AWC | AWC
000102 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 2 | 131242-WSW41-VI-0011 | 2024-06-07 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 2: Approved | 2024-06-28 | 2024-07-12 | 10 | Approved | NO |  | YES |  |  |  | R1_AWC | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | PEN | APP | APP
000103 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 0 | 131242-WSW41-VI-0004 | 2023-09-18 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 25 | Approved with Comments | YES | 2023-12-11 | YES | Resubmitted |  | 2025-02-20 |  | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | PEN | AWC | AWC
000103 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 1 | 131242-WSW41-VI-0004 | 2025-05-30 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev1: Approved | 2025-06-19 | 2025-08-01 | 31 | Approved | NO |  | YES |  |  | 2025-02-20 |  | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | PEN | APP | APP
000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0008 | 0 | 131242-WSW41-MI-0008 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | 105 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | P | 0009 | NA | 131242-WSW41-MI-0009 | 2023-09-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-17 | 2024-03-18 | 105 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Meeting Minutes 0009_20240220" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-07 | 2024-03-01 | 0 | 000000&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | PEN | INF | INF
000105 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0012 | 0 | 131242-WSW41-LT-0012 | 2023-09-19 | CV of Team Member (WSHO) | Approved | 2023-10-17 | 2023-10-18 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (WSHO)" | 2023-09-19 | 2023-09-19 | 0 | 000105 | 2023-09-19 | 00 | 1 | PEN | APP | APP
000106 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0004 | 0 | 131242-WSW41-PS-0004 | 2023-09-21 | Monthly Progress Presentation No. 04 (0823) | For Information | 2023-10-19 | 2023-09-25 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for November 2023" && "Monthly Progress Presentation No. 04 (0823)" | 2023-09-21 | 2024-03-12 | 0 | 000106&&000354 | 2023-09-21, 2024-03-12 | 00 | 2 | PEN | INF | INF
000107 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 0 | 131242-WSW41-VI-0006 | 2023-09-25 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Approved with Comments. To revise and resubmit. Refer to comments file. | 2023-10-23 | 2023-10-16 |  | Approved with Comments | YES | 2023-11-03 | YES | Resubmitted |  | 2024-07-31 | In Progress | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | AWC | AWC
000107 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 1 | 131242-WSW41-VI-0006 | 2024-07-31 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Rev 1: Approved | 2024-08-21 | 2024-09-02 | 8 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | APP | APP
000108 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | Superceded | 131242-WSW41-CT-0001 | 2023-09-27 | On-Demand Bond for THP System | Rev(0): Rejected as requested by Contractor. Note Contractor need to attach a transmittal signed by PUB to the said submittal. | 2023-10-25 | 2023-10-02 |  | Rejected | YES | 2023-10-20 | YES | Resubmitted |  |  |  | NA | "On-Demand Bond for THP System" | 2023-09-27 | 2023-10-03 | 0 | 000108 | 2023-09-27, 2023-10-03 | 00, 01 | 2 | PEN | REJ | REJ
000108 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | 0 | 131242-WSW41-CT-0001 | 2023-10-03 | On-Demand Bond for THP System | Approved. | 2023-10-23 | 2023-10-09 |  | Approved | NO |  | YES |  |  |  |  | NA | "On-Demand Bond for THP System" | 2023-09-27 | 2023-10-03 | 0 | 000108 | 2023-09-27, 2023-10-03 | 00, 01 | 2 | PEN | APP | APP
000109 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0010 | 0 | 131242-WSW41-MI-0010 | 2023-09-27 | CSA Meeting Minutes 0010_20230802 | For Information | 2023-10-25 | 2023-10-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-27 | 2024-04-04 | 0 | 000000&&000109&&000126&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | PEN | INF | INF
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | 0 | 131242-WST00-DR-0001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 | 2024-07-18 | MEICA layout released on 29/02/2024. Updating as per latest Layout changes of SSN-SH-002 area with Pump pit. Tenwit updating In-Progress. | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 0002_ST606 | NA | 131242-WST00-DR-0002_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 0003_ST606 | NA | 131242-WST00-DR-0003_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST606 | NA | 131242-WST02-DR-1006_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST606 | NA | 131242-WST02-DR-1007_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST606 | NA | 131242-WST02-DR-1008_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1013_ST606 | NA | 131242-WST02-DR-1013_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST606 | NA | 131242-WST02-DR-3000_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3001_ST606 | NA | 131242-WST02-DR-3001_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5000_ST606 | NA | 131242-WST02-DR-5000_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST606 | NA | 131242-WST02-DR-5001_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5002_ST606 | NA | 131242-WST02-DR-5002_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5005_ST606 | NA | 131242-WST02-DR-5005_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST606 | NA | 131242-WST02-DR-7000_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST606 | NA | 131242-WST02-DR-7001_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST606 | NA | 131242-WST02-DR-7002_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST606 | NA | 131242-WST02-DR-8001_ST606 | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-18 |  | Not Approved | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0003 | 0 | 131242-WSW41-PC-0003 | 2023-09-29 | PAYMENT CLAIM NO.3 | Approved | 2023-10-27 | 2023-10-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "PAYMENT CLAIM NO.3" | 2023-09-29 | 2023-09-29 | 0 | 000111 | 2023-09-29 | 00 | 1 | PEN | APP | APP
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-1_URA | 0 | 131242-WST02-DR-3D-1_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SSN URA Submission" | 2023-09-29 | 2023-09-29 | 0 | 000112 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3D-2_URA | NA | 131242-WST02-DR-3D-2_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1000_URA | NA | 131242-WST02-DR-1000_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN URA Submission" | 2023-09-29 | 2023-11-07 | A1 | 000000&&000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_URA | NA | 131242-WST02-DR-1001_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_URA | NA | 131242-WST02-DR-1002_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_URA | NA | 131242-WST02-DR-1003_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_URA | NA | 131242-WST02-DR-1004_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_URA | NA | 131242-WST02-DR-1006_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_URA | NA | 131242-WST02-DR-1009_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_URA | NA | 131242-WST02-DR-2000_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_URA | NA | 131242-WST02-DR-2001_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_URA | NA | 131242-WST02-DR-2002_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_URA | NA | 131242-WST02-DR-2003_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_URA | NA | 131242-WST02-DR-2007_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_URA | NA | 131242-WST02-DR-3000_URA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf-NA-NA-NA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx-NA-NA-NA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | GFA DWG Supporting Docs | NA | NA | NA | NA | NA | GFA DWG Supporting Docs-NA-NA-NA | 2023-09-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-10-27 | 2023-10-17 |  | Not Approved | YES | 2023-11-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-09-29 | NA | 000000 | 2023-09-29 | 00 | 1 | PEN | NAP | NAP
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-1000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-06 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN URA Submission" | 2023-09-29 | 2023-11-07 | A1 | 000000&&000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_URA | NA | 131242-WST02-DR-1001_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_URA | NA | 131242-WST02-DR-1002_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_URA | NA | 131242-WST02-DR-1003_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_URA | NA | 131242-WST02-DR-1004_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_URA | NA | 131242-WST02-DR-1006_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_URA | NA | 131242-WST02-DR-1009_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_URA | NA | 131242-WST02-DR-2000_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_URA | NA | 131242-WST02-DR-2001_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_URA | NA | 131242-WST02-DR-2002_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_URA | NA | 131242-WST02-DR-2003_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_URA | NA | 131242-WST02-DR-2007_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_URA | NA | 131242-WST02-DR-3000_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9000_URA | NA | 131242-WST02-DR-9000_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-11-07 | NA | 000000 | 2023-10-17, 2023-11-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9001_URA | NA | 131242-WST02-DR-9001_URA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-11-07 | NA | 000000 | 2023-10-17, 2023-11-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | S000112.0_Reply_2023 10 17 | NA | NA | NA | NA | NA | S000112.0_Reply_2023 10 17-NA-NA-NA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-10-17 | NA | 000000 | 2023-10-17 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | Supporting Docs | NA | NA | NA | NA | NA | Supporting Docs-NA-NA-NA | 2023-10-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-10-17 | NA | 000000 | 2023-10-17 | 00 | 1 | PEN | AWC | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-1000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 | 2024-08-16 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN URA Submission" | 2023-09-29 | 2023-11-07 | A1 | 000000&&000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_URA | NA | 131242-WST02-DR-1001_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_URA | NA | 131242-WST02-DR-1002_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_URA | NA | 131242-WST02-DR-1003_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_URA | NA | 131242-WST02-DR-1004_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_URA | NA | 131242-WST02-DR-1006_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_URA | NA | 131242-WST02-DR-1009_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_URA | NA | 131242-WST02-DR-2000_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_URA | NA | 131242-WST02-DR-2001_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_URA | NA | 131242-WST02-DR-2002_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_URA | NA | 131242-WST02-DR-2003_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_URA | NA | 131242-WST02-DR-2007_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_URA | NA | 131242-WST02-DR-3000_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2023-11-07 | NA | 000000 | 2023-09-29, 2023-10-17, 2023-11-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9000_URA | NA | 131242-WST02-DR-9000_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-11-07 | NA | 000000 | 2023-10-17, 2023-11-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9001_URA | NA | 131242-WST02-DR-9001_URA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-17 | 2023-11-07 | NA | 000000 | 2023-10-17, 2023-11-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | S000112.1_Reply_2023 10 17 | NA | NA | NA | NA | NA | S000112.1_Reply_2023 10 17-NA-NA-NA | 2023-11-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-06 | 2023-11-23 |  | Approved with Comments | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-07 | 2023-11-07 | NA | 000000 | 2023-11-07 | 00 | 1 | PEN | AWC | AWC
000113 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | E | 0001 | 0 | 131242-WSW41-MS-0001 | 2023-10-04 | MSRA, SWP for Soil Resistivity Test | Approved with Comments | 2023-11-01 | 2023-10-13 |  | Approved with Comments | YES | 2023-11-02 | NO | Overdue | 570 |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | AWC | AWC
000114 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0008 | 0 | 131242-WSW41-MI-0008 | 2023-10-05 | BIM Bi-Weekly Meeting Minutes 0008_20230920 | For Information | 2023-11-02 | 2023-10-16 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | PEN | INF | INF
000115 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 0 | 131242-WSW41-PP-0002 | 2023-10-05 | Project Control Plan | Rev. 0 - Approved with comments, need to re-submit (refer comment sheet) | 2023-11-02 | 2023-10-27 |  | Approved with Comments | YES | 2023-11-17 | YES | Resubmitted |  |  |  | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | PEN | AWC | AWC
000115 | 01 | Stanley | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 1 | 131242-WSW41-PP-0002 | 2023-11-10 | Project Control Plan | Rev. 1 - Approved. | 2023-12-01 | 2023-11-15 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | PEN | APP | APP
000116 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0002 | 0 | 131242-WSW41-CN-0002 | 2023-10-06 | Proposed change of Manufacturer for SSN Aeration blowers | Rejected as CES requested as No RFC is needed according to the discussion with S.O. | 2023-11-03 | 2023-10-25 |  | Rejected | YES | 2023-11-15 | YES | Resubmitted |  |  |  | NA | "Proposed change of Manufacturer for SSN Aeration blowers" && "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | 2023-10-06 | 2025-01-13 | 0 | 000116&&000973 | 2023-10-06, 2025-01-13 | 00 | 2 | PEN | REJ | REJ
000117 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 0 | 131242-WSW41-CN-0001 | 2023-10-06 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Rev 0: Not approved - Revise and Resubmit | 2023-11-03 | 2023-11-28 | 16 | Not Approved | YES | 2023-12-18 | YES | Resubmitted |  |  |  | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | NAP | NAP
000117 | 01 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 1 | 131242-WSW41-CN-0001 | 2023-12-12 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-03 | 2024-01-29 | 18 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | AWC | AWC
000118 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 0 | 131242-WSW41-MS-0004 | 2023-10-06 | MSRA, SWP for Bored Piling Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-18 |  | Approved with Comments | YES | 2023-11-07 | YES | Resubmitted |  |  |  | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | PEN | AWC | AWC
000118 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 1 | 131242-WSW41-MS-0004 | 2023-11-01 | MSRA, SWP for Bored Piling Work | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-22 | 2023-12-01 | 7 | Approved with Comments | YES | 2023-12-21 | NO | Overdue | 536 |  |  | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | PEN | AWC | AWC
000119 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0005 | 0 | 131242-WSW41-MS-0005 | 2023-10-06 | MSRA, SWP for Site Set-Up & Associated Works (Seong) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-19 |  | Approved with Comments | YES | 2023-11-08 | NO | Overdue | 566 |  |  | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | PEN | AWC | AWC
000120 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-0003 | 2023-10-06 | Milestone 1.1 (Sidewide piperack) | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-11-03 | 2024-03-28 | 100 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-06 | 2023-10-10 | 0 | 000120&&000121 | 2023-10-06, 2023-10-10 | 00 | 2 | PEN | AWC | AWC
000120 | 01 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 0 | 131242-WSW41-CD-0028 | 2024-05-27 | Milestone 1.2 Sitewide Pipe Rack | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 |  | Not Approved | YES | 2024-06-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 Sitewide Pipe Rack" | 2024-05-27 | 2024-06-05 | 1 | 000120 | 2024-05-27, 2024-06-05 | 01, 02 | 2 | PEN | NAP | NAP
000120 | 02 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 1 | 131242-WSW41-CD-0028 | 2024-06-05 | Milestone 1.2 Sitewide Pipe Rack | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 7 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 Sitewide Pipe Rack" | 2024-05-27 | 2024-06-05 | 1 | 000120 | 2024-05-27, 2024-06-05 | 01, 02 | 2 | PEN | AWC | AWC
000120 | 03 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-0042 | 2024-08-24 | Milestone 2 Sitewide Pipe Rack | Rev3: Not Approved, as requested by contractor. | 2024-09-12 | 2024-10-01 | 13 | Rejected | YES | 2024-10-21 | YES | Resubmitted |  |  |  | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | PEN | REJ | REJ
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-0042 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 1000 | NA | 131242-WSW41-DR-1000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 3000 | NA | 131242-WSW41-DR-3000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 1000 | NA | 131242-WSW41-DR-1000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3000 | NA | 131242-WSW41-DR-3000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3001 | NA | 131242-WSW41-DR-3001 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3002 | NA | 131242-WSW41-DR-3002 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3003 | NA | 131242-WSW41-DR-3003 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3004 | NA | 131242-WSW41-DR-3004 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3005 | NA | 131242-WSW41-DR-3005 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4000 | NA | 131242-WSW41-DR-4000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4001 | NA | 131242-WSW41-DR-4001 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4002 | NA | 131242-WSW41-DR-4002 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4003 | NA | 131242-WSW41-DR-4003 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4004 | NA | 131242-WSW41-DR-4004 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4005 | NA | 131242-WSW41-DR-4005 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 8000 | NA | 131242-WSW41-DR-8000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | NAP | NAP
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-0042 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 1000 | NA | 131242-WSW41-DR-1000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 3000 | NA | 131242-WSW41-DR-3000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 1000 | NA | 131242-WSW41-DR-1000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3000 | NA | 131242-WSW41-DR-3000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3001 | NA | 131242-WSW41-DR-3001 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3002 | NA | 131242-WSW41-DR-3002 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3003 | NA | 131242-WSW41-DR-3003 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3004 | NA | 131242-WSW41-DR-3004 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 3005 | NA | 131242-WSW41-DR-3005 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-04-07 | NA | 000000 | 2024-10-05, 2025-02-26, 2025-04-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4000 | NA | 131242-WSW41-DR-4000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4001 | NA | 131242-WSW41-DR-4001 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4002 | NA | 131242-WSW41-DR-4002 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4003 | NA | 131242-WSW41-DR-4003 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4004 | NA | 131242-WSW41-DR-4004 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 4005 | NA | 131242-WSW41-DR-4005 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 8000 | NA | 131242-WSW41-DR-8000 | 2025-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2025-02-26 | NA | 000000 | 2024-10-05, 2025-02-26 | 00 | 2 | PEN | AWC | AWC
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 1 | 131242-WSW41-CD-0042 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 67 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | E | 1130 | NA | 131242-WSW41-DR-1130 | 2025-10-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-28 | 2026-01-30 | 67 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-10-08 | 2025-10-08 | NA | 000000 | 2025-10-08 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | E | 3000 | NA | 131242-WSW41-DR-3000 | 2025-10-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-28 | 2026-01-30 | 67 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | AWC | AWC
000121 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-0003 | 2023-10-10 | Submission Of BIM Coordination VCM Model (Sept – 2023) | For Information | 2023-11-07 | 2023-10-23 |  | For Information | NO |  | YES |  |  |  |  | NA | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-06 | 2023-10-10 | 0 | 000120&&000121 | 2023-10-06, 2023-10-10 | 00 | 2 | PEN | INF | INF
000122 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0006 | 0 | 131242-WSW41-MS-0006 | 2023-10-10 | MSRA, SWP for Erection of Site Office (Cape) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-07 | 2023-10-18 |  | Approved with Comments | YES | 2023-11-07 | NO | Overdue | 567 |  |  | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | PEN | AWC | AWC
000123 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0006 | 0 | 131242-WSW41-PP-0006 | 2023-10-10 | Traffic Management Plan | Approved | 2023-11-07 | 2023-10-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "Traffic Management Plan " | 2023-10-10 | 2023-10-10 | 0 | 000123 | 2023-10-10 | 00 | 1 | PEN | APP | APP
000124 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | PP | PM | 0003 | 0 | 131242-WSW41-PP-0003 | 2023-10-10 | Project Execution Plan | Rev. 0 - Not Approved - need to re-submit (refer comment sheet) | 2023-11-07 | 2023-10-27 |  | Not Approved | YES | 2023-11-17 | NO | Overdue | 560 |  |  | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | PEN | NAP | NAP
000125 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0011 | 0 | 131242-WSW41-VI-0011 | 2023-10-11 | Vendor Approval of UXO Survey – EXPLOMO | Approved | 2023-11-08 | 2023-10-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | PEN | APP | APP
000126 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0010 | 0 | 131242-WSW41-MI-0010 | 2023-10-12 | Process & MEICA Meeting Minutes 0010_20230928 | For Information | 2023-11-09 | 2024-03-18 | 88 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-27 | 2024-04-04 | 0 | 000000&&000109&&000126&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | PEN | INF | INF
000127 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0005 | 0 | 131242-WSW41-RT-0005 | 2023-10-14 | C4B Monthly Progress Report Number No.05 (09/23) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-10 | 2023-10-27 |  | Not Approved | YES | 2023-11-17 | NO | Overdue | 560 |  |  | NA | "C4B Monthly Progress Report Number No.05 (09/23)" | 2023-10-14 | 2023-10-14 | 0 | 000127 | 2023-10-14 | 00 | 1 | PEN | NAP | NAP
000128 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A | 131242-WST00-DR-8001_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2023-10-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-14 | 2023-11-08 |  | Not Approved | YES | 2023-11-29 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000128 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | 1 | 131242-WST00-DR-8001_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-19 | 2024-02-14 | 17 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610 | NA | 131242-WST02-DR-3001_ST610 | 2023-12-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-29 | 2024-02-14 | 11 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-29 | 2024-07-11 | NA | 000000 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 5 | PEN | NAP | NAP
000128 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A.1 | 131242-WST00-DR-8001_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610 | NA | 131242-WST02-DR-3001_ST610 | 2024-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-29 | 2024-07-11 | NA | 000000 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 5 | PEN | NAP | NAP
000128 | 03 | Zora | CSA | NA | 131242 | NA | NA | NA | S# 128 Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-S# 128 Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  | To close after addressing the comments of S#475 . Zora to follow up with Grace for JMH calculation | NA | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-06-12 | 2024-06-12 | NA | 000128 | 2024-06-12 | 03 | 1 | PEN | NAP | NAP
000128 | 04 | Aaron | CSA | NA | 131242 | WST02 | NA | C | S# 128 Cmt Sheet Reply 2024 10 08 | NA | 131242-WST02-NA-S# 128 Cmt Sheet Reply 2024 10 08 | 2024-10-08 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-28 | 2024-10-29 | 1 | Not Approved | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-10-08 | 2024-10-08 | NA | 000128 | 2024-10-08 | 04 | 1 | PEN | NAP | NAP
000129 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0007 | 0 | 131242-WSW41-MS-0007 | 2023-10-17 | MSRA, SWP for Erection of Site Office (UXO) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 |  | Approved with Comments | YES | 2023-11-22 | NO | Overdue | 557 |  |  | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | PEN | AWC | AWC
000130 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0004 | 0 | 131242-WSW41-PC-0004 | 2023-10-18 | PAYMENT CLAIM NO.4 | Rev(0): Approved. Please refer to S.O. correspondence no. 73 dated 20 Oct 2023. | 2023-11-16 | 2023-10-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "PAYMENT CLAIM NO.4" | 2023-10-18 | 2023-10-18 | 0 | 000130 | 2023-10-18 | 00 | 1 | PEN | APP | APP
000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0011 | 0 | 131242-WSW41-MI-0011 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | 1 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0012 | NA | 131242-WSW41-MI-0012 | 2023-10-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-16 | 2023-11-17 | 1 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "Monthly Progress Meeting Minutes 0012_20240521" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-18 | 2024-06-04 | 0 | 000000&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | PEN | INF | INF
000132 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 0 | 131242-WSW41-SP-0003 | 2023-10-19 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-17 | 2023-11-17 |  | Approved with Comments | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-10-19 | 2023-12-21 | 1 | 000132 | 2023-10-19, 2023-12-21 | 00, 01 | 2 | PEN | AWC | AWC
000132 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 1 | 131242-WSW41-SP-0003 | 2023-12-21 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Approved | 2024-01-12 | 2024-01-15 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-10-19 | 2023-12-21 | 1 | 000132 | 2023-10-19, 2023-12-21 | 00, 01 | 2 | PEN | APP | APP
000133 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 0 | 131242-WSD11-BQ-0001 | 2023-10-20 | THP Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-20 | 2023-11-27 | 5 | Approved with Comments | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000133 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 1 | 131242-WSD11-BQ-0001 | 2024-04-26 | THP Equipment List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-17 | 2024-05-27 | 5 | Approved with Comments | YES | 2024-06-14 | NO | Overdue | 417 | 2024-07-31 |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000134 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0012 | 0 | 131242-WSW41-VI-0012 | 2023-10-23 | Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-11-17 |  | Approved with Comments | YES | 2023-12-07 | NO | Overdue | 546 |  |  | NA | "Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD." | 2023-10-23 | 2023-10-23 | 0 | 000134 | 2023-10-23 | 00 | 1 | PEN | AWC | AWC
000135 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 0 | 131242-WSW41-VI-0002 | 2023-10-23 | Preliminary Design and Vendor Approval of Blower (Robuschi) | Rev 0: Not approved - Revise and Resubmit | 2023-11-21 | 2023-11-27 | 4 | Not Approved | YES | 2023-12-15 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | NAP | NAP
000135 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 1 | 131242-WSW41-VI-0002 | 2023-12-26 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-16 | 2024-01-29 | 9 | Approved with Comments | YES | 2024-02-19 | YES | Resubmitted |  |  | To re-submit after vendor provide update data sheet and drawing. Kick-off meeting done on 26 March | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | AWC | AWC
000135 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 2 | 131242-WSW41-VI-0002 | 2024-06-25 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-07-15 | 2024-07-31 | 12 | Approved with Comments | NO |  | YES |  |  |  | R1_AWC | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | AWC | AWC
000136 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SK | Z | 0001 | 0 | 131242-WSW41-SK-0001 | 2023-10-23 | Time Lapse Camera Location | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-12-18 | 19 | Approved with Comments | YES | 2024-01-09 | NO | Overdue | 525 |  |  | NA | "Sidewide Pipe Rack GA and Reactions" && "Time Lapse Camera Location" | 2023-08-28 | 2023-10-23 | 0 | 000083&&000136 | 2023-08-28, 2023-10-23 | 00 | 2 | PEN | AWC | AWC
000137 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0005 | 0 | 131242-WSW41-PS-0005 | 2023-10-25 | Monthly Progress Presentation No. 05 (0923) | For Information | 2023-11-23 | 2023-10-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for December 2023" && "Monthly Progress Presentation No. 05 (0923)" | 2023-10-25 | 2024-03-12 | 0 | 000137&&000355 | 2023-10-25, 2024-03-12 | 00 | 2 | PEN | INF | INF
000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0003 | 0 | 131242-WSW41-MI-0003 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0003_20230712" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-07-18 | 2023-10-25 | 0 | 000052&&000138 | 2023-07-18, 2023-10-25 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | PM | 0004 | NA | 131242-WSW41-MI-0004 | 2023-10-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-23 | 2023-10-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-15 | 2023-10-25 | 0 | 000000&&000073 | 2023-08-15, 2023-10-25 | 00 | 2 | PEN | INF | INF
000139 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 0 | 131242-WSW41-VI-0003 | 2023-10-25 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-11-23 | 2023-12-22 | 21 | Approved with Comments | YES | 2024-01-15 | YES | Resubmitted |  | 2024-07-26 | Yibo to check with JK for process data. Vendor need to provide revised design data and layout drawings once Process confirmed. | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000139 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 1 | 131242-WSW41-VI-0003 | 2024-11-06 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 1: Approved | 2024-11-26 | 2025-03-04 | 66 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | APP | APP
000140 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0001 | 0 | 131242-WSD11-PS-0001 | 2023-10-25 | Thermal Hydrolysis Process Presentation | For Information | 2023-11-23 | 2023-11-27 | 2 | For Information | NO |  | YES |  |  |  |  | NA | "Thermal Hydrolysis Process Presentation" | 2023-10-25 | 2023-10-25 | 0 | 000140 | 2023-10-25 | 00 | 1 | PEN | INF | INF
000141 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 0 | 131242-WSD11-CH-0001 | 2023-10-25 | Process Functional Description | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-23 | 41 | Approved with Comments | YES | 2024-02-13 | YES | Resubmitted |  |  |  | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000141 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 1 | 131242-WSD11-CH-0001 | 2024-04-02 | Process Functional Description | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-04-26 | 3 | Approved with Comments | YES | 2024-05-17 | YES | Resubmitted |  | 2024-08-30 | R0: AWC | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000141 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 2 | 131242-WSD11-CH-0001 | 2024-07-28 | Process Functional Description | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 9 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  |  |  | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000141 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 3 | 131242-WSD11-CH-0001 | 2024-09-30 | Process Functional Description | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 |  |  | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000142 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 0 | 131242-WSD11-CH-0002 | 2023-10-25 | Process Design Basis | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-15 | 35 | Approved with Comments | YES | 2024-02-02 | YES | Resubmitted |  |  |  | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000142 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 1 | 131242-WSD11-CH-0002 | 2024-03-20 | THP Process Design Basis | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-26 | 11 | Approved with Comments | YES | 2024-05-17 | YES | Resubmitted |  | 2024-08-30 | R0: AWC | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000142 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 2 | 131242-WSD11-CH-0002 | 2024-07-28 | THP Process Design Basis | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 9 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  |  |  | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000142 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 3 | 131242-WSD11-CH-0002 | 2024-11-04 | THP Process Design Basis | Rev 3: Approved with Comments. No active comments on the document. Resubmittal is required if there are any changes during detail engineering. No resubmittal at the moment. | 2024-11-22 | 2025-01-02 | 27 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000143 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-7001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 40 | Not Approved | YES | 2024-02-13 | YES | Resubmitted |  |  |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | Z | 0001 | NA | 131242-WST00-DR-0001 | 2023-10-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-24 | 2024-01-23 | 40 | Not Approved | YES | 2024-02-13 | YES | Resubmitted |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | DGN FILES | WSD11 | DR | P | 7001 | NA | DGN FILES-WSD11-DR-7001 | 2023-10-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-24 | 2024-01-23 | 40 | Not Approved | YES | 2024-02-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-10-26 | 2023-10-26 | NA | 000000 | 2023-10-26 | 00 | 1 | PEN | NAP | NAP
000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-7001 | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-08 | 2024-03-28 |  | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  | 2024-07-31 |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 7002 | NA | 131242-WSD11-DR-7002 | 2024-03-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-17 | 2024-03-28 |  | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | AWC | AWC
000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | B | 131242-WSD11-DR-7001 | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | 19 | Approved with Comments | YES | 2024-10-30 | NO | Overdue | 321 |  |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 7002 | NA | 131242-WSD11-DR-7002 | 2024-08-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-13 | 2024-10-10 | 19 | Approved with Comments | YES | 2024-10-30 | NO | Overdue | 321 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | AWC | AWC
000144 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 0 | 131242-WSW41-QA-0001 | 2023-10-27 | Inspection Test Plan for Earthwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | NAP | NAP
000144 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 1 | 131242-WSW41-QA-0001 | 2023-12-21 | Inspection Test Plan for Earthwork | Approved | 2024-01-12 | 2024-01-15 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | APP | APP
000145 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 0 | 131242-WSW41-QA-0002 | 2023-10-27 | Inspection Test Plan for Bored piling work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000145 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-0002 | 2023-12-21 | Inspection Test Plan for Bored piling work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 1 | Approved with Comments | YES | 2024-02-02 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000145 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-0002 | 2024-01-29 | Inspection Test Plan for Bored piling work | Approved | 2024-02-19 | 2024-02-21 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000146 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 0 | 131242-WSW41-QA-0003 | 2023-10-27 | Inspection Test Plan for Reinforcement work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000146 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-0003 | 2023-12-21 | Inspection Test Plan for Reinforcement work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 1 | Approved with Comments | YES | 2024-02-02 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000146 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-0003 | 2024-01-29 | Inspection Test Plan for Reinforcement work | Approved | 2024-02-19 | 2024-02-21 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000147 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 0 | 131242-WSW41-QA-0004 | 2023-10-27 | Inspection Test Plan for Concreting Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | NAP | NAP
000147 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-0004 | 2023-12-21 | Inspection Test Plan for Concreting Work | Not Approved. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-12 |  | Not Approved | YES | 2024-02-01 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | NAP | NAP
000147 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-0004 | 2024-01-29 | Inspection Test Plan for Concreting Work | Approved | 2024-02-19 | 2024-02-21 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | APP | APP
000148 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 0 | 131242-WSW41-QA-0005 | 2023-10-27 | Inspection Test Plan for Formwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | YES | Resubmitted |  |  |  | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | PEN | NAP | NAP
000148 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 1 | 131242-WSW41-QA-0005 | 2023-12-21 | Inspection Test Plan for Formwork | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 1 | Approved with Comments | YES | 2024-02-02 | NO | Overdue | 507 | 2024-03-13 |  | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | PEN | AWC | AWC
000149 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0006 | 0 | 131242-WSW41-QA-0006 | 2023-10-27 | Inspection Test Plan for Waterproofing Concrete and Application Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | NO | Overdue | 546 | 2024-01-11 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | PEN | NAP | NAP
000150 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0007 | 0 | 131242-WSW41-QA-0007 | 2023-10-27 | Inspection Test Plan for Roadwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 |  | Not Approved | YES | 2023-12-07 | NO | Overdue | 546 | 2024-01-12 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | PEN | NAP | NAP
000151 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | E | 0000 | 0 | 131242-WSD11-BQ-0000 | 2023-10-27 | THP-Electrical Load List | Approved with comments. To Revise and resubmit. Please refer to the comment sheet. | 2023-11-27 | 2024-02-02 | 47 | Approved with Comments | YES | 2024-02-23 | YES | Resubmitted |  |  |  | NA | "THP-Electrical Load List" | 2023-10-27 | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000151 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 1 | 131242-WSD11-BQ-0000 | 2024-03-28 | THP-Electrical Load List | Rev 0: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2024-04-19 | 2024-08-23 | 86 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "THP-Electrical Load List" | 2023-10-27 | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000151 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 2 | 131242-WSD11-BQ-0000 | 2025-02-10 | THP-Electrical Load List | Rev 2: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 43 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "THP-Electrical Load List" | 2023-10-27 | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0009 | 0 | 131242-WSW41-MI-0009 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Meeting Minutes 0009_20240220" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-07 | 2024-03-01 | 0 | 000000&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | PS | IM | 0009 | NA | 131242-WSW41-PS-0009 | 2023-10-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-28 | 2023-11-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-05 | 0 | 000000&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0010 | NA | 131242-WSW41-MI-0010 | 2023-10-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-28 | 2023-11-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-27 | 2024-04-04 | 0 | 000000&&000109&&000126&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | PS | IM | 0010 | NA | 131242-WSW41-PS-0010 | 2023-10-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-11-28 | 2023-11-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-22 | 0 | 000000&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | PEN | INF | INF
000153 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0011 | 0 | 131242-WSW41-MI-0011 | 2023-10-30 | Process & MEICA Meeting Minutes 0011_20231012 | For Information | 2023-11-28 | 2024-03-18 | 76 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | PEN | INF | INF
000154 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0015 | 0 | 131242-WSW41-LT-0015 | 2023-10-31 | CV of Team Member (WSHC) | Approved | 2023-11-29 | 2023-12-04 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (WSHC)" | 2023-10-31 | 2023-10-31 | 0 | 000154 | 2023-10-31 | 00 | 1 | PEN | APP | APP
000155 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0002 | 0 | 131242-WSW41-CT-0002 | 2023-10-31 | Professional Indemnity Insurance Letter | Acceptable for information. | 2023-11-29 | 2023-11-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "Professional Indemnity Insurance Letter" | 2023-10-31 | 2023-10-31 | 0 | 000155 | 2023-10-31 | 00 | 1 | PEN | INF | INF
000156 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LT | AGC | 0001 | 0 | 131242-WSW41-LT-0001 | 2023-11-02 | Approval Letter to Commence Works Requiring Earth Control Measure | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-01 | 2023-11-09 |  | Approved with Comments | YES | 2023-11-30 | NO | Overdue | 551 |  |  | NA | "Approval Letter to Commence Works Requiring Earth Control Measure" && "Common Data Environment (CDE) Set-Up and Rollout" | 2023-11-02 | 2024-01-12 | 0 | 000156&&000273 | 2023-11-02, 2024-01-12 | 00 | 2 | PEN | AWC | AWC
000157 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0002 | 0 | 131242-WSW41-PS-0002 | 2023-11-02 | Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023 | For Information | 2023-12-01 | 2023-12-01 |  | For Information | NO |  | YES |  |  |  |  | NA | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" && "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | 2023-07-28 | 2023-11-02 | 0 | 000057&&000157 | 2023-07-28, 2023-11-02 | 00 | 2 | PEN | INF | INF
000158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 0 | 131242-WST02-BQ-0000 | 2023-11-03 | SSN Electrical Load List | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2023-12-04 | 2024-04-29 | 100 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "SSN Electrical Load List" | 2023-11-03 | 2025-02-10 | 1 | 000158 | 2023-11-03, 2025-02-10 | 00, 01 | 2 | PEN | AWC | AWC
000158 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 1 | 131242-WST02-BQ-0000 | 2025-02-10 | SSN Electrical Load List | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 43 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SSN Electrical Load List" | 2023-11-03 | 2025-02-10 | 1 | 000158 | 2023-11-03, 2025-02-10 | 00, 01 | 2 | PEN | AWC | AWC
000159 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0007 | 0 | 131242-WSW41-PP-0007 | 2023-11-03 | Haze Management Plan | Approved | 2023-12-04 | 2023-12-01 |  | Approved | NO |  | YES |  |  |  |  | NA | "Haze Management Plan " | 2023-11-03 | 2023-11-03 | 0 | 000159 | 2023-11-03 | 00 | 1 | PEN | APP | APP
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | A | 131242-WST02-DR-1000 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 51 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  | TBA |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1001 | NA | 131242-WST02-DR-1001 | 2023-11-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-04 | 2024-02-16 | 51 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1002 | NA | 131242-WST02-DR-1002 | 2023-11-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-04 | 2024-02-16 | 51 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003 | NA | 131242-WST02-DR-1003 | 2023-11-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-04 | 2024-02-16 | 51 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1004 | NA | 131242-WST02-DR-1004 | 2023-11-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-04 | 2024-02-16 | 51 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-1000 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 38 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  | TBA | PENDING C2D | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1001 | NA | 131242-WST02-DR-1001 | 2025-02-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-10 | 2025-05-06 | 38 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1002 | NA | 131242-WST02-DR-1002 | 2025-02-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-10 | 2025-05-06 | 38 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003 | NA | 131242-WST02-DR-1003 | 2025-02-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-10 | 2025-05-06 | 38 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1004 | NA | 131242-WST02-DR-1004 | 2025-02-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-10 | 2025-05-06 | 38 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | C | 131242-WST02-DR-1000 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 7 | Not Approved | YES | 2025-09-22 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1001 | NA | 131242-WST02-DR-1001 | 2025-08-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-22 | 2025-09-02 | 7 | Not Approved | YES | 2025-09-22 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1002 | NA | 131242-WST02-DR-1002 | 2025-08-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-22 | 2025-09-02 | 7 | Not Approved | YES | 2025-09-22 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003 | NA | 131242-WST02-DR-1003 | 2025-08-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-22 | 2025-09-02 | 7 | Not Approved | YES | 2025-09-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1004 | NA | 131242-WST02-DR-1004 | 2025-08-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-22 | 2025-09-02 | 7 | Not Approved | YES | 2025-09-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | D | 131242-WST02-DR-1000 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1001 | NA | 131242-WST02-DR-1001 | 2025-12-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-02 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1002 | NA | 131242-WST02-DR-1002 | 2025-12-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-02 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003 | NA | 131242-WST02-DR-1003 | 2025-12-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-02 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1004 | NA | 131242-WST02-DR-1004 | 2025-12-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-02 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000161 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0004 | D | 131242-WST02-CD-0004 | 2023-11-06 | Submission of Milestone 1.1 Underground Services Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 79 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Submission of Milestone 1.1 Underground Services Model" | 2023-11-06 | 2023-11-06 | D | 000161 | 2023-11-06 | 00 | 1 | PEN | AWC | AWC
000161 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-0022 | 2024-05-27 | Milestone 1.2 Underground Services | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 |  | Not Approved | YES | 2024-06-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | PEN | NAP | NAP
000161 | 02 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 1 | 131242-WST02-CD-0022 | 2024-06-05 | Milestone 1.2 Underground Services | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 7 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | PEN | AWC | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-0044 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  | This M2 submission includes all discipline documents for the relevant area. | NA | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2024-10-05 | 2025-09-29 | 0 | 000161 | 2024-10-05, 2025-09-29 | 03, 04 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-1100 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN Earthing Layout Plan" | 2023-12-18 | 2025-02-25 | B_endorsed | 000000&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1101 | NA | 131242-WST02-DR-1101 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1102 | NA | 131242-WST02-DR-1102 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7750 | NA | 131242-WST02-DR-7750 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7751 | NA | 131242-WST02-DR-7751 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7752 | NA | 131242-WST02-DR-7752 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1300 | NA | 131242-WST02-DR-1300 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2024-10-05 | NA | 000000 | 2024-10-05 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1301 | NA | 131242-WST02-DR-1301 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2024-10-05 | NA | 000000 | 2024-10-05 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1302 | NA | 131242-WST02-DR-1302 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2024-10-05 | NA | 000000 | 2024-10-05 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3300 | NA | 131242-WST02-DR-3300 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2024-10-05 | NA | 000000 | 2024-10-05 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3301 | NA | 131242-WST02-DR-3301 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-10-05 | 2024-10-05 | NA | 000000 | 2024-10-05 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1000 | NA | 131242-WST02-DR-1000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1001 | NA | 131242-WST02-DR-1001 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1002 | NA | 131242-WST02-DR-1002 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1003 | NA | 131242-WST02-DR-1003 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004 | NA | 131242-WST02-DR-1004 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1005 | NA | 131242-WST02-DR-1005 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2000 | NA | 131242-WST02-DR-2000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2001 | NA | 131242-WST02-DR-2001 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2002 | NA | 131242-WST02-DR-2002 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2003 | NA | 131242-WST02-DR-2003 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5000 | NA | 131242-WST02-DR-5000 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5001 | NA | 131242-WST02-DR-5001 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5002 | NA | 131242-WST02-DR-5002 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1022 | NA | 131242-WST02-DR-1022 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-09 | 2026-02-04 | A.1 | 000000&&000429 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5011 | NA | 131242-WST02-DR-5011 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5012 | NA | 131242-WST02-DR-5012 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5013 | NA | 131242-WST02-DR-5013 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5014 | NA | 131242-WST02-DR-5014 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5015 | NA | 131242-WST02-DR-5015 | 2024-10-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-24 | 2024-12-05 | 29 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000161 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-0044 | 2025-09-29 | Milestone 3 Underground Services | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-17 | 2026-01-27 | 70 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  | This M2 submission includes all discipline documents for the relevant area. | NA | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2024-10-05 | 2025-09-29 | 0 | 000161 | 2024-10-05, 2025-09-29 | 03, 04 | 2 | PEN | AWC | AWC
000162 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-0005 | 2023-11-06 | Submission of Milestone 1.1 Pump Stataion and Blower Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 79 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | PEN | AWC | AWC
000162 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-0025 | 2024-05-27 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 |  | Not Approved | YES | 2024-06-25 | YES | Resubmitted |  | Requested to reject on 03 June |  | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000162 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 1 | 131242-WST02-CD-0025 | 2024-06-05 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 7 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | PEN | AWC | AWC
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-0025 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1314 | NA | 131242-WST02-DR-1314 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-04-28, 2025-10-27 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3329 | NA | 131242-WST02-DR-3329 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3330 | NA | 131242-WST02-DR-3330 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3331 | NA | 131242-WST02-DR-3331 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3332 | NA | 131242-WST02-DR-3332 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004_MS2 | NA | 131242-WST02-DR-1004_MS2 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003_MS2 | NA | 131242-WST02-DR-1003_MS2 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1314 | NA | 131242-WST02-DR-1314 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-04-28, 2025-10-27 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1115 | NA | 131242-WST02-DR-1115 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1116 | NA | 131242-WST02-DR-1116 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1117 | NA | 131242-WST02-DR-1117 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3035 | NA | 131242-WST02-DR-3035 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2025-10-31 | A | 000000&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3036 | NA | 131242-WST02-DR-3036 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | 2026-02-03 | B | 000000&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3037 | NA | 131242-WST02-DR-3037 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1011 | NA | 131242-WST02-DR-1011 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4002 | NA | 131242-WST02-DR-4002 | 2025-04-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-27 | NA | 000000 | 2024-05-06, 2025-04-09, 2025-10-27 | 00 | 3 | PEN | AWC | AWC
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-0025 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1314 | NA | 131242-WST02-DR-1314 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-04-28, 2025-10-27 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3329 | NA | 131242-WST02-DR-3329 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3330 | NA | 131242-WST02-DR-3330 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3331 | NA | 131242-WST02-DR-3331 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3332 | NA | 131242-WST02-DR-3332 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004_MS2 | NA | 131242-WST02-DR-1004_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1003_MS2 | NA | 131242-WST02-DR-1003_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1314 | NA | 131242-WST02-DR-1314 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-04-28, 2025-10-27 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1115 | NA | 131242-WST02-DR-1115 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1116 | NA | 131242-WST02-DR-1116 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1117 | NA | 131242-WST02-DR-1117 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3035 | NA | 131242-WST02-DR-3035 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2025-10-31 | A | 000000&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3036 | NA | 131242-WST02-DR-3036 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | 2026-02-03 | B | 000000&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3037 | NA | 131242-WST02-DR-3037 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-10-27 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1011 | NA | 131242-WST02-DR-1011 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4002 | NA | 131242-WST02-DR-4002 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-14 | 2026-01-27 | 51 | Not Approved | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-27 | NA | 000000 | 2024-05-06, 2025-04-09, 2025-10-27 | 00 | 3 | PEN | NAP | NAP
000163 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0007 | 0 | 131242-WST02-CD-0007 | 2023-11-06 | Submission of Milestone 1.1 Water Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 79 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | AWC | AWC
000163 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-0023 | 2024-06-03 | Milestone 1.2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-24 | 2024-07-05 | 9 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - SSN Water Tank" && "Milestone 1.2 SSN Water Tank" | 2024-03-18 | 2024-06-03 | 0 | 000163&&000367 | 2024-03-18, 2024-06-03 | 00, 01 | 2 | PEN | AWC | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0055 | 0 | 131242-WST02-CD-0055 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-04-28 | 0 | 000163 | 2025-04-28 | 02 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1314 | NA | 131242-WST02-DR-1314 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-09 | 2025-10-27 | NA | 000000 | 2025-04-09, 2025-04-28, 2025-10-27 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1315 | NA | 131242-WST02-DR-1315 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3324 | NA | 131242-WST02-DR-3324 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3325 | NA | 131242-WST02-DR-3325 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3326 | NA | 131242-WST02-DR-3326 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3327 | NA | 131242-WST02-DR-3327 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3328 | NA | 131242-WST02-DR-3328 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-28 | 2025-04-28 | NA | 000000 | 2025-04-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1004 | NA | 131242-WST02-DR-1004 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1004 | NA | 131242-WST02-DR-1004 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1005 | NA | 131242-WST02-DR-1005 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1112 | NA | 131242-WST02-DR-1112 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1113 | NA | 131242-WST02-DR-1113 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1114 | NA | 131242-WST02-DR-1114 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3028 | NA | 131242-WST02-DR-3028 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3029 | NA | 131242-WST02-DR-3029 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3030 | NA | 131242-WST02-DR-3030 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | 2026-02-03 | B | 000000&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3031 | NA | 131242-WST02-DR-3031 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3033 | NA | 131242-WST02-DR-3033 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1003 | NA | 131242-WST02-DR-1003 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1006 | NA | 131242-WST02-DR-1006 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3001 | NA | 131242-WST02-DR-3001 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3002 | NA | 131242-WST02-DR-3002 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3005 | NA | 131242-WST02-DR-3005 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4001 | NA | 131242-WST02-DR-4001 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-04-28 | NA | 000000 | 2024-05-06, 2025-04-28 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1008 | NA | 131242-WST02-DR-1008 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1010 | NA | 131242-WST02-DR-1010 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1012 | NA | 131242-WST02-DR-1012 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1015 | NA | 131242-WST02-DR-1015 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1016 | NA | 131242-WST02-DR-1016 | 2025-04-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-16 | 2025-09-23 | 92 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000163 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-0052 | 2025-12-16 | Milestone 3 SSN Water Tank | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-01-27 | 16 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-02-10 | 2025-12-16 | 0 | 000163&&001034 | 2025-02-10, 2025-12-16 | 00, 03 | 2 | PEN | AWC | AWC
000164 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-0005 | 2023-11-06 | Submission of Milestone 1.1 Astrea Separator Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-03-28 | 79 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | PEN | AWC | AWC
000164 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-0024 | 2024-06-04 | Milestone 1.2 SSN Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 8 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-0024 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1318 | NA | 131242-WST02-DR-1318 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1319 | NA | 131242-WST02-DR-1319 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3335 | NA | 131242-WST02-DR-3335 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3336 | NA | 131242-WST02-DR-3336 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1106 | NA | 131242-WST02-DR-1106 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1107 | NA | 131242-WST02-DR-1107 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1108 | NA | 131242-WST02-DR-1108 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1109 | NA | 131242-WST02-DR-1109 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3018 | NA | 131242-WST02-DR-3018 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3019 | NA | 131242-WST02-DR-3019 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3020 | NA | 131242-WST02-DR-3020 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3021 | NA | 131242-WST02-DR-3021 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3022 | NA | 131242-WST02-DR-3022 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3023 | NA | 131242-WST02-DR-3023 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1110 | NA | 131242-WST02-DR-1110 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1111 | NA | 131242-WST02-DR-1111 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3024 | NA | 131242-WST02-DR-3024 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3026 | NA | 131242-WST02-DR-3026 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4000 | NA | 131242-WST02-DR-4000 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-31 | NA | 000000 | 2024-05-06, 2025-04-22, 2025-10-31 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1014 | NA | 131242-WST02-DR-1014 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1009 | NA | 131242-WST02-DR-1009 | 2025-04-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-12 | 2025-07-02 | 36 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | 2026-02-09 | A | 000000&&000812 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 16 | PEN | AWC | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-0024 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1318 | NA | 131242-WST02-DR-1318 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1319 | NA | 131242-WST02-DR-1319 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3335 | NA | 131242-WST02-DR-3335 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3336 | NA | 131242-WST02-DR-3336 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-04-22 | 2025-10-31 | NA | 000000 | 2025-04-22, 2025-10-31 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1106 | NA | 131242-WST02-DR-1106 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1107 | NA | 131242-WST02-DR-1107 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1108 | NA | 131242-WST02-DR-1108 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1109 | NA | 131242-WST02-DR-1109 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3018 | NA | 131242-WST02-DR-3018 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3019 | NA | 131242-WST02-DR-3019 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3020 | NA | 131242-WST02-DR-3020 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3021 | NA | 131242-WST02-DR-3021 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3022 | NA | 131242-WST02-DR-3022 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3023 | NA | 131242-WST02-DR-3023 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1110 | NA | 131242-WST02-DR-1110 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 1111 | NA | 131242-WST02-DR-1111 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3024 | NA | 131242-WST02-DR-3024 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 3026 | NA | 131242-WST02-DR-3026 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4000 | NA | 131242-WST02-DR-4000 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-31 | NA | 000000 | 2024-05-06, 2025-04-22, 2025-10-31 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1014 | NA | 131242-WST02-DR-1014 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1009 | NA | 131242-WST02-DR-1009 | 2025-10-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | 2026-02-09 | A | 000000&&000812 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 16 | PEN | AWC | AWC
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | A | 131242-WST02-CL-7000 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 50 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7001 | NA | 131242-WST02-CL-7001 | 2023-11-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-05 | 2024-02-16 | 50 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7002 | NA | 131242-WST02-CL-7002 | 2023-11-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-05 | 2024-02-16 | 50 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7003 | NA | 131242-WST02-CL-7003 | 2023-11-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-05 | 2024-02-16 | 50 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7004 | NA | 131242-WST02-CL-7004 | 2023-11-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-05 | 2024-02-16 | 50 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | NAP | NAP
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | B | 131242-WST02-CL-7000 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 65 | For Information | NO |  | YES |  |  |  |  | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7001 | NA | 131242-WST02-CL-7001 | 2024-07-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-29 | 2024-10-29 | 65 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7002 | NA | 131242-WST02-CL-7002 | 2024-07-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-29 | 2024-10-29 | 65 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7003 | NA | 131242-WST02-CL-7003 | 2024-07-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-29 | 2024-10-29 | 65 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | EL | 7004 | NA | 131242-WST02-CL-7004 | 2024-07-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-29 | 2024-10-29 | 65 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-06 | 2024-07-09 | NA | 000000 | 2023-11-06, 2024-07-09 | 00 | 2 | PEN | INF | INF
000166 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 0 | 131242-WSW41-QA-0001 | 2023-11-06 | Inspection Test Plan for Architectural work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-07 | 2 | Not Approved | YES | 2023-12-28 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | NAP | NAP
000166 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 1 | 131242-WSW41-QA-0001 | 2024-12-05 | Inspection Test Plan for Architectural work | Rev.1: Approved | 2024-12-26 | 2024-12-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | APP | APP
000167 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 0 | 131242-WSW41-QA-0002 | 2023-11-06 | Inspection Test Plan for Plastering and Painting Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 1 | Not Approved | YES | 2023-12-27 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000167 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 1 | 131242-WSW41-QA-0002 | 2024-12-13 | Inspection Test Plan for Plastering and Painting Work | Rev 1 Approved | 2025-01-03 | 2024-12-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000168 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0003 | 0 | 131242-WSW41-QA-0003 | 2023-11-06 | Inspection Test Plan for Installation of Raised Access Floor System Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 1 | Not Approved | YES | 2023-12-27 | NO | Overdue | 533 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000169 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0004 | 0 | 131242-WSW41-QA-0004 | 2023-11-06 | Inspection Test Plan for Installation of Door and Window Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-12 | 5 | Not Approved | YES | 2024-01-03 | NO | Overdue | 529 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | NAP | NAP
000170 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 0 | 131242-WSW41-VI-1001 | 2023-11-06 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-02-14 | 48 | Approved with Comments | YES | 2024-03-05 | YES | Resubmitted |  | 2024-07-31 |  | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000170 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 1 | 131242-WSW41-VI-1001 | 2024-11-23 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-14 | 1 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000170 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 2 | 131242-WSW41-VI-1001 | 2025-01-21 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-10 | 2025-04-27 | 52 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000171 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | A | 131242-WSD11-DR-7000 | 2023-11-06 | THP Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2023-12-05 | 2023-11-21 |  | Not Approved | YES | 2023-12-11 | YES | Resubmitted |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | NAP | NAP
000171 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | B | 131242-WSD11-DR-7000 | 2024-03-13 | THP Control System Architecture Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-03 | 2024-06-13 | 48 | Not Approved | YES | 2024-07-04 | YES | Resubmitted |  | TBA |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | NAP | NAP
000171 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7000 | C | 131242-WSD11-DR-7000 | 2024-07-29 | THP Control System Architecture Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-19 | 2024-08-30 | 9 | Approved with Comments | YES | 2024-09-19 | NO | Overdue | 350 |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000172 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 0 | 131242-WSD11-CL-0001 | 2023-11-08 | THP Compressed Air Calculation | Approved with Comments. To revise and resubmit. Refer to comments files | 2023-12-07 | 2024-01-17 | 27 | Approved with Comments | YES | 2024-02-06 | YES | Resubmitted |  |  |  | NA | "THP Compressed Air Calculation" | 2023-11-08 | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | PEN | AWC | AWC
000172 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 1 | 131242-WSD11-CL-0001 | 2024-04-19 | THP Compressed Air Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-07-26 | 53 | Approved with Comments | YES | 2024-08-16 | YES | Resubmitted |  |  |  | NA | "THP Compressed Air Calculation" | 2023-11-08 | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | PEN | AWC | AWC
000172 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 2 | 131242-WSD11-CL-0001 | 2024-08-15 | THP Compressed Air Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-11-07 | 45 | Approved with Comments | YES | 2024-11-27 | NO | Overdue | 302 |  |  | NA | "THP Compressed Air Calculation" | 2023-11-08 | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | PEN | AWC | AWC
000173 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 0 | 131242-WST02-CL-0001 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | 30 | Approved with Comments | YES | 2024-02-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7011 | NA | 131242-WST02-DR-7011 | 2023-11-08 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-07 | 2024-01-22 | 30 | Approved with Comments | YES | 2024-02-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | AWC | AWC
000173 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 1 | 131242-WST02-CL-0001 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7011 | NA | 131242-WST02-DR-7011 | 2024-05-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-27 | 2024-05-30 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | APP | APP
000173 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 2 | 131242-WST02-CL-0001 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | 30 | Approved | NO |  | YES |  |  |  | Resubmitted as per SO comments | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7011 | NA | 131242-WST02-DR-7011 | 2024-08-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-08-28 | 2024-10-09 | 30 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | APP | APP
000174 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0006 | 0 | 131242-WSW41-RT-0006 | 2023-11-08 | C4B Monthly Progress Report Number No.06 (10/23) | Rev. 0 - Approved | 2023-12-07 | 2023-11-21 |  | Approved | NO |  | YES |  |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" && "C4B Monthly Progress Report Number No.06 (10/23)" | 2023-11-08 | 2024-08-05 | 0 | 000174&&000619 | 2023-11-08, 2024-08-05 | 00 | 2 | PEN | APP | APP
000175 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0009 | 0 | 131242-WSW41-CD-0009 | 2023-11-08 | Submission Of BIM Coordination VCM Model (Oct – 2023) | For Information | 2023-12-07 | 2023-11-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Oct – 2023)" | 2023-11-08 | 2023-11-08 | 0 | 000175 | 2023-11-08 | 00 | 1 | PEN | INF | INF
000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0011 | 0 | 131242-WSW41-MI-0011 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | PS | IM | 0011 | NA | 131242-WSW41-PS-0011 | 2023-11-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-08 | 2023-11-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-09 | 2024-08-22 | 0 | 000000&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | PEN | INF | INF
000177 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 0 | 131242-WSD11-DS-0001 | 2023-11-09 | Data Sheet of Air Compressor | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-08 | 2024-01-22 | 29 | Approved with Comments | YES | 2024-02-09 | YES | Resubmitted |  |  |  | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 1 | 131242-WSD11-DS-0001 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-16 | 14 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  | 2024-07-26 | Rev 0: AWC | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0161 | NA | 131242-WSD11-DR-0161 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0101 | NA | 131242-WSD11-DR-0101 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0102 | NA | 131242-WSD11-DR-0102 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0103 | NA | 131242-WSD11-DR-0103 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0104 | NA | 131242-WSD11-DR-0104 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0131 | NA | 131242-WSD11-DR-0131 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0132 | NA | 131242-WSD11-DR-0132 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0133 | NA | 131242-WSD11-DR-0133 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2024-04-04 | NA | 000000 | 2024-04-04 | 00 | 1 | PEN | AWC | AWC
000177 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 2 | 131242-WSD11-DS-0001 | 2024-08-12 | Data Sheet of Air Compressor System | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-25 | 40 | Approved with Comments | YES | 2024-11-15 | YES | Resubmitted |  |  |  | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000177 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 3 | 131242-WSD11-DS-0001 | 2024-11-06 | Data Sheet of Air Compressor System | Rev 3: Approved | 2024-11-26 | 2024-12-05 | 7 | Approved | NO |  | YES |  |  |  |  | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | PEN | APP | APP
000178 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 0 | 131242-WSD11-DS-0005 | 2023-11-10 | Data Sheet of Pressure Vessel | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-18 | 26 | Approved with Comments | YES | 2024-02-07 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000178 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 1 | 131242-WSD11-DS-0005 | 2024-03-20 | Data Sheet of Pressure Vessel | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-29 | 12 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  | 2024-07-31 | Related to Detailed Design Report. | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000178 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 2 | 131242-WSD11-DS-0005 | 2024-07-28 | Data Sheet of Pressure Vessel | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 9 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000178 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 3 | 131242-WSD11-DS-0005 | 2024-11-22 | Data Sheet of Pressure Vessel | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. [Rev2 comments were not addressed by CES] | 2024-12-12 | 2024-12-05 |  | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000178 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 4 | 131242-WSD11-DS-0005 | 2025-03-04 | Data Sheet of Pressure Vessel | Rev 4: Approved. Please furnish PE Endorsement. | 2025-03-24 | 2025-10-06 | 136 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | APP | APP
000179 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 0 | 131242-WSD11-DS-0006 | 2023-11-10 | Data Sheet of PreCoolers | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-22 | 28 | Approved with Comments | YES | 2024-02-09 | YES | Resubmitted |  |  |  | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | PEN | AWC | AWC
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 1 | 131242-WSD11-DS-0006 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 13 | Approved with Comments | NO |  | YES |  |  |  | No re-submission required | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0007 | NA | 131242-WSD11-DR-0007 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-04-29 | 13 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2024-03-19 | NA | 000000 | 2024-03-19 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 0008 | NA | 131242-WSD11-DR-0008 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-09 | 2024-04-29 | 13 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2024-03-19 | NA | 000000 | 2024-03-19 | 00 | 1 | PEN | AWC | AWC
000180 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 0 | 131242-WSD11-DS-0007 | 2023-11-10 | Data Sheet of PGS | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 33 | Approved with Comments | YES | 2024-02-19 | YES | Resubmitted |  |  | Related to Detailed Design Report. | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000180 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 1 | 131242-WSD11-DS-0007 | 2024-03-25 | Data Sheet of PGS | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-16 | 2024-05-30 | 30 | Approved with Comments | YES | 2024-06-20 | YES | Resubmitted |  | 2024-07-31 | Rev 0: AWC | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000180 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 2 | 131242-WSD11-DS-0007 | 2024-07-28 | Data Sheet of PGS | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-09-02 | 11 | Approved with Comments | YES | 2024-09-20 | YES | Resubmitted |  |  |  | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 3 | 131242-WSD11-DS-0007 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DS | E | 0020 | NA | 131242-WSD11-DS-0020 | 2024-09-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-18 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-09-30 | 2024-09-30 | NA | 000000 | 2024-09-30 | 00 | 1 | PEN | AWC | AWC
000181 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 0 | 131242-WSD11-DS-0008 | 2023-11-10 | Data Sheet of PGC | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 33 | Approved with Comments | YES | 2024-02-19 | YES | Resubmitted |  |  |  | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000181 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 1 | 131242-WSD11-DS-0008 | 2024-03-19 | Data Sheet of PGC | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 13 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  | 2024-07-31 | Related to Detailed Design Report. | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000181 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 2 | 131242-WSD11-DS-0008 | 2025-03-06 | Data Sheet of PGC | Rev 2: Approved. | 2025-03-26 | 2025-10-06 | 134 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | PEN | APP | APP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-1000_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1001_FSSD | NA | 131242-WSD11-DR-1001_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1002_FSSD | NA | 131242-WSD11-DR-1002_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1003_FSSD | NA | 131242-WSD11-DR-1003_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1004_FSSD | NA | 131242-WSD11-DR-1004_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2023-12-12 | 1 | Not Approved | YES | 2024-01-03 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2023-11-10 | NA | 000000 | 2023-11-10 | 00 | 2 | PEN | NAP | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-1000_FSSD | 2024-01-04 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2024-01-24 | 2024-02-15 | 15 | For Information | NO |  | YES |  |  |  |  | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1001_FSSD | NA | 131242-WSD11-DR-1001_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-02-15 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1002_FSSD | NA | 131242-WSD11-DR-1002_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-02-15 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1003_FSSD | NA | 131242-WSD11-DR-1003_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-02-15 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1004_FSSD | NA | 131242-WSD11-DR-1004_FSSD | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-02-15 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-02-15 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2023-11-10 | NA | 000000 | 2023-11-10 | 00 | 2 | PEN | INF | INF
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0010 | 0 | 131242-WST02-CD-0010 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 75 | Rejected | NO |  | YES |  |  |  |  | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CD | IM | 0011 | NA | 131242-WST02-CD-0011 | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-03-28 | 75 | Rejected | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0401- I/O List" | 2023-11-10 | 2025-06-25 | 1 | 000000&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CD | IM | 0012 | NA | 131242-WST02-CD-0012 | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-03-28 | 75 | Rejected | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0203- I/O List " | 2023-11-10 | 2025-06-25 | 1 | 000000&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | M3 | Z | 8900 | NA | 131242-WST02-M3-8900 | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-03-28 | 75 | Rejected | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2023-11-10 | NA | 000000 | 2023-11-10 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | RT | IM | 9005 | NA | 131242-WSW41-RT-9005 | 2023-11-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-11 | 2024-03-28 | 75 | Rejected | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2023-11-10 | NA | 000000 | 2023-11-10 | 00 | 1 | PEN | REJ | REJ
000184 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0013 | 0 | 131242-WSW41-MI-0013 | 2023-11-14 | CSA Meeting Minutes 0013_20231019 | For Information | 2023-12-12 | 2023-11-23 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-14 | 2024-08-07 | 0 | 000000&&000184&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | PEN | INF | INF
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD | A | 131242-WST02-DR-1000_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  | To follow up to submit Prolog | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-15 | A | 000185 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD | NA | 131242-WST02-DR-1001_FSSD | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9000_FSSD | NA | 131242-WST02-DR-9000_FSSD | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 9001_FSSD | NA | 131242-WST02-DR-9001_FSSD | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7001_FSSD | NA | 131242-WST02-DR-7001_FSSD | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | AntiprexT AD 1020 XP_English | NA | NA | NA | NA | NA | AntiprexT AD 1020 XP_English-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | Caustic Soda 50% SDS | NA | NA | NA | NA | NA | Caustic Soda 50% SDS-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | Ferric Chloride SDS | NA | NA | NA | NA | NA | Ferric Chloride SDS-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG | NA | NA | NA | NA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022 | NA | NA | NA | NA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | TWRP C4B SSN_chemical inventory | NA | NA | NA | NA | NA | TWRP C4B SSN_chemical inventory-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | WST02_SSN-FSSD-WA 01 & 02 | NA | NA | NA | NA | NA | WST02_SSN-FSSD-WA 01 & 02-NA-NA-NA | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-11-23 |  | Not Approved | YES | 2023-12-13 | NO | Overdue | 542 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2023-11-15 | NA | 000000 | 2023-11-15 | 00 | 1 | PEN | NAP | NAP
000186 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0006 | 0 | 131242-WSW41-PS-0006 | 2023-11-15 | Monthly Progress Presentation No. 06 (1023) | For Information | 2023-12-13 | 2023-11-16 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for Jan 2024" && "Monthly Progress Presentation No. 06 (1023)" | 2023-11-15 | 2024-03-14 | 0 | 000186&&000361 | 2023-11-15, 2024-03-14 | 00 | 2 | PEN | INF | INF
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | 0 | 131242-WST02-DR-6300 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 61 | Approved with Comments | YES | 2024-04-02 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2024-03-12 | 61 | Approved with Comments | YES | 2024-04-02 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2024-03-12 | 61 | Approved with Comments | YES | 2024-04-02 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | B | 131242-WST02-DR-6300 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-16 | 2024-05-27 | 6 | Approved with Comments | YES | 2024-06-14 | YES | Resubmitted |  | 2024-07-31 |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2024-04-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-27 | 2024-05-27 |  | Approved with Comments | YES | 2024-06-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2024-04-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-27 | 2024-05-27 |  | Approved with Comments | YES | 2024-06-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000187 | 02 | Qili | Process | NA | 131242 | WST02 | NA | P | S#187 Cmt Reply Sheet | NA | 131242-WST02-NA-S#187 Cmt Reply Sheet | 2024-10-01 | Plant Drain and Safety Shower P&ID | Rev 2: The submittal is merged with SRC 731. All the open comments from this submittal are transferred to SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Plant Drain and Safety Shower P&ID" | 2024-10-01 | 2024-10-01 | NA | 000187 | 2024-10-01 | 02 | 1 | PEN | APP | APP
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | A | 131242-WST02-DR-1000 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 3 | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1001 | NA | 131242-WST02-DR-1001 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7000 | NA | 131242-WST02-DR-7000 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7003 | NA | 131242-WST02-DR-7003 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A.1 | 131242-WST02-DR-7000 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | 26 | Approved with Comments | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7003 | NA | 131242-WST02-DR-7003 | 2024-09-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-17 | 2024-11-25 | 26 | Approved with Comments | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | B | 131242-WST02-DR-1000 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 61 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1001 | NA | 131242-WST02-DR-1001 | 2025-09-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-01 | 2025-12-29 | 61 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1006 | NA | 131242-WST02-DR-1006 | 2025-09-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-01 | 2025-12-29 | 61 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 5003 | NA | 131242-WST02-DR-5003 | 2025-09-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-01 | 2025-12-29 | 61 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7003 | NA | 131242-WST02-DR-7003 | 2025-09-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-10-01 | 2025-12-29 | 61 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A | 131242-WST02-DR-1000 | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-12 | 61 | Not Approved | YES | 2024-04-02 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BP | 7000 | NA | 131242-WST02-DR-7000 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2024-03-13 | 62 | Not Approved | YES | 2024-04-03 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000189 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.1 | 131242-WST02-DR-7000 | 2024-09-26 | Plumbing and Sanitary (SSN Area) | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 27 | Not Approved | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-7000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 7 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BP | 1000 | NA | 131242-WST02-DR-1000 | 2025-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-14 | 2025-03-25 | 7 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BP | 5000 | NA | 131242-WST02-DR-5000 | 2025-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-14 | 2025-03-25 | 7 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-7000 | 2025-07-15 | SSN Plumbing and Sanitary | NA | 2025-08-04 |  | 122 | Awaiting S.O.'s response | [7 empty] | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BP | 1000 | NA | 131242-WST02-DR-1000 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-03-25 | 122 | Awaiting S.O.'s response | [7 empty] | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BP | 5000 | NA | 131242-WST02-DR-5000 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-03-25 | 122 | Awaiting S.O.'s response | [7 empty] | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | PEN | PEN
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A | 131242-WST02-DR-1002 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 3 | Approved with Comments | YES | 2024-01-09 | YES | Resubmitted |  | 2025-02-20 | Schemiatic to submit 27 Jul 24. Layout drawing shall be confirm with Digie | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1003 | NA | 131242-WST02-DR-1003 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Approved with Comments | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1004 | NA | 131242-WST02-DR-1004 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Approved with Comments | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7001 | NA | 131242-WST02-DR-7001 | 2023-11-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-13 | 2023-12-18 | 3 | Approved with Comments | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A.1 | 131242-WST02-DR-1002 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 3 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 | 2025-02-20 |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1003 | NA | 131242-WST02-DR-1003 | 2025-02-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-13 | 2025-03-18 | 3 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1004 | NA | 131242-WST02-DR-1004 | 2025-02-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-13 | 2025-03-18 | 3 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7001 | NA | 131242-WST02-DR-7001 | 2025-02-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-13 | 2025-03-18 | 3 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000191 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0010 | 0 | 131242-WSW41-CD-0010 | 2023-11-17 | Electrical Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 71 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Electrical Building" | 2023-11-17 | 2023-11-17 | 0 | 000191 | 2023-11-17 | 00 | 1 | PEN | AWC | AWC
000191 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-0027 | 2024-06-04 | Milestone 1.2 Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 8 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2024-06-04 | 2026-01-16 | 0 | 000191 | 2024-06-04, 2026-01-16 | 01, 03 | 2 | PEN | AWC | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0059 | 0 | 131242-WSW41-CD-0059 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-05-15 | 0 | 000191 | 2025-05-15 | 02 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1003 | NA | 131242-WST02-DR-1003 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1004 | NA | 131242-WST02-DR-1004 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1005 | NA | 131242-WST02-DR-1005 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1006 | NA | 131242-WST02-DR-1006 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1000 | NA | 131242-WST02-DR-1000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1001 | NA | 131242-WST02-DR-1001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1011 | NA | 131242-WST02-DR-1011 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1012 | NA | 131242-WST02-DR-1012 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1000 | NA | 131242-WST02-DR-1000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1001 | NA | 131242-WST02-DR-1001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1002 | NA | 131242-WST02-DR-1002 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1003 | NA | 131242-WST02-DR-1003 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1310 | NA | 131242-WST02-DR-1310 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1311 | NA | 131242-WST02-DR-1311 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1312 | NA | 131242-WST02-DR-1312 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1313 | NA | 131242-WST02-DR-1313 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3310 | NA | 131242-WST02-DR-3310 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3311 | NA | 131242-WST02-DR-3311 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3312 | NA | 131242-WST02-DR-3312 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3313 | NA | 131242-WST02-DR-3313 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3314 | NA | 131242-WST02-DR-3314 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3315 | NA | 131242-WST02-DR-3315 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3316 | NA | 131242-WST02-DR-3316 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3317 | NA | 131242-WST02-DR-3317 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3318 | NA | 131242-WST02-DR-3318 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3319 | NA | 131242-WST02-DR-3319 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3320 | NA | 131242-WST02-DR-3320 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3321 | NA | 131242-WST02-DR-3321 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-15 | 2025-05-15 | NA | 000000 | 2025-05-15 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-1000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1001 | NA | 131242-WST02-DR-1001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-1000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1001 | NA | 131242-WST02-DR-1001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1002 | NA | 131242-WST02-DR-1002 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-1000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EL | 1001 | NA | 131242-WST02-DR-1001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5000 | NA | 131242-WST02-DR-5000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5001 | NA | 131242-WST02-DR-5001 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5002 | NA | 131242-WST02-DR-5002 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5003 | NA | 131242-WST02-DR-5003 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5004 | NA | 131242-WST02-DR-5004 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5005 | NA | 131242-WST02-DR-5005 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4004 | NA | 131242-WST02-DR-4004 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-05-15 | NA | 000000 | 2024-05-06, 2025-05-15 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1002 | NA | 131242-WST02-DR-1002 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3000 | NA | 131242-WST02-DR-3000 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-09-23 | 79 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | AWC | AWC
000191 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-0027 | 2026-01-16 | Milestone 3 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2024-06-04 | 2026-01-16 | 0 | 000191 | 2024-06-04, 2026-01-16 | 01, 03 | 2 | PEN | PEN | PEN
000192 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0008 | 0 | 131242-WSW41-CD-0008 | 2023-11-17 | Chemical Dosing Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 71 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Chemical Dosing Area" | 2023-11-17 | 2023-11-17 | 0 | 000192 | 2023-11-17 | 00 | 1 | PEN | AWC | AWC
000192 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0026 | 1 | 131242-WSW41-CD-0026 | 2024-06-04 | Milestone 1.2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 8 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 SSN Chemical Dosing Area" | 2024-06-04 | 2024-06-04 | 1 | 000192 | 2024-06-04 | 01 | 1 | PEN | AWC | AWC
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-0057 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2025-05-15 | 2026-01-16 | 0 | 000192 | 2025-05-15, 2026-01-16 | 02, 03 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1002 | NA | 131242-WST02-DR-1002 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1004 | NA | 131242-WST02-DR-1004 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3003 | NA | 131242-WST02-DR-3003 | 2025-05-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-06-04 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | AWC | AWC
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-0057 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2025-05-15 | 2026-01-16 | 0 | 000192 | 2025-05-15, 2026-01-16 | 02, 03 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1317 | NA | 131242-WST02-DR-1317 | 2026-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-05 | 2025-07-02 |  | Awaiting S.O.'s response | [7 empty] | NA | "SITE OFFICE LAYOUT (Rev1)" | 2026-01-16 | 2026-01-16 | NA | 000000 | 2026-01-16 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3333 | NA | 131242-WST02-DR-3333 | 2026-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-05 | 2025-07-02 |  | Awaiting S.O.'s response | [7 empty] | NA | "SITE OFFICE LAYOUT (Rev1)" | 2026-01-16 | 2026-01-16 | NA | 000000 | 2026-01-16 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3334 | NA | 131242-WST02-DR-3334 | 2026-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-05 | 2025-07-02 |  | Awaiting S.O.'s response | [7 empty] | NA | "SITE OFFICE LAYOUT (Rev1)" | 2026-01-16 | 2026-01-16 | NA | 000000 | 2026-01-16 | 00 | 1 | PEN | PEN | PEN
000193 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0002 | 1 | 131242-WST02-CL-0002 | 2023-11-17 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-12-15 | 2023-12-18 | 1 | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | PEN | NAP | NAP
000193 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8001 | 0 | 131242-WST02-CL-8001 | 2024-04-04 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 1: Approved | 2024-04-25 | 2024-04-26 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | PEN | APP | APP
000194 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | CL | B | 0003 | 1 | 131242-WST02-CL-0003 | 2023-11-17 | Engineering Calculation Report for Potable Water Pipe | This submission is withdrown. As submitted wrongly as a new submission, which should be a Rev.1 for submittal no. 000097. | 2023-12-15 | 2023-12-06 |  | (VOID / NOT IN USE) | NO |  | YES |  |  | Resubmission of Submittal 000097 |  | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | PEN | PEN | PEN
000195 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0005 | 0 | 131242-WSW41-MI-0005 | 2023-11-20 | Monthly Progress Meeting Minutes 0005_20231017 | For Information | 2023-12-18 | 2023-11-23 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-06 | 2023-11-20 | 0 | 000000&&000041&&000068&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | PEN | INF | INF
000196 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0006 | 0 | 131242-WSW41-MI-0006 | 2023-11-15 | Monthly Progress Meeting Minutes 0006_20231114 | For Information | 2023-12-13 | 2023-11-23 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "SITE OFFICE LAYOUT (Rev1)" | 2023-07-14 | 2023-11-15 | 0 | 000000&&000050&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | PEN | INF | INF
000197 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | A | 131242-WSD11-DR-7000 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 89 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  | 2024-07-23 |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000197 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | B | 131242-WSD11-DR-7000 | 2025-01-21 | THP Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-02-10 | 2025-04-30 | 55 | Approved with Comments | YES | 2025-05-20 | NO | Overdue | 179 |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000198 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7001 | 0 | 131242-WSD11-DR-7001 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 89 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  | 2024-07-23 | To drop an email for combination of S198, S197. To reply the comment sheet as noted and to resubmit in order to close. | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000199 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 0 | 131242-WST02-CL-0001 | 2023-11-22 | SSN Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | NAP | NAP
000199 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 1 | 131242-WST02-CL-0001 | 2024-06-24 | SSN Cable Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 23 | Approved with Comments | YES | 2024-09-04 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | AWC | AWC
000199 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 2 | 131242-WST02-CL-0001 | 2025-05-30 | SSN Cable Sizing Calculations | Rev 2: Approved with comments. To revise and resubmit. | 2025-06-19 | 2025-07-23 | 24 | Approved with Comments | YES | 2025-08-12 | NO | Overdue | 119 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | AWC | AWC
000200 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 0 | 131242-WST02-VI-0000 | 2023-11-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet. | 2023-12-20 | 2023-12-22 | 2 | Approved with Comments | YES | 2024-01-15 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | PEN | AWC | AWC
000200 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 1 | 131242-WST02-VI-0000 | 2024-05-13 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-03 | 2024-07-04 | 22 | Approved with Comments | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | PEN | AWC | AWC
000200 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 2 | 131242-WST02-VI-0000 | 2024-07-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 2: Approved. | 2024-08-12 | 2024-10-29 | 56 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | PEN | APP | APP
000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | A | 131242-WST02-DR-7000 | 2023-11-22 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  | 2024-07-23 |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7001 | NA | 131242-WST02-DR-7001 | 2023-11-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-21 | 2024-04-29 | 87 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | B | 131242-WST02-DR-7000 | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | 40 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7001 | NA | 131242-WST02-DR-7001 | 2025-02-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-06 | 2024-04-29 | 225 | Awaiting S.O.'s response | [7 empty] | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | PEN | PEN
000202 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 0 | 131242-WSD11-BQ-0001 | 2023-11-22 | THP Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000202 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 1 | 131242-WSD11-BQ-0001 | 2024-06-12 | THP Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-03 | 2024-08-16 | 31 | Approved with Comments | YES | 2024-09-05 | YES | Resubmitted |  | 2025-02-24 |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000202 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 2 | 131242-WSD11-BQ-0001 | 2025-04-10 | THP Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-30 | 2025-05-08 | 5 | Approved with Comments | YES | 2025-05-28 | YES | Resubmitted |  | 2025-02-24 |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000202 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 3 | 131242-WSD11-BQ-0001 | 2025-07-21 | THP Cable List | Rev 3: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-02 | 17 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000203 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | A | 131242-WSD11-CL-0000 | 2023-11-22 | THP Cable sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "THP Cable sizing Calculations" | 2023-11-22 | 2024-06-12 | B | 000203 | 2023-11-22, 2024-06-12 | 00, 01 | 2 | PEN | NAP | NAP
000203 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | B | 131242-WSD11-CL-0000 | 2024-06-12 | THP Cable sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. | 2024-07-03 | 2024-08-16 | 31 | Approved with Comments | YES | 2024-09-05 | NO | Overdue | 360 |  |  | NA | "THP Cable sizing Calculations" | 2023-11-22 | 2024-06-12 | B | 000203 | 2023-11-22, 2024-06-12 | 00, 01 | 2 | PEN | AWC | AWC
000204 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 0 | 131242-WST02-BQ-0001 | 2023-11-22 | SSN Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | NAP | NAP
000204 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 1 | 131242-WST02-BQ-0001 | 2024-06-24 | SSN Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 23 | Approved with Comments | YES | 2024-09-04 | YES | Resubmitted |  | 2025-02-21 |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | AWC | AWC
000204 | 02 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 2 | 131242-WST02-BQ-0001 | 2025-04-18 | SSN Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-08 | 2025-05-07 |  | Approved with Comments | YES | 2025-05-27 | YES | Resubmitted |  | 2025-02-21 |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | AWC | AWC
000204 | 03 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 3 | 131242-WST02-BQ-0001 | 2025-07-11 | SSN Cable List | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-07-31 | 2025-07-23 |  | Approved with Comments | YES | 2025-08-12 | NO | Overdue | 119 |  |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | AWC | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-1000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1001 | NA | 131242-WST02-DR-1001 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1002 | NA | 131242-WST02-DR-1002 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1003 | NA | 131242-WST02-DR-1003 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004 | NA | 131242-WST02-DR-1004 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1005 | NA | 131242-WST02-DR-1005 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2000 | NA | 131242-WST02-DR-2000 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2001 | NA | 131242-WST02-DR-2001 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2002 | NA | 131242-WST02-DR-2002 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2003 | NA | 131242-WST02-DR-2003 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5000 | NA | 131242-WST02-DR-5000 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5001 | NA | 131242-WST02-DR-5001 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5002 | NA | 131242-WST02-DR-5002 | 2023-11-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-20 | 2024-04-29 | 88 | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | NAP | NAP
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | B | 131242-WST02-DR-1000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  | 2025-02-18 |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1001 | NA | 131242-WST02-DR-1001 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1002 | NA | 131242-WST02-DR-1002 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1003 | NA | 131242-WST02-DR-1003 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004 | NA | 131242-WST02-DR-1004 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1005 | NA | 131242-WST02-DR-1005 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2000 | NA | 131242-WST02-DR-2000 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2001 | NA | 131242-WST02-DR-2001 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2002 | NA | 131242-WST02-DR-2002 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2003 | NA | 131242-WST02-DR-2003 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5000 | NA | 131242-WST02-DR-5000 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5001 | NA | 131242-WST02-DR-5001 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5002 | NA | 131242-WST02-DR-5002 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-08-23 | 20 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-1000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1001 | NA | 131242-WST02-DR-1001 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1002 | NA | 131242-WST02-DR-1002 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1003 | NA | 131242-WST02-DR-1003 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1004 | NA | 131242-WST02-DR-1004 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 1005 | NA | 131242-WST02-DR-1005 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2000 | NA | 131242-WST02-DR-2000 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2001 | NA | 131242-WST02-DR-2001 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2002 | NA | 131242-WST02-DR-2002 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 2003 | NA | 131242-WST02-DR-2003 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5000 | NA | 131242-WST02-DR-5000 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5001 | NA | 131242-WST02-DR-5001 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EK | 5002 | NA | 131242-WST02-DR-5002 | 2025-02-20 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-12 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000206 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 0 | 131242-WST02-CL-0002 | 2023-11-22 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-02-26 | 45 | Approved with Comments | YES | 2024-03-15 | YES | Resubmitted |  | 2025-02-28 | pending Puriteq confirmation | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | PEN | AWC | AWC
000206 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 1 | 131242-WST02-CL-0002 | 2025-03-04 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 1: For Information | 2025-03-24 | 2025-10-06 | 136 | For Information | NO |  | YES |  |  |  |  | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | PEN | INF | INF
000207 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-0002 | 2023-11-22 | THP Equipment Sizing Calculation Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-03-07 | 53 | Approved with Comments | YES | 2024-03-27 | YES | Resubmitted |  |  |  | NA | "THP Equipment Sizing Calculation Sheet" | 2023-11-22 | 2023-11-24 | 0 | 000207&&000212 | 2023-11-22, 2023-11-24 | 00 | 2 | PEN | AWC | AWC
000207 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | Comment_CES Reply 2024 03 11 | NA | 131242-WSD11-CL-Comment_CES Reply 2024 03 11 | 2024-03-11 | THP Equipment Sizing Calculation Sheet | Rev 1: Approved | 2024-04-01 | 2024-04-29 | 19 | Approved | NO |  | YES |  |  |  | Rev 0 : AWC | NA | "THP Equipment Sizing Calculation Sheet" | 2024-03-11 | 2024-03-11 | NA | 000207 | 2024-03-11 | 01 | 1 | PEN | APP | APP
000208 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 0 | 131242-WSD11-RT-0001 | 2023-11-22 | THP Atex Hazardous Area Assessment Report | Rev 0: For Information. Response to comment sheet required. | 2023-12-20 | 2024-05-15 | 99 | For Information | YES | 2024-06-05 | YES | Resubmitted |  | 2024-07-31 |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | INF | INF
000208 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 1 | 131242-WSD11-RT-0001 | 2024-09-11 | THP Atex Hazardous Area Assessment Report | Rev 1: For Information. | 2024-10-01 | 2024-10-25 | 18 | For Information | NO |  | YES |  |  |  |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | INF | INF
000209 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0012 | 0 | 131242-WSW41-MI-0012 | 2023-11-24 | C4B Minutes of Engineering Process & MEICA Meeting No.0012 | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 101 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "Monthly Progress Meeting Minutes 0012_20240521" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-18 | 2024-06-04 | 0 | 000000&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | PEN | INF | INF
000210 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0003 | 0 | 131242-WST02-MI-0003 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 101 | For Information | NO |  | YES |  |  |  |  | NA | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | 2023-11-24 | 0 | 000210 | 2023-11-24 | 00 | 1 | PEN | INF | INF
000211 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0004 | 0 | 131242-WST02-MI-0004 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 101 | For Information | NO |  | YES |  |  |  |  | NA | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | 2023-11-24 | 0 | 000211 | 2023-11-24 | 00 | 1 | PEN | INF | INF
000212 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-0002 | 2023-11-24 | THP Equipment Sizing Calculation Sheet | This submittal is withdrawn. As already submitted these drawings under in the submittal 000207 on 22 Nov 2023. | 2023-12-22 | 2023-12-08 |  | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "THP Equipment Sizing Calculation Sheet" | 2023-11-22 | 2023-11-24 | 0 | 000207&&000212 | 2023-11-22, 2023-11-24 | 00 | 2 | PEN | PEN | PEN
000213 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0014 | 0 | 131242-WSW41-MI-0014 | 2023-11-27 | C4B Minutes of CSA Progress Meeting No.0014 | For Information | 2023-12-26 | 2023-12-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | PEN | INF | INF
000214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0005 | 0 | 131242-WSW41-PC-0005 | 2023-11-27 | PAYMENT CLAIM NO.5 | Approved. Please refer to S.O. Correspondence No. 0089 dated 1 Dec 2023. | 2023-12-26 | 2023-12-06 |  | Approved | NO |  | YES |  |  |  |  | NA | "PAYMENT CLAIM NO.5" | 2023-11-27 | 2023-11-27 | 0 | 000214 | 2023-11-27 | 00 | 1 | PEN | APP | APP
000215 | 00 | Franklin | PMT | NA | 131242 | WSW41 | LT | PM | 0016 | 0 | 131242-WSW41-LT-0016 | 2023-11-29 | Clarification on Anammox Reactor Design Capacity | Rev 0: For Information. Please find our respond as attached. | 2023-12-28 | 2024-07-26 | 144 | For Information | NO |  | YES |  |  |  |  | NA | "Clarification on Anammox Reactor Design Capacity" | 2023-11-29 | 2023-11-29 | 0 | 000215 | 2023-11-29 | 00 | 1 | PEN | INF | INF
000216 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 0 | 131242-WSW41-QA-0008 | 2023-11-30 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-29 | 2023-12-05 |  | Approved with Comments | YES | 2023-12-26 | YES | Resubmitted |  |  |  | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | PEN | AWC | AWC
000216 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 1 | 131242-WSW41-QA-0008 | 2023-12-12 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Approved | 2024-01-03 | 2024-01-12 | 7 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | PEN | APP | APP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | 0 | 131242-WSD11-DR-1000 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 |  | Rejected | YES | 2023-12-22 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-04 |  | Rejected | YES | 2023-12-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-04 |  | Rejected | YES | 2023-12-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-04 |  | Rejected | YES | 2023-12-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-04 |  | Rejected | YES | 2023-12-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | REJ | REJ
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | A | 131242-WSD11-DR-1000 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-26 | 2024-05-07 | 90 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1001 | NA | 131242-WSD11-DR-1001 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1002 | NA | 131242-WSD11-DR-1002 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1003 | NA | 131242-WSD11-DR-1003 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1004 | NA | 131242-WSD11-DR-1004 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-1000 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 73 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-02-20 |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1001 | NA | 131242-WSD11-DR-1001 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1002 | NA | 131242-WSD11-DR-1002 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1003 | NA | 131242-WSD11-DR-1003 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1004 | NA | 131242-WSD11-DR-1004 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | AWC | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | C | 131242-WSD11-DR-1000 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 2 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1001 | NA | 131242-WSD11-DR-1001 | 2025-04-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-06 | 2025-05-08 | 2 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1002 | NA | 131242-WSD11-DR-1002 | 2025-04-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-06 | 2025-05-08 | 2 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1003 | NA | 131242-WSD11-DR-1003 | 2025-04-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-06 | 2025-05-08 | 2 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1004 | NA | 131242-WSD11-DR-1004 | 2025-04-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-06 | 2025-05-08 | 2 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | AWC | AWC
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | A | 131242-WSD11-DR-1000 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 32 | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-02-15 | 32 | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-02-15 | 32 | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-02-15 | 32 | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-02-15 | 32 | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-1000 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 53 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2024-09-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-23 | 2024-12-06 | 53 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2024-09-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-23 | 2024-12-06 | 53 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2024-09-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-23 | 2024-12-06 | 53 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2024-09-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-23 | 2024-12-06 | 53 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-1000 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 1 | Not Approved | YES | 2025-05-28 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2025-04-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-07 | 2025-05-08 | 1 | Not Approved | YES | 2025-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2025-04-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-07 | 2025-05-08 | 1 | Not Approved | YES | 2025-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2025-04-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-07 | 2025-05-08 | 1 | Not Approved | YES | 2025-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2025-04-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-07 | 2025-05-08 | 1 | Not Approved | YES | 2025-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-1000 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 15 | Not Approved | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2025-08-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-10 | 2025-10-01 | 15 | Not Approved | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2025-08-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-10 | 2025-10-01 | 15 | Not Approved | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2025-08-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-10 | 2025-10-01 | 15 | Not Approved | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2025-08-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-10 | 2025-10-01 | 15 | Not Approved | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-1000 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 22 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2025-12-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-01 | 2026-02-02 | 22 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2025-12-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-01 | 2026-02-02 | 22 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2025-12-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-01 | 2026-02-02 | 22 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2025-12-14 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-01-01 | 2026-02-02 | 22 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | NAP | NAP
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A | 131242-WST02-DR-1000 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 |  | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1001 | NA | 131242-WST02-DR-1001 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-18 |  | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-18 |  | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2023-12-18 |  | Not Approved | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.1 | 131242-WST02-DR-7000 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 27 | Not Approved | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2024-09-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-10-16 | 2024-11-25 | 27 | Not Approved | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.2 | 131242-WST02-DR-5000 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 16 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2024-12-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-01-14 | 2025-02-07 | 16 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2024-12-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-01-14 | 2025-02-07 | 16 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.3 | 131242-WST02-DR-5000 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 14 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2025-02-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-05 | 2025-03-25 | 14 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2025-02-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-05 | 2025-03-25 | 14 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-1000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 25 | Approved with Comments | YES | 2025-09-26 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1001 | NA | 131242-WST02-DR-1001 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-09-08 | 25 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 5000 | NA | 131242-WST02-DR-5000 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-09-08 | 25 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-09-08 | 25 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2025-07-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-08-04 | 2025-09-08 | 25 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-1000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 28 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1001 | NA | 131242-WST02-DR-1001 | 2025-10-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-18 | 2025-12-29 | 28 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 5000 | NA | 131242-WST02-DR-5000 | 2025-10-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-18 | 2025-12-29 | 28 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2025-10-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-18 | 2025-12-29 | 28 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2025-10-29 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-18 | 2025-12-29 | 28 | Approved with Comments | YES | 2026-01-16 | NO | Overdue | 6 |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | A | 131242-WST02-DR-7000 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7001 | NA | 131242-WST02-DR-7001 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7002 | NA | 131242-WST02-DR-7002 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7003 | NA | 131242-WST02-DR-7003 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7004 | NA | 131242-WST02-DR-7004 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7005 | NA | 131242-WST02-DR-7005 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7006 | NA | 131242-WST02-DR-7006 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7007 | NA | 131242-WST02-DR-7007 | 2023-11-30 | SITE OFFICE LAYOUT (Rev1) | For Information | 2023-12-29 | 2024-05-09 | 89 | Not Approved | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | NAP | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | B | 131242-WST02-DR-7000 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 | TBA | Pending from C2D | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7001 | NA | 131242-WST02-DR-7001 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7002 | NA | 131242-WST02-DR-7002 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7003 | NA | 131242-WST02-DR-7003 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7004 | NA | 131242-WST02-DR-7004 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7005 | NA | 131242-WST02-DR-7005 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7006 | NA | 131242-WST02-DR-7006 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BE | 7007 | NA | 131242-WST02-DR-7007 | 2025-04-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-23 | 2025-06-17 | 37 | Not Approved | YES | 2025-07-07 | NO | Overdue | 145 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | NAP | NAP
000221 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0002 | 0 | 131242-WSD11-PO-0002 | 2023-12-01 | Unpriced PO for Air Compressor System | For Information | 2024-01-02 | 2024-01-17 | 11 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Air Compressor System" | 2023-12-01 | 2023-12-01 | 0 | 000221 | 2023-12-01 | 00 | 1 | PEN | INF | INF
000222 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0010 | 0 | 131242-WSD11-DS-0010 | 2023-12-01 | Progressive Cavity Pumps | Rev 0: Not approved - Revise and Resubmit | 2024-01-02 | 2024-03-07 | 46 | Not Approved | YES | 2024-03-27 | YES | Resubmitted |  |  |  | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | PEN | NAP | NAP
000222 | 01 | Joo Kwan | Process | NA | 131242 | NA | DS | M | S222 Cmt Sheet Reply 2024 07 22 | NA | 131242-NA-DS-S222 Cmt Sheet Reply 2024 07 22 | 2024-07-22 | Progressive Cavity Pumps | Rev 1: Rejected based on contractor's request. Reply to contractor reply is attached herewith. | 2024-08-12 | 2024-08-29 | 13 | Rejected | NO |  | YES |  |  |  |  | NA | "Progressive Cavity Pumps" | 2024-07-22 | 2024-07-22 | NA | 000222 | 2024-07-22 | 01 | 1 | PEN | REJ | REJ
000223 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 0 | 131242-WSD11-DS-0009 | 2023-12-01 | THP Plant Safety Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet | 2024-01-02 | 2024-03-07 | 46 | Approved with Comments | YES | 2024-03-27 | YES | Resubmitted |  |  | JV to follow up with JK to close the submittal | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | PEN | AWC | AWC
000223 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 1 | 131242-WSD11-DS-0009 | 2024-07-28 | THP Plant Safety Valve | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-16 | 2024-08-01 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | PEN | AWC | AWC
000224 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 0 | 131242-WSD11-SP-0001 | 2023-12-01 | THP System Control Philosophy | The submittal is approved with comments, resubmittal is required. | 2024-01-02 | 2024-01-26 | 18 | Approved with Comments | YES | 2024-02-16 | YES | Resubmitted |  |  |  | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | PEN | AWC | AWC
000224 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 1 | 131242-WSD11-SP-0001 | 2024-03-01 | THP System Control Philosophy | Rev1- The submittal is approved with comments, resubmittal is required. The comments are | 2024-03-21 | 2024-04-26 | 24 | Approved with Comments | YES | 2024-05-17 | YES | Resubmitted |  |  | JV to follow up with JK to close the submittal | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | PEN | AWC | AWC
000224 | 02 | Joo Kwan | Process | NA | 131242 | NA | SP | P | Cmt Sheet Reply S224.0 2024 07 30 | NA | 131242-NA-SP-Cmt Sheet Reply S224.0 2024 07 30 | 2024-07-30 | THP System Control Philosophy | Rev2- Although there are no active comments on the document, the document is still approved as noted to accommodate for the changes if any during the detail engineering. | 2024-08-20 | 2024-09-24 | 25 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "THP System Control Philosophy" | 2024-07-30 | 2024-07-30 | NA | 000224 | 2024-07-30 | 02 | 1 | PEN | AWC | AWC
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1000 | NA | 131242-WST02-DR-1000 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 |  | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 1001 | NA | 131242-WST02-DR-1001 | 2023-12-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-03 | 2023-12-08 |  | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7000 | NA | 131242-WST02-DR-7000 | 2023-12-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-03 | 2023-12-08 |  | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BH | 7001 | NA | 131242-WST02-DR-7001 | 2023-12-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-03 | 2023-12-08 |  | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | PEN | PEN
000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0012 | 0 | 131242-WSW41-MI-0012 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "Monthly Progress Meeting Minutes 0012_20240521" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-18 | 2024-06-04 | 0 | 000000&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0013 | NA | 131242-WSW41-MI-0013 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2023-12-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-14 | 2024-08-07 | 0 | 000000&&000184&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | PEN | INF | INF
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | A | 131242-WST02-DR-1000 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1001 | NA | 131242-WST02-DR-1001 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1002 | NA | 131242-WST02-DR-1002 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1003 | NA | 131242-WST02-DR-1003 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1004 | NA | 131242-WST02-DR-1004 | 2023-12-05 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-04 | 2024-05-07 | 84 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | B | 131242-WST02-DR-1000 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 73 | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1001 | NA | 131242-WST02-DR-1001 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1002 | NA | 131242-WST02-DR-1002 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1003 | NA | 131242-WST02-DR-1003 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1004 | NA | 131242-WST02-DR-1004 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-14 | 73 | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-1000 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 4 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  | TBA |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1001 | NA | 131242-WST02-DR-1001 | 2025-04-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-30 | 2025-05-07 | 4 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1002 | NA | 131242-WST02-DR-1002 | 2025-04-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-30 | 2025-05-07 | 4 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1003 | NA | 131242-WST02-DR-1003 | 2025-04-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-30 | 2025-05-07 | 4 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1004 | NA | 131242-WST02-DR-1004 | 2025-04-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-30 | 2025-05-07 | 4 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | D | 131242-WST02-DR-1000 | 2026-01-19 | SSN Power Layout Plan | NA | 2026-02-06 |  |  | Awaiting S.O.'s response | [5 empty] | TBA |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1001 | NA | 131242-WST02-DR-1001 | 2026-01-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-06 | 2025-05-07 |  | Awaiting S.O.'s response | [7 empty] | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1002 | NA | 131242-WST02-DR-1002 | 2026-01-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-06 | 2025-05-07 |  | Awaiting S.O.'s response | [7 empty] | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1003 | NA | 131242-WST02-DR-1003 | 2026-01-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-06 | 2025-05-07 |  | Awaiting S.O.'s response | [7 empty] | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1004 | NA | 131242-WST02-DR-1004 | 2026-01-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-06 | 2025-05-07 |  | Awaiting S.O.'s response | [7 empty] | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 1005 | NA | 131242-WST02-DR-1005 | 2026-01-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2026-02-06 | 2025-05-07 |  | Awaiting S.O.'s response | [7 empty] | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | PEN | PEN
000228 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | RT | C | 0001 | 0 | 131242-WSW41-RT-0001 | 2023-12-05 | UXO Scanning Report | Approved | 2024-01-04 | 2023-12-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | PEN | INF | INF
000229 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 0 | 131242-WSW41-VI-0005 | 2023-12-05 | Preliminary Design and Vendor Approval of Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-04 | 2024-04-17 | 71 | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  | 2024-07-26 | To provide Vendor drawings after PO issued. | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | AWC | AWC
000229 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 1 | 131242-WSW41-VI-0005 | 2024-08-20 | Preliminary Design and Vendor Approval of Mixer | Rev 1: Approved | 2024-09-09 | 2024-09-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | APP | APP
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | 0 | 131242-WSD11-DR-6000 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  | 2024-03-15 | To submit Detailed Design . Related to Detailed Design Report. | NA | "P&ID of THP Train 1" | 2023-12-06 | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6001 | NA | 131242-WSD11-DR-6001 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6002 | NA | 131242-WSD11-DR-6002 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6003 | NA | 131242-WSD11-DR-6003 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6004 | NA | 131242-WSD11-DR-6004 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6005 | NA | 131242-WSD11-DR-6005 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6006 | NA | 131242-WSD11-DR-6006 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6007 | NA | 131242-WSD11-DR-6007 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6008 | NA | 131242-WSD11-DR-6008 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6009 | NA | 131242-WSD11-DR-6009 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6010 | NA | 131242-WSD11-DR-6010 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6011 | NA | 131242-WSD11-DR-6011 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6012 | NA | 131242-WSD11-DR-6012 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6013 | NA | 131242-WSD11-DR-6013 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6014 | NA | 131242-WSD11-DR-6014 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6015 | NA | 131242-WSD11-DR-6015 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6016 | NA | 131242-WSD11-DR-6016 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6017 | NA | 131242-WSD11-DR-6017 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6018 | NA | 131242-WSD11-DR-6018 | 2023-12-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-05 | 2024-03-01 | 39 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | B | 131242-WSD11-DR-6000 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 11 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  | 2024-03-15 | Heng Peng to provide DGN dwg | NA | "P&ID of THP Train 1" | 2023-12-06 | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6001 | NA | 131242-WSD11-DR-6001 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6002 | NA | 131242-WSD11-DR-6002 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6003 | NA | 131242-WSD11-DR-6003 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6004 | NA | 131242-WSD11-DR-6004 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6005 | NA | 131242-WSD11-DR-6005 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6006 | NA | 131242-WSD11-DR-6006 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6007 | NA | 131242-WSD11-DR-6007 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6008 | NA | 131242-WSD11-DR-6008 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6009 | NA | 131242-WSD11-DR-6009 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6010 | NA | 131242-WSD11-DR-6010 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6011 | NA | 131242-WSD11-DR-6011 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6012 | NA | 131242-WSD11-DR-6012 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6013 | NA | 131242-WSD11-DR-6013 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6014 | NA | 131242-WSD11-DR-6014 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6015 | NA | 131242-WSD11-DR-6015 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6016 | NA | 131242-WSD11-DR-6016 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6017 | NA | 131242-WSD11-DR-6017 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6018 | NA | 131242-WSD11-DR-6018 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | C | 131242-WSD11-DR-6000 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "P&ID of THP Train 1" | 2023-12-06 | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6001 | NA | 131242-WSD11-DR-6001 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6002 | NA | 131242-WSD11-DR-6002 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6003 | NA | 131242-WSD11-DR-6003 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6004 | NA | 131242-WSD11-DR-6004 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6005 | NA | 131242-WSD11-DR-6005 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6006 | NA | 131242-WSD11-DR-6006 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6007 | NA | 131242-WSD11-DR-6007 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6008 | NA | 131242-WSD11-DR-6008 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6009 | NA | 131242-WSD11-DR-6009 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6010 | NA | 131242-WSD11-DR-6010 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6011 | NA | 131242-WSD11-DR-6011 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6012 | NA | 131242-WSD11-DR-6012 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6013 | NA | 131242-WSD11-DR-6013 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6014 | NA | 131242-WSD11-DR-6014 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6015 | NA | 131242-WSD11-DR-6015 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6016 | NA | 131242-WSD11-DR-6016 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6017 | NA | 131242-WSD11-DR-6017 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6018 | NA | 131242-WSD11-DR-6018 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6019 | NA | 131242-WSD11-DR-6019 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "P&ID of THP Train 2 " && "P&ID of THP Train 2 " && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6020 | NA | 131242-WSD11-DR-6020 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6021 | NA | 131242-WSD11-DR-6021 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6022 | NA | 131242-WSD11-DR-6022 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6023 | NA | 131242-WSD11-DR-6023 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6024 | NA | 131242-WSD11-DR-6024 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6025 | NA | 131242-WSD11-DR-6025 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6026 | NA | 131242-WSD11-DR-6026 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6027 | NA | 131242-WSD11-DR-6027 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6028 | NA | 131242-WSD11-DR-6028 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6029 | NA | 131242-WSD11-DR-6029 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6030 | NA | 131242-WSD11-DR-6030 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6031 | NA | 131242-WSD11-DR-6031 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6032 | NA | 131242-WSD11-DR-6032 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6033 | NA | 131242-WSD11-DR-6033 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6034 | NA | 131242-WSD11-DR-6034 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6035 | NA | 131242-WSD11-DR-6035 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6036 | NA | 131242-WSD11-DR-6036 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6050 | NA | 131242-WSD11-DR-6050 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "P&ID of THP General System [Part 2]" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6063 | NA | 131242-WSD11-DR-6063 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6070 | NA | 131242-WSD11-DR-6070 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6101 | NA | 131242-WSD11-DR-6101 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6121 | NA | 131242-WSD11-DR-6121 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6200 | NA | 131242-WSD11-DR-6200 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "P&ID of THP General System" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | B | 000000&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6300 | NA | 131242-WSD11-DR-6300 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6400 | NA | 131242-WSD11-DR-6400 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6600 | NA | 131242-WSD11-DR-6600 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6601 | NA | 131242-WSD11-DR-6601 | 2024-11-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-03 | 2025-01-16 | 30 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | D | 131242-WSD11-DR-6000 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "P&ID of THP Train 1" | 2023-12-06 | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6001 | NA | 131242-WSD11-DR-6001 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6002 | NA | 131242-WSD11-DR-6002 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6003 | NA | 131242-WSD11-DR-6003 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6004 | NA | 131242-WSD11-DR-6004 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6005 | NA | 131242-WSD11-DR-6005 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6006 | NA | 131242-WSD11-DR-6006 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6007 | NA | 131242-WSD11-DR-6007 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6008 | NA | 131242-WSD11-DR-6008 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6009 | NA | 131242-WSD11-DR-6009 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6010 | NA | 131242-WSD11-DR-6010 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6011 | NA | 131242-WSD11-DR-6011 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6012 | NA | 131242-WSD11-DR-6012 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6013 | NA | 131242-WSD11-DR-6013 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6014 | NA | 131242-WSD11-DR-6014 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6015 | NA | 131242-WSD11-DR-6015 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6016 | NA | 131242-WSD11-DR-6016 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6017 | NA | 131242-WSD11-DR-6017 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6018 | NA | 131242-WSD11-DR-6018 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-06 | 2025-06-17 | NA | 000000 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6019 | NA | 131242-WSD11-DR-6019 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "P&ID of THP Train 2 " && "P&ID of THP Train 2 " && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6020 | NA | 131242-WSD11-DR-6020 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6021 | NA | 131242-WSD11-DR-6021 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6022 | NA | 131242-WSD11-DR-6022 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6023 | NA | 131242-WSD11-DR-6023 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6024 | NA | 131242-WSD11-DR-6024 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6025 | NA | 131242-WSD11-DR-6025 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6026 | NA | 131242-WSD11-DR-6026 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6027 | NA | 131242-WSD11-DR-6027 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6028 | NA | 131242-WSD11-DR-6028 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6029 | NA | 131242-WSD11-DR-6029 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6030 | NA | 131242-WSD11-DR-6030 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6031 | NA | 131242-WSD11-DR-6031 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6032 | NA | 131242-WSD11-DR-6032 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6033 | NA | 131242-WSD11-DR-6033 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6034 | NA | 131242-WSD11-DR-6034 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6035 | NA | 131242-WSD11-DR-6035 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6036 | NA | 131242-WSD11-DR-6036 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6050 | NA | 131242-WSD11-DR-6050 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "P&ID of THP General System [Part 2]" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6051 | NA | 131242-WSD11-DR-6051 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-06-17 | 2025-06-17 | NA | 000000 | 2025-06-17 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6063 | NA | 131242-WSD11-DR-6063 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6070 | NA | 131242-WSD11-DR-6070 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6101 | NA | 131242-WSD11-DR-6101 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6121 | NA | 131242-WSD11-DR-6121 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6200 | NA | 131242-WSD11-DR-6200 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "P&ID of THP General System" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | B | 000000&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6300 | NA | 131242-WSD11-DR-6300 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6400 | NA | 131242-WSD11-DR-6400 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6600 | NA | 131242-WSD11-DR-6600 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6601 | NA | 131242-WSD11-DR-6601 | 2025-06-17 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-07-07 | 2025-08-28 | 38 | Approved with Comments | YES | 2025-09-17 | NO | Overdue | 93 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-1000_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 |  | Approved with Comments | YES | 2024-01-18 | YES | Resubmitted |  |  |  | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST604_BCA | NA | 131242-WST02-DR-1001_ST604_BCA | 2023-12-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-08 | 2023-12-28 |  | Approved with Comments | YES | 2024-01-18 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST604_BCA | NA | 131242-WST02-DR-5001_ST604_BCA | 2023-12-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-08 | 2023-12-28 |  | Approved with Comments | YES | 2024-01-18 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | NA | 131242-WST00-DR-8000_ST604_BCA | 2023-12-07 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-08 | 2023-12-28 |  | Approved with Comments | YES | 2024-01-18 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-1000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-05 | 2024-02-14 | 6 | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604_BCA | NA | 131242-WST02-DR-1001_ST604_BCA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1002_ST604_BCA | NA | 131242-WST02-DR-1002_ST604_BCA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-16 | 2024-01-16 | NA | 000000 | 2024-01-16 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604_BCA | NA | 131242-WST02-DR-5001_ST604_BCA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604_BCA | NA | 131242-WST02-DR-7000_ST604_BCA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-16 | 2024-01-16 | NA | 000000 | 2024-01-16 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | NA | 131242-WST00-DR-8000_ST604_BCA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-07 | 2024-01-16 | NA | 000000 | 2023-12-07, 2024-01-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | A1798-00002-2018-ST604_NOA | NA | NA | NA | NA | NA | A1798-00002-2018-ST604_NOA-NA-NA-NA | 2024-01-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-14 | 2024-02-14 |  | Approved with Comments | YES | 2024-03-05 | NO | Overdue | 486 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-16 | 2024-01-16 | NA | 000000 | 2024-01-16 | 00 | 1 | PEN | AWC | AWC
000232 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 0 | 131242-WSW41-VI-0007 | 2023-12-08 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-09 | 2024-02-26 | 33 | Approved with Comments | YES | 2024-03-15 | YES | Resubmitted |  | 2024-07-24 | Yibo WIP | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | PEN | AWC | AWC
000232 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 1 | 131242-WSW41-VI-0007 | 2024-07-29 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-19 | 2024-09-02 | 10 | Approved with Comments | YES | 2024-09-20 | YES | Resubmitted |  | 2025-02-28 | In progress. Only one ICA comment is open (s/n.19), will reconfirm with ICA team, Try resubmit in 1 week. | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | PEN | AWC | AWC
000232 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 2 | 131242-WSW41-VI-0007 | 2025-02-28 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 2: Approved | 2025-03-20 | 2025-11-24 | 172 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | PEN | APP | APP
000233 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0012 | 0 | 131242-WSW41-CD-0012 | 2023-12-08 | Submission Of BIM Coordination VCM Model (Nov – 2023) | For Information | 2024-01-09 | 2023-12-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Nov – 2023)" | 2023-12-08 | 2023-12-08 | 0 | 000233 | 2023-12-08 | 00 | 1 | PEN | INF | INF
000234 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0007 | 0 | 131242-WSW41-RT-0007 | 2023-12-11 | C4B Monthly Progress Report Number No.07 (11/23) | Rev. 0 - Approved with comments (need to re-submit) | 2024-01-10 | 2023-12-18 |  | Approved with Comments | YES | 2024-01-09 | NO | Overdue | 525 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" && "C4B Monthly Progress Report Number No.07 (11/23)" | 2023-12-11 | 2024-09-06 | 0 | 000234&&000713 | 2023-12-11, 2024-09-06 | 00 | 2 | PEN | AWC | AWC
000235 | 00 | Zora | CSA | NA | 131242 | WSW41 | RT | C | 0002 | 0 | 131242-WSW41-RT-0002 | 2023-12-12 | ULT Test Report of 600mm Dia. Bored Pile | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-11 | 2023-12-18 |  | Approved with Comments | YES | 2024-01-09 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | AWC | AWC
000235 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0002 | 1 | 131242-WSW41-RT-0002 | 2023-12-22 | ULT Test Report of 600mm Dia. Bored Pile | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-15 | 2024-01-16 | 1 | Approved with Comments | YES | 2024-02-05 | NO | Overdue | 506 |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | AWC | AWC
000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | A | 131242-WSD11-DR-1100 | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | 48 | Approved with Comments | YES | 2024-04-11 | YES | Resubmitted |  | 2024-07-19 |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Earthing Layout Plan" | 2023-12-12 | 2026-01-12 | C | 000000&&000236 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1101 | NA | 131242-WSD11-DR-1101 | 2023-12-12 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-11 | 2024-03-20 | 48 | Approved with Comments | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "WD for ST622 " | 2023-12-12 | 2026-01-26 | NA | 000000&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, NA | 8 | PEN | AWC | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-1100 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | 2025-02-28 |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Earthing Layout Plan" | 2023-12-12 | 2026-01-12 | C | 000000&&000236 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1101 | NA | 131242-WSD11-DR-1101 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "WD for ST622 " | 2023-12-12 | 2026-01-26 | NA | 000000&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1102 | NA | 131242-WSD11-DR-1102 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1103 | NA | 131242-WSD11-DR-1103 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1104 | NA | 131242-WSD11-DR-1104 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1105 | NA | 131242-WSD11-DR-1105 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-05-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1106 | NA | 131242-WSD11-DR-1106 | 2024-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-09-02 | 2024-12-07 | 68 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-05-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-28 | 00 | 3 | PEN | AWC | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | C | 131242-WSD11-DR-1100 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Earthing Layout Plan" | 2023-12-12 | 2026-01-12 | C | 000000&&000236 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1101 | NA | 131242-WSD11-DR-1101 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "WD for ST622 " | 2023-12-12 | 2026-01-26 | NA | 000000&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1102 | NA | 131242-WSD11-DR-1102 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1103 | NA | 131242-WSD11-DR-1103 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1104 | NA | 131242-WSD11-DR-1104 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1105 | NA | 131242-WSD11-DR-1105 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-05-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1106 | NA | 131242-WSD11-DR-1106 | 2025-03-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-05-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-28 | 00 | 3 | PEN | AWC | AWC
000237 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0001 | 0 | 131242-WST02-VI-0001 | 2023-12-12 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | Not Approved. To revise and resubmit. Please refer to comment sheet | 2024-01-11 | 2024-01-24 | 9 | Not Approved | YES | 2024-02-14 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
000237 | 01 | Freedomer | EICA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S237.0 2024 07 22 | NA | 131242-NA-NA-Cmt Sheet Reply S237.0 2024 07 22 | 2024-07-22 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | R1: Rejected as requested by C4B | 2024-08-12 | 2024-08-02 |  | Not Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | 2024-07-22 | 2024-07-22 | NA | 000237 | 2024-07-22 | 01 | 1 | PEN | NAP | NAP
000238 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 0 | 131242-WSW41-VI-1000 | 2023-12-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Not Approved. To revise and resubmit. | 2024-01-15 | 2024-02-19 | 24 | Not Approved | YES | 2024-03-08 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | PEN | NAP | NAP
000238 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 1 | 131242-WSW41-VI-1000 | 2024-03-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-04 | 2024-04-17 | 8 | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  | 2024-07-30 |  | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | PEN | AWC | AWC
000238 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 2 | 131242-WSW41-VI-1000 | 2024-08-07 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | PEN | APP | APP
000239 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 0 | 131242-WSW41-VI-1002 | 2023-12-14 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-02-19 | 24 | Not Approved | YES | 2024-03-08 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2023-12-14 | 2024-04-02 | 1 | 000239 | 2023-12-14, 2024-04-02 | 00, 01 | 2 | PEN | NAP | NAP
000239 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 1 | 131242-WSW41-VI-1002 | 2024-04-02 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. Please note, that the approval, corresponds to the brand/manufacturer proposed by contractor in this submittal. Approval does not include assessment for Trader/Distributor. | 2024-04-23 | 2024-04-15 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2023-12-14 | 2024-04-02 | 1 | 000239 | 2023-12-14, 2024-04-02 | 00, 01 | 2 | PEN | AWC | AWC
000240 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0015 | 0 | 131242-WSW41-MI-0015 | 2023-12-14 | CSA Meeting Minutes 0015_20231116 | For Information | 2024-01-15 | 2024-01-25 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-14 | 2024-09-04 | 0 | 000000&&000240&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | PEN | INF | INF
000241 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0001 | 0 | 131242-WST02-VI-0001 | 2023-12-14 | Preliminary design and Vendor Approval – SSN Package (ICA) | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-26 | 9 | Not Approved | YES | 2024-02-16 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
000241 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0001 | 1 | 131242-WST02-VI-0001 | 2024-05-02 | Preliminary design and Vendor Approval – SSN Package (ICA) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-23 | 2024-06-18 | 17 | Approved with Comments | YES | 2024-07-08 | NO | Overdue | 402 |  | Pending from MP | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | AWC | AWC
000242 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 0 | 131242-WSD11-DS-0003 | 2023-12-14 | THP PLC RIO Component Datasheet | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 12 | Not Approved | YES | 2024-02-21 | YES | Resubmitted |  |  |  | NA | "THP PLC RIO Component Datasheet" && "THP and SSN Earthing Material Specifications" | 2023-12-14 | 2026-01-12 | 0 | 000242&&001948 | 2023-12-14, 2024-03-11, 2026-01-12 | 00, 01 | 3 | PEN | NAP | NAP
000242 | 01 | Low | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 1 | 131242-WSD11-DS-0003 | 2024-03-11 | THP PLC RIO Component Datasheet | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-01 | 2024-05-15 | 30 | Not Approved | YES | 2024-06-05 | NO | Overdue | 424 |  |  | NA | "THP PLC RIO Component Datasheet" && "THP and SSN Earthing Material Specifications" | 2023-12-14 | 2026-01-12 | 0 | 000242&&001948 | 2023-12-14, 2024-03-11, 2026-01-12 | 00, 01 | 3 | PEN | NAP | NAP
000243 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 0 | 131242-WSD11-CH-0001 | 2023-12-14 | THP IO List | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 12 | Not Approved | YES | 2024-02-21 | YES | Resubmitted |  |  |  | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000243 | 01 | Low | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 1 | 131242-WSD11-CH-0001 | 2024-07-16 | THP IO List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. To revise and resubmit. | 2024-08-05 | 2024-09-17 | 30 | Not Approved | YES | 2024-10-07 | NO | Overdue | 338 |  |  | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000244 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0004 | 0 | 131242-WST02-CL-0004 | 2023-12-14 | Heat Load Calculation Report for ACMV | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-03-12 | 40 | Not Approved | YES | 2024-04-02 | YES | Resubmitted |  |  |  | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | PEN | NAP | NAP
000244 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 0 | 131242-WST02-CL-8001 | 2024-05-14 | Heat Load Calculation Report for ACMV | Not approved - Revise and Resubmit | 2024-06-04 | 2024-08-14 | 49 | Not Approved | YES | 2024-09-03 | YES | Resubmitted |  |  |  | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | PEN | NAP | NAP
000244 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 2 | 131242-WST02-CL-8001 | 2025-03-20 | Heat Load Calculation Report for ACMV | Rev 2: Approved | 2025-04-09 | 2025-05-25 | 29 | Approved | NO |  | YES |  |  | Pending EICA input | Doc name duplicate with S#193, Fire Hydrant Calculation/ Pending by EICA info and C2D . Freedomer follow up | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | PEN | APP | APP
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-1100 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 21 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN Earthing Layout Plan" | 2023-12-18 | 2025-02-25 | B_endorsed | 000000&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1101 | NA | 131242-WST02-DR-1101 | 2023-12-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-17 | 2024-02-16 | 21 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1102 | NA | 131242-WST02-DR-1102 | 2023-12-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-17 | 2024-02-16 | 21 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1103 | NA | 131242-WST02-DR-1103 | 2023-12-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-17 | 2024-02-16 | 21 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, NA | 3 | PEN | NAP | NAP
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B | 131242-WST02-DR-1100 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  | 2025-02-19 |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN Earthing Layout Plan" | 2023-12-18 | 2025-02-25 | B_endorsed | 000000&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1101 | NA | 131242-WST02-DR-1101 | 2024-06-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1102 | NA | 131242-WST02-DR-1102 | 2024-06-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7750 | NA | 131242-WST02-DR-7750 | 2024-06-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7751 | NA | 131242-WST02-DR-7751 | 2024-06-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7752 | NA | 131242-WST02-DR-7752 | 2024-06-11 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-02 | 2024-07-31 | 21 | Approved with Comments | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B_endorsed | 131242-WST02-DR-1100 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN Earthing Layout Plan" | 2023-12-18 | 2025-02-25 | B_endorsed | 000000&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1101 | NA | 131242-WST02-DR-1101 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 1102 | NA | 131242-WST02-DR-1102 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7750 | NA | 131242-WST02-DR-7750 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7751 | NA | 131242-WST02-DR-7751 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7752 | NA | 131242-WST02-DR-7752 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-06-11 | 2025-02-25 | NA | 000000 | 2024-06-11, 2024-10-05, 2025-02-25 | 00 | 3 | PEN | AWC | AWC
000246 | 00 | Lilian | PMT | NA | 131242 | WSW41 | LT | PM | 0017 | 0 | 131242-WSW41-LT-0017 | 2023-12-18 | THP Layout and Code Compliance | As requested by contractor via email dated 5 Feb 24 to withdraw the submission. | 2024-01-17 | 2024-02-06 | 14 | (VOID / NOT IN USE) | NO |  | YES |  |  |  |  | NA | "THP Layout and Code Compliance" | 2023-12-18 | 2023-12-18 | 0 | 000246 | 2023-12-18 | 00 | 1 | PEN | PEN | PEN
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1011 | 0 | 131242-WSW41-SD-1011 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 |  | Not Approved | YES | 2024-02-02 | NO | Overdue | 507 |  | Zora checking comment sheet | NA | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | 2023-12-21 | 0 | 000247 | 2023-12-21 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | SD | S | 1012 | NA | 131242-WSW41-SD-1012 | 2023-12-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-22 | 2024-01-15 |  | Not Approved | YES | 2024-02-02 | NO | Overdue | 507 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-21 | 2023-12-21 | NA | 000000 | 2023-12-21 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | SD | S | 1013 | NA | 131242-WSW41-SD-1013 | 2023-12-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-22 | 2024-01-15 |  | Not Approved | YES | 2024-02-02 | NO | Overdue | 507 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-21 | 2023-12-21 | NA | 000000 | 2023-12-21 | 00 | 1 | PEN | NAP | NAP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-8000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | A | 000000&&000248 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0001_ST601 | NA | 131242-WST00-DR-0001_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "IFC of ST601 – ERSS < 4m " && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | E | 000000&&000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601 | NA | 131242-WST00-DR-0002_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601 | NA | 131242-WST00-DR-1000_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1001_ST601 | NA | 131242-WST00-DR-1001_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1002_ST601 | NA | 131242-WST00-DR-1002_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1003_ST601 | NA | 131242-WST00-DR-1003_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601 | NA | 131242-WST00-DR-1004_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | CL | G | 0001_ST601 | NA | 131242-WST00-CL-0001_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3000_ST601 | NA | 131242-WST00-DR-3000_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | CH | IM | 0003_ST601 | NA | 131242-WST00-CH-0003_ST601 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 2 | PEN | NAP | NAP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-0001_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "IFC of ST601 – ERSS < 4m " && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | E | 000000&&000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601 | NA | 131242-WST00-DR-0002_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601 | NA | 131242-WST00-DR-1000_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1001_ST601 | NA | 131242-WST00-DR-1001_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1002_ST601 | NA | 131242-WST00-DR-1002_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1003_ST601 | NA | 131242-WST00-DR-1003_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601 | NA | 131242-WST00-DR-1004_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-8000_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | A | 000000&&000248 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3000_ST601 | NA | 131242-WST00-DR-3000_ST601 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00 | 4 | PEN | NAP | NAP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-0001_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-06 | 2024-05-20 | 10 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | 2024-07-19 | Heng Peng to clear BIM comments. Pending BIM updates | NA | "IFC of ST601 – ERSS < 4m " && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | E | 000000&&000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601 | NA | 131242-WST00-DR-0002_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601 | NA | 131242-WST00-DR-1000_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1001_ST601 | NA | 131242-WST00-DR-1001_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1002_ST601 | NA | 131242-WST00-DR-1002_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1003_ST601 | NA | 131242-WST00-DR-1003_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601 | NA | 131242-WST00-DR-1004_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-8000_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | A | 000000&&000248 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3000_ST601 | NA | 131242-WST00-DR-3000_ST601 | 2024-04-15 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-14 | 2024-05-20 | 4 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00 | 4 | PEN | AWC | AWC
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST602 | A | 131242-WST00-DR-8001_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0100_ST602 | NA | 131242-WST00-DR-0100_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0101_ST602 | NA | 131242-WST00-DR-0101_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1100_ST602 | NA | 131242-WST00-DR-1100_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1101_ST602 | NA | 131242-WST00-DR-1101_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1102_ST602 | NA | 131242-WST00-DR-1102_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | CL | G | 0002_ST602 | NA | 131242-WST00-CL-0002_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3100_ST602 | NA | 131242-WST00-DR-3100_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | CH | IM | 0004_ST602 | NA | 131242-WST00-CH-0004_ST602 | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA | 2023-12-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-23 | 2024-01-16 |  | Not Approved | YES | 2024-02-05 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2023-12-22 | NA | 000000 | 2023-12-22 | 00 | 2 | PEN | NAP | NAP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-8001_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0100_ST602 | NA | 131242-WST00-DR-0100_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0101_ST602 | NA | 131242-WST00-DR-0101_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1100_ST602 | NA | 131242-WST00-DR-1100_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1101_ST602 | NA | 131242-WST00-DR-1101_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1102_ST602 | NA | 131242-WST00-DR-1102_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3100_ST602 | NA | 131242-WST00-DR-3100_ST602 | 2024-02-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-22 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-8001_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-11 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | YES | Resubmitted |  |  | Pending Tenwit update. (Roobin) | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0100_ST602 | NA | 131242-WST00-DR-0100_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0101_ST602 | NA | 131242-WST00-DR-0101_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1100_ST602 | NA | 131242-WST00-DR-1100_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1101_ST602 | NA | 131242-WST00-DR-1101_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1102_ST602 | NA | 131242-WST00-DR-1102_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3100_ST602 | NA | 131242-WST00-DR-3100_ST602 | 2024-06-21 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-19 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | NAP | NAP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A.1 | 131242-WST00-DR-8001_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  | R2_APP | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0100_ST602 | NA | 131242-WST00-DR-0100_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0101_ST602 | NA | 131242-WST00-DR-0101_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1100_ST602 | NA | 131242-WST00-DR-1100_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1101_ST602 | NA | 131242-WST00-DR-1101_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1102_ST602 | NA | 131242-WST00-DR-1102_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3100_ST602 | NA | 131242-WST00-DR-3100_ST602 | 2024-07-02 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-22 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-02 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00 | 4 | PEN | APP | APP
000250 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0001 | 0 | 131242-WSW41-VI-0001 | 2023-12-22 | Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-23 | 2024-02-26 | 23 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | PEN | AWC | AWC
000251 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 0 | 131242-WST02-BQ-0001 | 2023-12-26 | C4B SSN PLC/ RIO Panel Component Catalogue | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-24 | 2024-01-29 | 3 | Not Approved | YES | 2024-02-19 | YES | Resubmitted |  |  |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | NAP | NAP
000251 | 01 | Low | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 1 | 131242-WST02-BQ-0001 | 2024-04-08 | C4B SSN PLC/ RIO Panel Component Catalogue | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-29 | 2024-05-15 | 11 | Not Approved | YES | 2024-06-05 | NO | Overdue | 424 |  | Pending from MP | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | NAP | NAP
000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | A | 131242-WSW41-DR-1000 | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | 15 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  | ?? |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 3000 | NA | 131242-WSW41-DR-3000 | 2023-12-27 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-25 | 2024-02-16 | 15 | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | NAP | NAP
000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-1000 | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | 32 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | 2025-02-19 |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 3000 | NA | 131242-WSW41-DR-3000 | 2024-07-06 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-07-25 | 2024-09-10 | 32 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | AWC | AWC
000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | C | 131242-WSW41-DR-1000 | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | 33 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Drawing of Pre-Con Topographical Survey" && "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | 2026-01-19 | C | 000000&&000051&&000252 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | EK | 3000 | NA | 131242-WSW41-DR-3000 | 2025-02-25 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-03-17 | 2025-05-06 | 33 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-27 | 2026-01-19 | NA | 000000 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, NA | 10 | PEN | AWC | AWC
000253 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0013 | 0 | 131242-WSW41-MI-0013 | 2023-12-27 | Process & MEICA Meeting Minutes 0013_20231123 | Rev 0: For Information | 2024-01-25 | 2024-05-21 | 79 | For Information | NO |  | YES |  |  | 2024-03-06 | Waiting for C2D reply | NA | "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-14 | 2024-08-07 | 0 | 000000&&000184&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | PEN | INF | INF
000254 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0018 | 0 | 131242-WSW41-LT-0018 | 2023-12-28 | CV of WSHS | Approved | 2024-01-26 | 2024-02-14 | 12 | Approved | NO |  | YES |  |  |  |  | NA | "CV of WSHS" | 2023-12-28 | 2023-12-28 | 0 | 000254 | 2023-12-28 | 00 | 1 | PEN | APP | APP
000255 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0011 | 0 | 131242-WSD11-CD-0011 | 2023-12-28 | Submission of Milestone 1.1 THP MCC Room | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-01-26 | 2024-03-28 | 43 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Submission of Milestone 1.1 THP MCC Room" | 2023-12-28 | 2023-12-28 | 0 | 000255 | 2023-12-28 | 00 | 1 | PEN | AWC | AWC
000255 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-0034 | 2024-06-04 | Milestone 1.2 THP MCC Room | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-12-05 | 115 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | PEN | AWC | AWC
000255 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-0034 | 2025-02-26 | Milestone 2 THP MCC Room | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 72 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | PEN | AWC | AWC
000255 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 1 | 131242-WSD11-CD-0034 | 2025-10-31 | Milestone 3 THP MCC Room | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-23 | 66 | Approved with Comments | YES | 2026-03-13 | NO |  |  |  |  | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | PEN | AWC | AWC
000256 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0003 | 0 | 131242-WSW41-CT-0003 | 2023-12-28 | On-Demand Bond for SSN | Approved. Address as per Chin Swee Rd address as the bond was submitted (in Nov 2023) was prior to the notice (in Dec 2023) of change of address. | 2024-01-26 | 2024-01-16 |  | Approved | NO |  | YES |  |  |  |  | NA | "On-Demand Bond for SSN" | 2023-12-28 | 2023-12-28 | 0 | 000256 | 2023-12-28 | 00 | 1 | PEN | APP | APP
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6200 | 0 | 131242-WSD11-DR-6200 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 24 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  | 2024-03-15 | Related to Detailed Design Report. | NA | "P&ID of THP General System" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | B | 000000&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6300 | NA | 131242-WSD11-DR-6300 | 2023-12-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-26 | 2024-03-01 | 24 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6400 | NA | 131242-WSD11-DR-6400 | 2023-12-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-26 | 2024-03-01 | 24 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6600 | NA | 131242-WSD11-DR-6600 | 2023-12-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-26 | 2024-03-01 | 24 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6601 | NA | 131242-WSD11-DR-6601 | 2023-12-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-26 | 2024-03-01 | 24 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | B | 131242-WSD11-DR-6200 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 11 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  | Heng Peng to provide DGN dwg | NA | "P&ID of THP General System" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | B | 000000&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6300 | NA | 131242-WSD11-DR-6300 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6400 | NA | 131242-WSD11-DR-6400 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6600 | NA | 131242-WSD11-DR-6600 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6601 | NA | 131242-WSD11-DR-6601 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-28 | 2025-06-17 | NA | 000000 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6101 | NA | 131242-WSD11-DR-6101 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6121 | NA | 131242-WSD11-DR-6121 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-03-19 | 2025-06-17 | NA | 000000 | 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 3 | PEN | AWC | AWC
000258 | 00 | Yi Hao | Contracts | NA | 131242 | WST02 | PO | P | 0001 | 0 | 131242-WST02-PO-0001 | 2024-01-03 | Unpriced PO for SSN Package (MattenPlant) | For Information | 2024-01-31 | 2024-04-26 | 59 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for SSN Package (MattenPlant)" | 2024-01-03 | 2024-01-03 | 0 | 000258 | 2024-01-03 | 00 | 1 | PEN | INF | INF
000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0014 | 0 | 131242-WSW41-MI-0014 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | 75 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | P | 0015 | NA | 131242-WSW41-MI-0015 | 2024-01-03 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-01-31 | 2024-05-21 | 75 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-14 | 2024-09-04 | 0 | 000000&&000240&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | PEN | INF | INF
000260 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0013 | 0 | 131242-WST02-CD-0013 | 2024-01-05 | Milestone 1.1 SSN Overall Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-02-02 | 2024-03-28 | 38 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Electrical Signal List for SSN -LVSG-0101A/0101B" && "Milestone 1.1 SSN Overall Area" | 2024-01-05 | 2025-06-09 | 1 | 000260&&001331 | 2024-01-05, 2025-05-30, 2025-06-09 | 00, 01 | 3 | PEN | AWC | AWC
000260 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0038 | 0 | 131242-WST02-CD-0038 | 2024-06-11 | Milestone 1.2 SSN Overall Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 3 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 SSN Overall Area" | 2024-06-11 | 2024-06-11 | 0 | 000260 | 2024-06-11 | 01 | 1 | PEN | AWC | AWC
000260 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-0058 | 2025-05-15 | Milestone 2 SSN Overall Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-05-15 | 2025-10-31 | 0 | 000260 | 2025-05-15, 2025-10-31 | 02, 03 | 2 | PEN | AWC | AWC
000260 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-0058 | 2025-10-31 | Milestone 3 SSN Overall Area | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 47 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-05-15 | 2025-10-31 | 0 | 000260 | 2025-05-15, 2025-10-31 | 02, 03 | 2 | PEN | AWC | AWC
000261 | 00 | Lilian | PMT | NA | 131242 | WSW41 | PC | W | 0006 | 0 | 131242-WSW41-PC-0006 | 2024-01-08 | PAYMENT CLAIM NO.6 | Approved. Please refer to S.O. correspondence no. 103 dated 8 Jan 2024. | 2024-02-05 | 2024-01-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "PAYMENT CLAIM NO.6" | 2024-01-08 | 2024-01-08 | 0 | 000261 | 2024-01-08 | 00 | 1 | PEN | APP | APP
000262 | 00 | Geno | Piping | NA | 131242 | WST02 | SH | M | 1002 | 0 | 131242-WST02-SH-1002 | 2024-01-08 | Tie in Schedule for SSN | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-05 | 2024-05-27 | 75 | Approved with Comments | YES | 2024-06-14 | NO | Overdue | 417 | 2025-02-26 | Waiting for SO RFI reply . KM & Qili to check with Karthic for the response | NA | "Tie in Schedule for SSN" | 2024-01-08 | 2024-01-08 | 0 | 000262 | 2024-01-08 | 00 | 1 | PEN | AWC | AWC
000263 | 00 | Geno | Piping | NA | 131242 | WSD11 | SH | M | 1001 | 0 | 131242-WSD11-SH-1001 | 2024-01-09 | Tie in Schedule for THP | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 74 | Approved with Comments | YES | 2024-06-14 | NO | Overdue | 417 | 2025-02-26 |  | NA | "Tie in Schedule for THP" | 2024-01-09 | 2024-01-09 | 0 | 000263 | 2024-01-09 | 00 | 1 | PEN | AWC | AWC
000264 | 00 | Geno | Piping | NA | 131242 | WSW41 | SH | M | 5000 | 0 | 131242-WSW41-SH-5000 | 2024-01-09 | Tie in Schedule for Side wide | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 74 | Approved with Comments | YES | 2024-06-14 | NO | Overdue | 417 | 2025-02-26 |  | NA | "Tie in Schedule for Side wide" | 2024-01-09 | 2024-01-09 | 0 | 000264 | 2024-01-09 | 00 | 1 | PEN | AWC | AWC
000265 | 00 | Lilian/ Yi Hao | PMT | NA | 131242 | WSW41 | LT | PM | 0019 | 0 | 131242-WSW41-LT-0019 | 2024-01-09 | Notice of Office Relocation | For Information | 2024-02-06 | 2024-05-02 | 58 | For Information | NO |  | YES |  |  |  |  | NA | "Notice of Office Relocation" | 2024-01-09 | 2024-01-09 | 0 | 000265 | 2024-01-09 | 00 | 1 | PEN | INF | INF
000266 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0013 | 0 | 131242-WSW41-CD-0013 | 2024-01-09 | Submission Of BIM Coordination VCM Model (Dec – 2023) | For Information | 2024-02-06 | 2024-01-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Dec – 2023)" | 2024-01-09 | 2024-01-09 | 0 | 000266 | 2024-01-09 | 00 | 1 | PEN | INF | INF
000267 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0016 | 0 | 131242-WSW41-MI-0016 | 2024-01-09 | CSA Meeting Minutes 0016_20231130 | For Information | 2024-02-06 | 2024-01-25 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | PEN | INF | INF
000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0014 | 0 | 131242-WSW41-MI-0014 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0015 | NA | 131242-WSW41-MI-0015 | 2024-01-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-06 | 2024-01-19 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-14 | 2024-09-04 | 0 | 000000&&000240&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | PEN | INF | INF
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6050 | A | 131242-WSD11-DR-6050 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  | 2024-03-15 | Related to Detailed Design Report. | NA | "P&ID of THP General System [Part 2]" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6063 | NA | 131242-WSD11-DR-6063 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6070 | NA | 131242-WSD11-DR-6070 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | B | 131242-WSD11-DR-6050 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 11 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  | Heng Peng to provide DGN dwg | NA | "P&ID of THP General System [Part 2]" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6063 | NA | 131242-WSD11-DR-6063 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6070 | NA | 131242-WSD11-DR-6070 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6019 | A | 131242-WSD11-DR-6019 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | Resubmitted | Related to Detailed Design Report. | NA | "P&ID of THP Train 2 " && "P&ID of THP Train 2 " && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6020 | NA | 131242-WSD11-DR-6020 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6021 | NA | 131242-WSD11-DR-6021 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6022 | NA | 131242-WSD11-DR-6022 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6023 | NA | 131242-WSD11-DR-6023 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6024 | NA | 131242-WSD11-DR-6024 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6025 | NA | 131242-WSD11-DR-6025 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6026 | NA | 131242-WSD11-DR-6026 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6027 | NA | 131242-WSD11-DR-6027 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6028 | NA | 131242-WSD11-DR-6028 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6029 | NA | 131242-WSD11-DR-6029 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6030 | NA | 131242-WSD11-DR-6030 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6031 | NA | 131242-WSD11-DR-6031 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6032 | NA | 131242-WSD11-DR-6032 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6033 | NA | 131242-WSD11-DR-6033 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6034 | NA | 131242-WSD11-DR-6034 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6035 | NA | 131242-WSD11-DR-6035 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6036 | NA | 131242-WSD11-DR-6036 | 2024-01-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-07 | 2024-03-01 | 16 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | B | 131242-WSD11-DR-6019 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 11 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 |  | Heng Peng to provide DGN dwg | NA | "P&ID of THP Train 2 " && "P&ID of THP Train 2 " && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | B | 000000&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6020 | NA | 131242-WSD11-DR-6020 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6021 | NA | 131242-WSD11-DR-6021 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6022 | NA | 131242-WSD11-DR-6022 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6023 | NA | 131242-WSD11-DR-6023 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6024 | NA | 131242-WSD11-DR-6024 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6025 | NA | 131242-WSD11-DR-6025 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6026 | NA | 131242-WSD11-DR-6026 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6027 | NA | 131242-WSD11-DR-6027 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6028 | NA | 131242-WSD11-DR-6028 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6029 | NA | 131242-WSD11-DR-6029 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6030 | NA | 131242-WSD11-DR-6030 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6031 | NA | 131242-WSD11-DR-6031 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6032 | NA | 131242-WSD11-DR-6032 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6033 | NA | 131242-WSD11-DR-6033 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6034 | NA | 131242-WSD11-DR-6034 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6035 | NA | 131242-WSD11-DR-6035 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | P | 6036 | NA | 131242-WSD11-DR-6036 | 2024-03-19 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-04-18 | 2024-04-25 | 5 | Approved with Comments | YES | 2024-05-16 | NO | Overdue | 437 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-10 | 2025-06-17 | NA | 000000 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00 | 4 | PEN | AWC | AWC
000271 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0013 | 0 | 131242-WSW41-VI-0013 | 2024-01-11 | Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd) | Approved | 2024-02-08 | 2024-01-22 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd)" | 2024-01-11 | 2024-01-11 | 0 | 000271 | 2024-01-11 | 00 | 1 | PEN | APP | APP
000272 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | E | 8001 | 0 | 131242-WSD11-DR-8001 | 2024-01-11 | THP ATEX Zone Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached files for comments. | 2024-02-08 | 2024-05-15 | 65 | Not Approved | YES | 2024-06-05 | NO | Overdue | 424 | 2024-07-26 |  | NA | "THP ATEX Zone Drawing" | 2024-01-11 | 2024-01-11 | 0 | 000272 | 2024-01-11 | 00 | 1 | PEN | NAP | NAP
000273 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | LT | IM | 0001 | 0 | 131242-WSW41-LT-0001 | 2024-01-12 | Common Data Environment (CDE) Set-Up and Rollout | For Information. This document should be part of BEP under CDE workflow | 2024-02-09 | 2024-02-27 | 11 | For Information | NO |  | YES |  |  |  |  | NA | "Approval Letter to Commence Works Requiring Earth Control Measure" && "Common Data Environment (CDE) Set-Up and Rollout" | 2023-11-02 | 2024-01-12 | 0 | 000156&&000273 | 2023-11-02, 2024-01-12 | 00 | 2 | PEN | INF | INF
000274 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 0 | 131242-WST02-CL-0003_ST612 | 2024-01-13 | ST612_Typical Railing Design Calculation | Rev 0: Not Approved. Please refer to comment sheet for resubmission. Drawing attached should be for information not "shop drawing". | 2024-02-09 | 2024-02-01 |  | Not Approved | YES | 2024-02-22 | YES | Resubmitted |  |  |  | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000274 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 1 | 131242-WST02-CL-0003_ST612 | 2024-02-16 | ST612_Typical Railing Design Calculation | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-03-05 |  | Not Approved | YES | 2024-03-25 | YES | Resubmitted |  |  |  | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000274 | 02 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 2 | 131242-WST02-CL-0003_ST612 | 2024-03-20 | ST612_Typical Railing Design Calculation | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-11 | 2024-05-13 | 21 | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  |  |  | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000274 | 03 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 3 | 131242-WST02-CL-0003_ST612 | 2024-06-06 | ST612_Typical Railing Design Calculation | Rev.3:Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-07-05 | 6 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | 2024-07-18 |  | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612 | A | 131242-WST02-DR-8600_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  |  |  | NA | "ST612_Typical Railing Design Calculation" | 2024-07-31 | 2024-07-31 | A | 000274 | 2024-07-31 | 04 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5600_ST612 | NA | 131242-WST02-DR-5600_ST612 | 2024-07-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-08-21 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST612_Typical Railing " | 2024-07-31 | 2025-08-13 | I | 000000&&000274 | 2024-07-31, 2025-08-13 | 00, 05 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5601_ST612 | NA | 131242-WST02-DR-5601_ST612 | 2024-07-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-08-21 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-07-31 | 2025-08-13 | NA | 000000 | 2024-07-31, 2025-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5602_ST612 | NA | 131242-WST02-DR-5602_ST612 | 2024-07-31 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-08-21 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-07-31 | 2025-08-13 | NA | 000000 | 2024-07-31, 2025-08-13 | 00 | 2 | PEN | AWC | AWC
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | I | 131242-WST02-DR-5600_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 4 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "ST612_Typical Railing " | 2024-07-31 | 2025-08-13 | I | 000000&&000274 | 2024-07-31, 2025-08-13 | 00, 05 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5601_ST612 | NA | 131242-WST02-DR-5601_ST612 | 2025-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-02 | 2025-09-08 | 4 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-07-31 | 2025-08-13 | NA | 000000 | 2024-07-31, 2025-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5602_ST612 | NA | 131242-WST02-DR-5602_ST612 | 2025-08-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-09-02 | 2025-09-08 | 4 | Approved with Comments | YES | 2025-09-26 | NO | Overdue | 86 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-07-31 | 2025-08-13 | NA | 000000 | 2024-07-31, 2025-08-13 | 00 | 2 | PEN | AWC | AWC
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A | 131242-WST02-DR-1000_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  |  |  | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST613 | NA | 131242-WST02-DR-1006_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST613 | NA | 131242-WST02-DR-1007_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST613 | NA | 131242-WST02-DR-1008_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1013_ST613 | NA | 131242-WST02-DR-1013_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1014_ST613 | NA | 131242-WST02-DR-1014_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1015_ST613 | NA | 131242-WST02-DR-1015_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1016_ST613 | NA | 131242-WST02-DR-1016_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1017_ST613 | NA | 131242-WST02-DR-1017_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1018_ST613 | NA | 131242-WST02-DR-1018_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1019_ST613 | NA | 131242-WST02-DR-1019_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1020_ST613 | NA | 131242-WST02-DR-1020_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1021_ST613 | NA | 131242-WST02-DR-1021_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1022_ST613 | NA | 131242-WST02-DR-1022_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3005_ST613 | NA | 131242-WST02-DR-3005_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3008_ST613 | NA | 131242-WST02-DR-3008_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3009_ST613 | NA | 131242-WST02-DR-3009_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5005_ST613 | NA | 131242-WST02-DR-5005_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5006_ST613 | NA | 131242-WST02-DR-5006_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST613 | NA | 131242-WST02-DR-7002_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7003_ST613 | NA | 131242-WST02-DR-7003_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7004_ST613 | NA | 131242-WST02-DR-7004_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7005_ST613 | NA | 131242-WST02-DR-7005_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8003_ST613 | NA | 131242-WST02-DR-8003_ST613 | 2024-01-13 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-09 | 2024-02-14 | 2 | Not Approved | YES | 2024-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A.1 | 131242-WST02-DR-1000_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-04-25 | 2024-05-16 | 14 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | 2024-07-19 | Heng Peng: BIM to clear Aaron comments | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST613 | NA | 131242-WST02-DR-1006_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST613 | NA | 131242-WST02-DR-1007_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST613 | NA | 131242-WST02-DR-1008_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1013_ST613 | NA | 131242-WST02-DR-1013_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1014_ST613 | NA | 131242-WST02-DR-1014_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1015_ST613 | NA | 131242-WST02-DR-1015_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1016_ST613 | NA | 131242-WST02-DR-1016_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1017_ST613 | NA | 131242-WST02-DR-1017_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1018_ST613 | NA | 131242-WST02-DR-1018_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1019_ST613 | NA | 131242-WST02-DR-1019_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1020_ST613 | NA | 131242-WST02-DR-1020_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1021_ST613 | NA | 131242-WST02-DR-1021_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1022_ST613 | NA | 131242-WST02-DR-1022_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3005_ST613 | NA | 131242-WST02-DR-3005_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3008_ST613 | NA | 131242-WST02-DR-3008_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3009_ST613 | NA | 131242-WST02-DR-3009_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5005_ST613 | NA | 131242-WST02-DR-5005_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5006_ST613 | NA | 131242-WST02-DR-5006_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST613 | NA | 131242-WST02-DR-7002_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7003_ST613 | NA | 131242-WST02-DR-7003_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7004_ST613 | NA | 131242-WST02-DR-7004_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7005_ST613 | NA | 131242-WST02-DR-7005_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8003_ST613 | NA | 131242-WST02-DR-8003_ST613 | 2024-04-04 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-06 | 2024-05-16 | 8 | Not Approved | YES | 2024-06-06 | NO | Overdue | 423 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | NAP | NAP
000276 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0008 | 0 | 131242-WSW41-RT-0008 | 2024-01-16 | C4B Monthly Progress Report Number No.08 (12/23) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-02-14 | 2024-01-31 |  | Approved with Comments | YES | 2024-02-21 | NO | Overdue | 495 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | PEN | AWC | AWC
000277 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 0 | 131242-WSW41-LC-0001 | 2024-01-16 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. Please append COS. | 2024-02-14 | 2024-01-22 |  | For Information | YES | 2024-02-09 | YES | Resubmitted |  |  |  | NA | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" && "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | 2025-08-25 | 0 | 000277&&001620 | 2024-01-16, 2024-02-02, 2025-08-25 | 00, 01 | 3 | PEN | INF | INF
000277 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 1 | 131242-WSW41-LC-0001 | 2024-02-02 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. | 2024-02-23 | 2024-02-19 |  | For Information | NO |  | YES |  |  |  |  | NA | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" && "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | 2025-08-25 | 0 | 000277&&001620 | 2024-01-16, 2024-02-02, 2025-08-25 | 00, 01 | 3 | PEN | INF | INF
000278 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0001 | 0 | 131242-WSD11-RT-0001 | 2024-01-17 | THP - Basis of Design Report | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-15 | 2024-03-01 | 11 | Approved with Comments | YES | 2024-03-21 | NO | Overdue | 474 | 2024-07-19 |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | AWC | AWC
000279 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0016 | 0 | 131242-WSW41-MI-0016 | 2024-01-18 | Process & MEICA Meeting Minutes 0016_20240104 | Rev 0: For Information | 2024-02-16 | 2024-05-21 | 64 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | PEN | INF | INF
000280 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0020 | 0 | 131242-WSW41-LT-0020 | 2024-01-20 | CV of Team Member (ECO cum ECMO) | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-19 | 2024-02-01 |  | Not Approved | YES | 2024-02-22 | YES | Resubmitted |  |  |  | NA | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-01-20 | 2024-04-12 | 1 | 000280 | 2024-01-20, 2024-04-12 | 00, 01 | 2 | PEN | NAP | NAP
000280 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0020 | 1 | 131242-WSW41-LT-0020 | 2024-04-12 | CV of Team Member (ECO) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 23 | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-01-20 | 2024-04-12 | 1 | 000280 | 2024-01-20, 2024-04-12 | 00, 01 | 2 | PEN | APP | APP
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 1100 | A | 131242-WSW41-DR-1100 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 57 | Approved with Comments | YES | 2024-06-05 | YES | Resubmitted |  | To withdraw | Combined with Prolog 000252 - Sitewide Piperack Lightning Protection System | NA | "Sitewide Piperack Earthing System" | 2024-01-23 | 2026-01-19 | A | 000000&&000281 | 2024-01-23, 2026-01-19 | 00, NA | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | E | 2000 | NA | 131242-WSW41-DR-2000 | 2024-01-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-21 | 2024-05-15 | 57 | Approved with Comments | YES | 2024-06-05 | NO | Overdue | 424 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-23 | 2026-01-19 | NA | 000000 | 2024-01-23, 2026-01-19 | 00, NA | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | E | 5000 | NA | 131242-WSW41-DR-5000 | 2024-01-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-21 | 2024-05-15 | 57 | Approved with Comments | YES | 2024-06-05 | NO | Overdue | 424 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2024-01-23 | 2026-01-19 | A | 000000&&001136 | 2024-01-23, 2025-03-20, 2026-01-19 | 00, NA | 3 | PEN | AWC | AWC
000282 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0021 | 0 | 131242-WSW41-LT-0021 | 2024-01-23 | Assign of Builder License (CES_SDC Pte. Ltd.) | For Information | 2024-02-21 | 2024-05-10 | 54 | For Information | NO |  | YES |  |  |  |  | NA | "Assign of Builder License (CES_SDC Pte. Ltd.)" | 2024-01-23 | 2024-01-23 | 0 | 000282 | 2024-01-23 | 00 | 1 | PEN | INF | INF
000283 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0007 | 0 | 131242-WSW41-MI-0007 | 2024-01-23 | Monthly Progress Meeting Minutes 0007_20231219 | For Information | 2024-02-21 | 2024-01-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | PEN | INF | INF
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-1000_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  |  |  | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-16 | B | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 8000_ST604 | NA | 131242-WST02-DR-8000_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-02-16 | 2024-02-16 | NA | 000000 | 2024-02-16 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604 | NA | 131242-WST02-DR-1001_ST604 | 2024-01-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-21 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1002_ST604 | NA | 131242-WST02-DR-1002_ST604 | 2024-01-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-21 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-23 | 2024-02-16 | NA | 000000 | 2024-01-23, 2024-02-16 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604 | NA | 131242-WST02-DR-7000_ST604 | 2024-01-23 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-21 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604 | NA | 131242-WST02-DR-5001_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-15 |  | Not Approved | YES | 2024-03-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00 | 5 | PEN | NAP | NAP
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-1000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 |  | Zora to reply. (Refer to submission 340 Amendment of ST604) | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-16 | B | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 8000_ST604 | NA | 131242-WST02-DR-8000_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-02-16 | 2024-02-16 | NA | 000000 | 2024-02-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1001_ST604 | NA | 131242-WST02-DR-1001_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1002_ST604 | NA | 131242-WST02-DR-1002_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-23 | 2024-02-16 | NA | 000000 | 2024-01-23, 2024-02-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7000_ST604 | NA | 131242-WST02-DR-7000_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5001_ST604 | NA | 131242-WST02-DR-5001_ST604 | 2024-02-16 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-15 | 2024-02-29 |  | Approved with Comments | YES | 2024-03-20 | NO | Overdue | 475 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-08-24 | 2024-02-16 | NA | 000000 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00 | 5 | PEN | AWC | AWC
000285 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0007 | 0 | 131242-WSW41-PS-0007 | 2024-01-24 | Monthly Progress Presentation No. 07 (1123) | For Information | 2024-02-22 | 2024-01-29 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for Feb 2024" && "Monthly Progress Presentation No. 07 (1123)" | 2024-01-24 | 2024-03-14 | 0 | 000285&&000362 | 2024-01-24, 2024-03-14 | 00 | 2 | PEN | INF | INF
000286 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0008 | 0 | 131242-WSW41-PS-0008 | 2024-01-24 | Monthly Progress Presentation No. 08 (1223) | For Information | 2024-02-22 | 2024-01-25 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 08 (1223)" && "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | 2024-01-24 | 2024-04-30 | 0 | 000286&&000457 | 2024-01-24, 2024-04-30 | 00 | 2 | PEN | INF | INF
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5000_ST604 | A | 131242-WST02-SD-5000_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  |  |  | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | C | 5001_ST604 | NA | 131242-WST02-SD-5001_ST604 | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | C | 5002_ST604 | NA | 131242-WST02-SD-5002_ST604 | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | C | 5003_ST604 | NA | 131242-WST02-SD-5003_ST604 | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | C | 5004_ST604 | NA | 131242-WST02-SD-5004_ST604 | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | C | 8000_ST604 | NA | 131242-WST02-SD-8000_ST604 | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing | NA | NA | NA | NA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing -NA-NA-NA | 2024-01-24 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-02-22 | 2024-02-21 |  | Not Approved | YES | 2024-03-12 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-01-24 | NA | 000000 | 2024-01-24 | 00 | 1 | PEN | NAP | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5000_ST604 | B | 131242-WST02-SD-5000_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-15 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  |  |  | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5001_ST604 | NA | 131242-WST02-SD-5001_ST604 | 2024-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5002_ST604 | NA | 131242-WST02-SD-5002_ST604 | 2024-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5003_ST604 | NA | 131242-WST02-SD-5003_ST604 | 2024-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5004_ST604 | NA | 131242-WST02-SD-5004_ST604 | 2024-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 8000_ST604 | NA | 131242-WST02-SD-8000_ST604 | 2024-02-26 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-01-24 | 2024-02-26 | NA | 000000 | 2024-01-24, 2024-02-26 | 00 | 2 | PEN | NAP | NAP
000287 | 02 | Zora | CSA | NA | 131242 | NA | SD | S | Relpy to comment Sheet | NA | 131242-NA-SD-Relpy to comment Sheet | 2024-02-28 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1&2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-03-20 | 1 | Approved with Comments | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-28 | 2024-02-28 | NA | 000287 | 2024-02-28 | 02 | 1 | PEN | AWC | AWC
000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5000_ST604 | D | 131242-WST02-SD-5000_ST604 | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-21 | 8 | Approved with Comments | YES | 2024-06-11 | NO | Overdue | 420 |  |  | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5012_ST604 | NA | 131242-WST02-SD-5012_ST604 | 2024-04-18 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-05-17 | 2024-05-21 | 2 | Approved with Comments | YES | 2024-06-11 | NO | Overdue | 420 | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-04-18 | 2024-04-18 | NA | 000000 | 2024-04-18 | 00 | 1 | PEN | AWC | AWC
000288 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0007 | 0 | 131242-WSW41-PC-0007 | 2024-01-24 | PAYMENT CLAIM NO.7 | Approved. Please refer to S.O. correspondence no. 116 dated 25 Jan 2024. | 2024-02-22 | 2024-02-15 |  | Approved | NO |  | YES |  |  |  |  | NA | "PAYMENT CLAIM NO.7" | 2024-01-24 | 2024-01-24 | 0 | 000288 | 2024-01-24 | 00 | 1 | PEN | APP | APP
000289 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 0 | 131242-WSW41-CN-0001 | 2024-01-26 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-02-26 | 2024-04-17 | 35 | Not Approved | YES | 2024-05-08 | YES | Resubmitted |  |  |  | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | NAP | NAP
000289 | 01 | Low | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 1 | 131242-WSW41-CN-0001 | 2024-04-19 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 1: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-05-21 | 7 | Rejected | YES | 2024-06-11 | NO | Overdue | 420 |  | (RFC) NO.: 1230207-RFC-0004 R1 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | REJ | REJ
000290 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | I | 0002 | 0 | 131242-WSD11-DS-0002 | 2024-02-01 | Control Valves Data Sheet (THP) | Rev 0: Not approved - Revise and Resubmit | 2024-03-01 | 2024-04-29 | 39 | Not Approved | YES | 2024-05-20 | NO | Overdue | 435 | 2024-08-02 |  | NA | "Control Valves Data Sheet (THP)" | 2024-02-01 | 2024-02-01 | 0 | 000290 | 2024-02-01 | 00 | 1 | PEN | NAP | NAP
000291 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0015 | 0 | 131242-WSD11-CD-0015 | 2024-02-01 | Milestone 1.1 THP EICA Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 19 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 THP EICA Silo Area inside Biosolid Building" | 2024-02-01 | 2024-02-01 | 0 | 000291 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000291 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-0033 | 2024-06-04 | Milestone 1.2 THP EICA Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 8 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0_wd | 131242-WSD11-CD-0033 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 12 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1030 | NA | 131242-WSD11-DR-1030 | 2024-12-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-31 | 2025-01-17 | 12 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-10 | 2025-10-28 | NA | 000000 | 2024-12-10, 2025-01-22, 2025-10-28 | 00 | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3010 | NA | 131242-WSD11-DR-3010 | 2024-12-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-31 | 2025-01-17 | 12 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3011 | NA | 131242-WSD11-DR-3011 | 2024-12-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-31 | 2025-01-17 | 12 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3012 | NA | 131242-WSD11-DR-3012 | 2024-12-10 | SITE OFFICE LAYOUT (Rev1) | For Information | 2024-12-31 | 2025-01-17 | 12 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | REJ | REJ
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-0033 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 97 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1030 | NA | 131242-WSD11-DR-1030 | 2025-01-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-02-11 | 2025-07-02 | 97 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-10 | 2025-10-28 | NA | 000000 | 2024-12-10, 2025-01-22, 2025-10-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3010 | NA | 131242-WSD11-DR-3010 | 2025-01-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-02-11 | 2025-07-02 | 97 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3011 | NA | 131242-WSD11-DR-3011 | 2025-01-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-02-11 | 2025-07-02 | 97 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3012 | NA | 131242-WSD11-DR-3012 | 2025-01-22 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-02-11 | 2025-07-02 | 97 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 1 | 131242-WSD11-CD-0033 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 70 | Approved with Comments | YES | 2026-03-16 | NO |  |  |  |  | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1030 | NA | 131242-WSD11-DR-1030 | 2025-10-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-17 | 2026-02-24 | 70 | Approved with Comments | YES | 2026-03-16 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-10 | 2025-10-28 | NA | 000000 | 2024-12-10, 2025-01-22, 2025-10-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3010 | NA | 131242-WSD11-DR-3010 | 2025-10-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-17 | 2026-02-24 | 70 | Approved with Comments | YES | 2026-03-16 | NO |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3011 | NA | 131242-WSD11-DR-3011 | 2025-10-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-17 | 2026-02-24 | 70 | Approved with Comments | YES | 2026-03-16 | NO |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3012 | NA | 131242-WSD11-DR-3012 | 2025-10-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-11-17 | 2026-02-24 | 70 | Approved with Comments | YES | 2026-03-16 | NO |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000292 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0017 | 0 | 131242-WSD11-CD-0017 | 2024-02-01 | Milestone 1.1 THP Overall & Equipment Layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 19 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 THP Overall & Equipment Layout" | 2024-02-01 | 2024-02-01 | 0 | 000292 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000292 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-0031 | 2024-06-11 | Milestone 1.2 THP Overall & Equipment Layout | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 3 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | PEN | AWC | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-0031 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 1000 | NA | 131242-WSD11-DR-1000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 1001 | NA | 131242-WSD11-DR-1001 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 3000 | NA | 131242-WSD11-DR-3000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1040 | NA | 131242-WSD11-DR-1040 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1041 | NA | 131242-WSD11-DR-1041 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1042 | NA | 131242-WSD11-DR-1042 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1043 | NA | 131242-WSD11-DR-1043 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3008 | NA | 131242-WSD11-DR-3008 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3009 | NA | 131242-WSD11-DR-3009 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3010 | NA | 131242-WSD11-DR-3010 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3011 | NA | 131242-WSD11-DR-3011 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1043 | NA | 131242-WSD11-DR-1043 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1100 | NA | 131242-WSD11-DR-1100 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Earthing Layout Plan" | 2023-12-12 | 2026-01-12 | C | 000000&&000236 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1101 | NA | 131242-WSD11-DR-1101 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "WD for ST622 " | 2023-12-12 | 2026-01-26 | NA | 000000&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1102 | NA | 131242-WSD11-DR-1102 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1103 | NA | 131242-WSD11-DR-1103 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1104 | NA | 131242-WSD11-DR-1104 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1000 | NA | 131242-WSD11-DR-1000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-1000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1001 | NA | 131242-WSD11-DR-1001 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1002 | NA | 131242-WSD11-DR-1002 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1003 | NA | 131242-WSD11-DR-1003 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1004 | NA | 131242-WSD11-DR-1004 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3018 | NA | 131242-WSD11-DR-3018 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3019 | NA | 131242-WSD11-DR-3019 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3020 | NA | 131242-WSD11-DR-3020 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3021 | NA | 131242-WSD11-DR-3021 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3022 | NA | 131242-WSD11-DR-3022 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3023 | NA | 131242-WSD11-DR-3023 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3024 | NA | 131242-WSD11-DR-3024 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3025 | NA | 131242-WSD11-DR-3025 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3026 | NA | 131242-WSD11-DR-3026 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3027 | NA | 131242-WSD11-DR-3027 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3028 | NA | 131242-WSD11-DR-3028 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-11, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3029 | NA | 131242-WSD11-DR-3029 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3030 | NA | 131242-WSD11-DR-3030 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | 2025-11-28 | A | 000000&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3031 | NA | 131242-WSD11-DR-3031 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3032 | NA | 131242-WSD11-DR-3032 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3033 | NA | 131242-WSD11-DR-3033 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3034 | NA | 131242-WSD11-DR-3034 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3035 | NA | 131242-WSD11-DR-3035 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1120 | NA | 131242-WSD11-DR-1120 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1121 | NA | 131242-WSD11-DR-1121 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1122 | NA | 131242-WSD11-DR-1122 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1123 | NA | 131242-WSD11-DR-1123 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1200 | NA | 131242-WSD11-DR-1200 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "THP Equipment layout" | 2024-08-23 | 2025-11-28 | A | 000000&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1201 | NA | 131242-WSD11-DR-1201 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1202 | NA | 131242-WSD11-DR-1202 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1203 | NA | 131242-WSD11-DR-1203 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1204 | NA | 131242-WSD11-DR-1204 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1205 | NA | 131242-WSD11-DR-1205 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 3000 | NA | 131242-WSD11-DR-3000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 8000 | NA | 131242-WSD11-DR-8000 | 2025-05-09 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-05-29 | 2025-11-14 | 120 | Approved with Comments | YES | 2025-12-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-0031 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | NA | 2025-12-18 |  | 25 | Awaiting S.O.'s response | [7 empty] | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 1000 | NA | 131242-WSD11-DR-1000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 1001 | NA | 131242-WSD11-DR-1001 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BF | 3000 | NA | 131242-WSD11-DR-3000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1040 | NA | 131242-WSD11-DR-1040 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1041 | NA | 131242-WSD11-DR-1041 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1042 | NA | 131242-WSD11-DR-1042 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1043 | NA | 131242-WSD11-DR-1043 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3008 | NA | 131242-WSD11-DR-3008 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3009 | NA | 131242-WSD11-DR-3009 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3010 | NA | 131242-WSD11-DR-3010 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3011 | NA | 131242-WSD11-DR-3011 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1043 | NA | 131242-WSD11-DR-1043 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1100 | NA | 131242-WSD11-DR-1100 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Earthing Layout Plan" | 2023-12-12 | 2026-01-12 | C | 000000&&000236 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, NA | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1101 | NA | 131242-WSD11-DR-1101 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "WD for ST622 " | 2023-12-12 | 2026-01-26 | NA | 000000&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, NA | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1102 | NA | 131242-WSD11-DR-1102 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1103 | NA | 131242-WSD11-DR-1103 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1104 | NA | 131242-WSD11-DR-1104 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-13 | 2025-11-28 | NA | 000000 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1000 | NA | 131242-WSD11-DR-1000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1001 | NA | 131242-WSD11-DR-1001 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1002 | NA | 131242-WSD11-DR-1002 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1003 | NA | 131242-WSD11-DR-1003 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EL | 1004 | NA | 131242-WSD11-DR-1004 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-1000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1001 | NA | 131242-WSD11-DR-1001 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1002 | NA | 131242-WSD11-DR-1002 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1003 | NA | 131242-WSD11-DR-1003 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 1004 | NA | 131242-WSD11-DR-1004 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3018 | NA | 131242-WSD11-DR-3018 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3019 | NA | 131242-WSD11-DR-3019 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3020 | NA | 131242-WSD11-DR-3020 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 10 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3021 | NA | 131242-WSD11-DR-3021 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3022 | NA | 131242-WSD11-DR-3022 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3023 | NA | 131242-WSD11-DR-3023 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3024 | NA | 131242-WSD11-DR-3024 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3025 | NA | 131242-WSD11-DR-3025 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3026 | NA | 131242-WSD11-DR-3026 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3027 | NA | 131242-WSD11-DR-3027 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3028 | NA | 131242-WSD11-DR-3028 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-11, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3029 | NA | 131242-WSD11-DR-3029 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3030 | NA | 131242-WSD11-DR-3030 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | 2025-11-28 | A | 000000&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3031 | NA | 131242-WSD11-DR-3031 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3032 | NA | 131242-WSD11-DR-3032 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3033 | NA | 131242-WSD11-DR-3033 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3034 | NA | 131242-WSD11-DR-3034 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-09-29, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3035 | NA | 131242-WSD11-DR-3035 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1120 | NA | 131242-WSD11-DR-1120 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1121 | NA | 131242-WSD11-DR-1121 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1122 | NA | 131242-WSD11-DR-1122 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1123 | NA | 131242-WSD11-DR-1123 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-05-28, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1200 | NA | 131242-WSD11-DR-1200 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "THP Equipment layout" | 2024-08-23 | 2025-11-28 | A | 000000&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1201 | NA | 131242-WSD11-DR-1201 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1202 | NA | 131242-WSD11-DR-1202 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1203 | NA | 131242-WSD11-DR-1203 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1204 | NA | 131242-WSD11-DR-1204 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1205 | NA | 131242-WSD11-DR-1205 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-05-09 | 2025-11-28 | NA | 000000 | 2025-05-09, 2025-11-28 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 3000 | NA | 131242-WSD11-DR-3000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 8000 | NA | 131242-WSD11-DR-8000 | 2025-11-28 | SITE OFFICE LAYOUT (Rev1) | For Information | 2025-12-18 | 2025-11-14 | 25 | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | PEN | PEN
000293 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0018 | 0 | 131242-WSD11-CD-0018 | 2024-02-01 | Milestone 1.1 THP A100 Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 19 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 THP A100 Silo Area inside Biosolid Building" | 2024-02-01 | 2024-02-01 | 0 | 000293 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000293 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-0030 | 2024-06-11 | Milestone 1.2 THP A100 Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 3 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-0030 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 2: Not approved - Revise and Resubmit. No Electrical / ICA Cutsheets attached with submittal. | 2024-11-28 | 2024-12-05 | 5 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1130 | NA | 131242-WSD11-DR-1130 | 2024-11-09 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 5 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-11-09 | 2024-11-09 | NA | 000000 | 2024-11-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1131 | NA | 131242-WSD11-DR-1131 | 2024-11-09 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 5 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-11-09 | 2024-11-09 | NA | 000000 | 2024-11-09 | 00 | 1 | PEN | NAP | NAP
000293 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-0030 | 2025-04-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 44 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000293 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-0030 | 2025-10-31 | Milestone 3 THP A100 Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-20 | 65 | Approved with Comments | YES | 2026-03-12 | NO | Overdue | -35 |  |  | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000294 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0019 | 0 | 131242-WSD11-CD-0019 | 2024-02-01 | Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 19 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-02-01 | 2024-02-01 | 0 | 000294 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000294 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-0032 | 2024-06-11 | Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 3 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-0032 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | B | 1003_WD | NA | 131242-WSD11-DR-1003_WD | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2024-12-03 | NA | 000000 | 2024-12-03 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1000_WD | NA | 131242-WSD11-DR-1000_WD | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2024-12-03 | NA | 000000 | 2024-12-03 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1001_WD | NA | 131242-WSD11-DR-1001_WD | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2024-12-03 | NA | 000000 | 2024-12-03 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1002_WD | NA | 131242-WSD11-DR-1002_WD | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2024-12-03 | NA | 000000 | 2024-12-03 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 3000_WD | NA | 131242-WSD11-DR-3000_WD | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2024-12-03 | NA | 000000 | 2024-12-03 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1175 | NA | 131242-WSD11-DR-1175 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1176 | NA | 131242-WSD11-DR-1176 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1177 | NA | 131242-WSD11-DR-1177 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1178 | NA | 131242-WSD11-DR-1178 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1179 | NA | 131242-WSD11-DR-1179 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1180 | NA | 131242-WSD11-DR-1180 | 2024-12-03 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-23 | 2025-01-17 | 17 | Rejected | YES | 2025-02-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-08-13 | NA | 000000 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | REJ | REJ
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-0032 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | B | 1003_MS2 | NA | 131242-WSD11-DR-1003_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | NA | 131242-WSD11-DR-1000_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | NA | 131242-WSD11-DR-1001_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | NA | 131242-WSD11-DR-1002_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | NA | 131242-WSD11-DR-3000_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1175_MS2 | NA | 131242-WSD11-DR-1175_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1176_MS2 | NA | 131242-WSD11-DR-1176_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1177_MS2 | NA | 131242-WSD11-DR-1177_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1178_MS2 | NA | 131242-WSD11-DR-1178_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1179_MS2 | NA | 131242-WSD11-DR-1179_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1180_MS2 | NA | 131242-WSD11-DR-1180_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1140_MS2 | NA | 131242-WSD11-DR-1140_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1141_MS2 | NA | 131242-WSD11-DR-1141_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1142_MS2 | NA | 131242-WSD11-DR-1142_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1143_MS2 | NA | 131242-WSD11-DR-1143_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1144_MS2 | NA | 131242-WSD11-DR-1144_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1145_MS2 | NA | 131242-WSD11-DR-1145_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1146_MS2 | NA | 131242-WSD11-DR-1146_MS2 | 2025-01-21 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-07-02 | 98 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-0032 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  |  |  | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | B | 1003_MS2 | NA | 131242-WSD11-DR-1003_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | NA | 131242-WSD11-DR-1000_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | NA | 131242-WSD11-DR-1001_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | NA | 131242-WSD11-DR-1002_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | NA | 131242-WSD11-DR-3000_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1175_MS2 | NA | 131242-WSD11-DR-1175_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1176_MS2 | NA | 131242-WSD11-DR-1176_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1177_MS2 | NA | 131242-WSD11-DR-1177_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1178_MS2 | NA | 131242-WSD11-DR-1178_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1179_MS2 | NA | 131242-WSD11-DR-1179_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1180_MS2 | NA | 131242-WSD11-DR-1180_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1140_MS2 | NA | 131242-WSD11-DR-1140_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1141_MS2 | NA | 131242-WSD11-DR-1141_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1142_MS2 | NA | 131242-WSD11-DR-1142_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1143_MS2 | NA | 131242-WSD11-DR-1143_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1144_MS2 | NA | 131242-WSD11-DR-1144_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1145_MS2 | NA | 131242-WSD11-DR-1145_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1146_MS2 | NA | 131242-WSD11-DR-1146_MS2 | 2025-10-27 | SITE OFFICE LAYOUT (Rev1) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  | NO |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-01-21 | 2025-10-27 | NA | 000000 | 2025-01-21, 2025-10-27 | 00 | 2 | PEN | AWC | AWC
000295 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 0 | 131242-WSW41-VI-0017 | 2024-02-01 | Preliminary Design and Vendor Approval of Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-04-16 | 30 | Approved with Comments | YES | 2024-05-07 | YES | Resubmitted |  | 2024-07-31 | Related to Tank accessories. In Progress. To check the lead time after PO issue to meet the ROS date (1st Wk of Oct 24) | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | PEN | AWC | AWC
000295 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 1 | 131242-WSW41-VI-0017 | 2024-07-31 | Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-21 | 2024-08-29 | 6 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | PEN | AWC | AWC
000296 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 0 | 131242-WSW41-SP-0004 | 2024-02-01 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-01 | 2024-02-16 |  | Not Approved | YES | 2024-03-07 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | PEN | NAP | NAP
000296 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 1 | 131242-WSW41-SP-0004 | 2024-06-13 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-28 |  | Not Approved | YES | 2024-07-18 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | PEN | NAP | NAP
000296 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 2 | 131242-WSW41-SP-0004 | 2024-07-15 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.2: Approved | 2024-08-02 | 2024-08-12 | 5 | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | PEN | APP | APP
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A | 131242-WSW41-DR-5100 | 2024-02-01 | Pipe Support Standard - General Notes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | 2025-02-25 |  | NA | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.1 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5101 | NA | 131242-WSW41-DR-5101 | 2024-02-01 | Pipe Support Standard - S01 U-Bolt | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S01 U-Bolt" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.2 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 02, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5102 | NA | 131242-WSW41-DR-5102 | 2024-02-01 | Pipe Support Standard - S02 SHOE (DN15 ~ DN450) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2026-01-19 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5103 | NA | 131242-WSW41-DR-5103 | 2024-02-01 | Pipe Support Standard - S03 PAD | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S03 PAD" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2026-01-19 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5104 | NA | 131242-WSW41-DR-5104 | 2024-02-01 | Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5105 | NA | 131242-WSW41-DR-5105 | 2024-02-01 | Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5106 | NA | 131242-WSW41-DR-5106 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 1 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-12-29 | 00, NA | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5107 | NA | 131242-WSW41-DR-5107 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 2 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S06 DUMMY PIPE SHEET 2" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5108 | NA | 131242-WSW41-DR-5108 | 2024-02-01 | Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5109 | NA | 131242-WSW41-DR-5109 | 2024-02-01 | Pipe Support Standard - S08 SLIDE STOOL | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S08 SLIDE STOOL" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5110 | NA | 131242-WSW41-DR-5110 | 2024-02-01 | Pipe Support Standard - S09 TIGHT STOOL | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S09 TIGHT STOOL" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5111 | NA | 131242-WSW41-DR-5111 | 2024-02-01 | Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-06-25 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5112 | NA | 131242-WSW41-DR-5112 | 2024-02-01 | Pipe Support Standard - S11 GUIDE FOR SHOE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5113 | NA | 131242-WSW41-DR-5113 | 2024-02-01 | Pipe Support Standard - S12 STOPPER FOR SHOE | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5114 | NA | 131242-WSW41-DR-5114 | 2024-02-01 | Pipe Support Standard - S13 BRACKET SUPPORT | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S13 BRACKET SUPPORT" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5115 | NA | 131242-WSW41-DR-5115 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5116 | NA | 131242-WSW41-DR-5116 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5117 | NA | 131242-WSW41-DR-5117 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5118 | NA | 131242-WSW41-DR-5118 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2 | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5119 | NA | 131242-WSW41-DR-5119 | 2024-02-01 | Pipe Support Standard - S16 STANCHION | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S16 STANCHION" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5120 | NA | 131242-WSW41-DR-5120 | 2024-02-01 | Pipe Support Standard - S17 STANCHION (REINFORCED) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S17 STANCHION (REINFORCED)" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5121 | NA | 131242-WSW41-DR-5121 | 2024-02-01 | Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5122 | NA | 131242-WSW41-DR-5122 | 2024-02-01 | Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5123 | NA | 131242-WSW41-DR-5123 | 2024-02-01 | Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5124 | NA | 131242-WSW41-DR-5124 | 2024-02-01 | Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5125 | NA | 131242-WSW41-DR-5125 | 2024-02-01 | Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450)" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5126 | NA | 131242-WSW41-DR-5126 | 2024-02-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-01 | 2024-05-29 | 59 | Approved with Comments | YES | 2024-06-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2024-02-01 | NA | 000000 | 2024-02-01 | 00 | 1 | PEN | AWC | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-5100 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | 2025-02-25 |  | NA | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.1 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5101 | NA | 131242-WSW41-DR-5101 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S01 U-Bolt" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.2 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 02, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5102 | NA | 131242-WSW41-DR-5102 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2026-01-19 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5103 | NA | 131242-WSW41-DR-5103 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S03 PAD" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2026-01-19 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5104 | NA | 131242-WSW41-DR-5104 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5105 | NA | 131242-WSW41-DR-5105 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-12-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5108 | NA | 131242-WSW41-DR-5108 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5109 | NA | 131242-WSW41-DR-5109 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S08 SLIDE STOOL" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5110 | NA | 131242-WSW41-DR-5110 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S09 TIGHT STOOL" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5111 | NA | 131242-WSW41-DR-5111 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-06-25 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5112 | NA | 131242-WSW41-DR-5112 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5113 | NA | 131242-WSW41-DR-5113 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5121 | NA | 131242-WSW41-DR-5121 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5123 | NA | 131242-WSW41-DR-5123 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5124 | NA | 131242-WSW41-DR-5124 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-03-13 | NA | 000000 | 2024-02-01, 2025-03-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5140 | NA | 131242-WSW41-DR-5140 | 2025-03-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-06-25 | NA | 000000 | 2025-03-13, 2025-06-25 | 00 | 2 | PEN | AWC | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.2 | 131242-WSW41-DR-5101 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S01 U-Bolt" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.2 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 02, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5104 | NA | 131242-WSW41-DR-5104 | 2025-06-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-12-29 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5111 | NA | 131242-WSW41-DR-5111 | 2025-06-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2025-06-25 | NA | 000000 | 2024-02-01, 2025-03-13, 2025-06-25 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5139 | NA | 131242-WSW41-DR-5139 | 2025-06-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-25 | 2025-06-25 | NA | 000000 | 2025-06-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | M | 5140 | NA | 131242-WSW41-DR-5140 | 2025-06-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-06-25 | NA | 000000 | 2025-03-13, 2025-06-25 | 00 | 2 | PEN | AWC | AWC
000298 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0017 | 0 | 131242-WSW41-MI-0017 | 2024-02-02 | Process & MEICA Meeting Minutes 0017_20240118 | Rev 0: For Information | 2024-03-04 | 2024-05-21 | 53 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | 2024-10-31 | 0 | 000000&&000298&&000320&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | PEN | INF | INF
000299 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 0 | 131242-WST02-VI-0002 | 2024-02-03 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-03-04 | 2024-03-01 |  | Approved with Comments | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000299 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 1 | 131242-WST02-VI-0002 | 2024-03-25 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-04-16 | 2024-05-23 | 25 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000299 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 2 | 131242-WST02-VI-0002 | 2024-06-07 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-06-28 | 2024-08-15 | 33 | Approved with Comments | YES | 2024-09-04 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000299 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 3 | 131242-WST02-VI-0002 | 2024-10-16 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 3: Approved. | 2024-11-06 | 2024-11-04 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | APP | APP
000300 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0003 | 0 | 131242-WSW41-PS-0003 | 2024-02-03 | Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024 | Rev 0: Noted for information | 2024-03-04 | 2024-03-18 | 10 | For Information | NO |  | YES |  |  |  |  | NA | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" && "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | 2023-08-28 | 2024-02-03 | 0 | 000077&&000300 | 2023-08-28, 2024-02-03 | 00 | 2 | PEN | INF | INF
000301 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0008 | 0 | 131242-WSW41-MI-0008 | 2024-02-05 | Monthly Progress Meeting Minutes 0008_20240123 | For Information | 2024-03-05 | 2024-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | PEN | INF | INF
000302 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0014 | 0 | 131242-WSD11-CD-0014 | 2024-02-06 | Milestone 1.1 THP Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-06 | 2024-03-28 | 16 | Approved with Comments | YES | 2024-04-19 | YES | Resubmitted |  |  |  | NA | "Milestone 1.1 THP Compressed Air System" | 2024-02-06 | 2024-02-06 | 0 | 000302 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000302 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0029 | 0 | 131242-WSD11-CD-0029 | 2024-06-11 | Milestone 1.2 THP Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 3 | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Milestone 1.2 THP Compressed Air System" | 2024-06-11 | 2024-06-11 | 0 | 000302 | 2024-06-11 | 01 | 1 | PEN | AWC | AWC
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 0 | 131242-WSD11-CD-0047 | 2024-10-17 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1165 | NA | 131242-WSD11-DR-1165 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Piping General Arrangement of Air Compressor system" | 2024-08-13 | 2025-08-13 | A | 000000&&000640 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1166 | NA | 131242-WSD11-DR-1166 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2025-08-13 | NA | 000000 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1020 | NA | 131242-WSD11-DR-1020 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-10-28 | NA | 000000 | 2024-10-18, 2025-05-28, 2025-10-28 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 1021 | NA | 131242-WSD11-DR-1021 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-10-28 | NA | 000000 | 2024-10-18, 2025-10-28 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3000 | NA | 131242-WSD11-DR-3000 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 3001 | NA | 131242-WSD11-DR-3001 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 1000 | NA | 131242-WSB01-DR-1000 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2025-01-14 | A.1 | 000000&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 3000 | NA | 131242-WSB01-DR-3000 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 5000 | NA | 131242-WSB01-DR-5000 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-12-05 | 20 | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | NAP | NAP
000302 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 1 | 131242-WSD11-CD-0047 | 2025-04-10 | Milestone 2 THP Compressed Air System | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-30 | 2025-07-02 | 43 | Approved with Comments | YES | 2025-07-22 | YES | Resubmitted |  |  |  | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | PEN | AWC | AWC
000302 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 2 | 131242-WSD11-CD-0047 | 2025-10-27 | Milestone 3 THP Compressed Air System | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 70 | Approved with Comments | YES | 2026-03-13 | NO |  |  |  |  | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | PEN | AWC | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1003_ST605_BCA | A1 | 131242-WST02-DR-1003_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | 2024-08-16 | Heng Peng to provide DGN drawing | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1004_ST605_BCA | NA | 131242-WST02-DR-1004_ST605_BCA | 2024-02-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-06 | 2024-02-06 | NA | 000000 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5002_ST605_BCA | NA | 131242-WST02-DR-5002_ST605_BCA | 2024-02-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-06 | 2024-02-06 | NA | 000000 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 7001_ST605_BCA | NA | 131242-WST02-DR-7001_ST605_BCA | 2024-02-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-06 | 2024-02-06 | NA | 000000 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | C | 8001_ST605_BCA | NA | 131242-WST00-DR-8001_ST605_BCA | 2024-02-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-06 | 2024-02-06 | NA | 000000 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | ST605-NOA | NA | 131242-WST02-DR-ST605-NOA | 2024-02-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-06 | 2024-02-21 |  | Approved with Comments | YES | 2024-03-12 | NO | Overdue | 481 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-06 | 2024-02-06 | NA | 000000 | 2024-02-06 | 00 | 1 | PEN | AWC | AWC
000304 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0020 | 0 | 131242-WSW41-CD-0020 | 2024-02-06 | Submission Of BIM Coordination VCM Model (Jan–2024) | For Information | 2024-03-06 | 2024-02-22 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Jan–2024)" | 2024-02-06 | 2024-02-06 | 0 | 000304 | 2024-02-06 | 00 | 1 | PEN | INF | INF
000305 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0009 | 0 | 131242-WSW41-RT-0009 | 2024-02-08 | C4B Monthly Progress Report Number No.09 (01 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-03-08 | 2024-03-08 |  | Approved with Comments | YES | 2024-03-28 | NO | Overdue | 469 |  |  | NA | "C4B Monthly Progress Report Number No.09 (01 24)" | 2024-02-08 | 2024-02-08 | 0 | 000305 | 2024-02-08 | 00 | 1 | PEN | AWC | AWC
000306 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0008 | 0 | 131242-WSW41-PC-0008 | 2024-02-08 | Payment Claim No. 8 | Rev(0): Approved. Refer to S.O. correspondence no. 121 dated 9 Feb 2024. | 2024-03-08 | 2024-05-10 | 42 | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No. 8" | 2024-02-08 | 2024-02-08 | 0 | 000306 | 2024-02-08 | 00 | 1 | PEN | APP | APP
000307 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | A | 131242-WST02-DR-5000 | 2024-02-13 | Typical Installation Details for Power | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 41 | Rejected | YES | 2024-06-03 | YES | Resubmitted |  | 2025-02-27 |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | REJ | REJ
000307 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | B | 131242-WST02-DR-5000 | 2025-03-25 | Typical Installation Details for Power | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 14 | Not Approved | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7002 | A | 131242-WST02-DR-7002 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 38 | Not Approved | YES | 2024-05-29 | YES | Resubmitted |  |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7003 | NA | 131242-WST02-DR-7003 | 2024-02-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-12 | 2024-05-08 | 38 | Not Approved | YES | 2024-05-29 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7004 | NA | 131242-WST02-DR-7004 | 2024-02-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-12 | 2024-05-08 | 38 | Not Approved | YES | 2024-05-29 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | NAP | NAP
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | B | 131242-WST02-DR-7003 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | 2025-02-25 |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7004 | NA | 131242-WST02-DR-7004 | 2024-07-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7005 | NA | 131242-WST02-DR-7005 | 2024-07-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7006 | NA | 131242-WST02-DR-7006 | 2024-07-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7007 | NA | 131242-WST02-DR-7007 | 2024-07-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7008 | NA | 131242-WST02-DR-7008 | 2024-07-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-10-29 | 67 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | AWC | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | C | 131242-WST02-DR-7003 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7004 | NA | 131242-WST02-DR-7004 | 2025-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7005 | NA | 131242-WST02-DR-7005 | 2025-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7006 | NA | 131242-WST02-DR-7006 | 2025-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7007 | NA | 131242-WST02-DR-7007 | 2025-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7008 | NA | 131242-WST02-DR-7008 | 2025-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-16 | 2025-05-08 | 14 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | AWC | AWC
000309 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | A | 131242-WST02-BQ-0003 | 2024-02-13 | SSN Listing of Interface Points | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 43 | Approved with Comments | YES | 2024-06-05 | YES | Resubmitted |  |  |  | NA | "SSN Listing of Interface Points" | 2024-02-13 | 2024-07-22 | B | 000309 | 2024-02-13, 2024-07-22 | 00, 01 | 2 | PEN | AWC | AWC
000309 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | B | 131242-WST02-BQ-0003 | 2024-07-22 | SSN Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | NO NEED TO RESUBMIT | No need to resubmit as there is no major updates made - "Please resubmit if there are major updates or changes to the information stated". | NA | "SSN Listing of Interface Points" | 2024-02-13 | 2024-07-22 | B | 000309 | 2024-02-13, 2024-07-22 | 00, 01 | 2 | PEN | AWC | AWC
000310 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | A | 131242-WST02-DR-5000 | 2024-02-13 | Typical Installation Details for Lighting | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 41 | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  | 2025-02-27 |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000310 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | B | 131242-WST02-DR-5000 | 2025-03-25 | Typical Installation Details for Lighting | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 14 | Not Approved | YES | 2025-05-26 | NO | Overdue | 175 |  | To check with C2D | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | A | 131242-WSD11-DR-1000 | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 43 | Not Approved | YES | 2024-06-05 | YES | Resubmitted |  | 2025-02-19 |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EK | 3000 | NA | 131242-WSD11-DR-3000 | 2024-02-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-12 | 2024-05-15 | 43 | Not Approved | YES | 2024-06-05 | YES | Resubmitted |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | NAP | NAP
000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | B | 131242-WSD11-DR-1000 | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EK | 3000 | NA | 131242-WSD11-DR-3000 | 2025-02-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-17 | 2025-05-05 | 32 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000312 | 00 | Soe Myat | PMT | NA | 131242 | WSW41 | LT | PM | 0022 | 0 | 131242-WSW41-LT-0022 | 2024-02-14 | CV of Team Member (QA/QC Manager) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-03-13 | 2024-02-19 |  | Approved with Comments | YES | 2024-03-08 | NO | Overdue | 483 |  |  | NA | "CV of Team Member (QA/QC Manager)" | 2024-02-14 | 2024-02-14 | 0 | 000312 | 2024-02-14 | 00 | 1 | PEN | AWC | AWC
000313 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0018 | 0 | 131242-WSW41-MI-0018 | 2024-02-15 | Process & MEICA Meeting Minutes 0018_20240201 | Rev 0: For Information | 2024-03-14 | 2024-05-21 | 45 | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Meeting Minutes 0018_20241113" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | 2024-11-30 | 0 | 000000&&000313&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | PEN | INF | INF
000314 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0001 | 0 | 131242-WSW41-RT-0001 | 2024-02-15 | 1st CONSAAS Audit report_2023 | Rev 0: Noted for information | 2024-03-14 | 2024-03-18 | 2 | For Information | NO |  | YES |  |  |  |  | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | PEN | INF | INF
000315 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 0 | 131242-WSW41-VI-0001 | 2024-02-19 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-03-18 | 2024-04-08 | 14 | Approved with Comments | YES | 2024-04-29 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | PEN | AWC | AWC
000315 | 01 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 1 | 131242-WSW41-VI-0001 | 2024-04-15 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-05-15 | 7 | Approved with Comments | YES | 2024-06-05 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | PEN | AWC | AWC
000315 | 02 | Balaji/ Karthik | EICA | NA | Comment Reply Sheet 20240716 | NA | NA | NA | NA | A.C | Comment Reply Sheet 20240716-NA-NA-NA | 2024-07-17 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 29 | Approved with Comments | YES | 2024-10-07 | NO | Overdue | 338 |  |  | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | 2024-07-17 | 2024-07-17 | A.C | 000315 | 2024-07-17 | 02 | 1 | PEN | AWC | AWC
000316 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0001 | 0 | 131242-WSW41-QA-0001 | 2024-02-20 | Inspection Test Plan for Structural Steel Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-08-14 | 100 | Not Approved | YES | 2024-09-03 | NO | Overdue | 362 |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | NAP | NAP
000317 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | VI | HS | 0002 | 0 | 131242-WSW41-VI-0002 | 2024-02-20 | Vendor Approval of CONSAAS Audit (ACE EHS) | Rev 0: Noted for information | 2024-03-19 | 2024-03-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | INF | INF
000318 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 0 | 131242-WST02-VI-0003 | 2024-02-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to the comment sheet | 2024-03-20 | 2024-03-20 |  | Approved with Comments | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000318 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 1 | 131242-WST02-VI-0003 | 2024-05-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-11 | 2024-07-04 | 16 | Approved with Comments | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000318 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 2 | 131242-WST02-VI-0003 | 2024-07-22 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 2: Approved. | 2024-08-12 | 2024-09-24 | 31 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | APP | APP
000319 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0009 | 0 | 131242-WSW41-PS-0009 | 2024-02-21 | Monthly Progress Presentation No. 09 (0124) | For Information | 2024-03-20 | 2024-02-22 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-05 | 0 | 000000&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | PEN | INF | INF
000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0017 | 0 | 131242-WSW41-MI-0017 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | 2024-10-31 | 0 | 000000&&000298&&000320&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0018 | NA | 131242-WSW41-MI-0018 | 2024-02-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-21 | 2024-03-01 |  | For Information | NO |  | YES |  |  | NO |  | NA | "Monthly Progress Meeting Minutes 0018_20241113" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | 2024-11-30 | 0 | 000000&&000313&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | PEN | INF | INF
000321 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 0 | 131242-WSD11-BQ-0003 | 2024-02-23 | THP Listing of Interface Points | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-03-22 | 2024-05-15 | 35 | Not Approved | YES | 2024-06-05 | YES | Resubmitted |  |  |  | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | PEN | NAP | NAP
000321 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 1 | 131242-WSD11-BQ-0003 | 2025-07-21 | THP Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-10-01 | 38 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | PEN | AWC | AWC
000322 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 0 | 131242-WST02-CH-0002 | 2024-02-23 | Process Functional Description | Rev 0 : There are no active comments on the submittal. However, if there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 2024-03-22 | 2024-03-13 |  | Approved with Comments | YES | 2024-04-03 | YES | Resubmitted |  | 2024-07-19 | If there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | NA | "Process Functional Description" | 2024-02-23 | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000322 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 1 | 131242-WST02-CH-0002 | 2024-07-23 | Process Functional Description | Rev 1: Approved | 2024-08-13 | 2024-08-29 | 12 | Approved | NO |  | YES |  |  |  |  | NA | "Process Functional Description" | 2024-02-23 | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | PEN | APP | APP
000322 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 2 | 131242-WST02-CH-0002 | 2024-10-15 | Process Functional Description | Rev 2: Approved with comments. Please address the comments and resubmit. | 2024-11-05 | 2024-12-18 | 31 | Approved with Comments | YES | 2025-01-08 | YES | Resubmitted |  | 2025-02-28 | Pending MP updates | NA | "Process Functional Description" | 2024-02-23 | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000322 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 3 | 131242-WST02-CH-0002 | 2025-03-04 | Process Functional Description | Rev 3: Approved with comments. Resubmittal is required if there are any changes during the detail engineering. | 2025-03-24 | 2025-04-28 | 23 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | 2025-02-28 | Pending MP updates | NA | "Process Functional Description" | 2024-02-23 | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000323 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0019 | 0 | 131242-WSW41-MI-0019 | 2024-02-23 | Process & MEICA Meeting Minutes 0019_20240215 | Rev 0: For Information | 2024-03-22 | 2024-05-21 | 39 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | PEN | INF | INF
000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0001 | 0 | 131242-WSD11-LT-0001 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | 69 | Rejected | NO |  | YES |  |  |  |  | NA | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | 2024-02-24 | 2024-02-24 | 0 | 000324 | 2024-02-24 | 00 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | LT | P | 0002 | NA | 131242-WSD11-LT-0002 | 2024-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-22 | 2024-07-04 | 69 | Rejected | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-24 | 2024-02-24 | NA | 000000 | 2024-02-24 | 00 | 1 | PEN | REJ | REJ
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-8001_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 |  | Rejected | YES | 2024-03-18 | YES | Resubmitted |  |  |  | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1003_ST605 | NA | 131242-WST02-DR-1003_ST605 | 2024-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1004_ST605 | NA | 131242-WST02-DR-1004_ST605 | 2024-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-02-29 | NA | 000000 | 2024-02-26, 2024-02-29 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5002_ST605 | NA | 131242-WST02-DR-5002_ST605 | 2024-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-02-29 | NA | 000000 | 2024-02-26, 2024-02-29 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST605 | NA | 131242-WST02-DR-7001_ST605 | 2024-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-25 | 2024-02-27 |  | Not Approved | YES | 2024-03-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-8001_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-20 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1003_ST605 | NA | 131242-WST02-DR-1003_ST605 | 2024-02-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-28 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1004_ST605 | NA | 131242-WST02-DR-1004_ST605 | 2024-02-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-28 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-02-29 | NA | 000000 | 2024-02-26, 2024-02-29 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5002_ST605 | NA | 131242-WST02-DR-5002_ST605 | 2024-02-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-28 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-02-29 | NA | 000000 | 2024-02-26, 2024-02-29 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST605 | NA | 131242-WST02-DR-7001_ST605 | 2024-02-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-03-28 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-8001_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-17 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  |  |  | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1003_ST605 | NA | 131242-WST02-DR-1003_ST605 | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST605 | NA | 131242-WST02-DR-7001_ST605 | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | NAP | NAP
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-8001_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-06 | 2024-06-03 | 19 | For Information | NO |  | YES |  |  |  |  | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1003_ST605 | NA | 131242-WST02-DR-1003_ST605 | 2024-04-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-14 | 2024-06-03 | 13 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST605 | NA | 131242-WST02-DR-7001_ST605 | 2024-04-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-14 | 2024-06-03 | 13 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-26 | 2024-04-26 | NA | 000000 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00 | 4 | PEN | INF | INF
000326 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 0 | 131242-WSD11-PO-0001 | 2024-02-26 | Unpriced PO for Transformer (Hitachi) | Rev 0: Rejected. Please refer to attached file to comments. | 2024-03-25 | 2024-03-20 |  | Rejected | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | PEN | REJ | REJ
000326 | 01 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 1 | 131242-WSD11-PO-0001 | 2024-03-20 | Unpriced PO for Transformer (Hitachi) | For Information | 2024-04-11 | 2024-04-29 | 12 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | PEN | INF | INF
000327 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0004 | 0 | 131242-WSD11-PO-0004 | 2024-02-26 | Unpriced PO for Blower (Aerzen) | For Information | 2024-03-25 | 2024-05-21 | 38 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Blower (Aerzen)" | 2024-02-26 | 2024-02-26 | 0 | 000327 | 2024-02-26 | 00 | 1 | PEN | INF | INF
000328 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0003 | 0 | 131242-WSD11-PO-0003 | 2024-02-26 | Unpriced PO for Diffuser (Xylem) | For Information | 2024-03-25 | 2024-05-21 | 38 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Diffuser (Xylem)" | 2024-02-26 | 2024-02-26 | 0 | 000328 | 2024-02-26 | 00 | 1 | PEN | INF | INF
000329 | 00 | Low | EICA | NA | 131242 | WST02 | VI | I | 0002 | 0 | 131242-WST02-VI-0002 | 2024-02-28 | Vendor Approval of SSN Package (ORP Analyser) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-04-08 | 7 | (VOID / NOT IN USE) | YES | 2024-04-29 | YES | Resubmitted |  |  | To check with Qili whether ORP required or not. | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | PEN | PEN
000330 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | MI | I | 0001 | 0 | 131242-WSD11-MI-0001 | 2024-02-28 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 0: Accepted for information. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-05-09 | 28 | Approved with Comments | YES | 2024-05-30 | YES | Resubmitted |  |  |  | NA | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" && "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2023-07-05 | 2024-02-28 | 0 | 000039&&000330 | 2023-07-05, 2024-02-28 | 00 | 2 | PEN | AWC | AWC
000330 | 01 | Freedomer | EICA | NA | 131242 | NA | MI | E | Comment Reply Sheet 20240716 S330.0 | NA | 131242-NA-MI-Comment Reply Sheet 20240716 S330.0 | 2024-07-17 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 1: Accepted for information. No resubmission required. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 29 | For Information | NO |  | YES |  |  |  |  | NA | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2024-07-17 | 2024-07-17 | NA | 000330 | 2024-07-17 | 01 | 1 | PEN | INF | INF
000331 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0003 | 0 | 131242-WSD11-LT-0003 | 2024-02-28 | THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-27 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | NO | Overdue | 461 | 2024-07-19 |  | NA | "THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor" | 2024-02-28 | 2024-02-28 | 0 | 000331 | 2024-02-28 | 00 | 1 | PEN | NAP | NAP
000332 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | A.1 | 131242-WSW41-VI-0018 | 2024-02-29 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rejected as requested by Contractor as there still need to attach the document | 2024-03-28 | 2024-03-01 |  | Rejected | YES | 2024-03-21 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | PEN | REJ | REJ
000332 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-0018 | 2024-03-04 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-22 | 2024-04-15 | 14 | Approved with Comments | YES | 2024-05-06 | NO | Overdue | 445 |  |  | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | PEN | AWC | AWC
000333 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0019 | 0 | 131242-WSW41-VI-0019 | 2024-02-29 | Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-28 | 2024-04-16 | 11 | Approved with Comments | YES | 2024-05-07 | NO | Overdue | 444 |  |  | NA | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." && "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | 2024-02-29 | 2024-09-06 | 0 | 000333&&000705 | 2024-02-29, 2024-09-06 | 00 | 2 | PEN | AWC | AWC
000334 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 0 | 131242-WST02-VI-0004 | 2024-02-29 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-28 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | NAP | NAP
000334 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 1 | 131242-WST02-VI-0004 | 2024-03-26 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-17 | 2024-04-29 | 8 | Approved with Comments | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000334 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 2 | 131242-WST02-VI-0004 | 2024-05-16 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-06 | 2024-07-04 | 19 | Approved with Comments | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000334 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 3 | 131242-WST02-VI-0004 | 2024-07-28 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-16 | 2024-08-16 |  | Approved with Comments | YES | 2024-09-05 | NO | Overdue | 360 |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000335 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0009 | 0 | 131242-WSW41-MI-0009 | 2024-03-01 | Monthly Progress Meeting Minutes 0009_20240220 | For Information | 2024-04-01 | 2024-03-04 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Meeting Minutes 0009_20240220" && "SITE OFFICE LAYOUT (Rev1)" | 2023-08-07 | 2024-03-01 | 0 | 000000&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | PEN | INF | INF
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | A | 131242-WST02-SD-8001_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-05-17 | C | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5005_ST605 | NA | 131242-WST02-SD-5005_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5006_ST605 | NA | 131242-WST02-SD-5006_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5007_ST605 | NA | 131242-WST02-SD-5007_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5008_ST605 | NA | 131242-WST02-SD-5008_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5009_ST605 | NA | 131242-WST02-SD-5009_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5010_ST605 | NA | 131242-WST02-SD-5010_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5011_ST605 | NA | 131242-WST02-SD-5011_ST605 | 2024-03-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | C | 131242-WST02-SD-8001_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | 2024-08-16 | Heng Peng to clear BIM comments. | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-05-17 | C | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5005_ST605 | NA | 131242-WST02-SD-5005_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5006_ST605 | NA | 131242-WST02-SD-5006_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5007_ST605 | NA | 131242-WST02-SD-5007_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5008_ST605 | NA | 131242-WST02-SD-5008_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5009_ST605 | NA | 131242-WST02-SD-5009_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5010_ST605 | NA | 131242-WST02-SD-5010_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5011_ST605 | NA | 131242-WST02-SD-5011_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2024-05-17 | NA | 000000 | 2024-03-01, 2024-05-17 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5013_ST605 | NA | 131242-WST02-SD-5013_ST605 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-17 | 2024-05-17 | NA | 000000 | 2024-05-17 | 00 | 1 | PEN | NAP | NAP
000337 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1003 | 0 | 131242-WSW41-VI-1003 | 2024-03-01 | Vendor Approval of cPVC Pipes & Fittings (GF) | Approved | 2024-04-01 | 2024-04-17 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of cPVC Pipes & Fittings (GF)" | 2024-03-01 | 2024-03-01 | 0 | 000337 | 2024-03-01 | 00 | 1 | PEN | APP | APP
000338 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-1001_PUB | 2024-03-01 | PUB DC Drainage Submission | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000338 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-1001_PUB | 2024-03-28 | PUB DC Drainage Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-13 | 15 | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A | 131242-WST02-DR-1000_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-1001_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_PUB | NA | 131242-WST02-DR-2001_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_PUB | NA | 131242-WST02-DR-2002_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_PUB | NA | 131242-WST02-DR-2003_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_PUB | NA | 131242-WST02-DR-2007_PUB | 2024-05-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-10 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_PUB | B | 131242-WST02-DR-0001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " | 2024-10-30 | 2024-10-30 | B | 000338 | 2024-10-30 | 03 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 0002_PUB | NA | 131242-WST02-DR-0002_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1000_PUB | NA | 131242-WST02-DR-1000_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_PUB | NA | 131242-WST02-DR-1006_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-12 | NA | 000000 | 2024-10-30, 2026-01-12 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_PUB | NA | 131242-WST02-DR-2001_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_PUB | NA | 131242-WST02-DR-2002_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_PUB | NA | 131242-WST02-DR-2003_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_PUB | NA | 131242-WST02-DR-2007_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_PUB | NA | 131242-WST02-DR-3000_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-12 | NA | 000000 | 2024-10-30, 2026-01-12 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 5004_PUB | NA | 131242-WST02-DR-5004_PUB | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-1000_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-1000_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-1000_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-14 | 31 | Not Approved | YES | 2025-11-03 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | NAP | NAP
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-1000_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  |  |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2025-11-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-05 | 2025-12-17 | 8 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | REJ | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.2 | 131242-WST02-DR-1000_PUB | 2026-01-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2026-01-30 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | A.2 | 000000&&000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 02, 04, 05, 06, 07, 08 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_PUB | NA | 131242-WST02-DR-1001_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "PUB DC Drainage Submission " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-01 | 2026-01-12 | A | 000000&&000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_PUB | NA | 131242-WST02-DR-1002_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_PUB | NA | 131242-WST02-DR-1003_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_PUB | NA | 131242-WST02-DR-1004_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_PUB | NA | 131242-WST02-DR-1005_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2026-01-12 | 2026-01-12 | NA | 000000 | 2026-01-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_PUB | NA | 131242-WST02-DR-1006_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-12 | NA | 000000 | 2024-10-30, 2026-01-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_PUB | NA | 131242-WST02-DR-1009_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_PUB | NA | 131242-WST02-DR-2000_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_PUB | NA | 131242-WST02-DR-2001_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_PUB | NA | 131242-WST02-DR-2002_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_PUB | NA | 131242-WST02-DR-2003_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_PUB | NA | 131242-WST02-DR-2007_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-20 | 2026-01-12 | NA | 000000 | 2024-05-20, 2024-10-30, 2026-01-12 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_PUB | NA | 131242-WST02-DR-3000_PUB | 2026-01-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-30 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-12 | NA | 000000 | 2024-10-30, 2026-01-12 | 00 | 2 | PEN | PEN | PEN
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0016 | 0 | 131242-WSW41-MI-0016 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0017 | NA | 131242-WSW41-MI-0017 | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-05 |  | For Information | NO |  | YES |  |  | NO |  | NA | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | 2024-10-31 | 0 | 000000&&000298&&000320&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | IM | 0018 | NA | 131242-WSW41-MI-0018 | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-05 |  | For Information | NO |  | YES |  |  | NO |  | NA | "Monthly Progress Meeting Minutes 0018_20241113" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | 2024-11-30 | 0 | 000000&&000313&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | PEN | INF | INF
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-1000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | NA | 131242-WST02-DR-1001_ST615_BCA | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | NA | 131242-WST02-DR-1002_ST615_BCA | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | NA | 131242-WST02-DR-5001_ST615_BCA | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | NA | 131242-WST02-DR-7000_ST615_BCA | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | NA | 131242-WST02-DR-8000_ST615_BCA | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | NA | DR | S | Submission Acknowledgement | NA | 131242-NA-DR-Submission Acknowledgement | 2024-03-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-03 | 2024-03-20 |  | For Information | YES | 2024-04-11 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-03-05 | NA | 000000 | 2024-03-05 | 00 | 1 | PEN | INF | INF
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-1000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | 2024-08-16 | Heng Peng to clear BIM comments and to provide Native files | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | NA | 131242-WST02-DR-1001_ST615_BCA | 2024-04-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-27 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | NA | 131242-WST02-DR-1002_ST615_BCA | 2024-04-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-27 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | NA | 131242-WST02-DR-5001_ST615_BCA | 2024-04-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-27 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | NA | 131242-WST02-DR-7000_ST615_BCA | 2024-04-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-27 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | NA | 131242-WST02-DR-8000_ST615_BCA | 2024-04-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-27 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000341 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 0 | 131242-WSD11-CD-0004 | 2024-03-05 | THP UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "THP UPS Loading List" | 2024-03-05 | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000341 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 1 | 131242-WSD11-CD-0004 | 2024-04-19 | THP UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 25 | Not Approved | YES | 2024-07-08 | YES | Resubmitted |  |  |  | NA | "THP UPS Loading List" | 2024-03-05 | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000341 | 02 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 2 | 131242-WSD11-CD-0004 | 2024-10-22 | THP UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2024-12-18 | 26 | Not Approved | YES | 2025-01-08 | YES | Resubmitted |  |  |  | NA | "THP UPS Loading List" | 2024-03-05 | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000341 | 03 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 3 | 131242-WSD11-CD-0004 | 2025-01-21 | THP UPS Loading List | Not Approved - Revise and resubmit | 2025-02-10 | 2025-05-15 | 64 | Not Approved | YES | 2025-06-04 | YES | Resubmitted |  |  |  | NA | "THP UPS Loading List" | 2024-03-05 | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000341 | 04 | Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 4 | 131242-WSD11-CD-0004 | 2025-05-27 | THP UPS Loading List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-16 | 2025-09-11 | 63 | Approved with Comments | YES | 2025-10-01 | NO | Overdue | 83 |  |  | NA | "THP UPS Loading List" | 2024-03-05 | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | PEN | AWC | AWC
000342 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | CD | I | 0007 | 0 | 131242-WST02-CD-0007 | 2024-03-05 | SSN UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 |  | Not Approved | YES | 2024-04-11 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000342 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0007 | 1 | 131242-WST02-CD-0007 | 2024-04-19 | SSN UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 25 | Not Approved | YES | 2024-07-08 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000342 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 2 | 131242-WST02-CD-0007 | 2024-11-20 | SSN UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-10 | 2024-12-30 | 13 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000342 | 03 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 3 | 131242-WST02-CD-0007 | 2025-01-21 | SSN UPS Loading List | Rev 3: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-10 | 2025-03-04 | 16 | Not Approved | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000342 | 04 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 4 | 131242-WST02-CD-0007 | 2025-03-06 | SSN UPS Loading List | Not Approved - Revise and resubmit | 2025-03-26 | 2025-05-15 | 32 | Not Approved | YES | 2025-06-04 | YES | Resubmitted |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | NAP | NAP
000342 | 05 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 5 | 131242-WST02-CD-0007 | 2025-06-16 | SSN UPS Loading List | Rev 5: Approved with comments. No need resubmission. Refer attached file for comments. | 2025-07-04 | 2025-09-11 | 49 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | PEN | AWC | AWC
000343 | 00 | Yuen Fatt | PMT | NA | 131242 | WSW41 | LT | PM | 0023 | 0 | 131242-WSW41-LT-0023 | 2024-03-06 | CV of Team Member (LEW) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-04 | 2024-05-20 | 30 | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 |  |  | NA | "CV of Team Member (LEW)" | 2024-03-06 | 2024-03-06 | 0 | 000343 | 2024-03-06 | 00 | 1 | PEN | AWC | AWC
000344 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 0 | 131242-WST02-VI-0004 | 2024-03-06 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-09 | 23 | Approved with Comments | YES | 2024-05-30 | YES | Resubmitted |  | TBA |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000344 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 1 | 131242-WST02-VI-0004 | 2024-12-05 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 87 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000345 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-0003 | 2024-03-06 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-15 | 27 | Approved with Comments | YES | 2024-06-05 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000345 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | NA | 131242-WST02-VI-0003 | 2024-10-04 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rejected as requested | 2024-10-24 | 2024-10-18 |  | Rejected | YES | 2024-11-08 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | REJ | REJ
000345 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 1 | 131242-WST02-VI-0003 | 2024-10-18 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 17 | Approved with Comments | YES | 2024-12-23 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000345 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 2 | 131242-WST02-VI-0003 | 2025-02-27 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 3: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 31 | Approved with Comments | NO |  | YES |  |  | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000346 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 0 | 131242-WST02-VI-0005 | 2024-03-07 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-05 | 2024-05-16 | 27 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  | TBA |  | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | PEN | AWC | AWC
000346 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 1 | 131242-WST02-VI-0005 | 2024-12-05 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 87 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | PEN | AWC | AWC
000347 | 00 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0008 | 0 | 131242-WSW41-MS-0008 | 2024-03-08 | MSRA, SWP for Time Lapse Camera Steel Pole Erection | Approved | 2024-04-08 | 2024-03-20 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | PEN | APP | APP
000348 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0014 | 0 | 131242-WSW41-CD-0014 | 2024-03-08 | Submission Of BIM Coordination VCM Model (Feb-2024) | For Information | 2024-04-08 | 2024-03-20 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Feb-2024)" | 2024-03-08 | 2024-03-08 | 0 | 000348 | 2024-03-08 | 00 | 1 | PEN | INF | INF
000349 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | 0 | 131242-WSD11-CL-7000 | 2024-03-08 | THP Lux Calculation and Luminaire Schedule | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-08 | 2024-05-07 | 19 | Not Approved | YES | 2024-05-28 | YES | Resubmitted |  |  |  | NA | "THP Lux Calculation and Luminaire Schedule" | 2024-03-08 | 2024-07-16 | B | 000349 | 2024-03-08, 2024-07-16 | 00, 01 | 2 | PEN | NAP | NAP
000349 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | B | 131242-WSD11-CL-7000 | 2024-07-16 | THP Lux Calculation and Luminaire Schedule | Rev 1: For Information. | 2024-08-05 | 2024-10-29 | 60 | For Information | NO |  | YES |  |  |  |  | NA | "THP Lux Calculation and Luminaire Schedule" | 2024-03-08 | 2024-07-16 | B | 000349 | 2024-03-08, 2024-07-16 | 00, 01 | 2 | PEN | INF | INF
000350 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 0 | 131242-WST02-VI-0006 | 2024-03-11 | Vendor Approval of SSN Package (pH Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-09 | 2024-05-14 | 23 | Approved with Comments | YES | 2024-06-04 | YES | Resubmitted |  | TBA |  | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | PEN | AWC | AWC
000350 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 1 | 131242-WST02-VI-0006 | 2024-12-05 | Vendor Approval of SSN Package (pH Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 87 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | PEN | AWC | AWC
000351 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 0 | 131242-WSW41-SP-0005 | 2024-03-11 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-04-09 | 2024-03-26 |  | Approved with Comments | YES | 2024-04-17 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-03-11 | 2024-06-20 | 1 | 000351 | 2024-03-11, 2024-06-20 | 00, 01 | 2 | PEN | AWC | AWC
000351 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 1 | 131242-WSW41-SP-0005 | 2024-06-20 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Rev.1: Approved | 2024-07-10 | 2024-06-28 |  | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-03-11 | 2024-06-20 | 1 | 000351 | 2024-03-11, 2024-06-20 | 00, 01 | 2 | PEN | APP | APP
000352 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 0 | 131242-WSW41-VI-1009 | 2024-03-12 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rejected. The proposed vendor is dealer/sales representative and not the manufacturer/brand of pipes and fittings. | 2024-04-11 | 2024-04-17 | 4 | Rejected | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-03-12 | 2024-05-10 | 1 | 000352 | 2024-03-12, 2024-05-10 | 00, 01 | 2 | PEN | REJ | REJ
000352 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 1 | 131242-WSW41-VI-1009 | 2024-05-10 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rev 0: Approved Please note, that the approval, corresponds to the brand (FROCH and JNDIA) proposed by CES_SDC in this submittal. Approval does not include assessment for TRADER. | 2024-05-31 | 2024-08-06 | 46 | Approved | NO |  | YES |  |  |  | R0_Rej | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-03-12 | 2024-05-10 | 1 | 000352 | 2024-03-12, 2024-05-10 | 00, 01 | 2 | PEN | APP | APP
000353 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0020 | 0 | 131242-WSW41-MI-0020 | 2024-03-12 | Process & MEICA Meeting Minutes 0020_20240229 | Rev 0: For Information | 2024-04-11 | 2024-05-21 | 27 | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Meeting Minutes 0020_20250122" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | 2025-02-18 | 0 | 000000&&000353&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | PEN | INF | INF
000354 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0004 | 0 | 131242-WSW41-PS-0004 | 2024-03-12 | Incentive / Disincentive Audit Scheme for November 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for November 2023" && "Monthly Progress Presentation No. 04 (0823)" | 2023-09-21 | 2024-03-12 | 0 | 000106&&000354 | 2023-09-21, 2024-03-12 | 00 | 2 | PEN | INF | INF
000355 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0005 | 0 | 131242-WSW41-PS-0005 | 2024-03-12 | Incentive / Disincentive Audit Scheme for December 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for December 2023" && "Monthly Progress Presentation No. 05 (0923)" | 2023-10-25 | 2024-03-12 | 0 | 000137&&000355 | 2023-10-25, 2024-03-12 | 00 | 2 | PEN | INF | INF
000356 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 0 | 131242-WST02-CL-0000 | 2024-03-12 | SSN Transformer Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-11 | 2024-05-20 | 26 | Not Approved | YES | 2024-06-10 | YES | Resubmitted |  |  |  | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | PEN | NAP | NAP
000356 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 1 | 131242-WST02-CL-0000 | 2024-12-14 | SSN Transformer Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-03 | 2025-02-13 | 27 | Approved with Comments | YES | 2025-03-05 | YES | Resubmitted |  | 2025-03-04 |  | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | PEN | AWC | AWC
000356 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 2 | 131242-WST02-CL-0000 | 2025-05-30 | SSN Transformer Sizing Calculations | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments | 2025-06-19 | 2025-07-23 | 24 | Approved with Comments | YES | 2025-08-12 | NO | Overdue | 119 |  | Pending Reply from Sunlight. Pending UPS details from Jacobs | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | PEN | AWC | AWC
000357 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0024 | 0 | 131242-WSW41-LT-0024 | 2024-03-12 | Notice of Unforeseeable Underground Obstruction Near Chemical Dosing | Refer to S.O. Correspondence No.150. | 2024-04-11 | 2024-05-10 | 20 | For Information | NO |  | YES |  |  |  | Refer to S.O. Correspondence No.150. | NA | "Notice of Unforeseeable Underground Obstruction Near Chemical Dosing" | 2024-03-12 | 2024-03-12 | 0 | 000357 | 2024-03-12 | 00 | 1 | PEN | INF | INF
000358 | 00 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 0 | 131242-WST02-BQ-0001 | 2024-03-12 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-05-23 | 28 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | 2024-07-26 |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | AWC | AWC
000358 | 01 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 1 | 131242-WST02-BQ-0001 | 2024-07-24 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-14 | 2024-08-29 | 11 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  |  |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | AWC | AWC
000358 | 02 | Qili | Process | NA | 131242 | WST02 | BQ | P | 0001 | 2 | 131242-WST02-BQ-0001 | 2024-11-15 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 2: For Information | 2024-12-05 | 2025-03-04 | 59 | For Information | NO |  | YES |  |  |  |  | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | PEN | INF | INF
000359 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 0 | 131242-WSD11-VI-0001 | 2024-03-13 | Vendor Approval of THP Train Instrument | Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-12 | 2024-05-16 | 23 | Not Approved | YES | 2024-06-06 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | NAP | NAP
000359 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 1 | 131242-WSD11-VI-0001 | 2024-06-07 | Vendor Approval of THP Train Instrument (Siemens) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-05 | 26 | Not Approved | YES | 2024-08-26 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | NAP | NAP
000359 | 02 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 2 | 131242-WSD11-VI-0001 | 2024-08-20 | Vendor Approval of THP Train Instrument (Siemens) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-09-03 |  | Approved with Comments | YES | 2024-09-23 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | AWC | AWC
000359 | 03 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 3 | 131242-WSD11-VI-0001 | 2025-03-21 | Vendor Approval of THP Train Instrument (Siemens) | Rev 3: Approved with comments (except Electromagnetic flowmeter). To revise and resubmit. Refer attached file for comments. | 2025-04-10 | 2025-05-06 | 16 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | PEN | AWC | AWC
000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | A | 131242-WST02-DR-7001 | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | 8 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2024-03-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-15 | 2024-04-25 | 8 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7001 | B | 131242-WST02-DR-7001 | 2024-06-19 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | 22 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  |  | R1_AWC | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2024-03-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-08-08 | 22 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-7001 | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | 15 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-18 | 2024-10-09 | 15 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-7001 | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | 40 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | 2025-02-28 | comments received on 14 Feb | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2024-10-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-16 | 40 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-7001 | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 |  | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2025-02-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-19 | 2025-03-13 |  | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | D | 131242-WST02-DR-7001 | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | 33 | Approved with Comments | NO |  | YES |  |  |  |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7002 | NA | 131242-WST02-DR-7002 | 2025-07-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-08-01 | 2025-09-17 | 33 | Approved with Comments | NO |  | YES |  |  | NO |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000361 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0006 | 0 | 131242-WSW41-PS-0006 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Jan 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for Jan 2024" && "Monthly Progress Presentation No. 06 (1023)" | 2023-11-15 | 2024-03-14 | 0 | 000186&&000361 | 2023-11-15, 2024-03-14 | 00 | 2 | PEN | INF | INF
000362 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0007 | 0 | 131242-WSW41-PS-0007 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Feb 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive / Disincentive Audit Scheme for Feb 2024" && "Monthly Progress Presentation No. 07 (1123)" | 2024-01-24 | 2024-03-14 | 0 | 000285&&000362 | 2024-01-24, 2024-03-14 | 00 | 2 | PEN | INF | INF
000363 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0022 | NA | 131242-WST02-CD-0022 | 2024-03-15 | Milestone 1.2 - Underground Services | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 24 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | PEN | REJ | REJ
000364 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0024 | NA | 131242-WST02-CD-0024 | 2024-03-15 | Milestone 1.2 - SSN Pump Station and Lamella Clarifier | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 24 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | PEN | REJ | REJ
000365 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0028 | NA | 131242-WST02-CD-0028 | 2024-03-15 | Milestone 1.2 - Sitewide Pipe Rack | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 24 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - Sitewide Pipe Rack" | 2024-03-15 | 2024-03-15 | NA | 000365 | 2024-03-15 | 00 | 1 | PEN | REJ | REJ
000366 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0035 | NA | 131242-WST02-CD-0035 | 2024-03-15 | Milestone 1.2 - SSN Minor Drain | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 24 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Minor Drain" | 2024-03-15 | 2024-03-15 | NA | 000366 | 2024-03-15 | 00 | 1 | PEN | REJ | REJ
000367 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0023 | NA | 131242-WST02-CD-0023 | 2024-03-18 | Milestone 1.2 - SSN Water Tank | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Water Tank" && "Milestone 1.2 SSN Water Tank" | 2024-03-18 | 2024-06-03 | 0 | 000163&&000367 | 2024-03-18, 2024-06-03 | 00, 01 | 2 | PEN | REJ | REJ
000368 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0025 | NA | 131242-WST02-CD-0025 | 2024-03-18 | Milestone 1.2 - SSN Pump Station and Blower | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | PEN | REJ | REJ
000369 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0026 | NA | 131242-WST02-CD-0026 | 2024-03-18 | Milestone 1.2 - SSN Chemical Dosing Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Chemical Dosing Area " | 2024-03-18 | 2024-03-18 | NA | 000369 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000370 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0027 | NA | 131242-WST02-CD-0027 | 2024-03-18 | Milestone 1.2 - SSN Electrical Building | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - SSN Electrical Building " | 2024-03-18 | 2024-03-18 | NA | 000370 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000371 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0029 | NA | 131242-WST02-CD-0029 | 2024-03-18 | Milestone 1.2 - THP Air Compress System | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP Air Compress System " | 2024-03-18 | 2024-03-18 | NA | 000371 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000372 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0030 | NA | 131242-WST02-CD-0030 | 2024-03-18 | Milestone 1.2 - THP Silo Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP Silo Area " | 2024-03-18 | 2024-03-18 | NA | 000372 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000373 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0031 | NA | 131242-WST02-CD-0031 | 2024-03-18 | Milestone 1.2 - THP Trains | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP Trains " | 2024-03-18 | 2024-03-18 | NA | 000373 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000374 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0032 | NA | 131242-WST02-CD-0032 | 2024-03-18 | Milestone 1.2 - THP Drainage | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP Drainage " | 2024-03-18 | 2024-03-18 | NA | 000374 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000375 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0033 | NA | 131242-WST02-CD-0033 | 2024-03-18 | Milestone 1.2 - THP Building Service | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP Building Service" | 2024-03-18 | 2024-03-18 | NA | 000375 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000376 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0034 | NA | 131242-WST02-CD-0034 | 2024-03-18 | Milestone 1.2 - THP MCC Room | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 23 | Rejected | NO |  | YES |  |  |  |  | NA | "Milestone 1.2 - THP MCC Room " | 2024-03-18 | 2024-03-18 | NA | 000376 | 2024-03-18 | 00 | 1 | PEN | REJ | REJ
000377 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0010 | 0 | 131242-WSW41-RT-0010 | 2024-03-18 | C4B Monthly Progress Report Number No.10 (02 24) | Rev. 0 - Approved with comments - need to re-submit (see attached comment sheet) | 2024-04-17 | 2024-04-01 |  | Approved with Comments | YES | 2024-04-22 | NO | Overdue | 454 |  |  | NA | "C4B Monthly Progress Report Number No.10 (02 24)" && "Report of DFS (GUIDE 3) for PIPE RACKS" | 2024-03-18 | 2024-10-28 | 0 | 000377&&000786 | 2024-03-18, 2024-10-28 | 00 | 2 | PEN | AWC | AWC
000378 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 0 | 131242-WSD11-SP-0002 | 2024-03-19 | Plant Control Narrative | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-30 | 8 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  |  | Pending MP info | NA | "Plant Control Narrative" | 2024-03-19 | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000378 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 1 | 131242-WSD11-SP-0002 | 2024-10-21 | Plant Control Narrative | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Plant Control Narrative" | 2024-03-19 | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000378 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 2 | 131242-WSD11-SP-0002 | 2024-10-21 | Plant Control Narrative | Rev 2: Approved. Please note: if there are any changes in controls, C4B will have to re-issue the document.” | 2024-11-11 | 2025-10-10 | 231 | Approved | NO |  | YES |  |  |  |  | NA | "Plant Control Narrative" | 2024-03-19 | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | PEN | APP | APP
000379 | 00 | Boopathi | PMT | NA | 131242 | WSW41 | VI | C | 0014 | 0 | 131242-WSW41-VI-0014 | 2024-03-19 | Vendor Approval for Waterproof Additive Specialist (CementAID) | Approved. | 2024-04-18 | 2024-03-26 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Waterproof Additive Specialist (CementAID)" | 2024-03-19 | 2024-03-19 | 0 | 000379 | 2024-03-19 | 00 | 1 | PEN | APP | APP
000380 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-0007 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 |  | Approved with Comments | YES | 2024-04-17 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | PEN | AWC | AWC
000380 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 1 | 131242-WSW41-SP-0007 | 2024-06-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-06-28 | 47 | Approved with Comments | YES | 2024-07-18 | NO | Overdue | 394 |  |  | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | PEN | AWC | AWC
000381 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0006 | 0 | 131242-WSW41-SP-0006 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 |  | Approved with Comments | YES | 2024-04-17 | NO | Overdue | 457 |  |  | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance)" | 2024-03-20 | 2024-03-20 | 0 | 000381 | 2024-03-20 | 00 | 1 | PEN | AWC | AWC
000382 | 00 | Zora | CSA | NA | 131242 | WSW41 | CN | C | 0001 | 0 | 131242-WSW41-CN-0001 | 2024-03-20 | RFC For SSN Surface Drainage Layout | Approved | 2024-04-19 | 2024-08-29 | 90 | Approved | NO |  | YES |  |  |  |  | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | PEN | APP | APP
000383 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0025 | 0 | 131242-WSW41-LT-0025 | 2024-03-20 | Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rejected | 2024-04-19 | 2024-06-21 | 42 | Rejected | YES | 2024-07-11 | YES | Resubmitted |  |  |  | NA | "Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-03-20 | 2024-03-20 | 0 | 000383 | 2024-03-20 | 00 | 1 | PEN | REJ | REJ
000383 | 01 | Theint Theint | Contracts | NA | 131242 | WSW41 | LT | PM | 0033 | 0 | 131242-WSW41-LT-0033 | 2024-06-22 | Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rev 1: Approved | 2024-07-11 | 2024-08-28 | 33 | Approved | NO |  | YES |  |  |  |  | NA | "Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-06-22 | 2024-06-22 | 0 | 000383 | 2024-06-22 | 01 | 1 | PEN | APP | APP
000384 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 0 | 131242-WST02-CL-0003 | 2024-03-20 | SSN Process Design Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-19 | 2024-04-25 | 4 | Approved with Comments | YES | 2024-05-16 | YES | Resubmitted |  |  | Pending MP info | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | PEN | AWC | AWC
000384 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 1 | 131242-WST02-CL-0003 | 2024-08-01 | SSN Process Design Calculation | Rev 1: Approved with Comments. Although there are no active comments the submittal is approved with comments to accommodate changes and resubmittal during the detail engineering. | 2024-08-22 | 2024-09-04 | 9 | Approved with Comments | YES | 2024-09-24 | NO | Overdue | 347 |  |  | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | PEN | AWC | AWC
000385 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 0 | 131242-WST02-CH-0001 | 2024-03-20 | SSN Process Design Basis | R0: Not Approved. Please resubmit | 2024-04-19 | 2024-04-30 | 7 | Not Approved | YES | 2024-05-21 | YES | Resubmitted |  |  |  | NA | "SSN Process Design Basis" | 2024-03-20 | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000385 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 1 | 131242-WST02-CH-0001 | 2024-08-02 | SSN Process Design Basis | R1: Approved with comments. Address the comments and resubmit. | 2024-08-23 | 2024-09-04 | 8 | Approved with Comments | YES | 2024-09-24 | YES | Resubmitted |  |  |  | NA | "SSN Process Design Basis" | 2024-03-20 | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000385 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 2 | 131242-WST02-CH-0001 | 2024-11-04 | SSN Process Design Basis | R2: Approved with comments. Address the comments and resubmit. | 2024-11-22 | 2025-01-09 | 32 | Approved with Comments | YES | 2025-01-29 | YES | Resubmitted |  | 2025-02-19 | comments received on 14 Feb | NA | "SSN Process Design Basis" | 2024-03-20 | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000385 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 3 | 131242-WST02-CH-0001 | 2025-02-24 | SSN Process Design Basis | R3: Approved with comments. | 2025-03-14 | 2025-03-13 |  | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 | 2025-02-19 |  | NA | "SSN Process Design Basis" | 2024-03-20 | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0001_ST617 | 0 | 131242-WSD11-CL-0001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-03-20 | 0 | 000386 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1000_ST617 | NA | 131242-WSW41-DR-1000_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1001_ST617 | NA | 131242-WSW41-DR-1001_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1002_ST617 | NA | 131242-WSW41-DR-1002_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 1003_ST617 | NA | 131242-WSW41-DR-1003_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2001_ST617 | NA | 131242-WSW41-DR-2001_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2002_ST617 | NA | 131242-WSW41-DR-2002_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | DR | S | 2003_ST617 | NA | 131242-WSW41-DR-2003_ST617 | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | CL | NA | THP_PF01 reaction table | NA | 131242-WSD11-CL-THP_PF01 reaction table | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | CL | NA | THP_PF02_PR01 reaction table | NA | 131242-WSD11-CL-THP_PF02_PR01 reaction table | 2024-03-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-19 | 2024-05-02 | 8 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-20 | 2024-03-20 | NA | 000000 | 2024-03-20 | 00 | 1 | PEN | NAP | NAP
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-0300_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  |  |  | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 0301_ST617 | NA | 131242-WSD11-DR-0301_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1000_ST617 | NA | 131242-WSD11-DR-1000_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1001_ST617 | NA | 131242-WSD11-DR-1001_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1002_ST617 | NA | 131242-WSD11-DR-1002_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1003_ST617 | NA | 131242-WSD11-DR-1003_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1004_ST617 | NA | 131242-WSD11-DR-1004_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-10-11 | NA | 000000 | 2024-07-04, 2024-10-11 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2000_ST617 | NA | 131242-WSD11-DR-2000_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2001_ST617 | NA | 131242-WSD11-DR-2001_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3000_ST617 | NA | 131242-WSD11-DR-3000_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3001_ST617 | NA | 131242-WSD11-DR-3001_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3002_ST617 | NA | 131242-WSD11-DR-3002_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5000_ST617 | NA | 131242-WSD11-DR-5000_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5001_ST617 | NA | 131242-WSD11-DR-5001_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5002_ST617 | NA | 131242-WSD11-DR-5002_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5003_ST617 | NA | 131242-WSD11-DR-5003_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5004_ST617 | NA | 131242-WSD11-DR-5004_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5005_ST617 | NA | 131242-WSD11-DR-5005_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5006_ST617 | NA | 131242-WSD11-DR-5006_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 8000_ST617 | NA | 131242-WSD11-DR-8000_ST617 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-24 | 2024-08-12 | 12 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | NAP | NAP
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | B | 131242-WSD11-DR-0300_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 0301_ST617 | NA | 131242-WSD11-DR-0301_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1000_ST617 | NA | 131242-WSD11-DR-1000_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1001_ST617 | NA | 131242-WSD11-DR-1001_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1002_ST617 | NA | 131242-WSD11-DR-1002_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1003_ST617 | NA | 131242-WSD11-DR-1003_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1004_ST617 | NA | 131242-WSD11-DR-1004_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-10-11 | NA | 000000 | 2024-07-04, 2024-10-11 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2000_ST617 | NA | 131242-WSD11-DR-2000_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2001_ST617 | NA | 131242-WSD11-DR-2001_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3000_ST617 | NA | 131242-WSD11-DR-3000_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3001_ST617 | NA | 131242-WSD11-DR-3001_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 3002_ST617 | NA | 131242-WSD11-DR-3002_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5000_ST617 | NA | 131242-WSD11-DR-5000_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5001_ST617 | NA | 131242-WSD11-DR-5001_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5002_ST617 | NA | 131242-WSD11-DR-5002_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5003_ST617 | NA | 131242-WSD11-DR-5003_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5004_ST617 | NA | 131242-WSD11-DR-5004_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5005_ST617 | NA | 131242-WSD11-DR-5005_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5006_ST617 | NA | 131242-WSD11-DR-5006_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 8000_ST617 | NA | 131242-WSD11-DR-8000_ST617 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000387 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0010 | 0 | 131242-WSW41-PS-0010 | 2024-03-22 | Monthly Progress Presentation No. 10 (0224) | For Information | 2024-04-23 | 2024-03-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-22 | 0 | 000000&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | PEN | INF | INF
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0019 | 0 | 131242-WSW41-MI-0019 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0020 | NA | 131242-WSW41-MI-0020 | 2024-03-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-10-29 | 443 | For Information | NO |  | YES |  |  | NO |  | NA | "Monthly Progress Meeting Minutes 0020_20250122" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | 2025-02-18 | 0 | 000000&&000353&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0021 | NA | 131242-WSW41-MI-0021 | 2024-03-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-10-29 | 443 | For Information | NO |  | YES |  |  | NO |  | NA | "Monthly Progress Meeting Minutes 0021_20250226" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | 2025-04-21 | 0 | 000000&&000460&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000389 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0009 | 0 | 131242-WSW41-PC-0009 | 2024-03-23 | Payment Claim No.9 | Rev(0): Approved. Refer to S.O. correspondence no. 137 dated 27 Mar 2024. | 2024-04-23 | 2024-05-10 | 12 | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.9" | 2024-03-23 | 2024-03-23 | 0 | 000389 | 2024-03-23 | 00 | 1 | PEN | APP | APP
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A | 131242-WSD11-DR-1000 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | 2024-07-16 |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1001 | NA | 131242-WSD11-DR-1001 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1002 | NA | 131242-WSD11-DR-1002 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1003 | NA | 131242-WSD11-DR-1003 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3000 | NA | 131242-WSD11-DR-3000 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3001 | NA | 131242-WSD11-DR-3001 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3002 | NA | 131242-WSD11-DR-3002 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-06-18 | 37 | For Information | YES | 2024-07-08 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | INF | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A.1 | 131242-WSD11-DR-1000 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-16 | 2024-10-29 | 31 | For Information | NO |  | YES |  |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1001 | NA | 131242-WSD11-DR-1001 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1002 | NA | 131242-WSD11-DR-1002 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 1003 | NA | 131242-WSD11-DR-1003 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3000 | NA | 131242-WSD11-DR-3000 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3001 | NA | 131242-WSD11-DR-3001 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 3002 | NA | 131242-WSD11-DR-3002 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-10-29 | 25 | For Information | NO |  | YES |  |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | INF | INF
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | 0 | 131242-WSD11-DR-1170 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 75 | For Information | YES | 2024-08-30 | NO | Overdue | 364 |  | Submitted as S000681.1 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | A.2 | 000000&&000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01, NA | 5 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1171 | NA | 131242-WSD11-DR-1171 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-08-12 | 75 | For Information | YES | 2024-08-30 | NO | Overdue | 364 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1172 | NA | 131242-WSD11-DR-1172 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-08-12 | 75 | For Information | YES | 2024-08-30 | NO | Overdue | 364 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 3170 | NA | 131242-WSD11-DR-3170 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-08-12 | 75 | For Information | YES | 2024-08-30 | NO | Overdue | 364 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 3171 | NA | 131242-WSD11-DR-3171 | 2024-03-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-23 | 2024-08-12 | 75 | For Information | YES | 2024-08-30 | NO | Overdue | 364 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | INF | INF
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7308 | A | 131242-WSD11-DR-7308 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  |  |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | 2026-01-27 | B | 000000&&000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7309 | NA | 131242-WSD11-DR-7309 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7310 | NA | 131242-WSD11-DR-7310 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7311 | NA | 131242-WSD11-DR-7311 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7312 | NA | 131242-WSD11-DR-7312 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7313 | NA | 131242-WSD11-DR-7313 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7314 | NA | 131242-WSD11-DR-7314 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7315 | NA | 131242-WSD11-DR-7315 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7316 | NA | 131242-WSD11-DR-7316 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7317 | NA | 131242-WSD11-DR-7317 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7318 | NA | 131242-WSD11-DR-7318 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7319 | NA | 131242-WSD11-DR-7319 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7320 | NA | 131242-WSD11-DR-7320 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7321 | NA | 131242-WSD11-DR-7321 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-04 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | B | 131242-WSD11-DR-7307 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  |  |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-26 | 2025-06-16 | B | 000000&&000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7308 | NA | 131242-WSD11-DR-7308 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | 2026-01-27 | B | 000000&&000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7309 | NA | 131242-WSD11-DR-7309 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7310 | NA | 131242-WSD11-DR-7310 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7311 | NA | 131242-WSD11-DR-7311 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7312 | NA | 131242-WSD11-DR-7312 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7313 | NA | 131242-WSD11-DR-7313 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7314 | NA | 131242-WSD11-DR-7314 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7315 | NA | 131242-WSD11-DR-7315 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7316 | NA | 131242-WSD11-DR-7316 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7317 | NA | 131242-WSD11-DR-7317 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7318 | NA | 131242-WSD11-DR-7318 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7319 | NA | 131242-WSD11-DR-7319 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7320 | NA | 131242-WSD11-DR-7320 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7321 | NA | 131242-WSD11-DR-7321 | 2024-06-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-16 | 2024-09-17 | 44 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | NAP | NAP
000392 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | C | 131242-WSD11-DR-7306 | 2024-11-19 | Compressor Sequencer Panel | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-09 | 2024-12-18 | 7 | Not Approved | YES | 2025-01-08 | YES | Resubmitted |  |  |  | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | PEN | NAP | NAP
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | D | 131242-WSD11-DR-7306 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7307 | NA | 131242-WSD11-DR-7307 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-26 | 2025-06-16 | B | 000000&&000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7308 | NA | 131242-WSD11-DR-7308 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | 2026-01-27 | B | 000000&&000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7309 | NA | 131242-WSD11-DR-7309 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7310 | NA | 131242-WSD11-DR-7310 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7311 | NA | 131242-WSD11-DR-7311 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7312 | NA | 131242-WSD11-DR-7312 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7313 | NA | 131242-WSD11-DR-7313 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7314 | NA | 131242-WSD11-DR-7314 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7315 | NA | 131242-WSD11-DR-7315 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7316 | NA | 131242-WSD11-DR-7316 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7317 | NA | 131242-WSD11-DR-7317 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7318 | NA | 131242-WSD11-DR-7318 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7319 | NA | 131242-WSD11-DR-7319 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7320 | NA | 131242-WSD11-DR-7320 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7321 | NA | 131242-WSD11-DR-7321 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7322 | NA | 131242-WSD11-DR-7322 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7323 | NA | 131242-WSD11-DR-7323 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7324 | NA | 131242-WSD11-DR-7324 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7325 | NA | 131242-WSD11-DR-7325 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7326 | NA | 131242-WSD11-DR-7326 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7327 | NA | 131242-WSD11-DR-7327 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7328 | NA | 131242-WSD11-DR-7328 | 2025-01-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-04 | 2025-03-25 | 35 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7306 | E | 131242-WSD11-DR-7306 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7307 | NA | 131242-WSD11-DR-7307 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-26 | 2025-06-16 | B | 000000&&000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7308 | NA | 131242-WSD11-DR-7308 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Compressor Sequencer Panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | 2026-01-27 | B | 000000&&000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7309 | NA | 131242-WSD11-DR-7309 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7310 | NA | 131242-WSD11-DR-7310 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7311 | NA | 131242-WSD11-DR-7311 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7312 | NA | 131242-WSD11-DR-7312 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-27 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7313 | NA | 131242-WSD11-DR-7313 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7314 | NA | 131242-WSD11-DR-7314 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7315 | NA | 131242-WSD11-DR-7315 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7316 | NA | 131242-WSD11-DR-7316 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7317 | NA | 131242-WSD11-DR-7317 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7318 | NA | 131242-WSD11-DR-7318 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7319 | NA | 131242-WSD11-DR-7319 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7320 | NA | 131242-WSD11-DR-7320 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7321 | NA | 131242-WSD11-DR-7321 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2025-06-16 | NA | 000000 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7322 | NA | 131242-WSD11-DR-7322 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7323 | NA | 131242-WSD11-DR-7323 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7324 | NA | 131242-WSD11-DR-7324 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7325 | NA | 131242-WSD11-DR-7325 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7326 | NA | 131242-WSD11-DR-7326 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7327 | NA | 131242-WSD11-DR-7327 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | I | 7328 | NA | 131242-WSD11-DR-7328 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-12-09 | 111 | Approved with Comments | YES | 2025-12-29 | NO | Overdue | 20 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-15 | 2025-06-16 | NA | 000000 | 2025-01-15, 2025-06-16 | 00 | 2 | PEN | AWC | AWC
000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-7700 | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | 2024-07-24 |  | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7701 | NA | 131242-WSD11-DR-7701 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-7700 | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | 48 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | TBA | To check with Yibo and will advise later the submission date. | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7701 | NA | 131242-WSD11-DR-7701 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-02 | 2024-11-08 | 48 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-7720 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | 2024-07-24 |  | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7721 | NA | 131242-WSD11-DR-7721 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7722 | NA | 131242-WSD11-DR-7722 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7723 | NA | 131242-WSD11-DR-7723 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7724 | NA | 131242-WSD11-DR-7724 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7725 | NA | 131242-WSD11-DR-7725 | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-17 | 16 | Approved with Comments | YES | 2024-06-07 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-7720 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-02 | 2024-11-08 | 48 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | TBA | To check with Yibo and will advise later the submission date. | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7721 | NA | 131242-WSD11-DR-7721 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-11-08 | 42 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7722 | NA | 131242-WSD11-DR-7722 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-11-08 | 42 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7723 | NA | 131242-WSD11-DR-7723 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-11-08 | 42 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7724 | NA | 131242-WSD11-DR-7724 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-11-08 | 42 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | E | 7725 | NA | 131242-WSD11-DR-7725 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-11-08 | 42 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2024-08-13 | NA | 000000 | 2024-03-25, 2024-08-13 | 00 | 2 | PEN | AWC | AWC
000395 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | A | 131242-WSD11-DR-3160 | 2024-03-25 | Air Compressor Motor Outline Drawing | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached files for comments. | 2024-04-24 | 2024-05-16 | 15 | Approved with Comments | YES | 2024-06-06 | YES | Resubmitted |  | 2024-07-24 |  | NA | "Air Compressor Motor Outline Drawing " | 2024-03-25 | 2024-08-16 | B | 000395 | 2024-03-25, 2024-08-16 | 00, 01 | 2 | PEN | AWC | AWC
000395 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | B | 131242-WSD11-DR-3160 | 2024-08-16 | Air Compressor Motor Outline Drawing | Rev 1: Approved. | 2024-09-05 | 2024-11-04 | 41 | Approved | NO |  | YES |  |  |  |  | NA | "Air Compressor Motor Outline Drawing " | 2024-03-25 | 2024-08-16 | B | 000395 | 2024-03-25, 2024-08-16 | 00, 01 | 2 | PEN | APP | APP
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-1000_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | NA | 131242-WST02-DR-2001_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | NA | 131242-WST02-DR-2002_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | NA | 131242-WST02-DR-2003_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | NA | 131242-WST02-DR-2007_LTA_NPKS | 2024-03-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-0001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2024-10-30 | A | 000000&&000396 | 2024-05-16, 2024-10-30 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-1000_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | NA | 131242-WST02-DR-2001_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | NA | 131242-WST02-DR-2002_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | NA | 131242-WST02-DR-2003_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | NA | 131242-WST02-DR-2007_LTA_NPKS | 2024-05-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-06 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-1000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | NA | 131242-WST02-DR-1006_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-09 | NA | 000000 | 2024-10-30, 2026-01-09 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | NA | 131242-WST02-DR-2001_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | NA | 131242-WST02-DR-2002_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | NA | 131242-WST02-DR-2003_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | NA | 131242-WST02-DR-2007_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | NA | 131242-WST02-DR-3000_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-09 | NA | 000000 | 2024-10-30, 2026-01-09 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 5004_LTA_NPKS | NA | 131242-WST02-DR-5004_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | NA | 131242-WST02-DR-0001_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2024-10-30 | A | 000000&&000396 | 2024-05-16, 2024-10-30 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 0002_LTA_NPKS | NA | 131242-WST02-DR-0002_LTA_NPKS | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-08 | 33 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-1000_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  |  | Rejected as CES requested as drawings need to be included PE endorsement | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | REJ | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-1000_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | NAP | NAP
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-1000_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2025-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-01 | 2025-10-13 | 30 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | NAP | NAP
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-1000_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  |  |  | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | REJ | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.2 | 131242-WST02-DR-1000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "LTA & Nparks submission Set" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | A.2 | 000000&&000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 02, 03, 04, 05, 06, 07 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | NA | 131242-WST02-DR-1001_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | NA | 131242-WST02-DR-1002_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | NA | 131242-WST02-DR-1003_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | NA | 131242-WST02-DR-1004_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_LTA_NPKS | NA | 131242-WST02-DR-1005_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2026-01-09 | 2026-01-09 | NA | 000000 | 2026-01-09 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | NA | 131242-WST02-DR-1006_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-09 | NA | 000000 | 2024-10-30, 2026-01-09 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | NA | 131242-WST02-DR-1009_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | NA | 131242-WST02-DR-2000_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-16 | 2026-01-09 | NA | 000000 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | NA | 131242-WST02-DR-2001_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | NA | 131242-WST02-DR-2002_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | NA | 131242-WST02-DR-2003_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | NA | 131242-WST02-DR-2007_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-25 | 2026-01-09 | NA | 000000 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00 | 4 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | NA | 131242-WST02-DR-3000_LTA_NPKS | 2026-01-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-29 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-09 | NA | 000000 | 2024-10-30, 2026-01-09 | 00 | 2 | PEN | PEN | PEN
000397 | 00 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0000_NEA | A | 131242-WST02-DR-0000_NEA | 2024-03-25 | NEA DC submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 5 | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "NEA DC submission Set " | 2024-03-25 | 2024-03-25 | A | 000397 | 2024-03-25 | 00 | 1 | PEN | NAP | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-1000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "NEA DC submission Set " | 2024-10-30 | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_NEA | NA | 131242-WST02-DR-1001_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_NEA | NA | 131242-WST02-DR-1002_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_NEA | NA | 131242-WST02-DR-1003_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_NEA | NA | 131242-WST02-DR-1004_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_NEA | NA | 131242-WST02-DR-1006_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_NEA | NA | 131242-WST02-DR-1009_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_NEA | NA | 131242-WST02-DR-2000_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-11-18, 2026-01-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_NEA | NA | 131242-WST02-DR-2001_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_NEA | NA | 131242-WST02-DR-2002_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_NEA | NA | 131242-WST02-DR-2003_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_NEA | NA | 131242-WST02-DR-2007_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_NEA | NA | 131242-WST02-DR-3000_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 5004_NEA | NA | 131242-WST02-DR-5004_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 0002_NEA | NA | 131242-WST02-DR-0002_NEA | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-16 | 39 | Not Approved | YES | 2025-02-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2024-10-30 | NA | 000000 | 2024-10-30 | 00 | 1 | PEN | NAP | NAP
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-1000_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  |  | Rejected as CES requested as drawings need to be included PE endorsement | NA | "NEA DC submission Set " | 2024-10-30 | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_NEA | NA | 131242-WST02-DR-1001_NEA | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_NEA | NA | 131242-WST02-DR-1002_NEA | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_NEA | NA | 131242-WST02-DR-1003_NEA | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_NEA | NA | 131242-WST02-DR-1004_NEA | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_NEA | NA | 131242-WST02-DR-1009_NEA | 2025-03-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-28 | 2025-03-21 |  | Rejected | YES | 2025-04-10 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-1000_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  |  |  | NA | "NEA DC submission Set " | 2024-10-30 | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_NEA | NA | 131242-WST02-DR-1001_NEA | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_NEA | NA | 131242-WST02-DR-1002_NEA | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_NEA | NA | 131242-WST02-DR-1003_NEA | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_NEA | NA | 131242-WST02-DR-1004_NEA | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_NEA | NA | 131242-WST02-DR-1009_NEA | 2025-03-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-10 | 2025-06-11 | 41 | Not Approved | YES | 2025-07-01 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | NAP | NAP
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-1000_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  |  |  | NA | "NEA DC submission Set " | 2024-10-30 | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_NEA | NA | 131242-WST02-DR-1001_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_NEA | NA | 131242-WST02-DR-1002_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_NEA | NA | 131242-WST02-DR-1003_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_NEA | NA | 131242-WST02-DR-1004_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_NEA | NA | 131242-WST02-DR-1009_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_NEA | NA | 131242-WST02-DR-2000_NEA | 2025-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-08 | 2025-12-17 | 7 | Rejected | YES | 2026-01-06 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-11-18, 2026-01-06 | 00 | 3 | PEN | REJ | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.2 | 131242-WST02-DR-1000_NEA | 2026-01-06 | NEA DC submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "NEA DC submission Set " | 2024-10-30 | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_NEA | NA | 131242-WST02-DR-1001_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_NEA | NA | 131242-WST02-DR-1002_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_NEA | NA | 131242-WST02-DR-1003_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_NEA | NA | 131242-WST02-DR-1004_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_NEA | NA | 131242-WST02-DR-1005_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2026-01-06 | 2026-01-06 | NA | 000000 | 2026-01-06 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_NEA | NA | 131242-WST02-DR-1006_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_NEA | NA | 131242-WST02-DR-1009_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_NEA | NA | 131242-WST02-DR-2000_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2025-11-18, 2026-01-06 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_NEA | NA | 131242-WST02-DR-2001_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_NEA | NA | 131242-WST02-DR-2002_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_NEA | NA | 131242-WST02-DR-2003_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_NEA | NA | 131242-WST02-DR-2007_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_NEA | NA | 131242-WST02-DR-3000_NEA | 2026-01-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-26 | 2025-12-17 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2026-01-06 | NA | 000000 | 2024-10-30, 2026-01-06 | 00 | 2 | PEN | PEN | PEN
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6000 | A | 131242-WST02-DR-6000 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  | Heng Peng to provide DGN dwg | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6001 | NA | 131242-WST02-DR-6001 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6002 | NA | 131242-WST02-DR-6002 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6003 | NA | 131242-WST02-DR-6003 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6004 | NA | 131242-WST02-DR-6004 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6005 | NA | 131242-WST02-DR-6005 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6006 | NA | 131242-WST02-DR-6006 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6007 | NA | 131242-WST02-DR-6007 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6008 | NA | 131242-WST02-DR-6008 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6009 | NA | 131242-WST02-DR-6009 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6010 | NA | 131242-WST02-DR-6010 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6011 | NA | 131242-WST02-DR-6011 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6012 | NA | 131242-WST02-DR-6012 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6013 | NA | 131242-WST02-DR-6013 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6014 | NA | 131242-WST02-DR-6014 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000398 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#398 CES Reply | NA | 131242-WST02-NA-S#398 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev 1: the submittal is closed as per the request of C4B contractor and merged to SRC 731 | 2024-10-21 | 2024-10-24 | 3 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "P&ID for SSN Process" | 2024-10-01 | 2024-10-01 | NA | 000398 | 2024-10-01 | 01 | 1 | PEN | AWC | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | A | 131242-WST02-DR-6015 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  |  | Heng Peng to provide DGN dwg | NA | "P&ID for SSN Chemical Dosing Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000399 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6016 | NA | 131242-WST02-DR-6016 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6017 | NA | 131242-WST02-DR-6017 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6018 | NA | 131242-WST02-DR-6018 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6019 | NA | 131242-WST02-DR-6019 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6020 | NA | 131242-WST02-DR-6020 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-04-30 | 3 | Approved with Comments | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000399 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | NA | NA | S#399 CES Reply | NA | 131242-WSD11-NA-S#399 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev1: The submittal is merged with SRC 731. | 2024-10-21 | 2024-11-07 | 12 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "P&ID for SSN Process" | 2024-10-01 | 2024-10-01 | NA | 000399 | 2024-10-01 | 01 | 1 | PEN | AWC | AWC
000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | A | 131242-WST02-DR-6200 | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  | Heng Peng to provide DGN dwg | NA | "P&ID for SSN Plant Water and Instrument Air" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000400 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 6600 | NA | 131242-WST02-DR-6600 | 2024-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-25 | 2024-05-23 | 18 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000400 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#400 CES Reply | NA | 131242-WST02-NA-S#400 CES Reply | 2024-10-01 | P&ID for SSN Plant Water and Instrument Air | Rev 1: The submittal is closed and merged with SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "P&ID for SSN Plant Water and Instrument Air" | 2024-10-01 | 2024-10-01 | NA | 000400 | 2024-10-01 | 01 | 1 | PEN | APP | APP
000401 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7000 | A | 131242-WST02-DR-7000 | 2024-03-26 | SSN Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-25 | 2024-04-30 | 3 | Not Approved | YES | 2024-05-21 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000401 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7000 | B | 131242-WST02-DR-7000 | 2024-08-26 | SSN Control System Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-13 | 2024-10-16 | 23 | Approved with Comments | YES | 2024-11-06 | NO | Overdue | 317 |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-1000_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2024-03-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-26 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-1000_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-10 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-1000_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2024-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-03 | 2024-05-24 |  | Not Approved | YES | 2024-06-13 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-1000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 5004_FSSD_BP | NA | 131242-WST02-DR-5004_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2024-10-16 | NA | 000000 | 2024-10-16 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | A | 0001_FSSD_BP | NA | 131242-WST02-CL-0001_FSSD_BP | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2025-02-13 | 67 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2024-10-16 | NA | 000000 | 2024-10-16 | 00 | 1 | PEN | NAP | NAP
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-1000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2025-03-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-15 | 2025-05-20 | 22 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-1000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-08 | 2025-10-13 | 25 | Not Approved | YES | 2025-10-31 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.2 | 131242-WST02-DR-1000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | NA | 131242-WST02-DR-1005_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-11-07 | 2026-01-07 | NA | 000000 | 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2025-11-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-27 | 2025-12-02 | 3 | Not Approved | YES | 2025-12-22 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | NAP | NAP
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-1000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  |  |  | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | NA | 131242-WST02-DR-1005_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-11-07 | 2026-01-07 | NA | 000000 | 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2025-12-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-12-23 | 2026-01-05 | 8 | Approved with Comments | YES | 2026-01-23 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | AWC | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-1000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | NA | 2026-01-27 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | NA | 131242-WST02-DR-1001_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | NA | 131242-WST02-DR-1002_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | NA | 131242-WST02-DR-1003_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | NA | 131242-WST02-DR-1004_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | NA | 131242-WST02-DR-1005_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-11-07 | 2026-01-07 | NA | 000000 | 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | NA | 131242-WST02-DR-1006_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | NA | 131242-WST02-DR-1009_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | NA | 131242-WST02-DR-2000_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-13 | 2026-01-07 | NA | 000000 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 7 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | NA | 131242-WST02-DR-2001_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | NA | 131242-WST02-DR-2002_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | NA | 131242-WST02-DR-2003_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 8 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | NA | 131242-WST02-DR-2007_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-27 | 2026-01-07 | NA | 000000 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 9 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | NA | 131242-WST02-DR-3000_FSSD_BP | 2026-01-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-01-27 | 2026-01-05 |  | Awaiting S.O.'s response | [5 empty] | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-16 | 2026-01-07 | NA | 000000 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00 | 6 | PEN | PEN | PEN
000403 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SP | P | 0001 | 0 | 131242-WST02-SP-0001 | 2024-03-27 | SSN Control Philosophy | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-26 | 2024-05-23 | 17 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  | Pending MP resubmission | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000403 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 1 | 131242-WST02-SP-0001 | 2024-08-12 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-03 | 2 | Approved with Comments | YES | 2024-09-23 | YES | Resubmitted |  |  |  | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000403 | 02 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 2 | 131242-WST02-SP-0001 | 2024-10-03 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-11-07 | 10 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | 2025-02-28 | Pending MP updates | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000403 | 03 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 3 | 131242-WST02-SP-0001 | 2025-03-14 | SSN Control Philosophy | Approved with Comments | 2025-04-03 | 2025-05-15 | 27 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 | 2025-02-28 | Pending MP updates | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000404 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0004 | 0 | 131242-WST02-CL-0004 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 16 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  |  | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | PEN | AWC | AWC
000404 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 1 | 131242-WST02-CL-0004 | 2024-07-28 | SSN Chemical Consumption Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 9 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  |  |  | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | PEN | AWC | AWC
000404 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 2 | 131242-WST02-CL-0004 | 2024-10-16 | SSN Chemical Consumption Calculation | Rev 2: Approved | 2024-11-06 | 2024-11-15 | 7 | Approved | NO |  | YES |  |  |  |  | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | PEN | APP | APP
000405 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0002 | 0 | 131242-WSD11-RT-0002 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-30 | 21 | Approved with Comments | YES | 2024-06-20 | NO | Overdue | 414 |  | After addressing BODR | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
000406 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 0 | 131242-WST02-CL-0005 | 2024-03-28 | SSN 22kV MV Power Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 16 | Not Approved | YES | 2024-06-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | NAP | NAP
000406 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 1 | 131242-WST02-CL-0005 | 2024-07-06 | SSN 22kV MV Power Cable Sizing Calculations | Rev 1: Approved with comments. To revise and resubmit. | 2024-07-25 | 2024-07-22 |  | Approved with Comments | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | AWC | AWC
000406 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 2 | 131242-WST02-CL-0005 | 2025-02-19 | SSN 22kV MV Power Cable Sizing Calculations | Rev 2: Approved. | 2025-03-11 | 2025-05-06 | 37 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | APP | APP
000407 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | P | 0001 | 0 | 131242-WST02-RT-0001 | 2024-03-28 | Basic Design Report of SSN Package | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-05-03 | 3 | Not Approved | YES | 2024-05-24 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | NAP | NAP
000407 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 1 | 131242-WST02-RT-0001 | 2024-05-23 | Basic Design Report of SSN Package | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-12 | 2024-07-04 | 15 | Approved with Comments | YES | 2024-07-24 | YES | Resubmitted |  |  | To follow up with MP for resubmission | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000407 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 2 | 131242-WST02-RT-0001 | 2024-11-18 | Basic Design Report of SSN Package | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-06 | 2025-01-08 | 21 | Approved with Comments | YES | 2025-01-28 | NO | Overdue | 259 | 2025-03-31 | comments received on 14 Feb | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0015 | 1 | 131242-WST02-DS-0015 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 |  | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  |  |  | NA | "Datasheet for Dissolved Oxygen Analyser " && "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | 2025-08-04 | 0 | 000408&&001551 | 2024-03-28, 2024-07-05, 2025-08-04 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0016 | NA | 131242-WST02-DR-0016 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-04-29 |  | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-07-05 | NA | 000000 | 2024-03-28, 2024-07-05 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0015 | NA | 131242-WST02-DR-0015 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-04-29 |  | Not Approved | YES | 2024-05-20 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-07-05 | NA | 000000 | 2024-03-28, 2024-07-05 | 00 | 2 | PEN | NAP | NAP
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0015 | 0 | 131242-WST02-DS-0015 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | 2025-02-28 | Pending MP updates | NA | "Datasheet for Dissolved Oxygen Analyser " && "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | 2025-08-04 | 0 | 000408&&001551 | 2024-03-28, 2024-07-05, 2025-08-04 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0016 | NA | 131242-WST02-DR-0016 | 2024-07-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-07-05 | NA | 000000 | 2024-03-28, 2024-07-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0015 | NA | 131242-WST02-DR-0015 | 2024-07-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-07-05 | NA | 000000 | 2024-03-28, 2024-07-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | M | 0001 | NA | 131242-WST02-CL-0001 | 2024-07-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | AWC | AWC
000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0016 | 0 | 131242-WST02-DS-0016 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | 1 | Not Approved | YES | 2024-05-21 | YES | Resubmitted |  |  |  | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0017 | NA | 131242-WST02-DR-0017 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-04-30 | 1 | Not Approved | YES | 2024-05-21 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2025-03-14 | NA | 000000 | 2024-03-28, 2024-07-05, 2025-03-14 | 00 | 3 | PEN | NAP | NAP
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 1 | 131242-WST02-DS-0016 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  | 2025-02-28 | Pending MP updates | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0017 | NA | 131242-WST02-DR-0017 | 2024-07-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2025-03-14 | NA | 000000 | 2024-03-28, 2024-07-05, 2025-03-14 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0018 | NA | 131242-WST02-DR-0018 | 2024-07-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-25 | 2024-08-29 | 24 | Approved with Comments | YES | 2024-09-18 | YES | Resubmitted |  | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-05 | 2025-03-14 | NA | 000000 | 2024-07-05, 2025-03-14 | 00 | 2 | PEN | AWC | AWC
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 2 | 131242-WST02-DS-0016 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 69 | Approved with Comments | YES | 2025-08-01 | NO | Overdue | 126 |  |  | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0017 | NA | 131242-WST02-DR-0017 | 2025-03-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-03 | 2025-07-14 | 69 | Approved with Comments | YES | 2025-08-01 | NO | Overdue | 126 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2025-03-14 | NA | 000000 | 2024-03-28, 2024-07-05, 2025-03-14 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0018 | NA | 131242-WST02-DR-0018 | 2025-03-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-03 | 2025-07-14 | 69 | Approved with Comments | YES | 2025-08-01 | NO | Overdue | 126 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-05 | 2025-03-14 | NA | 000000 | 2024-07-05, 2025-03-14 | 00 | 2 | PEN | AWC | AWC
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A | 131242-WST02-DR-1003_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | NO | Overdue | 433 | 2024-08-16 | Heng Peng to provide Native DGN sets | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST616 | NA | 131242-WST02-DR-7001_ST616 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | NO | Overdue | 433 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST616 | NA | 131242-WST02-DR-8001_ST616 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-02 | 2 | Not Approved | YES | 2024-05-23 | NO | Overdue | 433 | NO |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | NAP | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST609 | A | 131242-WST02-DR-1001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | 2024-07-26 | Tenwit in Progress | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2001_ST609 | NA | 131242-WST02-DR-2001_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3001_ST609 | NA | 131242-WST02-DR-3001_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST609 | NA | 131242-WST02-DR-1002_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1000_ST609 | NA | 131242-WST02-DR-1000_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2000_ST609 | NA | 131242-WST02-DR-2000_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST609 | NA | 131242-WST02-DR-3000_ST609 | 2024-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-04-29 | 2024-05-09 | 7 | Not Approved | YES | 2024-05-30 | NO | Overdue | 428 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-03-28 | NA | 000000 | 2024-03-28 | 00 | 1 | PEN | NAP | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-1000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | 2024-08-16 | Heng Peng to provide Native DGN sets and Aaron to address the comments | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | NA | 131242-WST02-DR-1001_ST615_BCA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | NA | 131242-WST02-DR-1002_ST615_BCA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | NA | 131242-WST02-DR-5001_ST615_BCA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | NA | 131242-WST02-DR-7000_ST615_BCA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | NA | 131242-WST02-DR-8000_ST615_BCA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-05 | 2024-04-25 | NA | 000000 | 2024-03-05, 2024-04-02, 2024-04-25 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_NOA | NA | 131242-WST02-DR-A1798-00002-2018-ST615_NOA | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-04-02 | NA | 000000 | 2024-04-02 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_Fdn Advice Letter | NA | 131242-WST02-DR-A1798-00002-2018-ST615_Fdn Advice Letter | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-05-14 | 8 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-04-02 | NA | 000000 | 2024-04-02 | 00 | 1 | PEN | NAP | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-1000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  |  |  | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST615 | NA | 131242-WST02-DR-1001_ST615 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST615 | NA | 131242-WST02-DR-1002_ST615 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST615 | NA | 131242-WST02-DR-5001_ST615 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST615 | NA | 131242-WST02-DR-7000_ST615 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8000_ST615 | NA | 131242-WST02-DR-8000_ST615 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-04-19 |  | Not Approved | YES | 2024-05-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-1000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-04 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | 2024-08-16 | Heng Peng: BIM Pending to clear BIM comments | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST615 | NA | 131242-WST02-DR-1001_ST615 | 2024-05-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-12 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST615 | NA | 131242-WST02-DR-1002_ST615 | 2024-05-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-12 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST615 | NA | 131242-WST02-DR-5001_ST615 | 2024-05-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-12 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST615 | NA | 131242-WST02-DR-7000_ST615 | 2024-05-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-12 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8000_ST615 | NA | 131242-WST02-DR-8000_ST615 | 2024-05-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-12 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-02 | 2024-05-14 | NA | 000000 | 2024-04-02, 2024-05-14 | 00 | 2 | PEN | NAP | NAP
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1000 | C01 | 131242-WSD11-DR-1000 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 23 | Approved with Comments | YES | 2024-06-26 | NO | Overdue | 410 |  | Pending DGN dwg drawing and CAMBI updates and to update Tagging | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1001 | NA | 131242-WSD11-DR-1001 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-06-05 | 23 | Approved with Comments | YES | 2024-06-26 | NO | Overdue | 410 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1002 | NA | 131242-WSD11-DR-1002 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-06-05 | 23 | Approved with Comments | YES | 2024-06-26 | NO | Overdue | 410 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1003 | NA | 131242-WSD11-DR-1003 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-06-05 | 23 | Approved with Comments | YES | 2024-06-26 | NO | Overdue | 410 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 1004 | NA | 131242-WSD11-DR-1004 | 2024-04-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-02 | 2024-06-05 | 23 | Approved with Comments | YES | 2024-06-26 | NO | Overdue | 410 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 18 | PEN | AWC | AWC
000415 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0006 | 0 | 131242-WST02-CL-0006 | 2024-04-03 | SSN Equipment Sizing Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-05-23 | 13 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  |  |  | NA | "SSN Equipment Sizing Calculation" | 2024-04-03 | 2024-08-12 | 1 | 000415 | 2024-04-03, 2024-08-12 | 00, 01 | 2 | PEN | AWC | AWC
000415 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0006 | 1 | 131242-WST02-CL-0006 | 2024-08-12 | SSN Equipment Sizing Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-11 | 30 | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  |  |  | NA | "SSN Equipment Sizing Calculation" | 2024-04-03 | 2024-08-12 | 1 | 000415 | 2024-04-03, 2024-08-12 | 00, 01 | 2 | PEN | AWC | AWC
000415 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | Comment Reply Sheet 20241118 S415.1 | NA | 131242-WST02-CL-Comment Reply Sheet 20241118 S415.1 | 2024-11-18 | SSN Equipment Sizing Calculation | Rev 2: Approved with Comments. The submittal is requested to be discontinued by CES. | 2024-12-06 | 2025-01-08 | 21 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "SSN Equipment Sizing Calculation" | 2024-11-18 | 2024-11-18 | NA | 000415 | 2024-11-18 | 02 | 1 | PEN | AWC | AWC
000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0005 | 0 | 131242-WST02-CL-0005 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | 22 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7010 | NA | 131242-WST02-DR-7010 | 2024-04-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-03 | 2024-06-05 | 22 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000416 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 1 | 131242-WST02-CL-0005 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | 33 | Approved with Comments | YES | 2024-11-15 | YES | Resubmitted |  | 2025-02-28 | Pending MP updates, Need PE endosement | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7010 | NA | 131242-WST02-DR-7010 | 2024-08-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-10-25 | 33 | Approved with Comments | YES | 2024-11-15 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000416 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 2 | 131242-WST02-CL-0005 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | 123 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | P | 7010 | NA | 131242-WST02-DR-7010 | 2025-03-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-11 | 2025-10-06 | 123 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | APP | APP
000417 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 0 | 131242-WSD11-VI-0002 | 2024-04-04 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-04-18 |  | Not Approved | YES | 2024-05-09 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | PEN | NAP | NAP
000417 | 01 | Karthik/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 1 | 131242-WSD11-VI-0002 | 2024-08-15 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-04 | 2024-11-08 | 46 | Approved with Comments | YES | 2024-11-28 | NO | Overdue | 301 |  |  | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | PEN | AWC | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1003 | A | 131242-WST02-DR-1003 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1004 | NA | 131242-WST02-DR-1004 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1005 | NA | 131242-WST02-DR-1005 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1006 | NA | 131242-WST02-DR-1006 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1007 | NA | 131242-WST02-DR-1007 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7001 | NA | 131242-WST02-DR-7001 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7002 | NA | 131242-WST02-DR-7002 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7003 | NA | 131242-WST02-DR-7003 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-18 | 51 | Not Approved | YES | 2024-08-07 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1003 | B | 131242-WST02-DR-1003 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1004 | NA | 131242-WST02-DR-1004 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1005 | NA | 131242-WST02-DR-1005 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1006 | NA | 131242-WST02-DR-1006 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 1007 | NA | 131242-WST02-DR-1007 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7001 | NA | 131242-WST02-DR-7001 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7002 | NA | 131242-WST02-DR-7002 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | B | 7003 | NA | 131242-WST02-DR-7003 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2025-03-25 | 91 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1011 | A | 131242-WST02-DR-1011 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 41 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1012 | NA | 131242-WST02-DR-1012 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-04 | 41 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1013 | NA | 131242-WST02-DR-1013 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-04 | 41 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7103 | NA | 131242-WST02-DR-7103 | 2024-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-06 | 2024-07-04 | 41 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | NAP | NAP
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1011 | B | 131242-WST02-DR-1011 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1012 | NA | 131242-WST02-DR-1012 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-08 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 1013 | NA | 131242-WST02-DR-1013 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-08 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | BF | 7103 | NA | 131242-WST02-DR-7103 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-08 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | AWC | AWC
000420 | 00 | Suresh | PCM | NA | 131242 | WSW41 | MI | PM | 0010 | 0 | 131242-WSW41-MI-0010 | 2024-04-04 | Monthly Progress Meeting Minutes 0010_20240319 | For Information | 2024-05-06 | 2024-04-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-27 | 2024-04-04 | 0 | 000000&&000109&&000126&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | PEN | INF | INF
000421 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 0 | 131242-WSD11-DS-0013 | 2024-04-05 | Data Sheet and Drawing of THP Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 26 | Approved with Comments | YES | 2024-07-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-05 | 2026-01-15 | A | 000000&&000421&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | PEN | AWC | AWC
000421 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 1 | 131242-WSD11-DS-0013 | 2024-08-12 | Data Sheet of THP Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 7 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-05 | 2026-01-15 | A | 000000&&000421&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | PEN | AWC | AWC
000421 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 2 | 131242-WSD11-DS-0013 | 2025-01-26 | Data Sheet of THP Feed Pump | Rev 2: Approved | 2025-02-13 | 2025-04-27 | 49 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-05 | 2026-01-15 | A | 000000&&000421&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | PEN | APP | APP
000422 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 0 | 131242-WSD11-DS-0014 | 2024-04-06 | Data Sheet and Drawing of Reactor Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 26 | Approved with Comments | YES | 2024-07-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-06 | 2026-01-20 | 0 | 000000&&000422&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | PEN | AWC | AWC
000422 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 1 | 131242-WSD11-DS-0014 | 2024-08-12 | Data Sheet and Drawing of Reactor Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 7 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-06 | 2026-01-20 | 0 | 000000&&000422&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | PEN | AWC | AWC
000422 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 2 | 131242-WSD11-DS-0014 | 2025-04-10 | Data Sheet and Drawing of Reactor Feed Pump | Rev 2: Approved | 2025-04-30 | 2025-10-06 | 111 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-06 | 2026-01-20 | 0 | 000000&&000422&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | PEN | APP | APP
000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0001 | A | 131242-WSD11-DR-0001 | 2024-04-06 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | CL | S | 0004 | NA | 131242-WSD11-CL-0004 | 2024-04-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-07 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | 2024-08-15 | 0 | 000000&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00 | 3 | PEN | NAP | NAP
000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301 | A | 131242-WSD11-DR-5301 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-06-26 | 2024-06-19 |  | Approved | NO |  | YES |  |  |  |  | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | 2024-06-26 | B | 000423&&000536 | 2024-06-05, 2024-06-26 | 00, 01 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | CL | S | 0004 | NA | 131242-WSD11-CL-0004 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-05-02 | 394 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | 2024-08-15 | 0 | 000000&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00 | 3 | PEN | PEN | PEN
000424 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0037 | 0 | 131242-WSW41-CD-0037 | 2024-04-08 | Submission Of BIM Coordination VCM Model (Mar-2024) | For Information | 2024-05-08 | 2024-04-19 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Mar-2024)" | 2024-04-08 | 2024-04-08 | 0 | 000424 | 2024-04-08 | 00 | 1 | PEN | INF | INF
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-1003_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 |  | Not Approved | YES | 2024-05-08 | YES | Resubmitted |  |  |  | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | NA | 131242-WST02-DR-7001_ST616_BCA | 2024-04-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-08 | 2024-04-17 |  | Not Approved | YES | 2024-05-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | NA | 131242-WST02-DR-8001_ST616_BCA | 2024-04-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-08 | 2024-04-17 |  | Not Approved | YES | 2024-05-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | NA | 131242-WST02-DR-A1798-00002-2018_NOA | 2024-04-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-08 | 2024-04-17 |  | Not Approved | YES | 2024-05-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-1003_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-14 | 3 | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | 2024-08-16 | Heng Peng to provide Native DGN sets and Aaron to address the comments | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | NA | 131242-WST02-DR-7001_ST616_BCA | 2024-04-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-17 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | NA | 131242-WST02-DR-8001_ST616_BCA | 2024-04-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-17 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | NA | 131242-WST02-DR-A1798-00002-2018_NOA | 2024-04-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-17 | 2024-05-14 |  | Not Approved | YES | 2024-06-04 | NO | Overdue | 425 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-08 | 2024-04-18 | NA | 000000 | 2024-04-08, 2024-04-18 | 00 | 2 | PEN | NAP | NAP
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A2 | 131242-WST02-DR-1003_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 |  | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  |  |  | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST616 | NA | 131242-WST02-DR-7001_ST616 | 2024-04-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-08 | 2024-04-17 |  | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST616 | NA | 131242-WST02-DR-8001_ST616 | 2024-04-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-08 | 2024-04-17 |  | Approved with Comments | YES | 2024-05-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | AWC | AWC
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A.2 | 131242-WST02-DR-1003_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-17 | 2024-05-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST616 | NA | 131242-WST02-DR-7001_ST616 | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-14 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8001_ST616 | NA | 131242-WST02-DR-8001_ST616 | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-14 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-28 | 2024-04-26 | NA | 000000 | 2024-03-28, 2024-04-08, 2024-04-26 | 00 | 3 | PEN | INF | INF
000427 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 0 | 131242-WSW41-CL-0004 | 2024-04-08 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-22 |  | Not Approved | YES | 2024-05-13 | YES | Resubmitted |  |  |  | NA | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-08 | 2024-04-23 | 1 | 000427 | 2024-04-08, 2024-04-23 | 00, 01 | 2 | PEN | NAP | NAP
000427 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 1 | 131242-WSW41-CL-0004 | 2024-04-23 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.1: Approved | 2024-05-14 | 2024-05-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-08 | 2024-04-23 | 1 | 000427 | 2024-04-08, 2024-04-23 | 00, 01 | 2 | PEN | APP | APP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608 | 0 | 131242-WST02-CL-0002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-04-09 | 0 | 000428 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1005_ST608 | NA | 131242-WST02-DR-1005_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1001_ST608 | NA | 131242-WST02-DR-1001_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1002_ST608 | NA | 131242-WST02-DR-1002_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2000_ST608 | NA | 131242-WST02-DR-2000_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST608 | NA | 131242-WST02-DR-3000_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1003_ST608 | NA | 131242-WST02-DR-1003_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2001_ST608 | NA | 131242-WST02-DR-2001_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3001_ST608 | NA | 131242-WST02-DR-3001_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1004_ST608 | NA | 131242-WST02-DR-1004_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2002_ST608 | NA | 131242-WST02-DR-2002_ST608 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2024-04-09 | NA | 000000 | 2024-04-09 | 00 | 1 | PEN | NAP | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608 | B | 131242-WST00-DR-8005_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-10 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  |  |  | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0302_ST608 | NA | 131242-WST02-DR-0302_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1200_ST608 | NA | 131242-WST02-DR-1200_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1201_ST608 | NA | 131242-WST02-DR-1201_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1202_ST608 | NA | 131242-WST02-DR-1202_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1203_ST608 | NA | 131242-WST02-DR-1203_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1204_ST608 | NA | 131242-WST02-DR-1204_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1205_ST608 | NA | 131242-WST02-DR-1205_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2200_ST608 | NA | 131242-WST02-DR-2200_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2201_ST608 | NA | 131242-WST02-DR-2201_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2202_ST608 | NA | 131242-WST02-DR-2202_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 2203_ST608 | NA | 131242-WST02-DR-2203_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3200_ST608 | NA | 131242-WST02-DR-3200_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3201_ST608 | NA | 131242-WST02-DR-3201_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3202_ST608 | NA | 131242-WST02-DR-3202_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5200_ST608 | NA | 131242-WST02-DR-5200_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5201_ST608 | NA | 131242-WST02-DR-5201_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5202_ST608 | NA | 131242-WST02-DR-5202_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5203_ST608 | NA | 131242-WST02-DR-5203_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5204_ST608 | NA | 131242-WST02-DR-5204_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5205_ST608 | NA | 131242-WST02-DR-5205_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5206_ST608 | NA | 131242-WST02-DR-5206_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5207_ST608 | NA | 131242-WST02-DR-5207_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5208_ST608 | NA | 131242-WST02-DR-5208_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5209_ST608 | NA | 131242-WST02-DR-5209_ST608 | 2024-09-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-18 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-20 | 2024-09-20 | NA | 000000 | 2024-09-20 | 00 | 1 | PEN | NAP | NAP
000428 | 02 | Aaron | CSA | NA | 131242 | WST02 | NA | C | NA | CES REPLY SHEET S428 | 131242-WST02-NA-NA | 2024-10-22 | ST608 – SSN Shelters Details | Rev.2: Not Approved. No updated drawings were submitted. | 2024-11-12 | 2024-12-18 | 26 | Not Approved | YES | 2025-01-08 | NO | Overdue | 273 |  |  | NA | "ST608 – SSN Shelters Details" | 2024-10-22 | 2024-10-22 | CES REPLY SHEET S428 | 000428 | 2024-10-22 | 02 | 1 | PEN | NAP | NAP
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A | 131242-WST02-DR-1022 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-09 | 2026-02-04 | A.1 | 000000&&000429 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1023 | NA | 131242-WST02-DR-1023 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | 2026-02-04 | C | 000000&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1024 | NA | 131242-WST02-DR-1024 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | 2026-02-04 | A | 000000&&000778 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1025 | NA | 131242-WST02-DR-1025 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1026 | NA | 131242-WST02-DR-1026 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2026-02-04 | NA | 000000 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1027 | NA | 131242-WST02-DR-1027 | 2024-04-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-09 | 2024-06-05 | 18 | Approved with Comments | YES | 2024-06-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | 2026-02-04 | A | 000000&&000860 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A.1 | 131242-WST02-DR-1022 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | 2025-02-26 | Shall update and submit under as built drawing | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-09 | 2026-02-04 | A.1 | 000000&&000429 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5011 | NA | 131242-WST02-DR-5011 | 2024-07-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5012 | NA | 131242-WST02-DR-5012 | 2024-07-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5013 | NA | 131242-WST02-DR-5013 | 2024-07-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5014 | NA | 131242-WST02-DR-5014 | 2024-07-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5015 | NA | 131242-WST02-DR-5015 | 2024-07-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-30 | 2024-08-29 | 21 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-10 | 2024-10-05 | NA | 000000 | 2024-07-10, 2024-10-05 | 00 | 2 | PEN | AWC | AWC
000430 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 0 | 131242-WSW41-SH-1002 | 2024-04-11 | Piping Special Item List | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-06-13 | 23 | For Information | YES | 2024-07-04 | YES | Resubmitted |  |  |  | NA | "Piping Special Item List" | 2024-04-11 | 2024-08-01 | 1 | 000430 | 2024-04-11, 2024-08-01 | 00, 01 | 2 | PEN | INF | INF
000430 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 1 | 131242-WSW41-SH-1002 | 2024-08-01 | Piping Special Item List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-08-22 | 2024-09-02 | 7 | For Information | YES | 2024-09-20 | NO | Overdue | 349 | 2025-03-31 | Piping Special Item List is "For Information", will update after design is freezed. | NA | "Piping Special Item List" | 2024-04-11 | 2024-08-01 | 1 | 000430 | 2024-04-11, 2024-08-01 | 00, 01 | 2 | PEN | INF | INF
000431 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0028 | 0 | 131242-WSW41-LT-0028 | 2024-04-12 | CV OF TEAM MEMBER (WSHO) | Not Approved. The proposed candidate doesn’t fully meet the requirement of 5 years’ experience as WSHO. Therefore, proposed candidate is disapproved. | 2024-05-13 | 2024-06-06 | 17 | Not Approved | YES | 2024-06-27 | NO | Overdue | 409 |  |  | NA | "CV OF TEAM MEMBER (WSHO)" | 2024-04-12 | 2024-04-12 | 0 | 000431 | 2024-04-12 | 00 | 1 | PEN | NAP | NAP
000432 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0002 | 0 | 131242-WSD11-BQ-0002 | 2024-04-12 | THP Valve List | Rev 0: For Information | 2024-05-13 | 2024-07-26 | 52 | For Information | NO |  | YES |  |  |  |  | NA | "THP Valve List" | 2024-04-12 | 2024-04-12 | 0 | 000432 | 2024-04-12 | 00 | 1 | PEN | INF | INF
000433 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-0007 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | PEN | NAP | NAP
000434 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0008 | 0 | 131242-WSW41-SP-0008 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024" | 2024-04-12 | 2024-04-12 | 0 | 000434 | 2024-04-12 | 00 | 1 | PEN | NAP | NAP
000435 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0026 | 0 | 131242-WSW41-LT-0026 | 2024-04-13 | Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project) | For Information | 2024-05-13 | 2024-05-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project)" | 2024-04-13 | 2024-04-13 | 0 | 000435 | 2024-04-13 | 00 | 1 | PEN | INF | INF
000436 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 0 | 131242-WST02-VI-0008 | 2024-04-15 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-14 | 2024-05-23 | 6 | Approved with Comments | YES | 2024-06-12 | YES | Resubmitted |  | TBA |  | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | PEN | AWC | AWC
000436 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 1 | 131242-WST02-VI-0008 | 2024-11-28 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 1: Approved with comments. No need resubmission. Refer attached file for comments. | 2024-12-18 | 2025-03-25 | 65 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | PEN | AWC | AWC
000437 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 11 | A.1 | 131242-WSW41-RT-11 | 2024-04-16 | C4B Monthly Progress Report Number No.11 (03 24) | Rejected as per CES request | 2024-05-15 | 2024-04-17 |  | Rejected | YES | 2024-05-08 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-04-16 | 2024-06-11 | 1 | 000437 | 2024-04-16, 2024-04-18, 2024-06-11 | 00, 01, 02 | 3 | PEN | REJ | REJ
000437 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 11 | 0 | 131242-WSW41-RT-11 | 2024-04-18 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-05-09 | 2024-05-13 | 2 | Approved with Comments | YES | 2024-06-03 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-04-16 | 2024-06-11 | 1 | 000437 | 2024-04-16, 2024-04-18, 2024-06-11 | 00, 01, 02 | 3 | PEN | AWC | AWC
000437 | 02 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 11 | 1 | 131242-WSW41-RT-11 | 2024-06-11 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 2 - Approved | 2024-07-02 | 2024-06-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-04-16 | 2024-06-11 | 1 | 000437 | 2024-04-16, 2024-04-18, 2024-06-11 | 00, 01, 02 | 3 | PEN | APP | APP
000438 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 0 | 131242-WST02-VI-0007 | 2024-04-16 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-05-23 | 5 | Not Approved | YES | 2024-06-12 | YES | Resubmitted |  |  |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | NAP | NAP
000438 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 1 | 131242-WST02-VI-0007 | 2024-07-28 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-16 | 2024-09-18 | 23 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  |  |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | NAP | NAP
000438 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 2 | 131242-WST02-VI-0007 | 2024-10-18 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 17 | Approved with Comments | YES | 2024-12-23 | YES | Resubmitted |  | 2025-02-21 |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | AWC | AWC
000438 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 3 | 131242-WST02-VI-0007 | 2025-02-27 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 31 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | AWC | AWC
000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | A | 131242-WST02-DR-3150 | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | 3 | Not Approved | YES | 2024-06-10 | YES | Resubmitted |  |  |  | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3151 | NA | 131242-WST02-DR-3151 | 2024-04-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-15 | 2024-05-20 | 3 | Not Approved | YES | 2024-06-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-16 | 2024-12-11 | NA | 000000 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 4 | PEN | NAP | NAP
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | C | 131242-WST02-DR-3150 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3151 | NA | 131242-WST02-DR-3151 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-16 | 2024-12-11 | NA | 000000 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3152 | NA | 131242-WST02-DR-3152 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3153 | NA | 131242-WST02-DR-3153 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3154 | NA | 131242-WST02-DR-3154 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3155 | NA | 131242-WST02-DR-3155 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3156 | NA | 131242-WST02-DR-3156 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3157 | NA | 131242-WST02-DR-3157 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3158 | NA | 131242-WST02-DR-3158 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3159 | NA | 131242-WST02-DR-3159 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7010 | NA | 131242-WST02-DR-7010 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7011 | NA | 131242-WST02-DR-7011 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-09-10 | 27 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | AWC | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | D | 131242-WST02-DR-3150 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  |  |  | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3151 | NA | 131242-WST02-DR-3151 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-16 | 2024-12-11 | NA | 000000 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3152 | NA | 131242-WST02-DR-3152 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3153 | NA | 131242-WST02-DR-3153 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3154 | NA | 131242-WST02-DR-3154 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3155 | NA | 131242-WST02-DR-3155 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3156 | NA | 131242-WST02-DR-3156 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3157 | NA | 131242-WST02-DR-3157 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3158 | NA | 131242-WST02-DR-3158 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3159 | NA | 131242-WST02-DR-3159 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7010 | NA | 131242-WST02-DR-7010 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7011 | NA | 131242-WST02-DR-7011 | 2024-10-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-06 | 2024-11-07 | 1 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | AWC | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | E | 131242-WST02-DR-3150 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 |  |  | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3151 | NA | 131242-WST02-DR-3151 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-16 | 2024-12-11 | NA | 000000 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3152 | NA | 131242-WST02-DR-3152 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3153 | NA | 131242-WST02-DR-3153 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3154 | NA | 131242-WST02-DR-3154 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3155 | NA | 131242-WST02-DR-3155 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3156 | NA | 131242-WST02-DR-3156 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3157 | NA | 131242-WST02-DR-3157 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3158 | NA | 131242-WST02-DR-3158 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 3159 | NA | 131242-WST02-DR-3159 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-12 | 2024-12-11 | NA | 000000 | 2024-07-12, 2024-10-16, 2024-12-11 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7010 | NA | 131242-WST02-DR-7010 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7011 | NA | 131242-WST02-DR-7011 | 2024-12-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-01 | 2025-02-13 | 28 | Approved with Comments | YES | 2025-03-05 | NO | Overdue | 233 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | AWC | AWC
000440 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | 0 | 131242-WST02-DR-7010 | 2024-04-16 | SSN Transformer Marshalling Box Schematic Wiring Diagram | Rev 0: Rejected. Not required to resubmit. Please refer to attached comments sheet. | 2024-05-15 | 2024-05-20 | 3 | Rejected | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | REJ | REJ
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7005 | A | 131242-WST02-DR-7005 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 34 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7006 | NA | 131242-WST02-DR-7006 | 2024-04-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-15 | 2024-07-04 | 34 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7007 | NA | 131242-WST02-DR-7007 | 2024-04-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-15 | 2024-07-04 | 34 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | NAP | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7007 | B | 131242-WST02-DR-7007 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 |  | Pending from MP | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7008 | NA | 131242-WST02-DR-7008 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7009 | NA | 131242-WST02-DR-7009 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7010 | NA | 131242-WST02-DR-7010 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7011 | NA | 131242-WST02-DR-7011 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7012 | NA | 131242-WST02-DR-7012 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-20 | 2026-02-03 | NA | 000000 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 7013 | NA | 131242-WST02-DR-7013 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-17 | 28 | Not Approved | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-20 | 2026-02-03 | NA | 000000 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000442 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0038 | 0 | 131242-WSW41-CD-0038 | 2024-04-17 | Milestone 1.2 - SSN Overall Changes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-16 | 2024-07-05 | 34 | Approved with Comments | YES | 2024-07-25 | NO | Overdue | 389 |  |  | NA | "Milestone 1.2 - SSN Overall Changes" | 2024-04-17 | 2024-04-17 | 0 | 000442 | 2024-04-17 | 00 | 1 | PEN | AWC | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-0001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | 2024-04-26 | A | 000000&&000443 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | NA | 131242-WST02-DR-0002_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | NA | 131242-WST02-DR-0003_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | NA | 131242-WST02-DR-1006_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | NA | 131242-WST02-DR-1007_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | NA | 131242-WST02-DR-1008_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | NA | 131242-WST02-DR-3000_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | NA | 131242-WST02-DR-5001_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | NA | 131242-WST02-DR-5002_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | NA | 131242-WST02-DR-7000_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | NA | 131242-WST02-DR-7001_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | NA | 131242-WST02-DR-7002_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-8002_ST606_BCA | 2024-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-16 | 2024-05-13 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-04-26 | A | 000000&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | INF | INF
000444 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0009 | 0 | 131242-WSW41-SP-0009 | 2024-04-17 | Reinforcement Bar delivery & Testing Summary -February 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-02 |  | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "Reinforcement Bar delivery & Testing Summary -February 2024" | 2024-04-17 | 2024-04-17 | 0 | 000444 | 2024-04-17 | 00 | 1 | PEN | AWC | AWC
000445 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-0001 | 2024-04-17 | Sidewide Piperack Line List | Rev 0: Not approved - Revise and Resubmit | 2024-05-16 | 2024-07-26 | 49 | Not Approved | YES | 2024-08-16 | NO | Overdue | 374 |  |  | NA | "Line List for Hydrotest (Sitewide PipeRack)" && "Sidewide Piperack Line List" | 2024-04-17 | 2025-10-16 | 0 | 000445&&001749 | 2024-04-17, 2025-10-16 | 00 | 2 | PEN | NAP | NAP
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000 | 0 | 131242-WSD11-DR-1000 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 |  | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1001 | NA | 131242-WSD11-DR-1001 | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-13 |  | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | CL | S | 0005 | NA | 131242-WSD11-CL-0005 | 2024-04-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-20 | 2024-05-13 |  | Not Approved | YES | 2024-06-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-11-22 | 0 | 000000&&000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | PEN | NAP | NAP
000446 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 1 | 131242-WSD11-CL-0005 | 2024-05-31 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-10 |  | Not Approved | YES | 2024-07-01 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-11-22 | 0 | 000000&&000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | PEN | NAP | NAP
000446 | 02 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 5 | 131242-WSD11-CL-0005 | 2024-07-16 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-05 | 2024-08-16 | 8 | Not Approved | YES | 2024-09-05 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-11-22 | 0 | 000000&&000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | PEN | NAP | NAP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 7 | 131242-WSD11-CL-0005 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-11-22 | 0 | 000000&&000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1400 | NA | 131242-WSD11-DR-1400 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | B | 000000&&000446 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 04 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1401 | NA | 131242-WSD11-DR-1401 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1402 | NA | 131242-WSD11-DR-1402 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1403 | NA | 131242-WSD11-DR-1403 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2400 | NA | 131242-WSD11-DR-2400 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2024-10-07 | NA | 000000 | 2024-08-28, 2024-10-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5400 | NA | 131242-WSD11-DR-5400 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2024-10-07 | NA | 000000 | 2024-08-28, 2024-10-07 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 8003 | NA | 131242-WSD11-DR-8003 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-22 | 3 | Approved with Comments | YES | 2024-10-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2024-08-28 | NA | 000000 | 2024-08-28 | 00 | 1 | PEN | AWC | AWC
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1400 | B | 131242-WSD11-DR-1400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | B | 000000&&000446 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 04 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1401 | NA | 131242-WSD11-DR-1401 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1402 | NA | 131242-WSD11-DR-1402 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 1403 | NA | 131242-WSD11-DR-1403 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 2400 | NA | 131242-WSD11-DR-2400 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2024-10-07 | NA | 000000 | 2024-08-28, 2024-10-07 | 00 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | S | 5400 | NA | 131242-WSD11-DR-5400 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2024-10-07 | NA | 000000 | 2024-08-28, 2024-10-07 | 00 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 8003 | NA | 131242-WST00-DR-8003 | 2024-10-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-25 | 2024-10-29 | 2 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-07 | 2024-10-07 | NA | 000000 | 2024-10-07 | 00 | 1 | PEN | APP | APP
000447 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0011 | 0 | 131242-WSW41-SP-0011 | 2024-04-22 | Reinforcement Bar Test Reports -Rebar Size (H10 &H16) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-05-21 | 2024-05-02 |  | Approved with Comments | YES | 2024-05-23 | NO | Overdue | 433 |  |  | NA | "Reinforcement Bar Test Reports -Rebar Size (H10 &H16)" | 2024-04-22 | 2024-04-22 | 0 | 000447 | 2024-04-22 | 00 | 1 | PEN | AWC | AWC
000448 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 0 | 131242-WSW41-MS-0009 | 2024-04-24 | MSRA,SWP for Bored Piling WLT | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-24 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "MSRA,SWP for Bored Piling WLT" | 2024-04-24 | 2024-05-10 | 1 | 000448 | 2024-04-24, 2024-05-10 | 00, 01 | 2 | PEN | NAP | NAP
000448 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 1 | 131242-WSW41-MS-0009 | 2024-05-10 | MSRA,SWP for Bored Piling WLT | Rev.1: Approved | 2024-05-31 | 2024-05-20 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA,SWP for Bored Piling WLT" | 2024-04-24 | 2024-05-10 | 1 | 000448 | 2024-04-24, 2024-05-10 | 00, 01 | 2 | PEN | APP | APP
000449 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | VI | S | 0003 | 0 | 131242-WSW41-VI-0003 | 2024-04-25 | Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd) | Approved | 2024-05-27 | 2024-05-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | APP | APP
000450 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0004 | 0 | 131242-WSW41-VI-0004 | 2024-04-25 | Vendor Approval of ERSS Works (Singlee) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-02 |  | Not Approved | YES | 2024-05-23 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | PEN | NAP | NAP
000450 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | G | 0002 | 0 | 131242-WSW41-VI-0002 | 2024-07-09 | Vendor Approval of ERSS Works (Singlee) | Rev.1: Not Approved. Submission incomplete, proposed vendor is different in R0 and R1. Please resubmit with comment respond sheet. | 2024-07-29 | 2024-07-17 |  | Not Approved | YES | 2024-08-06 | NO | Overdue | 381 |  |  | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | NAP | NAP
000451 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0010 | 0 | 131242-WSW41-PC-0010 | 2024-04-25 | Payment Claim No.10 | Rev(0): Approved. Please refer to S.O. correspondence no. 15 dated 7 May 2024. | 2024-05-27 | 2024-05-13 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.10" | 2024-04-25 | 2024-04-25 | 0 | 000451 | 2024-04-25 | 00 | 1 | PEN | APP | APP
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-8002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-04-26 | A | 000000&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-0001_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | 2024-04-26 | A | 000000&&000443 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | NA | 131242-WST02-DR-0002_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | NA | 131242-WST02-DR-0003_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | NA | 131242-WST02-DR-5001_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | NA | 131242-WST02-DR-5002_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | NA | 131242-WST02-DR-1006_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | NA | 131242-WST02-DR-1007_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | NA | 131242-WST02-DR-1008_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | NA | 131242-WST02-DR-7000_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | NA | 131242-WST02-DR-7001_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | NA | 131242-WST02-DR-7002_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | NA | 131242-WST02-DR-3000_ST606_BCA | 2024-04-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-28 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-17 | 2024-04-26 | NA | 000000 | 2024-04-17, 2024-04-26 | 00 | 2 | PEN | AWC | AWC
000453 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0011 | 0 | 131242-WSW41-PS-0011 | 2024-04-26 | Monthly Progress Presentation No. 11 (0324) | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-09 | 2024-08-22 | 0 | 000000&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | PEN | INF | INF
000454 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0011 | 0 | 131242-WSW41-MI-0011 | 2024-04-26 | Monthly Progress Meeting Minutes 0011_20240423 | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | PEN | INF | INF
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | B | 131242-WST02-DR-8001_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 |  | To close after addressing the comments of S#475 & S#128.3. | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " && "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-07 | 0 | 000455&&000466 | 2024-04-30, 2024-05-07 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610_BCA | NA | 131242-WST02-DR-1023_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610_BCA | NA | 131242-WST02-DR-1024_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610_BCA | NA | 131242-WST02-DR-3000_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610_BCA | NA | 131242-WST02-DR-3001_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610_BCA | NA | 131242-WST02-DR-5004_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610_BCA | NA | 131242-WST02-DR-5005_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610_BCA | NA | 131242-WST02-DR-5006_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610_BCA | NA | 131242-WST02-DR-5007_ST610_BCA | 2024-04-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-05-30 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | NO | Overdue | 421 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-30 | 2024-04-30 | NA | 000000 | 2024-04-30 | 00 | 1 | PEN | NAP | NAP
000456 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 0 | 131242-WSW41-QA-0002 | 2024-04-30 | Inspection and test plan for Compressed Air System | Rev 0: Not approved - Revise and Resubmit | 2024-05-30 | 2024-07-15 | 31 | Not Approved | YES | 2024-08-02 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000456 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 1 | 131242-WSW41-QA-0002 | 2024-07-22 | Inspection and test plan for Compressed Air System | Rev 1: Approved | 2024-08-12 | 2024-08-20 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000457 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0008 | 0 | 131242-WSW41-PS-0008 | 2024-04-30 | Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024 | For Information | 2024-05-30 | 2024-06-06 | 5 | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 08 (1223)" && "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | 2024-01-24 | 2024-04-30 | 0 | 000286&&000457 | 2024-01-24, 2024-04-30 | 00 | 2 | PEN | INF | INF
000458 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 0 | 131242-WST02-DS-0007 | 2024-04-30 | SSN Transformer Data Sheet | Rev 0: Approved with comments. To revise and resubmit.Please refer to attached file for comments. | 2024-05-30 | 2024-05-20 |  | Approved with Comments | YES | 2024-06-10 | YES | Resubmitted |  |  |  | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | PEN | AWC | AWC
000458 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 1 | 131242-WST02-DS-0007 | 2024-07-09 | SSN Transformer Data Sheet | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-29 | 2024-09-10 | 30 | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | PEN | AWC | AWC
000458 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 2 | 131242-WST02-DS-0007 | 2024-10-15 | SSN Transformer Data Sheet | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-05 | 2024-11-04 |  | Approved with Comments | YES | 2024-11-22 | NO | Overdue | 305 |  |  | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | PEN | AWC | AWC
000459 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0009 | 0 | 131242-WST02-VI-0009 | 2024-05-02 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-31 | 2024-07-02 | 21 | Approved with Comments | YES | 2024-07-22 | YES | Resubmitted |  | 2024-07-26 |  | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | PEN | AWC | AWC
000459 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 1 | 131242-WST02-VI-0009 | 2024-07-30 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-18 | 21 | Approved with Comments | YES | 2024-10-08 | YES | Resubmitted |  | 2025-02-24 |  | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | PEN | AWC | AWC
000459 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 2 | 131242-WST02-VI-0009 | 2025-02-27 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 16 | Approved with Comments | NO |  | YES |  |  | 2025-02-24 |  | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | PEN | AWC | AWC
000460 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0021 | 0 | 131242-WSW41-MI-0021 | 2024-05-02 | Process & MEICA Meeting Minutes 0021_20240328 | For information | 2024-05-31 | 2024-07-26 | 39 | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Meeting Minutes 0021_20250226" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | 2025-04-21 | 0 | 000000&&000460&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1000 | 0 | 131242-WST02-DR-1000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | 2025-02-28 | 2nd priority | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4000 | NA | 131242-WST02-DR-4000 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-31 | NA | 000000 | 2024-05-06, 2025-04-22, 2025-10-31 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4001 | NA | 131242-WST02-DR-4001 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-04-28 | NA | 000000 | 2024-05-06, 2025-04-28 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4002 | NA | 131242-WST02-DR-4002 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-10-27 | NA | 000000 | 2024-05-06, 2025-04-09, 2025-10-27 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4003 | NA | 131242-WST02-DR-4003 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-06 | 2024-05-06 | NA | 000000 | 2024-05-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 4004 | NA | 131242-WST02-DR-4004 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-06 | 2025-05-15 | NA | 000000 | 2024-05-06, 2025-05-15 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7000 | NA | 131242-WST02-DR-7000 | 2024-05-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-04 | 2024-07-26 | 37 | Approved with Comments | YES | 2024-08-16 | NO | Overdue | 374 | Tenwit in Progress |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000462 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 0 | 131242-WST02-VI-0010 | 2024-05-07 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 18 | Approved with Comments | YES | 2024-07-22 | YES | Resubmitted |  | 2024-07-26 |  | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000462 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 1 | 131242-WST02-VI-0010 | 2024-08-01 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 19 | Approved with Comments | YES | 2024-10-08 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000462 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 2 | 131242-WST02-VI-0010 | 2025-02-27 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 16 | Approved with Comments | NO |  | YES |  |  | 2025-02-21 |  | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000463 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 0 | 131242-WST02-VI-0011 | 2024-05-07 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 18 | Not Approved | YES | 2024-07-22 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | PEN | NAP | NAP
000463 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 1 | 131242-WST02-VI-0011 | 2024-07-24 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-18 | 25 | Approved with Comments | YES | 2024-10-08 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000463 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 2 | 131242-WST02-VI-0011 | 2024-11-09 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000464 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 0 | 131242-WST02-VI-0012 | 2024-05-07 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 18 | Not Approved | YES | 2024-07-22 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | PEN | NAP | NAP
000464 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 1 | 131242-WST02-VI-0012 | 2024-08-01 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 19 | Approved with Comments | YES | 2024-10-08 | YES | Resubmitted |  |  |  | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000464 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 2 | 131242-WST02-VI-0012 | 2024-11-08 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000465 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 0 | 131242-WSW41-MS-0010 | 2024-05-07 | MSRA,SWP for Bored Piling PDA Test | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-06-12 | 5 | Approved with Comments | YES | 2024-07-03 | YES | Resubmitted |  |  |  | NA | "MSRA,SWP for Bored Piling PDA Test" | 2024-05-07 | 2024-06-19 | 1 | 000465 | 2024-05-07, 2024-06-19 | 00, 01 | 2 | PEN | AWC | AWC
000465 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 1 | 131242-WSW41-MS-0010 | 2024-06-19 | MSRA,SWP for Bored Piling PDA Test | Approved | 2024-07-09 | 2024-07-01 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA,SWP for Bored Piling PDA Test" | 2024-05-07 | 2024-06-19 | 1 | 000465 | 2024-05-07, 2024-06-19 | 00, 01 | 2 | PEN | APP | APP
000466 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | 0 | 131242-WST02-DR-8001_ST610_BCA | 2024-05-07 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-05-20 |  | Not Approved | YES | 2024-06-10 | YES | Resubmitted |  |  |  | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " && "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-07 | 0 | 000455&&000466 | 2024-04-30, 2024-05-07 | 00 | 2 | PEN | NAP | NAP
000466 | 01 | Aaron | CSA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 |  | Not Approved | YES | 2024-07-19 | NO | Overdue | 393 |  | To close after addressing the comments of S#475, S#128.3 | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | 2024-06-12 | 2024-06-12 | NA | 000466 | 2024-06-12 | 01 | 1 | PEN | NAP | NAP
000467 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0039 | 0 | 131242-WSW41-CD-0039 | 2024-05-08 | Submission Of BIM Coordination VCM Model (Apr-2024) | For Information | 2024-06-06 | 2024-05-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Apr-2024)" | 2024-05-08 | 2024-05-08 | 0 | 000467 | 2024-05-08 | 00 | 1 | PEN | INF | INF
000468 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 0 | 131242-WST02-RT-0001 | 2024-05-09 | Design for Safety Report 2 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-06 |  | Not Approved | YES | 2024-06-27 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | NAP | NAP
000468 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 1 | 131242-WST02-RT-0001 | 2024-06-07 | Design for Safety Report 2 | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-05 | 5 | Not Approved | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | NAP | NAP
000468 | 02 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-0001 | 2024-08-21 | Design for Safety Report 2 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-17 | 5 | Approved with Comments | YES | 2024-10-07 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000468 | 03 | Leslie | Project | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-0001 | 2024-11-03 | Design for Safety Report 2 | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000469 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | C | 0005 | 0 | 131242-WSW41-CL-0005 | 2024-05-10 | Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47) | Rev.0: Approved | 2024-06-10 | 2024-05-20 |  | Approved | NO |  | YES |  |  |  |  | NA | "Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47)" | 2024-05-10 | 2024-05-10 | 0 | 000469 | 2024-05-10 | 00 | 1 | PEN | APP | APP
000470 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0022 | 0 | 131242-WSW41-MI-0022 | 2024-05-13 | Process & MEICA Meeting Minutes 0022_20240425 | Rev 0: For Information | 2024-06-11 | 2024-08-14 | 44 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | 2025-04-21 | 0 | 000000&&000470&&000472&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000471 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-1000 | 2024-05-13 | NEA Waiver Submission of SSN Plant | For Information | 2024-06-11 | 2024-05-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | INF | INF
000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0022 | 0 | 131242-WSW41-MI-0022 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | 2025-04-21 | 0 | 000000&&000470&&000472&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0023 | NA | 131242-WSW41-MI-0023 | 2024-05-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | 2024-08-29 | 0 | 000000&&000477 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | PEN | INF | INF
000473 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 0 | 131242-WSW41-RT-0012 | 2024-04-18 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-05-17 | 2024-06-03 | 10 | Approved with Comments | YES | 2024-06-24 | YES | Resubmitted |  |  |  | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | PEN | AWC | AWC
000473 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 1 | 131242-WSW41-RT-0012 | 2024-06-11 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 1 - Approved | 2024-07-02 | 2024-06-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | PEN | APP | APP
000474 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 0 | 131242-WSW41-VI-1010 | 2024-05-18 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 0: Not approved - Revise and Resubmit | 2024-06-18 | 2024-07-04 | 12 | Not Approved | YES | 2024-07-24 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | PEN | NAP | NAP
000474 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 1 | 131242-WSW41-VI-1010 | 2024-09-06 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 1: Not approved - Revise and Resubmit | 2024-09-26 | 2024-09-12 |  | Not Approved | YES | 2024-10-02 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | PEN | NAP | NAP
000474 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 2 | 131242-WSW41-VI-1010 | 2024-10-17 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-07 | 2024-11-15 | 6 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-8001_ST610 | 2024-05-18 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610 | NA | 131242-WST02-DR-3001_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-29 | 2024-07-11 | NA | 000000 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-18 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000475 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-8001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610 | NA | 131242-WST02-DR-3001_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-29 | 2024-07-11 | NA | 000000 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2024-06-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-28 | 2024-07-01 | 1 | Not Approved | YES | 2024-07-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | NAP | NAP
000475 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | D | 131242-WST00-DR-8001_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  |  |  | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1023_ST610 | NA | 131242-WST02-DR-1023_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 1024_ST610 | NA | 131242-WST02-DR-1024_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5004_ST610 | NA | 131242-WST02-DR-5004_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5005_ST610 | NA | 131242-WST02-DR-5005_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5006_ST610 | NA | 131242-WST02-DR-5006_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3000_ST610 | NA | 131242-WST02-DR-3000_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 3001_ST610 | NA | 131242-WST02-DR-3001_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-29 | 2024-07-11 | NA | 000000 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | C | 5007_ST610 | NA | 131242-WST02-DR-5007_ST610 | 2024-07-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-08-21 | 14 | Approved with Comments | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-16 | 2024-07-11 | NA | 000000 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00 | 6 | PEN | AWC | AWC
000475 | 03 | Zora | CSA | NA | 131242 | WST02 | NA | C | Cmt Sheet Reply 2024 10 07 | NA | 131242-WST02-NA-Cmt Sheet Reply 2024 10 07 | 2024-10-09 | IFC of ST610 (Underground Services) | Rev.3: Approved with comments. | 2024-10-29 | 2024-10-24 |  | Approved with Comments | YES | 2024-11-14 | NO | Overdue | 311 |  |  | NA | "IFC of ST610 (Underground Services) " | 2024-10-09 | 2024-10-09 | NA | 000475 | 2024-10-09 | 03 | 1 | PEN | AWC | AWC
000476 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 0 | 131242-WST02-VI-0016 | 2024-05-21 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-20 | 2024-07-02 | 8 | Approved with Comments | YES | 2024-07-22 | YES | Resubmitted |  | 2025-02-20 |  | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | PEN | AWC | AWC
000476 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 1 | 131242-WST02-VI-0016 | 2025-03-17 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 20 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | PEN | AWC | AWC
000477 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0023 | 0 | 131242-WSW41-MI-0023 | 2024-05-23 | Process & MEICA Meeting Minutes 0023_20240509 | Rev 0: For Information | 2024-06-21 | 2024-08-14 | 37 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | 2024-08-29 | 0 | 000000&&000477 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | PEN | INF | INF
000478 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CN | S | 0001 | 0 | 131242-WSD11-CN-0001 | 2024-05-23 | Handrail design loading & Testing of THP Train by CAMBI | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 |  | Resubmission on hold and to resubmit after BCA approval of CAMBI Steel Structure | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | PEN | NAP | NAP
000479 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0001 | 0 | 131242-WSD11-CN-0001 | 2024-05-23 | Proposed change of SS316 Cable Tray within THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-18 |  | Rejected | NO |  | YES |  |  |  |  | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | PEN | REJ | REJ
000480 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0002 | 0 | 131242-WSD11-CN-0002 | 2024-05-23 | Proposed change of Carbon loaded GRP Junction Box within THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 9 | Rejected | NO |  | YES |  |  |  |  | NA | "Pressure Instrument Mounting in THP Module" && "Proposed change of Carbon loaded GRP Junction Box within THP Module" | 2024-05-23 | 2024-05-23 | 0 | 000480&&000483 | 2024-05-23 | 00 | 2 | PEN | REJ | REJ
000481 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0003 | 0 | 131242-WSD11-CN-0003 | 2024-05-23 | Separate Terminal Box for Motor Space Heater | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Separate Terminal Box for Motor Space Heater" | 2024-05-23 | 2024-05-23 | 0 | 000481 | 2024-05-23 | 00 | 1 | PEN | REJ | REJ
000482 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0004 | 0 | 131242-WSD11-CN-0004 | 2024-05-23 | Local Control Station with THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Local Control Station with THP Module" | 2024-05-23 | 2024-05-23 | 0 | 000482 | 2024-05-23 | 00 | 1 | PEN | REJ | REJ
000483 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | I | 0002 | 0 | 131242-WSD11-CN-0002 | 2024-05-23 | Pressure Instrument Mounting in THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 9 | Rejected | NO |  | YES |  |  |  |  | NA | "Pressure Instrument Mounting in THP Module" && "Proposed change of Carbon loaded GRP Junction Box within THP Module" | 2024-05-23 | 2024-05-23 | 0 | 000480&&000483 | 2024-05-23 | 00 | 2 | PEN | REJ | REJ
000484 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | M | 0001 | 0 | 131242-WSD11-CN-0001 | 2024-05-23 | Pump Color within THP Module | Rev 0: Rejected Refer to attached file for comments. | 2024-06-21 | 2024-08-08 | 34 | Rejected | NO |  | YES |  |  |  |  | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | PEN | REJ | REJ
000485 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0020 | 0 | 131242-WSW41-VI-0020 | 2024-05-23 | Vendor Approval of Electrical Installer (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-21 | 2024-07-04 | 9 | Approved with Comments | YES | 2024-07-24 | NO | Overdue | 390 |  |  | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | PEN | AWC | AWC
000486 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | I | 0020 | 0 | 131242-WSW41-VI-0020 | 2024-05-23 | Vendor Approval of ICA Installer Submission (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-21 | 2024-07-02 | 7 | Approved with Comments | YES | 2024-07-22 | NO | Overdue | 392 |  |  | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | PEN | AWC | AWC
000487 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | K | 0001 | 0 | 131242-WSW41-MS-0001 | 2024-05-27 | MSRA & SWP for Mobilization and Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 |  | Approved with Comments | YES | 2024-07-01 | NO | Overdue | 407 |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | AWC | AWC
000488 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0001 | 0 | 131242-WSW41-MS-0001 | 2024-05-27 | MSRA & SWP for Sheet Piling Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 |  | Not Approved | YES | 2024-07-01 | NO | Overdue | 407 |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | NAP | NAP
000489 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0002 | 0 | 131242-WST02-RT-0002 | 2024-05-28 | Project Safety Review for ERSS | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-18 |  | Approved with Comments | YES | 2024-07-08 | YES | Resubmitted |  |  |  | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | PEN | AWC | AWC
000489 | 01 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0002 | 1 | 131242-WST02-RT-0002 | 2024-07-09 | Project Safety Review for ERSS | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-29 | 2024-08-12 | 9 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 |  |  | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | PEN | AWC | AWC
000490 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 0 | 131242-WST02-RT-0003 | 2024-05-28 | Report of DFS (Guide 3) for ERSS | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-13 |  | Not Approved | YES | 2024-07-04 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | 2025-07-01 | 2 | 000000&&000490&&000752 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | PEN | NAP | NAP
000490 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 1 | 131242-WST02-RT-0003 | 2024-06-19 | Report of DFS (Guide 3) for ERSS | Rev.1: Approved | 2024-07-09 | 2024-07-12 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | 2025-07-01 | 2 | 000000&&000490&&000752 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | PEN | APP | APP
000491 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0030 | 0 | 131242-WSW41-LT-0030 | 2024-05-28 | CV of Team member (Planner) | Rev. 0 - Approved with comments. Please refer to attached comment sheet | 2024-06-26 | 2024-06-10 |  | Approved with Comments | YES | 2024-07-01 | NO | Overdue | 407 |  |  | NA | "CV of Team member (Planner)" | 2024-05-28 | 2024-05-28 | 0 | 000491 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | A | 131242-WST02-DR-5000 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5001 | NA | 131242-WST02-DR-5001 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5002 | NA | 131242-WST02-DR-5002 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5003 | NA | 131242-WST02-DR-5003 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5004 | NA | 131242-WST02-DR-5004 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5005 | NA | 131242-WST02-DR-5005 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5006 | NA | 131242-WST02-DR-5006 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Fire Seal Detail" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | A | 000000&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5007 | NA | 131242-WST02-DR-5007 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5008 | NA | 131242-WST02-DR-5008 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7001 | NA | 131242-WST02-SH-7001 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7002 | NA | 131242-WST02-SH-7002 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7003 | NA | 131242-WST02-SH-7003 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7004 | NA | 131242-WST02-SH-7004 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7005 | NA | 131242-WST02-SH-7005 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7006 | NA | 131242-WST02-SH-7006 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7007 | NA | 131242-WST02-SH-7007 | 2024-05-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-06-26 | 2024-08-08 | 31 | Approved with Comments | YES | 2024-08-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2024-05-28 | NA | 000000 | 2024-05-28 | 00 | 1 | PEN | AWC | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | B | 131242-WST02-DR-5000 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  | 2025-02-24 |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5001 | NA | 131242-WST02-DR-5001 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5002 | NA | 131242-WST02-DR-5002 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5003 | NA | 131242-WST02-DR-5003 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5004 | NA | 131242-WST02-DR-5004 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5005 | NA | 131242-WST02-DR-5005 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5006 | NA | 131242-WST02-DR-5006 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Fire Seal Detail" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | A | 000000&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5007 | NA | 131242-WST02-DR-5007 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5008 | NA | 131242-WST02-DR-5008 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7001 | NA | 131242-WST02-DR-7001 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7002 | NA | 131242-WST02-DR-7002 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7003 | NA | 131242-WST02-DR-7003 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7004 | NA | 131242-WST02-DR-7004 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7005 | NA | 131242-WST02-DR-7005 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7006 | NA | 131242-WST02-DR-7006 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7007 | NA | 131242-WST02-DR-7007 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-12-05 | 18 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | AWC | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | C.1 | 131242-WST02-DR-5000 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | 2025-02-24 |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5001 | NA | 131242-WST02-DR-5001 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5002 | NA | 131242-WST02-DR-5002 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5003 | NA | 131242-WST02-DR-5003 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5004 | NA | 131242-WST02-DR-5004 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5005 | NA | 131242-WST02-DR-5005 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5006 | NA | 131242-WST02-DR-5006 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Fire Seal Detail" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | A | 000000&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5007 | NA | 131242-WST02-DR-5007 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5008 | NA | 131242-WST02-DR-5008 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7001 | NA | 131242-WST02-DR-7001 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7002 | NA | 131242-WST02-DR-7002 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7003 | NA | 131242-WST02-DR-7003 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7004 | NA | 131242-WST02-DR-7004 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7005 | NA | 131242-WST02-DR-7005 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7006 | NA | 131242-WST02-DR-7006 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 7007 | NA | 131242-WST02-DR-7007 | 2025-02-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-28 | 27 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | AWC | AWC
000493 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0015 | 0 | 131242-WSW41-VI-0015 | 2024-05-29 | Vendor Approval of Testing Laboratory (TUV) | Approved | 2024-06-27 | 2024-06-03 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Distribution Boards (GSM)" && "Vendor Approval of Testing Laboratory (TUV)" | 2024-05-29 | 2025-10-01 | 1 | 000493&&001437 | 2024-05-29, 2025-07-07, 2025-10-01 | 00, 01 | 3 | PEN | APP | APP
000494 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 0 | 131242-WSW41-MS-0011 | 2024-05-29 | Method Statement for Concrete Temperature Control and Monitoring | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-10 |  | Not Approved | YES | 2024-07-01 | YES | Resubmitted |  |  |  | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | PEN | NAP | NAP
000494 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 1 | 131242-WSW41-MS-0011 | 2024-06-18 | Method Statement for Concrete Temperature Control and Monitoring | Rev.1:Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-08 | 2024-07-25 | 13 | Approved with Comments | YES | 2024-08-15 | YES | Resubmitted |  |  |  | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | PEN | AWC | AWC
000494 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 2 | 131242-WSW41-MS-0011 | 2024-07-28 | Method Statement for Concrete Temperature Control and Monitoring | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2024-08-16 | 2024-08-13 |  | Approved with Comments | YES | 2024-09-02 | NO | Overdue | 363 |  |  | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | PEN | AWC | AWC
000495 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SU | K | 0001 | 0 | 131242-WSW41-SU-0001 | 2024-05-29 | Time Lapse Surveys_Apr 24 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-03 |  | Not Approved | YES | 2024-06-24 | NO | Overdue | 412 |  |  | NA | "Time Lapse Surveys_Apr 24" | 2024-05-29 | 2024-05-29 | 0 | 000495 | 2024-05-29 | 00 | 1 | PEN | NAP | NAP
000496 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0029 | 0 | 131242-WSW41-LT-0029 | 2024-05-30 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24 | Rev(0): Received for S.O.'s assessment. Please refer to S.O. correspondence no. 211 dated 22 Aug 2024. | 2024-06-28 | 2024-08-26 | 40 | For Information | NO |  | YES |  |  |  |  | NA | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24" | 2024-05-30 | 2024-05-30 | 0 | 000496 | 2024-05-30 | 00 | 1 | PEN | INF | INF
000497 | 00 | Low | EICA | NA | 131242 | WSD11 | CN | I | 0001 | 0 | 131242-WSD11-CN-0001 | 2024-05-30 | General Deviation from ICA G & P Spec | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-27 | 41 | Rejected | YES | 2024-09-16 | NO | Overdue | 353 |  | (RFC) NO.: 1230207-RFC-0013 | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | PEN | REJ | REJ
000498 | 00 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0012 | 0 | 131242-WSW41-SP-0012 | 2024-05-30 | Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-06-12 |  | Approved with Comments | YES | 2024-07-03 | NO | Overdue | 405 |  |  | NA | "Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115)" | 2024-05-30 | 2024-05-30 | 0 | 000498 | 2024-05-30 | 00 | 1 | PEN | AWC | AWC
000499 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 0 | 131242-WSD11-VI-0002 | 2024-05-30 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-28 | 2024-07-18 | 14 | Approved with Comments | YES | 2024-08-07 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | PEN | AWC | AWC
000499 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 1 | 131242-WSD11-VI-0002 | 2025-03-14 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 65 | Approved with Comments | YES | 2025-07-28 | NO | Overdue | 130 |  |  | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | PEN | AWC | AWC
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601_BCA | B | 131242-WST00-DR-8000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-05-31 | B | 000500 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0001_ST601_BCA | NA | 131242-WST00-DR-0001_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601_BCA | NA | 131242-WST00-DR-0002_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601_BCA | NA | 131242-WST00-DR-1000_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1001_ST601_BCA | NA | 131242-WST00-DR-1001_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1002_ST601_BCA | NA | 131242-WST00-DR-1002_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1003_ST601_BCA | NA | 131242-WST00-DR-1003_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601_BCA | NA | 131242-WST00-DR-1004_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3000_ST601_BCA | NA | 131242-WST00-DR-3000_ST601_BCA | 2024-05-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-01 | 2024-06-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-31 | 2024-05-31 | NA | 000000 | 2024-05-31 | 00 | 1 | PEN | INF | INF
000501 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 0 | 131242-WST02-VI-0014 | 2024-05-31 | Vendor Approval of SSN Package (Thermal Flow Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 15 | Not Approved | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | PEN | NAP | NAP
000501 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 1 | 131242-WST02-VI-0014 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow Switches) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-05-06 | 65 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | PEN | AWC | AWC
000502 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 0 | 131242-WST02-VI-0015 | 2024-05-31 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 15 | Approved with Comments | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-05-31 | 2024-08-27 | 1 | 000502 | 2024-05-31, 2024-08-27 | 00, 01 | 2 | PEN | AWC | AWC
000502 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 1 | 131242-WST02-VI-0015 | 2024-08-27 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 1: Approved. | 2024-09-16 | 2024-11-08 | 38 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-05-31 | 2024-08-27 | 1 | 000502 | 2024-05-31, 2024-08-27 | 00, 01 | 2 | PEN | APP | APP
000503 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 0 | 131242-WST02-VI-0013 | 2024-06-01 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 15 | Not Approved | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2024-06-01 | 2025-01-08 | 1 | 000503 | 2024-06-01, 2025-01-08 | 00, 01 | 2 | PEN | NAP | NAP
000503 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 1 | 131242-WST02-VI-0013 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-03-17 | 32 | Approved with Comments | YES | 2025-04-04 | NO | Overdue | 211 |  |  | NA | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2024-06-01 | 2025-01-08 | 1 | 000503 | 2024-06-01, 2025-01-08 | 00, 01 | 2 | PEN | AWC | AWC
000504 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 0 | 131242-WSW41-VI-1011 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-01 | 2024-07-18 | 13 | Approved with Comments | YES | 2024-08-07 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-06-01 | 2024-11-02 | 1 | 000504 | 2024-06-01, 2024-11-02 | 00, 01 | 2 | PEN | AWC | AWC
000504 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 1 | 131242-WSW41-VI-1011 | 2024-11-02 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-21 | 2024-12-05 | 10 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-06-01 | 2024-11-02 | 1 | 000504 | 2024-06-01, 2024-11-02 | 00, 01 | 2 | PEN | AWC | AWC
000505 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1012 | 0 | 131242-WSW41-VI-1012 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves) | Rev 0: Not approved - Revise and Resubmit | 2024-07-01 | 2024-08-01 | 23 | Not Approved | YES | 2024-08-22 | NO | Overdue | 370 |  | This document is no longer valid and should be marked as "Voided." | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves)" | 2024-06-01 | 2024-06-01 | 0 | 000505 | 2024-06-01 | 00 | 1 | PEN | NAP | NAP
000506 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0011 | 0 | 131242-WSW41-PC-0011 | 2024-06-03 | Payment Claim No.11 | For Information | 2024-07-02 | 2024-06-27 |  | For Information | NO |  | YES |  |  |  |  | NA | "Payment Claim No.11" | 2024-06-03 | 2024-06-03 | 0 | 000506 | 2024-06-03 | 00 | 1 | PEN | INF | INF
000507 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0010 | 0 | 131242-WST02-CL-0010 | 2024-06-03 | Blower Pressure Loss Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-07-02 | 2024-07-31 | 21 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | PEN | NAP | NAP
000507 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 1 | 131242-WST02-CL-0010 | 2024-10-22 | Blower Pressure Loss Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2024-11-19 | 5 | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  |  |  | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000507 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 2 | 131242-WST02-CL-0010 | 2025-09-10 | Blower Pressure Loss Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. Provide PE endorsement | 2025-09-30 | 2026-02-23 | 102 | Approved with Comments | YES | 2026-03-13 | NO |  |  |  |  | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000508 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0031 | 0 | 131242-WSW41-LT-0031 | 2024-06-04 | Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump] | Refer to S.O. Correspondence No.0194. | 2024-07-03 | 2024-08-16 | 31 | For Information | NO |  | YES |  |  |  |  | NA | "Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump]" | 2024-06-04 | 2024-06-04 | 0 | 000508 | 2024-06-04 | 00 | 1 | PEN | INF | INF
000509 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0012 | 0 | 131242-WSW41-MI-0012 | 2024-06-04 | Monthly Progress Meeting Minutes 0012_20240521 | For Information | 2024-07-03 | 2024-06-04 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "Monthly Progress Meeting Minutes 0012_20240521" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-18 | 2024-06-04 | 0 | 000000&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | PEN | INF | INF
000510 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0012 | 0 | 131242-WSW41-PS-0012 | 2024-06-04 | Monthly Progress Presentation No. 12 (0424) | For Information | 2024-07-03 | 2024-06-04 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for May 2024" && "Monthly Progress Presentation No. 12 (0424)" | 2024-06-04 | 2024-08-22 | 0 | 000510&&000668 | 2024-06-04, 2024-08-22 | 00 | 2 | PEN | INF | INF
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3180 | A | 131242-WST02-DR-3180 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2025-10-08 | A | 000000&&000511 | 2024-06-05, 2025-07-08, 2025-10-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3181 | NA | 131242-WST02-DR-3181 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-10-08 | NA | 000000 | 2024-06-05, 2025-07-08, 2025-10-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3182 | NA | 131242-WST02-DR-3182 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-10-08 | NA | 000000 | 2024-06-05, 2025-07-08, 2025-10-08 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5131 | NA | 131242-WST02-DR-5131 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5132 | NA | 131242-WST02-DR-5132 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5133 | NA | 131242-WST02-DR-5133 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5101 | NA | 131242-WST02-DR-5101 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5102 | NA | 131242-WST02-DR-5102 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0002 | NA | 131242-WST02-DS-0002 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2025-06-26 | 1 | 000000&&000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | E | 0011 | NA | 131242-WST02-DS-0011 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Data sheet for Autosampler" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-06-16 | 0 | 000000&&001378 | 2024-06-05, 2025-06-16 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | E | 0017 | NA | 131242-WST02-DS-0017 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Datasheet for Ammonia Analyser (SSN)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-12-08 | 0 | 000000&&001884 | 2024-06-05, 2025-12-08 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | I | 0003 | NA | 131242-WST02-DS-0003 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-06-06 | 2 | 000000&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | OM | I | 0001 | NA | 131242-WST02-OM-0001 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2024-06-05 | NA | 000000 | 2024-06-05 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | OM | I | 0002 | NA | 131242-WST02-OM-0002 | 2024-06-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-04 | 2024-07-31 | 19 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "O&M Manual for Aeration Blower" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-05 | 2025-05-26 | 0 | 000000&&001318 | 2024-06-05, 2025-05-26 | 00 | 2 | PEN | NAP | NAP
000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 1 | 131242-WST02-DS-0002 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | 5 | Approved with Comments | YES | 2024-12-12 | NO | Overdue | 291 |  |  | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2025-06-26 | 1 | 000000&&000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0101 | NA | 131242-WST02-DR-0101 | 2024-10-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-24 | 5 | Approved with Comments | YES | 2024-12-12 | NO | Overdue | 291 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-25 | 2024-10-25 | NA | 000000 | 2024-10-25 | 00 | 1 | PEN | AWC | AWC
000512 | 00 | Radha | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 0 | 131242-WSW41-MS-0012 | 2024-06-05 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-27 |  | Approved with Comments | YES | 2024-07-17 | YES | Resubmitted |  |  |  | NA | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-06-05 | 2024-07-02 | 1 | 000512 | 2024-06-05, 2024-07-02 | 00, 01 | 2 | PEN | AWC | AWC
000512 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 1 | 131242-WSW41-MS-0012 | 2024-07-02 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.1: Approved | 2024-07-22 | 2024-07-26 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-06-05 | 2024-07-02 | 1 | 000512 | 2024-06-05, 2024-07-02 | 00, 01 | 2 | PEN | APP | APP
000513 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 0 | 131242-WST02-VI-0017 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 11 | Not Approved | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000513 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 1 | 131242-WST02-VI-0017 | 2024-09-16 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 24 | Approved with Comments | YES | 2024-11-28 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000513 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 2 | 131242-WST02-VI-0017 | 2025-01-10 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-30 | 2025-02-12 | 8 | Not Approved | YES | 2025-03-04 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
000513 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 3 | 131242-WST02-VI-0017 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 20 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000514 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 0 | 131242-WST02-VI-0018 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Switch) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 11 | Approved with Comments | YES | 2024-08-12 | YES | Resubmitted |  | 2025-02-24 |  | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000514 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 1 | 131242-WST02-VI-0018 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Switch) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 20 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | 2025-02-24 |  | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000514 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 2 | 131242-WST02-VI-0018 | 2025-05-20 | Vendor Approval of SSN Package (Pressure Switch) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-09 | 2025-10-01 | 82 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000515 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 0 | 131242-WST02-VI-0019 | 2024-06-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 11 | Not Approved | YES | 2024-08-12 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | PEN | NAP | NAP
000515 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 1 | 131242-WST02-VI-0019 | 2024-08-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-27 | 2024-09-18 | 16 | Approved with Comments | YES | 2024-10-08 | YES | Resubmitted |  | 2025-02-28 |  | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000515 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 2 | 131242-WST02-VI-0019 | 2025-03-17 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 20 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000516 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0040 | 0 | 131242-WSW41-CD-0040 | 2024-06-07 | Submission Of BIM Coordination VCM Model (May-2024) | For Information | 2024-07-08 | 2024-06-22 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (May-2024)" | 2024-06-07 | 2024-06-07 | 0 | 000516 | 2024-06-07 | 00 | 1 | PEN | INF | INF
000517 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0024 | 0 | 131242-WSW41-MI-0024 | 2024-06-10 | Process & MEICA Meeting Minutes 0024_20240523 | Minutes of meeting are accepted for information. | 2024-07-09 | 2024-07-02 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0024,0025,0026_May" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | 2024-08-29 | 0 | 000000&&000517&&000561 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000518 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 0 | 131242-WSW41-MS-0013 | 2024-06-10 | MSRA, SWP for Plate Load Test | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-06-27 |  | Not Approved | YES | 2024-07-17 | YES | Resubmitted |  |  |  | NA | "MSRA, SWP for Plate Load Test" | 2024-06-10 | 2024-07-04 | 1 | 000518 | 2024-06-10, 2024-07-04 | 00, 01 | 2 | PEN | NAP | NAP
000518 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 1 | 131242-WSW41-MS-0013 | 2024-07-04 | MSRA, SWP for Plate Load Test | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-05 | 8 | Approved with Comments | YES | 2024-08-26 | NO | Overdue | 368 |  |  | NA | "MSRA, SWP for Plate Load Test" | 2024-06-10 | 2024-07-04 | 1 | 000518 | 2024-06-10, 2024-07-04 | 00, 01 | 2 | PEN | AWC | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 8003_ST613_BCA | A | 131242-WST00-DR-8003_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1000_ST613_BCA | NA | 131242-WST02-DR-1000_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST613_BCA | NA | 131242-WST02-DR-1006_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST613_BCA | NA | 131242-WST02-DR-1007_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST613_BCA | NA | 131242-WST02-DR-1008_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1013_ST613_BCA | NA | 131242-WST02-DR-1013_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5005_ST613_BCA | NA | 131242-WST02-DR-5005_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1014_ST613_BCA | NA | 131242-WST02-DR-1014_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1015_ST613_BCA | NA | 131242-WST02-DR-1015_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1016_ST613_BCA | NA | 131242-WST02-DR-1016_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1017_ST613_BCA | NA | 131242-WST02-DR-1017_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1018_ST613_BCA | NA | 131242-WST02-DR-1018_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1019_ST613_BCA | NA | 131242-WST02-DR-1019_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1020_ST613_BCA | NA | 131242-WST02-DR-1020_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1021_ST613_BCA | NA | 131242-WST02-DR-1021_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1022_ST613_BCA | NA | 131242-WST02-DR-1022_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3005_ST613_BCA | NA | 131242-WST02-DR-3005_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3008_ST613_BCA | NA | 131242-WST02-DR-3008_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3009_ST613_BCA | NA | 131242-WST02-DR-3009_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST613_BCA | NA | 131242-WST02-DR-7002_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7003_ST613_BCA | NA | 131242-WST02-DR-7003_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7004_ST613_BCA | NA | 131242-WST02-DR-7004_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7005_ST613_BCA | NA | 131242-WST02-DR-7005_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5006_ST613_BCA | NA | 131242-WST02-DR-5006_ST613_BCA | 2024-06-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-09 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-10 | 2024-06-10 | NA | 000000 | 2024-06-10 | 00 | 1 | PEN | AWC | AWC
000520 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0013 | 0 | 131242-WSW41-RT-0013 | 2024-06-12 | C4B Monthly Progress Report Number No.13 (05 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-07-11 | 2024-06-28 |  | Approved with Comments | YES | 2024-07-18 | NO | Overdue | 394 |  |  | NA | "C4B Monthly Progress Report Number No.13 (05 24)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Quarterly Safety Review Follow Up on SSN RC Works" | 2024-06-12 | 2025-07-01 | 0 | 000000&&000520&&000852 | 2024-06-12, 2024-11-28, 2025-07-01 | 00 | 3 | PEN | AWC | AWC
000521 | 00 | David | Mech | NA | 131242 | WSW41 | SP | M | 8002 | 0 | 131242-WSW41-SP-8002 | 2024-06-12 | Datasheet for Thermal Insulation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-11 | 2024-08-29 | 34 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 | 2025-03-28 | In Progress | NA | "Datasheet for Thermal Insulation" | 2024-06-12 | 2024-06-12 | 0 | 000521 | 2024-06-12 | 00 | 1 | PEN | AWC | AWC
000522 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 0 | 131242-WSW41-VI-0016 | 2024-06-13 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-12 | 2024-06-28 |  | Not Approved | YES | 2024-07-18 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | PEN | NAP | NAP
000522 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 1 | 131242-WSW41-VI-0016 | 2024-07-04 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-17 |  | Not Approved | YES | 2024-08-06 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | PEN | NAP | NAP
000522 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 2 | 131242-WSW41-VI-0016 | 2024-07-22 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | R2: Approved | 2024-08-12 | 2024-08-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | PEN | APP | APP
000523 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0006 | 0 | 131242-WSW41-CL-0006 | 2024-06-14 | Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94 | Rev.0: Approved | 2024-07-15 | 2024-06-28 |  | Approved | NO |  | YES |  |  |  |  | NA | "Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94" | 2024-06-14 | 2024-06-14 | 0 | 000523 | 2024-06-14 | 00 | 1 | PEN | APP | APP
000524 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0032 | 0 | 131242-WSW41-LT-0032 | 2024-06-14 | NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source | Refer to S.O. Correspondence No.000213 dated 23-Aug-2024. | 2024-07-15 | 2024-08-26 | 29 | For Information | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source " | 2024-06-14 | 2024-06-14 | 0 | 000524 | 2024-06-14 | 00 | 1 | PEN | INF | INF
000525 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0014 | 0 | 131242-WSW41-MS-0014 | 2024-06-18 | MSRA & SWP of Civil & Structure Work (Substructure) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "MSRA & SWP of Civil & Structure Work (Substructure)" && "MSRA for Protection Relay Replacement Works " | 2024-06-18 | 2025-05-04 | 0 | 000525&&001266 | 2024-06-18, 2025-05-04 | 00 | 2 | PEN | AWC | AWC
000526 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0015 | 0 | 131242-WSW41-MS-0015 | 2024-06-18 | MSRA & SWP of Mobilization & Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 |  | Approved with Comments | YES | 2024-07-19 | NO | Overdue | 393 |  |  | NA | "MSRA & SWP of Mobilization & Demobilization of Machinery" | 2024-06-18 | 2024-06-18 | 0 | 000526 | 2024-06-18 | 00 | 1 | PEN | AWC | AWC
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A | 131242-WSB01-DR-1000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 17 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2025-01-14 | A.1 | 000000&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 3000 | NA | 131242-WSB01-DR-3000 | 2024-06-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-17 | 2024-08-12 | 17 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 5000 | NA | 131242-WSB01-DR-5000 | 2024-06-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-17 | 2024-08-12 | 17 | Not Approved | YES | 2024-08-30 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | NAP | NAP
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A.1 | 131242-WSB01-DR-1000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2025-01-14 | A.1 | 000000&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 3000 | NA | 131242-WSB01-DR-3000 | 2025-01-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-03 | 2025-01-20 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSB01 | DR | BH | 5000 | NA | 131242-WSB01-DR-5000 | 2025-01-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-03 | 2025-01-20 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-19 | 2025-01-14 | NA | 000000 | 2024-06-19, 2024-10-18, 2025-01-14 | 00 | 3 | PEN | AWC | AWC
000528 | 00 | Balaji | EICA | NA | 131242 | WSW41 | VI | I | 0002 | 0 | 131242-WSW41-VI-0002 | 2024-06-19 | Vendor Approval of Communication Cable (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-17 | 2024-08-05 | 13 | Approved with Comments | YES | 2024-08-26 | NO | Overdue | 368 |  |  | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | PEN | AWC | AWC
000529 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0025 | 0 | 131242-WSW41-MI-0025 | 2024-06-20 | Process & MEICA Meeting Minutes 0025_20240606 | For Information | 2024-07-18 | 2024-08-08 | 15 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | 2024-08-29 | 0 | 000000&&000529 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | C | 131242-WST00-DR-0001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 |  |  | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 0002_ST606 | NA | 131242-WST00-DR-0002_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 0003_ST606 | NA | 131242-WST00-DR-0003_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST606 | NA | 131242-WST02-DR-1006_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST606 | NA | 131242-WST02-DR-1007_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST606 | NA | 131242-WST02-DR-1008_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3000_ST606 | NA | 131242-WST02-DR-3000_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 5001_ST606 | NA | 131242-WST00-DR-5001_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-21 | 2024-06-21 | NA | 000000 | 2024-06-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 5002_ST606 | NA | 131242-WST00-DR-5002_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-21 | 2024-06-21 | NA | 000000 | 2024-06-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7000_ST606 | NA | 131242-WST02-DR-7000_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7001_ST606 | NA | 131242-WST02-DR-7001_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST606 | NA | 131242-WST02-DR-7002_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-09-29 | 2024-06-21 | NA | 000000 | 2023-09-29, 2024-06-21 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | S | 8002_ST606 | NA | 131242-WST00-DR-8002_ST606 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-08-12 | 15 | Approved with Comments | YES | 2024-08-30 | NO | Overdue | 364 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-21 | 2024-06-21 | NA | 000000 | 2024-06-21 | 00 | 1 | PEN | AWC | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | D | 131242-WST00-DR-0001_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  |  |  | NA | "IFC of ST601 – ERSS < 4m " && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | E | 000000&&000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601 | NA | 131242-WST00-DR-0002_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601 | NA | 131242-WST00-DR-1000_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1001_ST601 | NA | 131242-WST00-DR-1001_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1002_ST601 | NA | 131242-WST00-DR-1002_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1003_ST601 | NA | 131242-WST00-DR-1003_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-06-21 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601 | NA | 131242-WST00-DR-1004_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 5100_ST601 | NA | 131242-WST00-DR-5100_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-06-21 | 2024-06-21 | NA | 000000 | 2024-06-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 8000_ST601 | NA | 131242-WST00-DR-8000_ST601 | 2024-06-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-19 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | A | 000000&&000248 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | AWC | AWC
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | E | 131242-WST00-DR-0001_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-12 | 2024-08-13 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "IFC of ST601 – ERSS < 4m " && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | E | 000000&&000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 0002_ST601 | NA | 131242-WST00-DR-0002_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1000_ST601 | NA | 131242-WST00-DR-1000_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 1004_ST601 | NA | 131242-WST00-DR-1004_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3000_ST601 | NA | 131242-WST00-DR-3000_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-22 | 2024-07-22 | NA | 000000 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3001_ST601 | NA | 131242-WST00-DR-3001_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-22 | 2024-07-22 | NA | 000000 | 2024-07-22 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3002_ST601 | NA | 131242-WST00-DR-3002_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-22 | 2024-07-22 | NA | 000000 | 2024-07-22 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 3003_ST601 | NA | 131242-WST00-DR-3003_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-22 | 2024-07-22 | NA | 000000 | 2024-07-22 | 00 | 1 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST00 | DR | G | 8000_ST601 | NA | 131242-WST00-DR-8000_ST601 | 2024-07-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-20 | 2024-08-13 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-07-22 | A | 000000&&000248 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00 | 5 | PEN | APP | APP
000532 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0009 | 0 | 131242-WSW41-QA-0009 | 2024-06-25 | Monthly Concrete Cube Records for Structural works (02 24) | For Information | 2024-07-23 | 2024-07-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation)" && "Monthly Concrete Cube Records for Structural works (02 24)" | 2024-06-25 | 2025-06-18 | 0 | 000532&&001387 | 2024-06-25, 2025-06-18 | 00 | 2 | PEN | INF | INF
000533 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 0 | 131242-WSW41-PC-0012 | 2024-06-25 | Payment Claim No.12 | Rev (0): Rejected due to some PDA test were done in June 2024. | 2024-07-23 | 2024-06-28 |  | Rejected | YES | 2024-07-18 | YES | Resubmitted |  |  |  | NA | "Payment Claim No.12" | 2024-06-25 | 2024-06-28 | 1 | 000533 | 2024-06-25, 2024-06-28 | 00, 01 | 2 | PEN | REJ | REJ
000533 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 1 | 131242-WSW41-PC-0012 | 2024-06-28 | Payment Claim No.12 | Rev (1): Approved, refer to SO Correspondence No. 0181 dated 2 July 2024. | 2024-07-18 | 2024-11-07 | 78 | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.12" | 2024-06-25 | 2024-06-28 | 1 | 000533 | 2024-06-25, 2024-06-28 | 00, 01 | 2 | PEN | APP | APP
000534 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6601 | 0 | 131242-WST02-DR-6601 | 2024-06-26 | SSN Blower P&ID | Rev 0: Not approved - Revise and Resubmit | 2024-07-24 | 2024-07-31 | 5 | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "SSN Blower P&ID" | 2024-06-26 | 2024-06-26 | 0 | 000534 | 2024-06-26 | 00 | 1 | PEN | NAP | NAP
000534 | 01 | Qili | Process | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S000534 | NA | 131242-NA-NA-Cmt Sheet Reply S000534 | 2024-08-15 | SSN Blower P&ID | Rev 1: Rejected | 2024-09-04 | 2024-09-06 | 2 | Rejected | NO |  | YES |  |  |  |  | NA | "SSN Blower P&ID" | 2024-08-15 | 2024-08-15 | NA | 000534 | 2024-08-15 | 01 | 1 | PEN | REJ | REJ
000535 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0003 | 0 | 131242-WSD11-BQ-0003 | 2024-06-26 | THP Line List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-24 | 2024-08-29 | 25 | Approved with Comments | YES | 2024-09-18 | NO | Overdue | 351 |  |  | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | PEN | AWC | AWC
000536 | 00 | Zora/ HP | CSA | NA | 131242 | WSD11 | DR | S | 5301 | B | 131242-WSD11-DR-5301 | 2024-06-26 | IFC of Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-05 |  | Approved with Comments | YES | 2024-07-25 | NO | Overdue | 389 | 2024-07-16 | Zora obtain QP endorsement on the drawing and Heng Peng to provide latest DGN and Tenwit (Kalaban) updating the minor comments | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | 2024-06-26 | B | 000423&&000536 | 2024-06-05, 2024-06-26 | 00, 01 | 2 | PEN | AWC | AWC
000537 | 00 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 0 | 131242-WSD11-CL-0010 | 2024-06-27 | Design Calculation for Instrument Air Receiver | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-06 | 8 | Approved with Comments | YES | 2024-08-27 | YES | Resubmitted |  |  |  | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | PEN | AWC | AWC
000537 | 01 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 1 | 131242-WSD11-CL-0010 | 2024-09-03 | Design Calculation for Instrument Air Receiver | Rev 1: Approved | 2024-09-23 | 2024-09-05 |  | Approved | NO |  | YES |  |  |  |  | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | PEN | APP | APP
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009_ST607_BCA | A | 131242-WST02-DR-1009_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 |  |  | NA | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-01 | A | 000538 | 2024-07-01 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-1010_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | A | 000000&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | NA | 131242-WST02-DR-1011_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | NA | 131242-WST02-DR-1012_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | NA | 131242-WST02-DR-3002_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | NA | 131242-WST02-DR-7003_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | NA | 131242-WST02-DR-7004_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | NA | 131242-WST02-DR-8003_ST607_BCA | 2024-07-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-29 | 2024-07-15 |  | Not Approved | YES | 2024-08-02 | NO | Overdue | 383 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | NAP | NAP
000539 | 00 | Mohan | QAQC | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-0004 | 2024-07-02 | Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-30 | 2024-07-15 |  | Approved with Comments | YES | 2024-08-02 | NO | Overdue | 383 |  |  | NA | "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " && "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" | 2024-07-02 | 2024-07-15 | 0 | 000539&&000567 | 2024-07-02, 2024-07-15 | 00 | 2 | PEN | AWC | AWC
000540 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-0005 | 2024-07-02 | Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616) | For Information | 2024-07-30 | 2024-07-15 |  | For Information | NO |  | YES |  |  |  |  | NA | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " && "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" | 2024-07-02 | 2025-07-24 | 0 | 000540&&000568&&001524 | 2024-07-02, 2024-07-15, 2025-07-24 | 00 | 3 | PEN | INF | INF
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | A | 131242-WST02-DR-5103 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 |  | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  |  |  | NA | "Blower Encapsulation GA" | 2024-07-03 | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5104 | NA | 131242-WST02-DR-5104 | 2024-07-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-07-31 |  | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5105 | NA | 131242-WST02-DR-5105 | 2024-07-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-07-31 | 2024-07-31 |  | Not Approved | YES | 2024-08-21 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | NAP | NAP
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | B | 131242-WST02-DR-5103 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  |  |  | NA | "Blower Encapsulation GA" | 2024-07-03 | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5104 | NA | 131242-WST02-DR-5104 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5105 | NA | 131242-WST02-DR-5105 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5106 | NA | 131242-WST02-DR-5106 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5107 | NA | 131242-WST02-DR-5107 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5108 | NA | 131242-WST02-DR-5108 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0031 | NA | 131242-WST02-DS-0031 | 2025-01-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-05 | 2025-03-21 | 32 | Approved with Comments | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-01-16 | NA | 000000 | 2025-01-16 | 00 | 1 | PEN | AWC | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | D | 131242-WST02-DR-5103 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Blower Encapsulation GA" | 2024-07-03 | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5104 | NA | 131242-WST02-DR-5104 | 2025-06-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5105 | NA | 131242-WST02-DR-5105 | 2025-06-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-03 | 2025-06-06 | NA | 000000 | 2024-07-03, 2025-01-16, 2025-06-06 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5106 | NA | 131242-WST02-DR-5106 | 2025-06-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5107 | NA | 131242-WST02-DR-5107 | 2025-06-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5108 | NA | 131242-WST02-DR-5108 | 2025-06-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-26 | 2025-07-17 | 15 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-16 | 2025-06-06 | NA | 000000 | 2025-01-16, 2025-06-06 | 00 | 2 | PEN | AWC | AWC
000542 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0026 | A | 131242-WSW41-MI-0026 | 2024-07-03 | Process & MEICA Meeting Minutes 0026_20240624 | Rev 0: For Information | 2024-07-31 | 2024-08-29 | 20 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | 2024-08-29 | A | 000000&&000542 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7700 | C | 131242-WST02-DR-7700 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "Blower Circuit Diagram" | 2024-07-04 | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7701 | NA | 131242-WST02-DR-7701 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7702 | NA | 131242-WST02-DR-7702 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7703 | NA | 131242-WST02-DR-7703 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7704 | NA | 131242-WST02-DR-7704 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7705 | NA | 131242-WST02-DR-7705 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7706 | NA | 131242-WST02-DR-7706 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7707 | NA | 131242-WST02-DR-7707 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7708 | NA | 131242-WST02-DR-7708 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7709 | NA | 131242-WST02-DR-7709 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7710 | NA | 131242-WST02-DR-7710 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7711 | NA | 131242-WST02-DR-7711 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7712 | NA | 131242-WST02-DR-7712 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7713 | NA | 131242-WST02-DR-7713 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7714 | NA | 131242-WST02-DR-7714 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7715 | NA | 131242-WST02-DR-7715 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | E | 7716 | NA | 131242-WST02-DR-7716 | 2024-07-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-01 | 2024-10-29 | 62 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-07-04 | NA | 000000 | 2024-07-04 | 00 | 1 | PEN | AWC | AWC
000544 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0034 | 0 | 131242-WSW41-LT-0034 | 2024-07-04 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Please refer to comment sheet for resubmission. | 2024-08-01 | 2024-07-16 |  | For Information | YES | 2024-08-05 | YES | Resubmitted |  |  |  | NA | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-07-04 | 2024-07-04 | 0 | 000544 | 2024-07-04 | 00 | 1 | PEN | INF | INF
000544 | 01 | Yuen Fatt | Project | NA | 131242 | NA | LT | PM | NA | NA | 131242-NA-LT-NA | 2024-08-03 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Rev.1: Please refer to comment sheet for resubmission. | 2024-08-23 | 2024-08-19 |  | Not Approved | YES | 2024-09-06 | NO | Overdue | 359 |  | To change the title : Request Owner’s Approval for Use of Linabond Concrete Corrosion Protection Material | NA | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-08-03 | 2024-08-03 | NA | 000544 | 2024-08-03 | 01 | 1 | PEN | NAP | NAP
000545 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0006 | 0 | 131242-WST02-RT-0006 | 2024-07-04 | Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615) | Approved | 2024-08-01 | 2024-07-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "SSN Hazardous Area Assessment Report" && "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" && "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | 2025-11-20 | 0 | 000545&&000772&&001856 | 2024-07-04, 2024-10-23, 2025-11-20 | 00 | 3 | PEN | APP | APP
000546 | 00 | Theint Theint | Project | NA | 131242 | WSW41 | VI | S | 0005 | 0 | 131242-WSW41-VI-0005 | 2024-07-05 | Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-02 | 2024-07-18 |  | Not Approved | YES | 2024-08-07 | NO | Overdue | 380 |  |  | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | NAP | NAP
000547 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0002 | 0 | 131242-WSW41-PO-0002 | 2024-07-08 | Unpriced PO for Cables (Keystone) | For Information | 2024-08-05 | 2024-08-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Ball Valve (OVS Engineering)" && "Unpriced PO for Cables (Keystone)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-07-08 | 2025-08-22 | 0 | 000547&&001501&&001513 | 2024-07-08, 2025-07-22, 2025-08-22 | 00, 01 | 3 | PEN | INF | INF
000548 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-0005 | 2024-07-08 | Unpriced PO for Sludge Pump (Netzsch) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 17 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | PEN | INF | INF
000549 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-0006 | 2024-07-08 | Unpriced PO for cPVC Pipes (George Fischer) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 17 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | PEN | INF | INF
000550 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jun-2024) | For Information | 2024-08-05 | 2024-07-23 |  | For Information | YES | 2024-08-13 | YES | Resubmitted |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | PEN | INF | INF
000551 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0002 | 0 | 131242-WSW41-MS-0002 | 2024-07-08 | MSRA & SWP for Pre-Augering Work | Rev.0: Approved | 2024-08-05 | 2024-08-08 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | PEN | APP | APP
000552 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 0 | 131242-WSW41-RT-0014 | 2024-07-09 | C4B Monthly Progress Report Number No.14 (06 24) | Rejected as requested by Contractor | 2024-08-06 | 2024-07-09 |  | Rejected | YES | 2024-07-29 | YES | Resubmitted |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | PEN | REJ | REJ
000552 | 01 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 1 | 131242-WSW41-RT-0014 | 2024-07-13 | C4B Monthly Progress Report Number No.14 (06 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-08-01 | 2024-07-30 |  | Approved with Comments | YES | 2024-08-20 | NO | Overdue | 372 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | PEN | AWC | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 0 | 131242-WST02-CL-0007 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 4 | Approved with Comments | YES | 2024-09-02 | YES | Resubmitted |  |  |  | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | I | 0004 | NA | 131242-WST02-DS-0004 | 2024-07-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-06 | 2024-08-13 | 4 | Approved with Comments | YES | 2024-09-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | 2025-04-25 | 0 | 000000&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0018 | NA | 131242-WST02-DS-0018 | 2024-07-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-06 | 2024-08-13 | 4 | Approved with Comments | YES | 2024-09-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Datasheet for Pressure Gauge" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-08-22 | 0 | 000000&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5020 | NA | 131242-WST02-DR-5020 | 2024-07-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-06 | 2024-08-13 | 4 | Approved with Comments | YES | 2024-09-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2024-11-02 | NA | 000000 | 2024-07-09, 2024-11-02 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5021 | NA | 131242-WST02-DR-5021 | 2024-07-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-06 | 2024-08-13 | 4 | Approved with Comments | YES | 2024-09-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-03-06 | NA | 000000 | 2024-07-09, 2024-11-02, 2025-03-06 | 00 | 3 | PEN | AWC | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 1 | 131242-WST02-CL-0007 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-21 | 2024-11-19 |  | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0025 | NA | 131242-WST02-DR-0025 | 2024-11-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-29 | 2024-11-19 |  | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-02 | 2024-11-02 | NA | 000000 | 2024-11-02 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 0026 | NA | 131242-WST02-DR-0026 | 2024-11-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-29 | 2024-11-19 |  | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-02 | 2024-11-02 | NA | 000000 | 2024-11-02 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5020 | NA | 131242-WST02-DR-5020 | 2024-11-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-29 | 2024-11-19 |  | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2024-11-02 | NA | 000000 | 2024-07-09, 2024-11-02 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | I | 5021 | NA | 131242-WST02-DR-5021 | 2024-11-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-29 | 2024-11-19 |  | Approved with Comments | YES | 2024-12-09 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-03-06 | NA | 000000 | 2024-07-09, 2024-11-02, 2025-03-06 | 00 | 3 | PEN | AWC | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-0007 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | P | 0008 | NA | 131242-WST02-CL-0008 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | M | 5020 | NA | 131242-WST02-CL-5020 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | M | 5021 | NA | 131242-WST02-CL-5021 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0018 | NA | 131242-WST02-DS-0018 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Datasheet for Pressure Gauge" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-08-22 | 0 | 000000&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0019 | NA | 131242-WST02-DS-0019 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Datasheet for Rotameter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-09-10 | 0 | 000000&&001672 | 2025-03-06, 2025-08-22, 2025-09-10 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5741 | NA | 131242-WST02-DS-5741 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5021 | NA | 131242-WST02-DR-5021 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-03-06 | NA | 000000 | 2024-07-09, 2024-11-02, 2025-03-06 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5022 | NA | 131242-WST02-DR-5022 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1200 | NA | 131242-WST02-DR-1200 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1201 | NA | 131242-WST02-DR-1201 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1202 | NA | 131242-WST02-DR-1202 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1203 | NA | 131242-WST02-DR-1203 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST608 drawings Connection Details" | 2025-03-06 | 2025-07-29 | F | 000000&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1204 | NA | 131242-WST02-DR-1204 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1205 | NA | 131242-WST02-DR-1205 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1206 | NA | 131242-WST02-DR-1206 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1207 | NA | 131242-WST02-DR-1207 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1208 | NA | 131242-WST02-DR-1208 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1209 | NA | 131242-WST02-DR-1209 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 1210 | NA | 131242-WST02-DR-1210 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3203 | NA | 131242-WST02-DR-3203 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-18 | 2025-03-06 | A | 000000&&001052 | 2025-02-18, 2025-03-06 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3204 | NA | 131242-WST02-DR-3204 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-18 | 2025-03-06 | NA | 000000 | 2025-02-18, 2025-03-06 | 00, NA | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3205 | NA | 131242-WST02-DR-3205 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3206 | NA | 131242-WST02-DR-3206 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3207 | NA | 131242-WST02-DR-3207 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3208 | NA | 131242-WST02-DR-3208 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3209 | NA | 131242-WST02-DR-3209 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 3210 | NA | 131242-WST02-DR-3210 | 2025-03-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-26 | 2025-04-23 | 18 | Approved with Comments | YES | 2025-05-13 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-03-06 | NA | 000000 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-0007 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | P | 0008 | NA | 131242-WST02-CL-0008 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | M | 5020 | NA | 131242-WST02-CL-5020 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | CL | M | 5021 | NA | 131242-WST02-CL-5021 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0018 | NA | 131242-WST02-DS-0018 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Datasheet for Pressure Gauge" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-09 | 2025-08-22 | 0 | 000000&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0019 | NA | 131242-WST02-DS-0019 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Datasheet for Rotameter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-09-10 | 0 | 000000&&001672 | 2025-03-06, 2025-08-22, 2025-09-10 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 0020 | NA | 131242-WST02-DS-0020 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Datasheet for Conductive Level Switch" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-08-22 | 2025-09-10 | 0 | 000000&&001673 | 2025-08-22, 2025-09-10 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5741 | NA | 131242-WST02-DS-5741 | 2025-08-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-09-11 | 2025-10-06 | 17 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-08-22 | NA | 000000 | 2025-03-06, 2025-08-22 | 00 | 2 | PEN | AWC | AWC
000554 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-5000 | 2024-07-10 | SSN UPS and Battery Room Layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 17 | Not Approved | YES | 2024-09-20 | NO | Overdue | 349 |  |  | NA | "Building Services ACMV" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Cast-in Schedule & Details" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | 2025-10-29 | A | 000000&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 21 | PEN | NAP | NAP
000555 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-5001 | 2024-07-10 | SSN Process Non-Process room layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 17 | Not Approved | YES | 2024-09-20 | NO | Overdue | 349 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | NAP | NAP
000556 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 0 | 131242-WSD11-RT-0000 | 2024-07-10 | THP LPS Risk Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 33 | Approved with Comments | YES | 2024-10-14 | YES | Resubmitted |  |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000556 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 1 | 131242-WSD11-RT-0000 | 2024-10-28 | THP LPS Risk Assessment Report | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-12-08 | 14 | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | 2025-02-24 |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000556 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 2 | 131242-WSD11-RT-0000 | 2025-07-07 | THP LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 27 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 0 | 131242-WST02-RT-0000 | 2024-07-10 | SSN LPS Risk Assessment Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 33 | Not Approved | YES | 2024-10-14 | YES | Resubmitted |  |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000557 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 1 | 131242-WST02-RT-0000 | 2024-10-24 | SSN LPS Risk Assessment Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-11-14 | 2024-12-08 | 16 | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000557 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 2 | 131242-WST02-RT-0000 | 2025-07-07 | SSN LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 27 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000558 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0028 | 0 | 131242-WSW41-MI-0028 | 2024-07-10 | BIM Bi-Weekly Meeting Minutes 0028_20240626 | For Information | 2024-08-07 | 2024-08-30 | 16 | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | 2024-08-06 | 0 | 000000&&000558&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | PEN | INF | INF
000559 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-0018 | 2024-07-12 | Preliminary Design and Vendor Approval for Parabolic Screen | Rev 0: Approved | 2024-08-12 | 2024-09-02 | 15 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | PEN | APP | APP
000560 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 0 | 131242-WSW41-VI-0020 | 2024-07-12 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 9 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | PEN | AWC | AWC
000560 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 1 | 131242-WSW41-VI-0020 | 2024-09-16 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 1: Approved | 2024-10-04 | 2024-09-24 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | PEN | APP | APP
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0024 | 0 | 131242-WSW41-MI-0024 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0024,0025,0026_May" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | 2024-08-29 | 0 | 000000&&000517&&000561 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0025 | NA | 131242-WSW41-MI-0025 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-12 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | 2024-08-29 | 0 | 000000&&000529 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0026 | NA | 131242-WSW41-MI-0026 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-12 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | 2024-08-29 | A | 000000&&000542 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0027 | 0 | 131242-WSW41-MI-0027 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0027,0028_June" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | 2024-08-29 | 0 | 000000&&000562&&000584 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | MI | C | 0028 | NA | 131242-WSW41-MI-0028 | 2024-07-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-12 | 2024-07-30 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | 2024-08-06 | 0 | 000000&&000558&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | PEN | INF | INF
000563 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0010 | 0 | 131242-WSW41-QA-0010 | 2024-07-12 | Monthly Concrete Cube Records for Structural works (03 24) | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-08-12 | 2024-08-12 |  | Not Approved | YES | 2024-08-30 | NO | Overdue | 364 |  |  | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | PEN | NAP | NAP
000564 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0002 | 0 | 131242-WSW41-MS-0002 | 2024-07-12 | MSRA, SWP for Electrical Work | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-12 | 2024-09-24 | 31 | Not Approved | YES | 2024-10-14 | NO | Overdue | 333 |  |  | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | PEN | NAP | NAP
000565 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 0 | 131242-WSW41-MS-0001 | 2024-07-13 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 9 | Approved with Comments | YES | 2024-09-12 | YES | Resubmitted |  |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | AWC | AWC
000565 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 1 | 131242-WSW41-MS-0001 | 2024-09-05 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 1: Approved | 2024-09-25 | 2024-10-03 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | APP | APP
000566 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0020 | 0 | 131242-WST02-VI-0020 | 2024-07-13 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-12 | 2024-08-06 |  | Approved with Comments | YES | 2024-08-27 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-07-13 | 2024-08-16 | 1 | 000566 | 2024-07-13, 2024-08-16 | 00, 01 | 2 | PEN | AWC | AWC
000566 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0020 | 1 | 131242-WST02-VI-0020 | 2024-08-16 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-05 | 2024-10-10 | 25 | Approved with Comments | YES | 2024-10-30 | NO | Overdue | 321 |  | Vendor Changed to Fox | NA | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-07-13 | 2024-08-16 | 1 | 000566 | 2024-07-13, 2024-08-16 | 00, 01 | 2 | PEN | AWC | AWC
000567 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-0004 | 2024-07-15 | Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area | Approved | 2024-08-13 | 2024-08-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " && "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" | 2024-07-02 | 2024-07-15 | 0 | 000539&&000567 | 2024-07-02, 2024-07-15 | 00 | 2 | PEN | APP | APP
000568 | 00 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-0005 | 2024-07-15 | Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-13 | 2024-08-22 | 7 | Approved with Comments | YES | 2024-09-11 | NO | Overdue | 356 |  |  | NA | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " && "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" | 2024-07-02 | 2025-07-24 | 0 | 000540&&000568&&001524 | 2024-07-02, 2024-07-15, 2025-07-24 | 00 | 3 | PEN | AWC | AWC
000569 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 0 | 131242-WSD11-CD-0002 | 2024-07-16 | THP Instrument Lists | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-17 | 24 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  |  |  | NA | "THP Instrument Lists" | 2024-07-16 | 2024-12-13 | 1 | 000569 | 2024-07-16, 2024-12-13 | 00, 01 | 2 | PEN | NAP | NAP
000569 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 1 | 131242-WSD11-CD-0002 | 2024-12-13 | THP Instrument Lists | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-03 | 2025-02-13 | 27 | Not Approved | YES | 2025-03-05 | NO | Overdue | 233 |  |  | NA | "THP Instrument Lists" | 2024-07-16 | 2024-12-13 | 1 | 000569 | 2024-07-16, 2024-12-13 | 00, 01 | 2 | PEN | NAP | NAP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | A | 131242-WSD11-DR-7100 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-21 | 5 | Not Approved | YES | 2024-09-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | NAP | NAP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-7000 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-21 | 2024-10-03 |  | Not Approved | YES | 2024-10-23 | YES | Resubmitted |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7009 | NA | 131242-WSD11-DR-7009 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7010 | NA | 131242-WSD11-DR-7010 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7028 | NA | 131242-WSD11-DR-7028 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7029 | NA | 131242-WSD11-DR-7029 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7030 | NA | 131242-WSD11-DR-7030 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3000 | NA | 131242-WSD11-DR-3000 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3010 | NA | 131242-WSD11-DR-3010 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3011 | NA | 131242-WSD11-DR-3011 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3012 | NA | 131242-WSD11-DR-3012 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3013 | NA | 131242-WSD11-DR-3013 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7100 | NA | 131242-WSD11-DR-7100 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2024-10-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-29 | 2024-10-03 |  | Rejected | YES | 2024-10-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-7000 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-10-29 | 4 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7009 | NA | 131242-WSD11-DR-7009 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7010 | NA | 131242-WSD11-DR-7010 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7028 | NA | 131242-WSD11-DR-7028 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7029 | NA | 131242-WSD11-DR-7029 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7030 | NA | 131242-WSD11-DR-7030 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3000 | NA | 131242-WSD11-DR-3000 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3010 | NA | 131242-WSD11-DR-3010 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3011 | NA | 131242-WSD11-DR-3011 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3012 | NA | 131242-WSD11-DR-3012 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3013 | NA | 131242-WSD11-DR-3013 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7100 | NA | 131242-WSD11-DR-7100 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2024-10-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-01 | 2024-10-29 |  | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | C | 131242-WSD11-DR-7000 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-30 | 12 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | TBA |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7009 | NA | 131242-WSD11-DR-7009 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7010 | NA | 131242-WSD11-DR-7010 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7028 | NA | 131242-WSD11-DR-7028 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7029 | NA | 131242-WSD11-DR-7029 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7030 | NA | 131242-WSD11-DR-7030 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7031 | NA | 131242-WSD11-DR-7031 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-10-23 | NA | 000000 | 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3000 | NA | 131242-WSD11-DR-3000 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3010 | NA | 131242-WSD11-DR-3010 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3011 | NA | 131242-WSD11-DR-3011 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3012 | NA | 131242-WSD11-DR-3012 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3013 | NA | 131242-WSD11-DR-3013 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7100 | NA | 131242-WSD11-DR-7100 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-19 | 2024-12-30 | 6 | Approved with Comments | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | D | 131242-WSD11-DR-7000 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7009 | NA | 131242-WSD11-DR-7009 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7010 | NA | 131242-WSD11-DR-7010 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7011 | NA | 131242-WSD11-DR-7011 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7028 | NA | 131242-WSD11-DR-7028 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7029 | NA | 131242-WSD11-DR-7029 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7030 | NA | 131242-WSD11-DR-7030 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7031 | NA | 131242-WSD11-DR-7031 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-10-23 | NA | 000000 | 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3000 | NA | 131242-WSD11-DR-3000 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3010 | NA | 131242-WSD11-DR-3010 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3011 | NA | 131242-WSD11-DR-3011 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3012 | NA | 131242-WSD11-DR-3012 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3013 | NA | 131242-WSD11-DR-3013 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7100 | NA | 131242-WSD11-DR-7100 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-27 | 2025-05-06 | 25 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | AWC | AWC
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | E | 131242-WSD11-DR-7000 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7009 | NA | 131242-WSD11-DR-7009 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7010 | NA | 131242-WSD11-DR-7010 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7011 | NA | 131242-WSD11-DR-7011 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7028 | NA | 131242-WSD11-DR-7028 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7029 | NA | 131242-WSD11-DR-7029 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7030 | NA | 131242-WSD11-DR-7030 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-10-23 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7031 | NA | 131242-WSD11-DR-7031 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-10-23 | NA | 000000 | 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3000 | NA | 131242-WSD11-DR-3000 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3010 | NA | 131242-WSD11-DR-3010 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2026-02-03 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 17 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3011 | NA | 131242-WSD11-DR-3011 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP LDB-0001B SLD, Schematic and GA Drawing" | 2024-10-01 | 2026-02-03 | A | 000000&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00 | 15 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3012 | NA | 131242-WSD11-DR-3012 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3013 | NA | 131242-WSD11-DR-3013 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-01 | 2025-11-11 | NA | 000000 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7100 | NA | 131242-WSD11-DR-7100 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP SLD" | 2024-07-16 | 2025-10-23 | A | 000000&&000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7101 | NA | 131242-WSD11-DR-7101 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7102 | NA | 131242-WSD11-DR-7102 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7103 | NA | 131242-WSD11-DR-7103 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7104 | NA | 131242-WSD11-DR-7104 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7105 | NA | 131242-WSD11-DR-7105 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7106 | NA | 131242-WSD11-DR-7106 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7107 | NA | 131242-WSD11-DR-7107 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7108 | NA | 131242-WSD11-DR-7108 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 7109 | NA | 131242-WSD11-DR-7109 | 2025-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-11-12 | 2026-02-02 | 57 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | APP | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | A | 131242-WSD11-DR-7000 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7001 | NA | 131242-WSD11-DR-7001 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7002 | NA | 131242-WSD11-DR-7002 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-03-18 | 2025-10-23 | NA | 000000 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00 | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7003 | NA | 131242-WSD11-DR-7003 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7004 | NA | 131242-WSD11-DR-7004 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7005 | NA | 131242-WSD11-DR-7005 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7006 | NA | 131242-WSD11-DR-7006 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7007 | NA | 131242-WSD11-DR-7007 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7008 | NA | 131242-WSD11-DR-7008 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7020 | NA | 131242-WSD11-DR-7020 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7021 | NA | 131242-WSD11-DR-7021 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7022 | NA | 131242-WSD11-DR-7022 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7023 | NA | 131242-WSD11-DR-7023 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7024 | NA | 131242-WSD11-DR-7024 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2025-10-23 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7025 | NA | 131242-WSD11-DR-7025 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7026 | NA | 131242-WSD11-DR-7026 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EI | 7027 | NA | 131242-WSD11-DR-7027 | 2024-07-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-14 | 2024-08-23 | 7 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-16 | 2026-02-03 | NA | 000000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, NA | 7 | PEN | REJ | REJ
000571 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#571 Cmt Reply Sht | NA | 131242-WSD11-NA-S#571 Cmt Reply Sht | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 |  | Not Approved | NO |  | YES |  |  |  |  | NA | "THP SLD" | 2024-10-01 | 2024-10-01 | NA | 000571 | 2024-10-01 | 01 | 1 | PEN | NAP | NAP
000572 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302 | A | 131242-WSD11-DR-5302 | 2024-07-17 | IFC of BSB Silo Area Pump Plinth Details | For Information | 2024-08-15 | 2024-08-28 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "IFC of BSB Silo Area Pump Plinth Details " | 2024-07-17 | 2024-07-17 | A | 000572 | 2024-07-17 | 00 | 1 | PEN | INF | INF
000573 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5501 | A | 131242-WST02-DR-5501 | 2024-07-17 | IFC of SSN Electrical Building Transformer Plinth Details | Rev.0: Approved with comments. Revise and resubmit. | 2024-08-15 | 2024-09-14 | 21 | Approved with Comments | YES | 2024-10-03 | NO | Overdue | 340 |  |  | NA | "GA Drawing for Dosing Pump" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | 2026-01-20 | B | 000000&&000573&&000917 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01, NA | 4 | PEN | AWC | AWC
000574 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0006 | 0 | 131242-WSW41-VI-0006 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | APP | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | A | 131242-WSD11-DR-3000 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3001 | NA | 131242-WSD11-DR-3001 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3002 | NA | 131242-WSD11-DR-3002 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-11-11 | NA | 000000 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3003 | NA | 131242-WSD11-DR-3003 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3004 | NA | 131242-WSD11-DR-3004 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3005 | NA | 131242-WSD11-DR-3005 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2026-02-03 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3006 | NA | 131242-WSD11-DR-3006 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2024-07-17 | 2026-02-03 | B | 000000&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01 | 13 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3007 | NA | 131242-WSD11-DR-3007 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-17 | 2025-11-11 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00 | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3008 | NA | 131242-WSD11-DR-3008 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | EP | 3009 | NA | 131242-WSD11-DR-3009 | 2024-07-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-15 | 2024-08-15 |  | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-07-17 | 2025-11-28 | NA | 000000 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00 | 12 | PEN | REJ | REJ
000575 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#575 Cmt Reply Sht | NA | 131242-WSD11-NA-S#575 Cmt Reply Sht | 2024-10-01 | THP MCC Outline Drawing | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 |  | Not Approved | NO |  | YES |  |  |  |  | NA | "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-01 | NA | 000575 | 2024-10-01 | 01 | 1 | PEN | NAP | NAP
000576 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0007 | 0 | 131242-WSW41-VI-0007 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | PEN | APP | APP
000577 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0017 | 0 | 131242-WSW41-VI-0017 | 2024-07-17 | Vendor Approval for PVC Lining System - (Linabond) | Approved | 2024-08-15 | 2024-08-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | PEN | APP | APP
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | C | 131242-WST02-DR-1000_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  |  |  | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1006_ST613 | NA | 131242-WST02-DR-1006_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1007_ST613 | NA | 131242-WST02-DR-1007_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1008_ST613 | NA | 131242-WST02-DR-1008_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1013_ST613 | NA | 131242-WST02-DR-1013_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1014_ST613 | NA | 131242-WST02-DR-1014_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1015_ST613 | NA | 131242-WST02-DR-1015_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1016_ST613 | NA | 131242-WST02-DR-1016_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1017_ST613 | NA | 131242-WST02-DR-1017_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1018_ST613 | NA | 131242-WST02-DR-1018_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1019_ST613 | NA | 131242-WST02-DR-1019_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1020_ST613 | NA | 131242-WST02-DR-1020_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1021_ST613 | NA | 131242-WST02-DR-1021_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 1022_ST613 | NA | 131242-WST02-DR-1022_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3005_ST613 | NA | 131242-WST02-DR-3005_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3008_ST613 | NA | 131242-WST02-DR-3008_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 3009_ST613 | NA | 131242-WST02-DR-3009_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5005_ST613 | NA | 131242-WST02-DR-5005_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 5006_ST613 | NA | 131242-WST02-DR-5006_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7002_ST613 | NA | 131242-WST02-DR-7002_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7003_ST613 | NA | 131242-WST02-DR-7003_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7004_ST613 | NA | 131242-WST02-DR-7004_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 7005_ST613 | NA | 131242-WST02-DR-7005_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | S | 8003_ST613 | NA | 131242-WST02-DR-8003_ST613 | 2024-07-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-19 | 2024-08-21 | 2 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-01-13 | 2024-07-20 | NA | 000000 | 2024-01-13, 2024-04-04, 2024-07-20 | 00 | 3 | PEN | INF | INF
000579 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0001 | 0 | 131242-WST02-CD-0001 | 2024-07-22 | SSN PLC I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-17 | 20 | Not Approved | YES | 2024-10-07 | YES | Resubmitted |  |  |  | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | PEN | NAP | NAP
000579 | 01 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 1 | 131242-WST02-CD-0001 | 2024-11-06 | SSN RIO 0201 I/O List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-26 | 2024-12-18 | 16 | Not Approved | YES | 2025-01-08 | YES | Resubmitted |  |  |  | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | PEN | NAP | NAP
000579 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 2 | 131242-WST02-CD-0001 | 2025-03-06 | SSN RIO 0201 I/O List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-26 | 2025-05-07 | 27 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | PEN | NAP | NAP
000579 | 03 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 3 | 131242-WST02-CD-0001 | 2025-06-16 | SSN RIO 0201 I/O List | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 4 | Approved with Comments | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | PEN | AWC | AWC
000579 | 04 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 4 | 131242-WST02-CD-0001 | 2025-08-19 | SSN RIO 0201 I/O List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-15 | 5 | Approved with Comments | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | PEN | AWC | AWC
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1191 | A | 131242-WSD11-DR-1191 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 32 | Approved with Comments | YES | 2024-10-24 | NO | Overdue | 325 | 2025-02-26 | To check with relevent area discipline (Target 28 Feb 2025) | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | 2025-08-13 | A | 000000&&000580 | 2024-07-23, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 3190 | NA | 131242-WSD11-DR-3190 | 2024-07-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-21 | 2024-10-04 | 32 | Approved with Comments | YES | 2024-10-24 | NO | Overdue | 325 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-23 | 2024-07-23 | NA | 000000 | 2024-07-23 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 4000 | NA | 131242-WSD11-DR-4000 | 2024-07-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-21 | 2024-10-04 | 32 | Approved with Comments | YES | 2024-10-24 | NO | Overdue | 325 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-23 | 2024-07-23 | NA | 000000 | 2024-07-23 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 9000 | NA | 131242-WSD11-DR-9000 | 2024-07-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-21 | 2024-10-04 | 32 | Approved with Comments | YES | 2024-10-24 | NO | Overdue | 325 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-23 | 2024-07-23 | NA | 000000 | 2024-07-23 | 00 | 1 | PEN | AWC | AWC
000581 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 3100 | A.1 | 131242-WSW41-SD-3100 | 2024-07-23 | Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details | For Information | 2024-08-21 | 2024-08-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" | 2024-07-23 | 2025-12-17 | A.1 | 000000&&000581 | 2024-07-23, 2025-03-04, 2025-12-17 | 00, NA | 3 | PEN | INF | INF
000582 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 1150 | A.1 | 131242-WSW41-SD-1150 | 2024-07-23 | Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details | For Information | 2024-08-21 | 2024-08-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details" | 2024-07-23 | 2024-07-23 | A.1 | 000582 | 2024-07-23 | 00 | 1 | PEN | INF | INF
000583 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 0 | 131242-WSW41-VI-0003 | 2024-07-24 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2024-08-22 | 2024-09-02 | 7 | Not Approved | YES | 2024-09-20 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000583 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 1 | 131242-WSW41-VI-0003 | 2024-11-29 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-19 | 2025-02-25 | 44 | Not Approved | YES | 2025-03-17 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000583 | 02 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 2 | 131242-WSW41-VI-0003 | 2025-03-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-08 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000583 | 03 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 3 | 131242-WSW41-VI-0003 | 2025-06-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-09 | 2025-07-10 | 1 | Approved with Comments | YES | 2025-07-30 | NO | Overdue | 128 |  |  | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000584 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0027 | 0 | 131242-WSW41-MI-0027 | 2024-07-24 | Process & MEICA Meeting Minutes 0027_20240704 | Rev 0: For Information | 2024-08-22 | 2024-08-29 | 5 | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0027,0028_June" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | 2024-08-29 | 0 | 000000&&000562&&000584 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | PEN | INF | INF
000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0013 | 0 | 131242-WSW41-SP-0013 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | 2024-07-25 | 2024-07-25 | 0 | 000585 | 2024-07-25 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | SP | C | 0014 | NA | 131242-WSW41-SP-0014 | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-07-25 | NA | 000000 | 2024-07-25 | 00 | 1 | PEN | INF | INF
000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0016 | 0 | 131242-WSW41-SP-0016 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | 2024-07-25 | 2024-07-25 | 0 | 000586 | 2024-07-25 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | SP | C | 0017 | NA | 131242-WSW41-SP-0017 | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-07-25 | NA | 000000 | 2024-07-25 | 00 | 1 | PEN | INF | INF
000587 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0008 | 0 | 131242-WSW41-VI-0008 | 2024-07-25 | Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd. | Approved | 2024-08-23 | 2024-08-12 |  | Approved | YES | 2024-08-30 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | PEN | APP | APP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-0001_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  |  |  | NA | "THP URA Submission" | 2024-07-25 | 2025-06-23 | A | 000000&&000588 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0002_URA | NA | 131242-WSD11-DR-0002_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0003_URA | NA | 131242-WSD11-DR-0003_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-1000_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2025-06-23 | A | 000000&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1001_URA | NA | 131242-WSD11-DR-1001_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1002_URA | NA | 131242-WSD11-DR-1002_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1003_URA | NA | 131242-WSD11-DR-1003_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1004_URA | NA | 131242-WSD11-DR-1004_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 2000_URA | NA | 131242-WSD11-DR-2000_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 3000_URA | NA | 131242-WSD11-DR-3000_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 9000_URA | NA | 131242-WSD11-DR-9000_URA | 2024-07-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-23 | 2024-08-02 |  | Not Approved | YES | 2024-08-23 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | NAP | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-0001_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-12 | 2024-09-13 | 1 | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  |  |  | NA | "THP URA Submission" | 2024-07-25 | 2025-06-23 | A | 000000&&000588 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0002_URA | NA | 131242-WSD11-DR-0002_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0003_URA | NA | 131242-WSD11-DR-0003_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-1000_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2025-06-23 | A | 000000&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1001_URA | NA | 131242-WSD11-DR-1001_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1002_URA | NA | 131242-WSD11-DR-1002_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1003_URA | NA | 131242-WSD11-DR-1003_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1004_URA | NA | 131242-WSD11-DR-1004_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 2000_URA | NA | 131242-WSD11-DR-2000_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 3000_URA | NA | 131242-WSD11-DR-3000_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 9000_URA | NA | 131242-WSD11-DR-9000_URA | 2024-08-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | NAP | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-0001_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-10-29 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "THP URA Submission" | 2024-07-25 | 2025-06-23 | A | 000000&&000588 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0002_URA | NA | 131242-WSD11-DR-0002_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 0003_URA | NA | 131242-WSD11-DR-0003_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-1000_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2025-06-23 | A | 000000&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1001_URA | NA | 131242-WSD11-DR-1001_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1002_URA | NA | 131242-WSD11-DR-1002_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1003_URA | NA | 131242-WSD11-DR-1003_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 1004_URA | NA | 131242-WSD11-DR-1004_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 2000_URA | NA | 131242-WSD11-DR-2000_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2025-06-23 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 3000_URA | NA | 131242-WSD11-DR-3000_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | A | 9000_URA | NA | 131242-WSD11-DR-9000_URA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-29 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-25 | 2024-10-09 | NA | 000000 | 2024-07-25, 2024-08-24, 2024-10-09 | 00 | 3 | PEN | AWC | AWC
000589 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 0 | 131242-WST02-VI-0007 | 2024-07-26 | Vendor Approval of Earthing System & LPS Material | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached sheet for comments | 2024-08-26 | 2024-08-05 |  | Approved with Comments | YES | 2024-08-26 | YES | Resubmitted |  |  |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | AWC | AWC
000589 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 1 | 131242-WST02-VI-0007 | 2024-09-02 | Vendor Approval of Earthing System & LPS Material (Heng) | Rev 1: Approved. | 2024-09-20 | 2024-10-29 | 27 | Approved | NO |  | YES |  |  |  |  | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | PEN | APP | APP
000590 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 0 | 131242-WST02-DS-0004 | 2024-07-27 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 |  | Rejected | YES | 2024-09-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | 2025-04-25 | 0 | 000000&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | PEN | REJ | REJ
000590 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 1 | 131242-WST02-DS-0004 | 2024-12-02 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-20 | 2025-01-16 | 17 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | TBA |  | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | 2025-04-25 | 0 | 000000&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | PEN | AWC | AWC
000590 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 2 | 131242-WST02-DS-0004 | 2025-04-09 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-29 | 2025-05-08 | 6 | Approved with Comments | YES | 2025-05-28 | NO | Overdue | 173 |  | Pending reply from Sunlight. Will follow-up with Sunlight. | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | 2025-04-25 | 0 | 000000&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | PEN | AWC | AWC
000591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 0 | 131242-WSD11-CL-0003 | 2024-07-28 | PLant Drain Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-08-26 | 2024-09-02 | 5 | Not Approved | YES | 2024-09-20 | YES | Resubmitted |  |  |  | NA | "PLant Drain Hydraulic Calculation" | 2024-07-28 | 2024-10-21 | 1 | 000591 | 2024-07-28, 2024-10-21 | 00, 01 | 2 | PEN | NAP | NAP
000591 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 1 | 131242-WSD11-CL-0003 | 2024-10-21 | PLant Drain Hydraulic Calculation | Rev 1: Approved | 2024-11-11 | 2024-11-15 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "PLant Drain Hydraulic Calculation" | 2024-07-28 | 2024-10-21 | 1 | 000591 | 2024-07-28, 2024-10-21 | 00, 01 | 2 | PEN | APP | APP
000592 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0006 | 0 | 131242-WST02-VI-0006 | 2024-07-28 | Vendor Approval of SS Cable Ladder, Trays and Accessories | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 |  | Approved with Comments | YES | 2024-09-04 | NO | Overdue | 361 |  | To follow-up with UNITED ULI. | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | PEN | AWC | AWC
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5351 | 0 | 131242-WST02-DS-5351 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 32 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5361 | NA | 131242-WST02-DS-5361 | 2024-07-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-26 | 2024-10-09 | 32 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5371 | NA | 131242-WST02-DS-5371 | 2024-07-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-26 | 2024-10-09 | 32 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5381 | NA | 131242-WST02-DS-5381 | 2024-07-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-26 | 2024-10-09 | 32 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5351 | 1 | 131242-WST02-DS-5351 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 56 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5361 | NA | 131242-WST02-DS-5361 | 2024-12-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-13 | 2025-04-05 | 56 | Approved with Comments | YES | 2025-04-24 | NO | Overdue | 197 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5371 | NA | 131242-WST02-DS-5371 | 2024-12-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-13 | 2025-04-05 | 56 | Approved with Comments | YES | 2025-04-24 | NO | Overdue | 197 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DS | M | 5381 | NA | 131242-WST02-DS-5381 | 2024-12-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-13 | 2025-04-05 | 56 | Approved with Comments | YES | 2025-04-24 | NO | Overdue | 197 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-28 | 2024-12-23 | NA | 000000 | 2024-07-28, 2024-12-23 | 00 | 2 | PEN | AWC | AWC
000594 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0003 | 0 | 131242-WSW41-PO-0003 | 2024-07-29 | Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight) | Rev 0: For Information. | 2024-08-27 | 2024-08-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" && "Unpriced PO for Non-return Check Valve (Breen International)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-07-29 | 2025-08-01 | 0 | 000594&&001502&&001514 | 2024-07-29, 2025-07-22, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000595 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0007 | 0 | 131242-WSW41-PO-0007 | 2024-07-30 | Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen) | For Information | 2024-08-28 | 2024-08-29 | 1 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Support System (Jiangsu HDMann) " && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | 2025-08-01 | 0 | 000595&&001115&&001506 | 2024-07-30, 2025-03-11, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000596 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0035 | 0 | 131242-WSW41-LT-0035 | 2024-07-30 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024 | Please refer to S.O. Correspondence No.229. | 2024-08-28 | 2024-10-07 | 28 | Approved | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024" | 2024-07-30 | 2024-07-30 | 0 | 000596 | 2024-07-30 | 00 | 1 | PEN | APP | APP
000597 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 0 | 131242-WSD11-CL-0006 | 2024-07-30 | Air Compressor Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-04 | 5 | Approved with Comments | YES | 2024-09-24 | YES | Resubmitted |  |  |  | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | PEN | AWC | AWC
000597 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 1 | 131242-WSD11-CL-0006 | 2024-09-30 | Air Compressor Pressure Loss Calculation | Rev 1: Approved with Comments. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 11 | Approved with Comments | YES | 2024-11-25 | NO | Overdue | 304 |  |  | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | PEN | AWC | AWC
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5009 | A | 131242-WST02-DR-5009 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 3 | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 | 2025-03-07 | Shall update and submit under as built drawing | NA | "Underground Cast In Schedule and Details" | 2024-07-30 | 2024-07-30 | A | 000598 | 2024-07-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | M | 5010 | NA | 131242-WST02-DR-5010 | 2024-07-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-28 | 2024-09-02 | 3 | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-30 | 2024-07-30 | NA | 000000 | 2024-07-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7008 | NA | 131242-WST02-SH-7008 | 2024-07-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-28 | 2024-09-02 | 3 | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-30 | 2024-07-30 | NA | 000000 | 2024-07-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SH | M | 7009 | NA | 131242-WST02-SH-7009 | 2024-07-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-28 | 2024-09-02 | 3 | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-30 | 2024-07-30 | NA | 000000 | 2024-07-30 | 00 | 1 | PEN | AWC | AWC
000599 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 0 | 131242-WSW41-VI-0004 | 2024-07-30 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-28 | 2024-10-10 | 31 | Not Approved | YES | 2024-10-30 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | PEN | NAP | NAP
000599 | 01 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 1 | 131242-WSW41-VI-0004 | 2024-11-02 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-21 | 2024-12-18 | 19 | Not Approved | YES | 2025-01-08 | NO | Overdue | 273 |  |  | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | PEN | NAP | NAP
000600 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0004 | 0 | 131242-WSW41-QA-0004 | 2024-07-31 | Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings | Rev 0: Approved | 2024-08-29 | 2024-09-02 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | APP | APP
000601 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 0 | 131242-WSD11-SP-0001 | 2024-07-31 | THP Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-29 | 2024-10-09 | 29 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | PEN | AWC | AWC
000601 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 1 | 131242-WSD11-SP-0001 | 2025-05-19 | THP Functional Design Specification | Rev.1: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-06-06 | 2025-07-04 | 20 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | PEN | AWC | AWC
000601 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 2 | 131242-WSD11-SP-0001 | 2025-08-12 | THP Functional Design Specification | Rev.2: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-09-01 | 2025-10-08 | 27 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | PEN | AWC | AWC
000602 | 00 | Low | EICA | NA | 131242 | WSD11 | SP | I | 0003 | 0 | 131242-WSD11-SP-0003 | 2024-07-31 | THP Alarm List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-29 | 2024-11-08 | 50 | Not Approved | YES | 2024-11-28 | NO | Overdue | 301 |  |  | NA | "THP Alarm List" | 2024-07-31 | 2024-07-31 | 0 | 000602 | 2024-07-31 | 00 | 1 | PEN | NAP | NAP
000603 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1000 | 0 | 131242-WST02-CL-1000 | 2024-07-31 | SSN Underground Piping Stress Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-08-29 | 2024-09-02 | 2 | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 |  | The Only comment is to get PE endorsement (Mech Piping PE) | NA | "SSN Underground Piping Stress Calculation Report" | 2024-07-31 | 2026-02-24 | 0 | 000000&&000603 | 2024-07-31, 2026-02-24 | 00, NA | 2 | PEN | AWC | AWC
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | A | 131242-WST02-DR-7000 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7001 | NA | 131242-WST02-DR-7001 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7002 | NA | 131242-WST02-DR-7002 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7003 | NA | 131242-WST02-DR-7003 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7004 | NA | 131242-WST02-DR-7004 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7005 | NA | 131242-WST02-DR-7005 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7006 | NA | 131242-WST02-DR-7006 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7007 | NA | 131242-WST02-DR-7007 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7008 | NA | 131242-WST02-DR-7008 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7009 | NA | 131242-WST02-DR-7009 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7010 | NA | 131242-WST02-DR-7010 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7011 | NA | 131242-WST02-DR-7011 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7020 | NA | 131242-WST02-DR-7020 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Control Network Connection Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7021 | NA | 131242-WST02-DR-7021 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7022 | NA | 131242-WST02-DR-7022 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7023 | NA | 131242-WST02-DR-7023 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7024 | NA | 131242-WST02-DR-7024 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7025 | NA | 131242-WST02-DR-7025 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7026 | NA | 131242-WST02-DR-7026 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7027 | NA | 131242-WST02-DR-7027 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7028 | NA | 131242-WST02-DR-7028 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7029 | NA | 131242-WST02-DR-7029 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 4 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7030 | NA | 131242-WST02-DR-7030 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00 | 4 | PEN | REJ | REJ
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | A | 131242-WST02-DR-7100 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7101 | NA | 131242-WST02-DR-7101 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7102 | NA | 131242-WST02-DR-7102 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7103 | NA | 131242-WST02-DR-7103 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7104 | NA | 131242-WST02-DR-7104 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7105 | NA | 131242-WST02-DR-7105 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7106 | NA | 131242-WST02-DR-7106 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7107 | NA | 131242-WST02-DR-7107 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7108 | NA | 131242-WST02-DR-7108 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7109 | NA | 131242-WST02-DR-7109 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | B | 131242-WST02-DR-7000 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7001 | NA | 131242-WST02-DR-7001 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7002 | NA | 131242-WST02-DR-7002 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7003 | NA | 131242-WST02-DR-7003 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7004 | NA | 131242-WST02-DR-7004 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7005 | NA | 131242-WST02-DR-7005 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7006 | NA | 131242-WST02-DR-7006 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7007 | NA | 131242-WST02-DR-7007 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7008 | NA | 131242-WST02-DR-7008 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7009 | NA | 131242-WST02-DR-7009 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7010 | NA | 131242-WST02-DR-7010 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7011 | NA | 131242-WST02-DR-7011 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-08 | 2026-02-03 | NA | 000000 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 16 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7020 | NA | 131242-WST02-DR-7020 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Control Network Connection Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7021 | NA | 131242-WST02-DR-7021 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7022 | NA | 131242-WST02-DR-7022 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7023 | NA | 131242-WST02-DR-7023 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7024 | NA | 131242-WST02-DR-7024 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7025 | NA | 131242-WST02-DR-7025 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7026 | NA | 131242-WST02-DR-7026 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7027 | NA | 131242-WST02-DR-7027 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7028 | NA | 131242-WST02-DR-7028 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7029 | NA | 131242-WST02-DR-7029 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7030 | NA | 131242-WST02-DR-7030 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3000 | NA | 131242-WST02-DR-3000 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3001 | NA | 131242-WST02-DR-3001 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3002 | NA | 131242-WST02-DR-3002 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3003 | NA | 131242-WST02-DR-3003 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3004 | NA | 131242-WST02-DR-3004 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3005 | NA | 131242-WST02-DR-3005 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3006 | NA | 131242-WST02-DR-3006 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3007 | NA | 131242-WST02-DR-3007 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7100 | NA | 131242-WST02-DR-7100 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7101 | NA | 131242-WST02-DR-7101 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7102 | NA | 131242-WST02-DR-7102 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7103 | NA | 131242-WST02-DR-7103 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7104 | NA | 131242-WST02-DR-7104 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7105 | NA | 131242-WST02-DR-7105 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7106 | NA | 131242-WST02-DR-7106 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7107 | NA | 131242-WST02-DR-7107 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7108 | NA | 131242-WST02-DR-7108 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7109 | NA | 131242-WST02-DR-7109 | 2024-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-11 | 2024-12-30 | 12 | Not Approved | YES | 2025-01-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | C | 131242-WST02-DR-7000 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | TBA |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7001 | NA | 131242-WST02-DR-7001 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7002 | NA | 131242-WST02-DR-7002 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7003 | NA | 131242-WST02-DR-7003 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7004 | NA | 131242-WST02-DR-7004 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7005 | NA | 131242-WST02-DR-7005 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7006 | NA | 131242-WST02-DR-7006 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7007 | NA | 131242-WST02-DR-7007 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7008 | NA | 131242-WST02-DR-7008 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7009 | NA | 131242-WST02-DR-7009 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7010 | NA | 131242-WST02-DR-7010 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7020 | NA | 131242-WST02-DR-7020 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Control Network Connection Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7021 | NA | 131242-WST02-DR-7021 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7022 | NA | 131242-WST02-DR-7022 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7023 | NA | 131242-WST02-DR-7023 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7024 | NA | 131242-WST02-DR-7024 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7025 | NA | 131242-WST02-DR-7025 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7026 | NA | 131242-WST02-DR-7026 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7027 | NA | 131242-WST02-DR-7027 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7028 | NA | 131242-WST02-DR-7028 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7029 | NA | 131242-WST02-DR-7029 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3000 | NA | 131242-WST02-DR-3000 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3001 | NA | 131242-WST02-DR-3001 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3002 | NA | 131242-WST02-DR-3002 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3003 | NA | 131242-WST02-DR-3003 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3004 | NA | 131242-WST02-DR-3004 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3005 | NA | 131242-WST02-DR-3005 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3006 | NA | 131242-WST02-DR-3006 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3007 | NA | 131242-WST02-DR-3007 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7100 | NA | 131242-WST02-DR-7100 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7101 | NA | 131242-WST02-DR-7101 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7102 | NA | 131242-WST02-DR-7102 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7103 | NA | 131242-WST02-DR-7103 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7104 | NA | 131242-WST02-DR-7104 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7105 | NA | 131242-WST02-DR-7105 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7106 | NA | 131242-WST02-DR-7106 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7107 | NA | 131242-WST02-DR-7107 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7108 | NA | 131242-WST02-DR-7108 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7109 | NA | 131242-WST02-DR-7109 | 2025-01-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-02-10 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | D | 131242-WST02-DR-7000 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | TBA |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2025-10-29 | A.2 | 000000&&000188&&000189&&000201&&000219&&000220&&000401&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03 | 24 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7001 | NA | 131242-WST02-DR-7001 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | " THP Overall Network Diagrams" && "Panel GA & Wiring drawing for BS Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Over All Network Archtecture Drawings" && "SSN PFD" | 2023-11-15 | 2025-10-29 | A | 000000&&000360&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7002 | NA | 131242-WST02-DR-7002 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7003 | NA | 131242-WST02-DR-7003 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | 2025-10-28 | C | 000000&&000308 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02 | 18 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7004 | NA | 131242-WST02-DR-7004 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-18 | NA | 000000 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00 | 13 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7005 | NA | 131242-WST02-DR-7005 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | 2025-05-18 | A | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7006 | NA | 131242-WST02-DR-7006 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2025-05-04 | NA | 000000 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00 | 11 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7007 | NA | 131242-WST02-DR-7007 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN IO Sample Schematic Drawing" | 2023-11-30 | 2025-05-04 | B | 000000&&000441 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01 | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7008 | NA | 131242-WST02-DR-7008 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-06 | 2025-05-04 | NA | 000000 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00 | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7009 | NA | 131242-WST02-DR-7009 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7010 | NA | 131242-WST02-DR-7010 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-03 | 2026-02-03 | 0 | 000000&&000440 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, NA | 19 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7020 | NA | 131242-WST02-DR-7020 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Control Network Connection Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7021 | NA | 131242-WST02-DR-7021 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7022 | NA | 131242-WST02-DR-7022 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7023 | NA | 131242-WST02-DR-7023 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7024 | NA | 131242-WST02-DR-7024 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7025 | NA | 131242-WST02-DR-7025 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7026 | NA | 131242-WST02-DR-7026 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7027 | NA | 131242-WST02-DR-7027 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7028 | NA | 131242-WST02-DR-7028 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 6 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EI | 7029 | NA | 131242-WST02-DR-7029 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3000 | NA | 131242-WST02-DR-3000 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3001 | NA | 131242-WST02-DR-3001 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3002 | NA | 131242-WST02-DR-3002 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3003 | NA | 131242-WST02-DR-3003 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3004 | NA | 131242-WST02-DR-3004 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3005 | NA | 131242-WST02-DR-3005 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3006 | NA | 131242-WST02-DR-3006 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3007 | NA | 131242-WST02-DR-3007 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7100 | NA | 131242-WST02-DR-7100 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7101 | NA | 131242-WST02-DR-7101 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7102 | NA | 131242-WST02-DR-7102 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7103 | NA | 131242-WST02-DR-7103 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7104 | NA | 131242-WST02-DR-7104 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7105 | NA | 131242-WST02-DR-7105 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7106 | NA | 131242-WST02-DR-7106 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7107 | NA | 131242-WST02-DR-7107 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7108 | NA | 131242-WST02-DR-7108 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 7109 | NA | 131242-WST02-DR-7109 | 2025-05-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-05-22 | 2025-05-25 | 1 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | APP | APP
000606 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 0 | 131242-WST02-VI-0008 | 2024-08-01 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-24 | 17 | Approved with Comments | YES | 2024-10-14 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | PEN | AWC | AWC
000606 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 1 | 131242-WST02-VI-0008 | 2024-10-28 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 1: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2024-11-18 | 2024-11-24 | 4 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | PEN | AWC | AWC
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | A | 131242-WST02-DR-3000 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3001 | NA | 131242-WST02-DR-3001 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3002 | NA | 131242-WST02-DR-3002 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3003 | NA | 131242-WST02-DR-3003 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3004 | NA | 131242-WST02-DR-3004 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3005 | NA | 131242-WST02-DR-3005 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3006 | NA | 131242-WST02-DR-3006 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | DR | EP | 3007 | NA | 131242-WST02-DR-3007 | 2024-08-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-08-30 | 2024-09-18 | 13 | Rejected | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | REJ | REJ
000608 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0008 | 0 | 131242-WSW41-PO-0008 | 2024-08-01 | Unpriced PO for Centrifugal Pump (KSB) | For Information | 2024-08-30 | 2024-08-29 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" && "Unpriced PO for Centrifugal Pump (KSB)" && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2024-08-01 | 2025-08-01 | 0 | 000608&&001163&&001507 | 2024-08-01, 2025-03-25, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000609 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0009 | 0 | 131242-WSW41-PO-0009 | 2024-08-01 | Unpriced PO for FRP Tank (Jizhou Zhongyi) | For Information | 2024-08-30 | 2024-08-29 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" && "Unpriced PO for FRP Tank (Jizhou Zhongyi)" && "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2024-08-01 | 2025-08-01 | 0 | 000609&&001286&&001508 | 2024-08-01, 2025-05-13, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000610 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | K | 2001 | 0 | 131242-WST02-VI-2001 | 2024-08-01 | LPS Sample Materials – U-Clamp Connector | Rev 0: Approved. Please refer to attached sheet for comments | 2024-08-30 | 2024-08-05 |  | Approved | NO |  | YES |  |  |  |  | NA | "LPS Sample Materials – U-Clamp Connector" | 2024-08-01 | 2024-08-01 | 0 | 000610 | 2024-08-01 | 00 | 1 | PEN | APP | APP
000611 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 0 | 131242-WSW41-SP-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-02 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | 2024-08-02 | 0 | 000611 | 2024-08-02 | 00, 01 | 2 | PEN | AWC | AWC
000611 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 1 | 131242-WSW41-SP-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Approved | 2024-08-23 | 2024-09-17 | 17 | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | 2024-08-02 | 0 | 000611 | 2024-08-02 | 00, 01 | 2 | PEN | APP | APP
000612 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0005 | 0 | 131242-WSW41-QA-0005 | 2024-08-02 | Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings | Rev 0: Approved | 2024-09-02 | 2024-09-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | PEN | APP | APP
000613 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0013 | 0 | 131242-WSW41-PC-0013 | 2024-08-02 | Payment Claim No.13 | Rev(0): Approved. Please refer to S.O. correspondence no. 0196 dated 5 August 2024. | 2024-09-02 | 2024-08-16 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.13" | 2024-08-02 | 2024-08-02 | 0 | 000613 | 2024-08-02 | 00 | 1 | PEN | APP | APP
000614 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0036 | 0 | 131242-WSW41-LT-0036 | 2024-08-02 | NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions | Please refer to S.O. Correspondence No.229. | 2024-09-02 | 2024-10-07 | 25 | Approved | NO |  | YES |  |  |  |  | NA | "NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions" | 2024-08-02 | 2024-08-02 | 0 | 000614 | 2024-08-02 | 00 | 1 | PEN | APP | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-1100 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  |  |  | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-27 | A.2 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 1104 | NA | 131242-WST02-SD-1104 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5100 | NA | 131242-WST02-SD-5100 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-04-08 | NA | 000000 | 2024-08-05, 2024-08-27, 2025-04-08 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5101 | NA | 131242-WST02-SD-5101 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-04-08 | NA | 000000 | 2024-08-05, 2024-08-27, 2025-04-08 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5102 | NA | 131242-WST02-SD-5102 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5103 | NA | 131242-WST02-SD-5103 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5104 | NA | 131242-WST02-SD-5104 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | AWC | AWC
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-1100 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-16 | 2024-09-10 |  | Approved | NO |  | YES |  |  |  |  | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-27 | A.2 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 1104 | NA | 131242-WST02-SD-1104 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5100 | NA | 131242-WST02-SD-5100 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-04-08 | NA | 000000 | 2024-08-05, 2024-08-27, 2025-04-08 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5101 | NA | 131242-WST02-SD-5101 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-04-08 | NA | 000000 | 2024-08-05, 2024-08-27, 2025-04-08 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5102 | NA | 131242-WST02-SD-5102 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5103 | NA | 131242-WST02-SD-5103 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | BS | NA | 131242 | WST02 | SD | S | 5104 | NA | 131242-WST02-SD-5104 | 2024-08-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-24 | 2024-09-10 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-27 | NA | 000000 | 2024-08-05, 2024-08-27 | 00 | 2 | PEN | APP | APP
000616 | 00 | Qili | Process | NA | 131242 | WST02 | CL | M | 0002 | 0 | 131242-WST02-CL-0002 | 2024-08-05 | Strength Calculation for Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-02 |  | Approved with Comments | YES | 2024-09-20 | NO | Overdue | 349 | 2025-02-28 | Pending MP updates | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | PEN | AWC | AWC
000617 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0009 | 0 | 131242-WSW41-PS-0009 | 2024-08-05 | Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024 | For Information | 2024-09-03 | 2024-08-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-05 | 0 | 000000&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | PEN | INF | INF
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | A | 131242-WSD11-DR-5051 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  |  |  | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5052 | NA | 131242-WSD11-DR-5052 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5053 | NA | 131242-WSD11-DR-5053 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5054 | NA | 131242-WSD11-DR-5054 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5071 | NA | 131242-WSD11-DR-5071 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5072 | NA | 131242-WSD11-DR-5072 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5073 | NA | 131242-WSD11-DR-5073 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5081 | NA | 131242-WSD11-DR-5081 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-09-05 | 2 | Approved with Comments | YES | 2024-09-25 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | B | 131242-WSD11-DR-5051 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2025-01-13 | 42 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | 2025-03-07 | All comments on 2D Drawing (Mech/Elec.) was closed, minor cmt on 3D, need QA/QC checklist, Drafting team will follow up..-> in 1 to 2 weeks | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5052 | NA | 131242-WSD11-DR-5052 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5053 | NA | 131242-WSD11-DR-5053 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5054 | NA | 131242-WSD11-DR-5054 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5071 | NA | 131242-WSD11-DR-5071 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5072 | NA | 131242-WSD11-DR-5072 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5073 | NA | 131242-WSD11-DR-5073 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5081 | NA | 131242-WSD11-DR-5081 | 2024-10-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-20 | 2025-01-13 | 36 | Approved with Comments | YES | 2025-01-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | AWC | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | C | 131242-WSD11-DR-5051 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-02 |  | 167 | Awaiting S.O.'s response | [7 empty] | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5052 | NA | 131242-WSD11-DR-5052 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5053 | NA | 131242-WSD11-DR-5053 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5054 | NA | 131242-WSD11-DR-5054 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5071 | NA | 131242-WSD11-DR-5071 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5072 | NA | 131242-WSD11-DR-5072 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5073 | NA | 131242-WSD11-DR-5073 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSD11 | DR | M | 5081 | NA | 131242-WSD11-DR-5081 | 2025-05-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-06-10 | 2025-01-13 | 161 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2025-05-13 | NA | 000000 | 2024-08-05, 2024-10-22, 2025-05-13 | 00 | 3 | PEN | PEN | PEN
000619 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0006 | 0 | 131242-WSW41-RT-0006 | 2024-08-05 | Bored Piling Pile Eccentricity Reports (ECC 01 to 07) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 |  | Not Approved | YES | 2024-09-06 | NO | Overdue | 359 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" && "C4B Monthly Progress Report Number No.06 (10/23)" | 2023-11-08 | 2024-08-05 | 0 | 000174&&000619 | 2023-11-08, 2024-08-05 | 00 | 2 | PEN | NAP | NAP
000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0015 | 0 | 131242-WSW41-SP-0015 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | 2024-08-05 | 2024-08-05 | 0 | 000620 | 2024-08-05 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | BS | NA | 131242 | WSW41 | SP | C | 0018 | NA | 131242-WSW41-SP-0018 | 2024-08-05 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-03 | 2024-08-19 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-05 | 2024-08-05 | NA | 000000 | 2024-08-05 | 00 | 1 | PEN | INF | INF
000621 | 00 | Qili | Process | NA | 131242 | WST02 | MM | P | 0001 | 0 | 131242-WST02-MM-0001 | 2024-08-05 | SSN Reactor Floor flat Design Memo | For Information | 2024-09-03 | 2024-08-21 |  | For Information | NO |  | YES |  |  |  |  | NA | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " && "SSN Reactor Floor flat Design Memo" | 2024-08-05 | 2025-07-22 | 1 | 000621&&001188 | 2024-08-05, 2025-04-03, 2025-07-22 | 00, 01 | 3 | PEN | INF | INF
000622 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0028 | 0 | 131242-WSW41-MI-0028 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | 2024-08-06 | 0 | 000000&&000558&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0029 | NA | 131242-WSW41-MI-0029 | 2024-08-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-04 | 2024-08-15 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000683 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000623 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 0 | 131242-WSW41-QA-0001 | 2024-08-06 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-10-29 | 39 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | AWC | AWC
000623 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 1 | 131242-WSW41-QA-0001 | 2024-11-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-14 | 2 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | AWC | AWC
000623 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 2 | 131242-WSW41-QA-0001 | 2025-01-16 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 9 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | APP | APP
000623 | 03 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 3 | 131242-WSW41-QA-0001 | 2025-02-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 3: Approved. | 2025-03-13 | 2025-04-27 | 29 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | APP | APP
000623 | 04 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 4 | 131242-WSW41-QA-0001 | 2025-07-03 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 4: Approved with comments. To revise and resubmit. | 2025-07-23 | 2025-09-15 | 38 | Approved with Comments | YES | 2025-10-03 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | AWC | AWC
000623 | 05 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 5 | 131242-WSW41-QA-0001 | 2025-10-08 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 5: Approved | 2025-10-28 | 2026-02-20 | 82 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | APP | APP
000624 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 0 | 131242-WSW41-QA-0003 | 2024-08-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 0: Not approved - Revise and Resubmit | 2024-09-04 | 2024-09-06 | 2 | Not Approved | YES | 2024-09-26 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000624 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 1 | 131242-WSW41-QA-0003 | 2024-10-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 1: Not approved - Revise and Resubmit | 2024-10-29 | 2024-10-25 |  | Not Approved | YES | 2024-11-15 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | NAP | NAP
000624 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 2 | 131242-WSW41-QA-0003 | 2024-11-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 2: Approved | 2024-12-11 | 2024-12-05 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000625 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0007 | 0 | 131242-WSW41-QA-0007 | 2024-08-06 | FAT Procedure for Air Receiver and Air Dryer (Compressor air system) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-09-04 |  | Approved with Comments | YES | 2024-09-24 | NO | Overdue | 347 |  |  | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | PEN | AWC | AWC
000626 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 0 | 131242-WST02-DS-0000 | 2024-08-07 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-05 | 2024-10-29 | 38 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-08-07 | 2024-12-19 | 1 | 000626 | 2024-08-07, 2024-12-19 | 00, 01 | 2 | PEN | AWC | AWC
000626 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 1 | 131242-WST02-DS-0000 | 2024-12-19 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-01-16 | 5 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 |  |  | NA | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-08-07 | 2024-12-19 | 1 | 000626 | 2024-08-07, 2024-12-19 | 00, 01 | 2 | PEN | AWC | AWC
000627 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0011 | 0 | 131242-WSW41-QA-0011 | 2024-08-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | NO | Overdue | 359 |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | PEN | AWC | AWC
000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0013 | 0 | 131242-WSW41-MI-0013 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-14 | 2024-08-07 | 0 | 000000&&000184&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | PS | PM | 0013 | NA | 131242-WSW41-PS-0013 | 2024-08-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-05 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Incentive/ Disincentive Audit Scheme for Jun 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-07 | 2024-08-22 | 0 | 000000&&000669 | 2024-08-07, 2024-08-22 | 00 | 2 | PEN | INF | INF
000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0014 | 0 | 131242-WSW41-MI-0014 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | PS | PM | 0014 | NA | 131242-WSW41-PS-0014 | 2024-08-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-05 | 2024-08-12 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Incentive/ Disincentive Audit Scheme for Jul 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-07 | 2024-10-14 | 0 | 000000&&000760 | 2024-08-07, 2024-10-14 | 00 | 2 | PEN | INF | INF
000630 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 0 | 131242-WSW41-SP-0020 | 2024-08-07 | Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | YES | Resubmitted |  |  |  | NA | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-08-07 | 2024-10-02 | 1 | 000630 | 2024-08-07, 2024-10-02 | 00, 01 | 2 | PEN | AWC | AWC
000630 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 1 | 131242-WSW41-SP-0020 | 2024-10-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.1: Approved | 2024-10-22 | 2024-10-14 |  | Approved | NO |  | YES |  |  |  |  | NA | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-08-07 | 2024-10-02 | 1 | 000630 | 2024-08-07, 2024-10-02 | 00, 01 | 2 | PEN | APP | APP
000631 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jul-2024) | Resubmit: Considering the VCM submitted only contains link, Contractor to provide full list of contents (from the link) per folder/zip file with file size and timestamp (Transmittal Cover). Also, Contractor to ensure that the link provided should be Contractor's OneDrive link or link to Contractor's CDE. | 2024-08-05 | 2024-08-08 | 3 | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | PEN | INF | INF
000631 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-0041 | 2024-08-12 | Submission Of BIM Coordination VCM Model (Jul-2024) | For Information | 2024-08-30 | 2024-08-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | PEN | INF | INF
000632 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0016 | 0 | 131242-WSW41-MS-0016 | 2024-08-12 | MSRA, SWP for Erection, Dismantling and Use of Scaffold | Approved | 2024-09-09 | 2024-08-30 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA for MCCB Replacement Works" && "MSRA, SWP for Erection, Dismantling and Use of Scaffold " && "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | 2024-08-12 | 2025-10-28 | 0 | 000632&&001797&&001798 | 2024-08-12, 2025-10-28 | 00 | 3 | PEN | APP | APP
000633 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0017 | 0 | 131242-WSW41-MS-0017 | 2024-08-12 | MSRA, SWP for Jet Grouting | Approved | 2024-09-09 | 2024-09-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA & Safe Work Procedure For NDT Activities" && "MSRA, SWP for Jet Grouting" | 2024-08-12 | 2025-10-31 | 0 | 000633&&001811 | 2024-08-12, 2025-10-31 | 00 | 2 | PEN | APP | APP
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0010 | 0 | 131242-WSD11-DS-0010 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0012 | NA | 131242-WSD11-DS-0012 | 2024-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Data Sheet of Desuperheater " && "Datasheet for Thermal Flow Switch (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-12 | 2026-01-15 | 0 | 000000&&000648&&001956 | 2024-08-12, 2026-01-15 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0013 | NA | 131242-WSD11-DS-0013 | 2024-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-05 | 2026-01-15 | A | 000000&&000421&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0014 | NA | 131242-WSD11-DS-0014 | 2024-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-06 | 2026-01-20 | 0 | 000000&&000422&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0015 | NA | 131242-WSD11-DS-0015 | 2024-08-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-09 | 2024-10-29 | 36 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 | Tenwit in Progress |  | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-12 | 2026-01-29 | 0 | 000000&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | PEN | AWC | AWC
000635 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 0 | 131242-WSD11-DS-0015 | 2024-08-12 | Data Sheet of Flash Tank Discharge Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 22 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-12 | 2026-01-29 | 0 | 000000&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | PEN | AWC | AWC
000635 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 1 | 131242-WSD11-DS-0015 | 2024-11-13 | Data Sheet of Flash Tank Discharge Pump | Rev 1: Approved | 2024-12-03 | 2024-12-06 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-12 | 2026-01-29 | 0 | 000000&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | PEN | APP | APP
000636 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 0 | 131242-WSD11-DS-0016 | 2024-08-12 | Data Sheet of Precooler S2 CIRC Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 22 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Precooler S2 CIRC Pump" && "Datasheet for Pressure Transmitter (THP-BOP) " | 2024-08-12 | 2026-01-30 | 0 | 000636&&001999 | 2024-08-12, 2024-11-13, 2026-01-30 | 00, 01 | 3 | PEN | AWC | AWC
000636 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 1 | 131242-WSD11-DS-0016 | 2024-11-13 | Data Sheet of Precooler S2 CIRC Pump | Rev 1: Approved | 2024-12-03 | 2024-06-12 |  | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of Precooler S2 CIRC Pump" && "Datasheet for Pressure Transmitter (THP-BOP) " | 2024-08-12 | 2026-01-30 | 0 | 000636&&001999 | 2024-08-12, 2024-11-13, 2026-01-30 | 00, 01 | 3 | PEN | APP | APP
000637 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 0 | 131242-WSD11-DS-0017 | 2024-08-12 | Data Sheet of Digester Feed Pump | Rev 0: Not approved - Revise and Resubmit | 2024-09-09 | 2024-10-09 | 22 | Not Approved | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Digester Feed Pump" && "Datasheet for Temperature Sensor (THP-BOP) " | 2024-08-12 | 2026-03-02 | 0 | 000637&&002020 | 2024-08-12, 2025-03-04, 2026-03-02 | 00, 01 | 3 | PEN | NAP | NAP
000637 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 1 | 131242-WSD11-DS-0017 | 2025-03-04 | Data Sheet of Digester Feed Pump | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 136 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of Digester Feed Pump" && "Datasheet for Temperature Sensor (THP-BOP) " | 2024-08-12 | 2026-03-02 | 0 | 000637&&002020 | 2024-08-12, 2025-03-04, 2026-03-02 | 00, 01 | 3 | PEN | APP | APP
000638 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0018 | 0 | 131242-WSW41-VI-0018 | 2024-08-13 | Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-08-19 |  | Approved with Comments | YES | 2024-09-06 | NO | Overdue | 359 |  |  | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | PEN | AWC | AWC
000639 | 00 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 0 | 131242-WST02-SP-0002 | 2024-08-13 | SSN Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-10-09 | 21 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | PEN | AWC | AWC
000639 | 01 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 1 | 131242-WST02-SP-0002 | 2025-02-21 | SSN Functional Design Specification | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-13 | 2025-03-13 |  | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | PEN | AWC | AWC
000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1165 | A | 131242-WSD11-DR-1165 | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | 21 | Approved with Comments | YES | 2024-10-29 | NO | Overdue | 322 | 2025-02-28 | 2nd priority (Shall update and submit under as built drawing) | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Piping General Arrangement of Air Compressor system" | 2024-08-13 | 2025-08-13 | A | 000000&&000640 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1166 | NA | 131242-WSD11-DR-1166 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-10-09 | 21 | Approved with Comments | YES | 2024-10-29 | NO | Overdue | 322 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2025-08-13 | NA | 000000 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | AWC | AWC
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612_BCA | F | 131242-WST02-DR-5600_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | 2024-08-13 | F | 000641 | 2024-08-13 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5601_ST612_BCA | NA | 131242-WST02-DR-5601_ST612_BCA | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-08-30 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2024-08-13 | NA | 000000 | 2024-08-13 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5602_ST612_BCA | NA | 131242-WST02-DR-5602_ST612_BCA | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-08-30 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2024-08-13 | NA | 000000 | 2024-08-13 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 8600_ST612_BCA | NA | 131242-WST02-DR-8600_ST612_BCA | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-08-30 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2024-08-13 | NA | 000000 | 2024-08-13 | 00 | 1 | PEN | INF | INF
000642 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 0 | 131242-WSW41-QA-0008 | 2024-08-13 | Inspection Test Plan for HDPE Pipe Installation | As requested to reject this submittal. | 2024-09-10 | 2024-09-24 | 10 | Rejected | YES | 2024-10-14 | YES | Resubmitted |  |  |  | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | PEN | REJ | REJ
000642 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 1 | 131242-WSW41-QA-0008 | 2024-10-01 | Inspection Test Plan for HDPE Pipe Installation | Rev 1: Approved | 2024-10-21 | 2024-10-25 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | PEN | APP | APP
000643 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 0 | 131242-WSW41-QA-0006 | 2024-08-13 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-10 | 2024-10-16 | 26 | Not Approved | YES | 2024-11-06 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | PEN | NAP | NAP
000643 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-0006 | 2024-12-12 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 1: Approved | 2025-01-02 | 2025-01-20 | 12 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | PEN | APP | APP
000643 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-0006 | 2025-09-25 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 2: Approved | 2025-10-15 | 2025-10-06 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | PEN | APP | APP
000644 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 0 | 131242-WSD11-RT-0000 | 2024-08-13 | THP Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 12 | Not Approved | YES | 2024-10-16 | YES | Resubmitted |  |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000644 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 1 | 131242-WSD11-RT-0000 | 2025-04-22 | THP Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-05-06 |  | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000644 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-0000 | 2025-06-20 | THP Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-08-04 | 17 | Not Approved | YES | 2025-08-22 | YES | Resubmitted |  |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000644 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-0000 | 2025-12-15 | THP Lux Simulation Report | Rev 3: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 21 | Not Approved | YES | 2026-02-20 | NO | Overdue | -21 |  |  | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000645 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 0 | 131242-WST02-RT-0000 | 2024-08-13 | SSN Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 12 | Not Approved | YES | 2024-10-16 | YES | Resubmitted |  |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000645 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 1 | 131242-WST02-RT-0000 | 2025-03-12 | SSN Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-05-06 | 23 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000645 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 2 | 131242-WST02-RT-0000 | 2025-06-20 | SSN Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. | 2025-07-10 | 2025-08-04 | 17 | Not Approved | YES | 2025-08-22 | YES | Resubmitted |  |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | NAP | NAP
000645 | 03 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 3 | 131242-WST02-RT-0000 | 2025-11-20 | SSN Lux Simulation Report | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-10 | 2025-12-17 | 5 | Approved with Comments | YES | 2026-01-06 | NO | Overdue | 14 |  |  | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | PEN | AWC | AWC
000646 | 00 | Low/ Fox | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-7002 | 2024-08-13 | Aeration Blower System Architecture Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-10 | 2024-08-27 |  | Approved with Comments | YES | 2024-09-16 | NO | Overdue | 353 |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 1900 | A | 131242-WST02-DR-1900 | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | 1 | Approved with Comments | YES | 2024-10-01 | NO | Overdue | 342 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | 2025-07-29 | A | 000000&&000647 | 2024-08-13, 2025-07-29 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3900 | NA | 131242-WST02-DR-3900 | 2024-08-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-10 | 2024-09-11 | 1 | Approved with Comments | YES | 2024-10-01 | NO | Overdue | 342 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-13 | 2024-08-13 | NA | 000000 | 2024-08-13 | 00 | 1 | PEN | AWC | AWC
000648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0012 | 0 | 131242-WSD11-DS-0012 | 2024-08-12 | Data Sheet of Desuperheater | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-09-03 |  | Approved with Comments | YES | 2024-09-23 | NO | Overdue | 348 |  |  | NA | "Data Sheet of Desuperheater " && "Datasheet for Thermal Flow Switch (THP-BOP)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-12 | 2026-01-15 | 0 | 000000&&000648&&001956 | 2024-08-12, 2026-01-15 | 00 | 3 | PEN | AWC | AWC
000649 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0004 | 0 | 131242-WSD11-CL-0004 | 2024-08-15 | THP Feed Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-08 | 18 | Approved with Comments | YES | 2024-10-28 | NO | Overdue | 323 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | 2024-08-15 | 0 | 000000&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00 | 3 | PEN | AWC | AWC
000650 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0008 | 0 | 131242-WSD11-CL-0008 | 2024-08-15 | Desuperheater Calculation | Rev 0: Approved with Comments. To revise and resubmit. Please include PE Endorsement. | 2024-09-12 | 2024-08-23 |  | Approved with Comments | YES | 2024-09-12 | NO | Overdue | 355 |  |  | NA | "Desuperheater Calculation" | 2024-08-15 | 2024-08-15 | 0 | 000650 | 2024-08-15 | 00 | 1 | PEN | AWC | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | A | 131242-WSD11-DR-5100 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 19 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "THP PC Pump GA Drawings" | 2024-08-15 | 2026-01-12 | B | 000000&&000651 | 2024-08-15, 2025-06-12, 2026-01-12 | 00, 01, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | NA | 131242-WSD11-DR-5110 | 2024-08-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-12 | 2024-10-09 | 19 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | NA | 131242-WSD11-DR-5120 | 2024-08-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-12 | 2024-10-09 | 19 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | NA | 131242-WSD11-DR-5130 | 2024-08-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-12 | 2024-10-09 | 19 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | NA | 131242-WSD11-DR-5140 | 2024-08-15 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-12 | 2024-10-09 | 19 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | B | 131242-WSD11-DR-5100 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 145 | Awaiting S.O.'s response | [7 empty] | NA | "THP PC Pump GA Drawings" | 2024-08-15 | 2026-01-12 | B | 000000&&000651 | 2024-08-15, 2025-06-12, 2026-01-12 | 00, 01, NA | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | NA | 131242-WSD11-DR-5110 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | NA | 131242-WSD11-DR-5120 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5121 | NA | 131242-WSD11-DR-5121 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-12 | 2025-06-12 | NA | 000000 | 2025-06-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | NA | 131242-WSD11-DR-5130 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5131 | NA | 131242-WSD11-DR-5131 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-12 | 2025-06-12 | NA | 000000 | 2025-06-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5132 | NA | 131242-WSD11-DR-5132 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-12 | 2025-06-12 | NA | 000000 | 2025-06-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | NA | 131242-WSD11-DR-5140 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-15 | 2025-06-12 | NA | 000000 | 2024-08-15, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5141 | NA | 131242-WSD11-DR-5141 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-12 | 2025-06-12 | NA | 000000 | 2025-06-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5142 | NA | 131242-WSD11-DR-5142 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-06-12 | 2025-06-12 | NA | 000000 | 2025-06-12 | 00 | 1 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | NA | 131242-WSD11-DR-5150 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Ring Circulation Pump Drawing" | 2024-10-28 | 2025-06-12 | A | 000000&&000784 | 2024-10-28, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | NA | 131242-WSD11-DR-5160 | 2025-06-12 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-02 | 2024-10-09 | 145 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-28 | 2025-06-12 | NA | 000000 | 2024-10-28, 2025-06-12 | 00 | 2 | PEN | PEN | PEN
000652 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0030 | 0 | 131242-WSW41-MI-0030 | 2024-08-06 | Process & MEICA Meeting Minutes 0030_20240801 | Rev 0: For Information | 2024-09-04 | 2024-09-03 |  | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000652 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000653 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0010 | 0 | 131242-WSW41-PO-0010 | 2024-07-08 | Unpriced PO for Hyperbolix Mixer (Entec International) | For Information | 2024-08-05 | 2024-08-29 | 17 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Hyperbolix Mixer (Entec International)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2024-07-08 | 2025-08-01 | 0 | 000653&&001500&&001509 | 2024-07-08, 2025-07-22, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000654 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0011 | 0 | 131242-WSW41-PO-0011 | 2024-08-15 | Unpriced PO for Dosing Pump (ProMinent) | Rev 0: For Information | 2024-09-12 | 2024-08-29 |  | Approved | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Dosing Pump (ProMinent)" && "Unpriced PO for Pressure Transmitter (Emerson)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-08-15 | 2025-08-01 | 0 | 000654&&001501&&001510 | 2024-08-15, 2025-07-22, 2025-08-01 | 00, 01 | 3 | PEN | APP | APP
000655 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0010 | 0 | 131242-WSW41-QA-0010 | 2024-08-15 | Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-09-03 |  | Approved with Comments | YES | 2024-09-23 | NO | Overdue | 348 |  |  | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | PEN | AWC | AWC
000656 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 0 | 131242-WSD11-DS-0011 | 2024-08-16 | Data Sheet for Steam Sparger Package | Rev 0: Not approved - Revise and Resubmit | 2024-09-13 | 2024-09-10 |  | Not Approved | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | PEN | NAP | NAP
000656 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 1 | 131242-WSD11-DS-0011 | 2025-02-18 | Data Sheet for Steam Sparger Package | Rev 1: Approved | 2025-03-10 | 2025-03-10 |  | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | PEN | APP | APP
000657 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0011 | 0 | 131242-WSW41-QA-0011 | 2024-08-19 | Procedure for Welding of Underground HDPE Pipe | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-16 | 2024-09-10 |  | Approved with Comments | YES | 2024-09-30 | NO | Overdue | 343 |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | PEN | AWC | AWC
000658 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0015 | 0 | 131242-WSW41-RT-0015 | 2024-08-19 | C4B Monthly Progress Report Number No.15 (07 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-09-16 | 2024-09-06 |  | Approved with Comments | YES | 2024-09-26 | NO | Overdue | 345 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report " && "C4B Monthly Progress Report Number No.15 (07 24)" | 2024-08-19 | 2025-06-27 | 0 | 000658&&001416 | 2024-08-19, 2025-06-27 | 00 | 2 | PEN | AWC | AWC
000659 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1382 | 0 | 131242-WST02-DS-1382 | 2024-08-19 | Sample Board Submission for uPVC Pipe 6” & 4” | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-09-16 | 2024-09-26 | 8 | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for uPVC Pipe 6” & 4” " | 2024-08-19 | 2024-08-19 | 0 | 000659 | 2024-08-19 | 00 | 1 | PEN | APP | APP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7020 | A | 131242-WST02-DR-7020 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Control Network Connection Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | I | 7021 | NA | 131242-WST02-DR-7021 | 2024-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | I | 7022 | NA | 131242-WST02-DR-7022 | 2024-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | I | 7023 | NA | 131242-WST02-DR-7023 | 2024-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | I | 7024 | NA | 131242-WST02-DR-7024 | 2024-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-05-04 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00 | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | I | 7025 | NA | 131242-WST02-DR-7025 | 2024-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-16 | 2024-09-06 |  | Not Approved | YES | 2024-09-26 | NO | Overdue | 345 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-03 | NA | 000000 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00 | 7 | PEN | NAP | NAP
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-7002 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 4 | Not Approved | YES | 2024-10-11 | YES | Resubmitted |  |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | BF | 1005 | NA | 131242-WST02-DR-1005 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-23 | 4 | Not Approved | YES | 2024-10-11 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | BF | 5001 | NA | 131242-WST02-DR-5001 | 2024-08-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-17 | 2024-09-23 | 4 | Not Approved | YES | 2024-10-11 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | NAP | NAP
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A.1 | 131242-WST02-DR-7002 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 60 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Aeration Blower System Architecture Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN External Fire Hydrant Layout & Details " && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | 2025-10-28 | A | 000000&&000308&&000646&&000661 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01 | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | BF | 1005 | NA | 131242-WST02-DR-1005 | 2025-06-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-09 | 2025-10-01 | 60 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | BF | 5001 | NA | 131242-WST02-DR-5001 | 2025-06-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-09 | 2025-10-01 | 60 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | BF | 5002 | NA | 131242-WST02-DR-5002 | 2025-06-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-09 | 2025-10-01 | 60 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000662 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0009 | 0 | 131242-WSD11-CL-0009 | 2024-08-20 | Flash Tank Discharge Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-09 | 16 | Approved with Comments | YES | 2024-10-29 | NO | Overdue | 322 |  |  | NA | "Flash Tank Discharge Pump Pressure Loss Calculation" | 2024-08-20 | 2024-08-20 | 0 | 000662 | 2024-08-20 | 00 | 1 | PEN | AWC | AWC
000663 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0010 | 0 | 131242-WSD11-CL-0010 | 2024-08-20 | Precooler S2 Circ Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-08 | 15 | Approved with Comments | YES | 2024-10-28 | NO | Overdue | 323 |  |  | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | PEN | AWC | AWC
000664 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 0 | 131242-WSD11-CL-0007 | 2024-08-20 | Steam Sparger Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-09-10 |  | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  |  |  | NA | "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | 2026-01-12 | 1 | 000000&&000664&&000960 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01, NA | 4 | PEN | AWC | AWC
000664 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 1 | 131242-WSD11-CL-0007 | 2025-04-10 | Steam Sparger Calculation | Rev 1: Approved. Please furnish PE Endorsement. | 2025-04-30 | 2025-10-06 | 111 | Approved | NO |  | YES |  |  |  |  | NA | "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | 2026-01-12 | 1 | 000000&&000664&&000960 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01, NA | 4 | PEN | APP | APP
000665 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 0 | 131242-WST02-QA-0002 | 2024-08-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-09-24 | 4 | Not Approved | YES | 2024-10-14 | YES | Resubmitted |  |  |  | NA | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " && "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | 2025-08-19 | 0 | 000665&&001603 | 2024-08-21, 2024-10-25, 2025-08-19 | 00, 01 | 3 | PEN | NAP | NAP
000665 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 1 | 131242-WST02-QA-0002 | 2024-10-25 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-04 |  | Approved with Comments | YES | 2024-11-22 | NO | Overdue | 305 |  |  | NA | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " && "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | 2025-08-19 | 0 | 000665&&001603 | 2024-08-21, 2024-10-25, 2025-08-19 | 00, 01 | 3 | PEN | AWC | AWC
000666 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0010 | 0 | 131242-WSW41-PS-0010 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Mar 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-10-30 | 2024-08-22 | 0 | 000000&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | PEN | INF | INF
000667 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0011 | 0 | 131242-WSW41-PS-0011 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Apr 2024 | Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-09 | 2024-08-22 | 0 | 000000&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | PEN | INF | INF
000668 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0012 | 0 | 131242-WSW41-PS-0012 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for May 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for May 2024" && "Monthly Progress Presentation No. 12 (0424)" | 2024-06-04 | 2024-08-22 | 0 | 000510&&000668 | 2024-06-04, 2024-08-22 | 00 | 2 | PEN | INF | INF
000669 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0013 | 0 | 131242-WSW41-PS-0013 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Jun 2024 | Rev 0: Scoring confirmed to be at 93/100 | 2024-09-19 | 2024-08-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Jun 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-07 | 2024-08-22 | 0 | 000000&&000669 | 2024-08-07, 2024-08-22 | 00 | 2 | PEN | INF | INF
000670 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | - | 131242-WSW41-QA-0013 | 2024-08-22 | Monthly Concrete Cube Records for Structural works for Apr 2024 | Rejected as requested by Contractor | 2024-09-19 | 2024-08-30 |  | Rejected | YES | 2024-09-19 | YES | Resubmitted |  |  | Request for Reject | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | REJ | REJ
000670 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | 0 | 131242-WSW41-QA-0013 | 2024-08-27 | Monthly Concrete Cube Records for Structural works for May 2024 | NA | 2024-09-16 |  | 343 | Awaiting S.O.'s response | [7 empty] | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | PEN | PEN
000671 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 0 | 131242-WSW41-VI-0010 | 2024-08-23 | Vendor Approval of Surge Diverter | Rev 0: Approved with comments. Refer to attached file for comments. | 2024-09-20 | 2024-09-26 | 4 | Approved with Comments | YES | 2024-10-16 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | AWC | AWC
000671 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 1 | 131242-WSW41-VI-0010 | 2024-10-04 | Vendor Approval of Surge Diverter | Rev 1: Approved. | 2024-10-24 | 2024-10-29 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | APP | APP
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1200 | A | 131242-WSD11-DR-1200 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | 2025-03-05 | Submission unsuccessful on 11 Jul 2024. | NA | "SITE OFFICE LAYOUT (Rev1)" && "THP Equipment layout" | 2024-08-23 | 2025-11-28 | A | 000000&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1201 | NA | 131242-WSD11-DR-1201 | 2024-08-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1202 | NA | 131242-WSD11-DR-1202 | 2024-08-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1203 | NA | 131242-WSD11-DR-1203 | 2024-08-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1204 | NA | 131242-WSD11-DR-1204 | 2024-08-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 8000 | NA | 131242-WSD11-DR-8000 | 2024-08-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-20 | 2024-10-17 | 19 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-23 | 2025-11-28 | NA | 000000 | 2024-08-23, 2025-05-09, 2025-11-28 | 00 | 3 | PEN | AWC | AWC
000673 | 00 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-0001 | 2024-08-23 | SSN 30 Percent ALMOP Report | Rev 0: Not approved - Revise and Resubmit | 2024-09-20 | 2024-09-06 |  | Rejected | YES | 2024-09-26 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | REJ | REJ
000673 | 01 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-0001 | 2024-09-06 | SSN 30 Percent ALMOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-14 | 12 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000673 | 02 | Qili | Process | NA | 131242 | WST02 | RT | Z | Comment Reply Sheet 20240716 S673.2 | 0 | 131242-WST02-RT-Comment Reply Sheet 20240716 S673.2 | 2024-10-29 | SSN 30 Percent ALMOP Report | Rev 2: Approved | 2024-11-19 | 2024-11-27 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "SSN 30 Percent ALMOP Report" | 2024-10-29 | 2024-10-29 | 0 | 000673 | 2024-10-29 | 02 | 1 | PEN | APP | APP
000674 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0037 | 0 | 131242-WSW41-LT-0037 | 2024-08-23 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements | Received for information. Please refer to S.O. Correspondence no. 241 dated 23 Oct 2024. | 2024-09-20 | 2025-11-20 | 294 | For Information | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements " | 2024-08-23 | 2024-08-23 | 0 | 000674 | 2024-08-23 | 00 | 1 | PEN | INF | INF
000675 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 0 | 131242-WSW41-VI-0021 | 2024-08-23 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-09-10 |  | Approved with Comments | YES | 2024-09-30 | YES | Resubmitted |  | 2025-03-14 | In Progress | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | PEN | AWC | AWC
000675 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 1 | 131242-WSW41-VI-0021 | 2025-07-02 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 1: Approved | 2025-07-22 | 2025-11-24 | 88 | Approved | NO |  | YES |  |  | 2025-03-14 | In Progress | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | PEN | APP | APP
000676 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 0 | 131242-WST02-QA-0003 | 2024-08-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-29 | 26 | Not Approved | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | PEN | NAP | NAP
000676 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 1 | 131242-WST02-QA-0003 | 2024-12-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-02-03 | 11 | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | PEN | AWC | AWC
000676 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 2 | 131242-WST02-QA-0003 | 2025-02-07 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-27 | 2025-02-18 |  | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | PEN | AWC | AWC
000677 | 00 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 0 | 131242-WST02-SP-0001 | 2024-08-26 | SSN Control Narrative | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-23 | 2024-10-09 | 12 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000677 | 01 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 1 | 131242-WST02-SP-0001 | 2025-03-24 | SSN Control Narrative | Approved with Comments | 2025-04-11 | 2025-05-15 | 21 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000678 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 0 | 131242-WSD11-RT-0003 | 2024-08-26 | THP HAZOP Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-09 | 12 | Approved with Comments | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | PEN | AWC | AWC
000678 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 1 | 131242-WSD11-RT-0003 | 2024-10-28 | THP HAZOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2025-04-08 | 96 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | PEN | AWC | AWC
000679 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0021 | 0 | 131242-WSW41-VI-0021 | 2024-08-26 | Vendor Approval of Electrical Consultant – YHW LLP | Approved | 2024-09-23 | 2024-09-26 | 3 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | PEN | APP | APP
000680 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | QA | C | 0014 | 0 | 131242-WST02-QA-0014 | 2024-08-27 | Laboratory Test Report on Soil Samples | For Information | 2024-09-24 | 2024-09-17 |  | For Information | NO |  | YES |  |  |  |  | NA | "Factory Acceptance Test Report for Clean Gas System Panel" && "Laboratory Test Report on Soil Samples" | 2024-08-27 | 2025-07-30 | 0 | 000680&&001539 | 2024-08-27, 2025-07-30 | 00 | 2 | PEN | INF | INF
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.1 | 131242-WSD11-DR-1170 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | A.2 | 000000&&000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1171 | NA | 131242-WSD11-DR-1171 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1172 | NA | 131242-WSD11-DR-1172 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1173 | NA | 131242-WSD11-DR-1173 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 3170 | NA | 131242-WSD11-DR-3170 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 3171 | NA | 131242-WSD11-DR-3171 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 4100 | NA | 131242-WSD11-DR-4100 | 2024-08-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-25 | 2024-10-16 | 15 | Approved with Comments | YES | 2024-11-06 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-02-18 | NA | 000000 | 2024-08-28, 2025-02-18 | 00 | 2 | PEN | AWC | AWC
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.2 | 131242-WSD11-DR-1170 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-10 | 2025-04-27 | 32 | Approved | NO |  | YES |  |  |  |  | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | A.2 | 000000&&000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01, NA | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1171 | NA | 131242-WSD11-DR-1171 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1172 | NA | 131242-WSD11-DR-1172 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-08-13 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 5 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1173 | NA | 131242-WSD11-DR-1173 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-08-13 | NA | 000000 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, NA | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 3170 | NA | 131242-WSD11-DR-3170 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 3171 | NA | 131242-WSD11-DR-3171 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-23 | 2025-02-18 | NA | 000000 | 2024-03-23, 2024-08-28, 2025-02-18 | 00 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 4100 | NA | 131242-WSD11-DR-4100 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-18 | 2025-04-27 | 26 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-28 | 2025-02-18 | NA | 000000 | 2024-08-28, 2025-02-18 | 00 | 2 | PEN | APP | APP
000682 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 0 | 131242-WSW41-QA-0015 | 2024-08-29 | Plate Load test report | Rev.0:Not Approved. Please refer to attached comment sheet for resubmission. | 2024-09-26 | 2024-09-18 |  | Not Approved | YES | 2024-10-08 | YES | Resubmitted |  |  |  | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plate Load test report " | 2024-08-29 | 2026-01-28 | 1 | 000000&&000682&&000694 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | PEN | NAP | NAP
000682 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 1 | 131242-WSW41-QA-0015 | 2024-10-30 | Plate Load test report | Approved | 2024-11-20 | 2024-11-08 |  | Approved | NO |  | YES |  |  |  |  | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plate Load test report " | 2024-08-29 | 2026-01-28 | 1 | 000000&&000682&&000694 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | PEN | APP | APP
000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0029 | 0 | 131242-WSW41-MI-0029 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000683 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | C | 0030 | NA | 131242-WSW41-MI-0030 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000652 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0019 | 0 | 131242-WSW41-MI-0019 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0020 | NA | 131242-WSW41-MI-0020 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Monthly Progress Meeting Minutes 0020_20250122" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | 2025-02-18 | 0 | 000000&&000353&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0021 | NA | 131242-WSW41-MI-0021 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Monthly Progress Meeting Minutes 0021_20250226" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | 2025-04-21 | 0 | 000000&&000460&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0022 | NA | 131242-WSW41-MI-0022 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | 2025-04-21 | 0 | 000000&&000470&&000472&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0023 | NA | 131242-WSW41-MI-0023 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | 2024-08-29 | 0 | 000000&&000477 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0024 | NA | 131242-WSW41-MI-0024 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0024,0025,0026_May" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | 2024-08-29 | 0 | 000000&&000517&&000561 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0025 | NA | 131242-WSW41-MI-0025 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | 2024-08-29 | 0 | 000000&&000529 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0026 | NA | 131242-WSW41-MI-0026 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | 2024-08-29 | A | 000000&&000542 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0027 | NA | 131242-WSW41-MI-0027 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0027,0028_June" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | 2024-08-29 | 0 | 000000&&000562&&000584 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0029 | NA | 131242-WSW41-MI-0029 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000683 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0030 | NA | 131242-WSW41-MI-0030 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | 2024-08-29 | 0 | 000000&&000652 | 2024-08-06, 2024-08-29 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | IM | 0031 | NA | 131242-WSW41-MI-0031 | 2024-08-29 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | 2024-10-14 | 0 | 000000&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | PEN | INF | INF
000685 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0031 | 0 | 131242-WSW41-MI-0031 | 2024-08-29 | Process & MEICA Meeting Minutes 0031_20240815 | Rev. 0 - For Information | 2024-09-26 | 2024-09-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | 2024-10-14 | 0 | 000000&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | PEN | INF | INF
000686 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 0 | 131242-WSD11-DS-0021 | 2024-08-29 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 0: Not approved - Revise and Resubmit | 2024-09-26 | 2024-10-17 | 15 | Not Approved | YES | 2024-11-07 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | PEN | NAP | NAP
000686 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 1 | 131242-WSD11-DS-0021 | 2024-11-07 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-27 | 2024-12-05 | 6 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000686 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 2 | 131242-WSD11-DS-0021 | 2025-01-20 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 53 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | PEN | APP | APP
000687 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0001 | 0 | 131242-WSD11-RT-0001 | 2024-08-29 | THP 30 Percent ALMOP Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-17 | 15 | Approved with Comments | YES | 2024-11-07 | NO | Overdue | 316 |  |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | AWC | AWC
000688 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 0 | 131242-WSD11-QA-0012 | 2024-08-30 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-11-05 | 26 | Approved with Comments | YES | 2024-11-25 | YES | Resubmitted |  |  |  | NA | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2024-08-30 | 2025-04-21 | 1 | 000688 | 2024-08-30, 2025-04-21 | 00, 01 | 2 | PEN | AWC | AWC
000688 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 1 | 131242-WSD11-QA-0012 | 2025-04-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | NA | 2025-05-09 | 2025-09-08 | 85 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2024-08-30 | 2025-04-21 | 1 | 000688 | 2024-08-30, 2025-04-21 | 00, 01 | 2 | PEN | AWC | AWC
000689 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 0 | 131242-WSW41-QA-0004 | 2024-08-30 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 0: Rejected. Refer to the attached file for comments. | 2024-09-27 | 2024-11-25 | 40 | Rejected | YES | 2024-12-13 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | REJ | REJ
000689 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 1 | 131242-WSW41-QA-0004 | 2025-02-07 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Refer to the attached file for comments. | 2025-02-27 | 2025-03-13 | 10 | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | AWC | AWC
000689 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 2 | 131242-WSW41-QA-0004 | 2025-03-14 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 2: Approved. | 2025-04-03 | 2025-05-07 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | PEN | APP | APP
000690 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0011 | 0 | 131242-WSD11-CL-0011 | 2024-08-30 | THP Plant Process Water Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-09-27 | 2024-10-29 | 22 | Not Approved | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "THP Plant Process Water Hydraulic Calculation" | 2024-08-30 | 2024-08-30 | 0 | 000690 | 2024-08-30 | 00 | 1 | PEN | NAP | NAP
000691 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 0 | 131242-WSW41-QA-0013 | 2024-08-31 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-10-14 | 11 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | AWC | AWC
000691 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 1 | 131242-WSW41-QA-0013 | 2025-04-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Approved | 2025-05-07 | 2025-05-19 | 7 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | APP | APP
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-1010_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | A | 000000&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | NA | 131242-WST02-DR-1011_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | NA | 131242-WST02-DR-1012_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3000_ST607_BCA | NA | 131242-WST02-DR-3000_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-31 | 2024-08-31 | NA | 000000 | 2024-08-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | NA | 131242-WST02-DR-3002_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | NA | 131242-WST02-DR-7003_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | NA | 131242-WST02-DR-7004_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | NA | 131242-WST02-DR-8003_ST607_BCA | 2024-08-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-09-27 | 2024-09-11 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-01 | 2024-08-31 | NA | 000000 | 2024-07-01, 2024-08-31 | 00 | 2 | PEN | INF | INF
000693 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-0016 | 2024-08-31 | Monthly Concrete Cube Records for Structural works for July 2024 | For Information | 2024-09-27 | 2024-09-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | INF | INF
000694 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 0 | 131242-WSW41-QA-0015 | 2024-09-02 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-30 | 2024-10-13 | 9 | Not Approved | YES | 2024-11-01 | YES | Resubmitted |  |  |  | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plate Load test report " | 2024-08-29 | 2026-01-28 | 1 | 000000&&000682&&000694 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | PEN | NAP | NAP
000694 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 1 | 131242-WSW41-QA-0015 | 2025-03-27 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Approved | 2025-04-16 | 2025-05-19 | 20 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plate Load test report " | 2024-08-29 | 2026-01-28 | 1 | 000000&&000682&&000694 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | PEN | APP | APP
000695 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0038 | 0 | 131242-WSW41-LT-0038 | 2024-09-03 | Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions | Rev(0): Rejected. Please refer to S.O. Correspondence No. 246 dated 7 Nov 2024. | 2024-10-01 | 2025-11-20 | 287 | Rejected | YES | 2025-12-10 | NO | Overdue | 33 |  |  | NA | "Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions" | 2024-09-03 | 2024-09-03 | 0 | 000695 | 2024-09-03 | 00 | 1 | PEN | REJ | REJ
000696 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0014 | 0 | 131242-WSW41-PC-0014 | 2024-09-03 | Payment Claim No.14 | Rev(0): Approved. See S.O. correspondence no. 219 dated 6 Sep 2024. | 2024-10-01 | 2024-10-09 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.14" | 2024-09-03 | 2024-09-03 | 0 | 000696 | 2024-09-03 | 00 | 1 | PEN | APP | APP
000697 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 0 | 131242-WSD11-DS-0018 | 2024-09-03 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-14 | 9 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Pre Cooler Cooling Water Control Valve" && "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2024-09-03 | 2026-03-02 | 0 | 000697&&002021 | 2024-09-03, 2025-05-05, 2026-03-02 | 00, 01 | 3 | PEN | AWC | AWC
000697 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 1 | 131242-WSD11-DS-0018 | 2025-05-05 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | 173 | Awaiting S.O.'s response | [7 empty] | NA | "Data Sheet for Pre Cooler Cooling Water Control Valve" && "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2024-09-03 | 2026-03-02 | 0 | 000697&&002021 | 2024-09-03, 2025-05-05, 2026-03-02 | 00, 01 | 3 | PEN | PEN | PEN
000698 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 0 | 131242-WSD11-DS-0019 | 2024-09-03 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-13 | 8 | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000698 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 1 | 131242-WSD11-DS-0019 | 2024-11-13 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 2 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000698 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 2 | 131242-WSD11-DS-0019 | 2025-01-20 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 53 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | APP | APP
000699 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0039 | 0 | 131242-WSW41-LT-0039 | 2024-09-04 | Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024) | Rejected. Please refer to S.O. Correspondence no. 257 dated 2 Dec 2024. | 2024-10-02 | 2025-02-24 | 98 | Rejected | NO |  | YES |  |  |  | SO Corres 000258. Sent to Vincent on 03 Dec 2025 | NA | "Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024)" | 2024-09-04 | 2024-09-04 | 0 | 000699 | 2024-09-04 | 00 | 1 | PEN | REJ | REJ
000700 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0015 | 0 | 131242-WSW41-MI-0015 | 2024-09-04 | Monthly Progress Meeting Minutes 0015_20240827 | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "SITE OFFICE LAYOUT (Rev1)" | 2023-12-14 | 2024-09-04 | 0 | 000000&&000240&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | PEN | INF | INF
000701 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0015 | 0 | 131242-WSW41-PS-0015 | 2024-09-04 | Monthly Progress Presentation No. 15 (0824) | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Aug 2024" && "Monthly Progress Presentation No. 15 (0824)" | 2024-09-04 | 2024-10-14 | 0 | 000701&&000761 | 2024-09-04, 2024-10-14 | 00 | 2 | PEN | INF | INF
000702 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0012 | 0 | 131242-WSW41-PO-0012 | 2024-09-05 | Unpriced LOA for Structural Steel Works (Sanhe) | Rev 0: For Information | 2024-10-03 | 2024-10-13 | 6 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced LOA for Structural Steel Works (Sanhe) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-09-05 | 2025-08-01 | 1 | 000702&&001502&&001511 | 2024-09-05, 2025-07-22, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
000703 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0018 | 0 | 131242-WSW41-MS-0018 | 2024-09-05 | MSRA for RC Super-Structural Work | Rev.0: Approved. Please refer to comment sheet. | 2024-10-03 | 2024-09-26 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA for RC Super-Structural Work" | 2024-09-05 | 2024-09-05 | 0 | 000703 | 2024-09-05 | 00 | 1 | PEN | APP | APP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-1000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 |  |  | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1001_FSSD | NA | 131242-WSD11-DR-1001_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1002_FSSD | NA | 131242-WSD11-DR-1002_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1003_FSSD | NA | 131242-WSD11-DR-1003_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1004_FSSD | NA | 131242-WSD11-DR-1004_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-10 | 2024-09-06 | NA | 000000 | 2023-11-10, 2024-09-06 | 00 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 2000_FSSD | NA | 131242-WSD11-DR-2000_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-06 | 2024-09-06 | NA | 000000 | 2024-09-06 | 00 | 1 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 3000_FSSD | NA | 131242-WSD11-DR-3000_FSSD | 2024-09-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-04 | 2024-10-02 |  | Not Approved | YES | 2024-10-22 | NO | Overdue | 327 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-06 | 2024-09-06 | NA | 000000 | 2024-09-06 | 00 | 1 | PEN | NAP | NAP
000705 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0019 | 0 | 131242-WSW41-VI-0019 | 2024-09-06 | Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-04 | 2024-09-26 |  | Approved with Comments | YES | 2024-10-16 | NO | Overdue | 331 |  |  | NA | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." && "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | 2024-02-29 | 2024-09-06 | 0 | 000333&&000705 | 2024-02-29, 2024-09-06 | 00 | 2 | PEN | AWC | AWC
000706 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 0 | 131242-WST02-QA-0005 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 17 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | PEN | AWC | AWC
000706 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 1 | 131242-WST02-QA-0005 | 2024-11-20 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-10 | 2024-12-14 | 3 | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | PEN | AWC | AWC
000706 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 2 | 131242-WST02-QA-0005 | 2025-01-16 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 9 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | PEN | APP | APP
000706 | 03 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 3 | 131242-WST02-QA-0005 | 2025-02-26 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-03-18 | 2025-05-06 | 32 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | PEN | APP | APP
000706 | 04 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 4 | 131242-WST02-QA-0005 | 2025-07-03 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-07-23 | 2025-10-01 | 50 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | PEN | APP | APP
000707 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 0 | 131242-WST02-QA-0006 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 17 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | PEN | AWC | AWC
000707 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 1 | 131242-WST02-QA-0006 | 2024-12-20 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-02-20 | 27 | Approved with Comments | YES | 2025-03-12 | YES | Resubmitted |  |  |  | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | PEN | AWC | AWC
000707 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 2 | 131242-WST02-QA-0006 | 2025-10-08 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 2: Approved | 2025-10-28 | 2026-02-20 | 82 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | PEN | APP | APP
000708 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0001 | 0 | 131242-WSW41-QA-0001 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 24 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | PEN | AWC | AWC
000709 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 0 | 131242-WSW41-QA-0002 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 24 | Approved with Comments | YES | 2024-11-28 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000709 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 1 | 131242-WSW41-QA-0002 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 28 | Approved with Comments | YES | 2025-03-14 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000709 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 2 | 131242-WSW41-QA-0002 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-29 |  | 61 | Awaiting S.O.'s response | [7 empty] | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | PEN | PEN
000710 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 0 | 131242-WSW41-QA-0003 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 24 | Approved with Comments | YES | 2024-11-28 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000710 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 1 | 131242-WSW41-QA-0003 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 28 | Approved with Comments | YES | 2025-03-14 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | AWC | AWC
000710 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 2 | 131242-WSW41-QA-0003 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 2: Approved | 2025-10-29 | 2026-02-20 | 81 | Approved |  | 2026-03-12 |  | Overdue | -35 |  |  | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | PEN | APP | APP
000711 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0011 | 0 | 131242-WST02-VI-0011 | 2024-09-06 | Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-09 | 3 | Approved with Comments | YES | 2024-10-29 | NO | Overdue | 322 |  | To follow-up with VICPLAS. | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | PEN | AWC | AWC
000712 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-0007 | 2024-09-06 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev.0: Rejected as per Contractor's request. | 2024-10-04 | 2024-09-09 |  | Rejected | YES | 2024-09-27 | YES | Resubmitted |  |  |  | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | PEN | REJ | REJ
000712 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-0007 | 2024-09-09 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev 1: Approved. Please refer to attached file and note our comments. | 2024-09-27 | 2024-10-29 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | PEN | APP | APP
000713 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0007 | 0 | 131242-WSW41-RT-0007 | 2024-09-06 | Bored Piling Pile Eccentricity Reports (ECC 08 to 12) | Not Approved | 2024-10-04 | 2024-09-13 |  | Not Approved | YES | 2024-10-03 | NO | Overdue | 340 |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" && "C4B Monthly Progress Report Number No.07 (11/23)" | 2023-12-11 | 2024-09-06 | 0 | 000234&&000713 | 2023-12-11, 2024-09-06 | 00 | 2 | PEN | NAP | NAP
000714 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | DS | C | 1384 | 0 | 131242-WST02-DS-1384 | 2024-09-09 | Sample Board Submission for PVC lining System (Linabond) | For Information | 2024-10-07 | 2024-09-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for PVC lining System (Linabond)" | 2024-09-09 | 2024-09-09 | 0 | 000714 | 2024-09-09 | 00 | 1 | PEN | INF | INF
000715 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SP | C | 0021 | 0 | 131242-WSW41-SP-0021 | 2024-09-09 | Datat Sheet for Steel Structure and Painting | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-07 | 2024-10-09 | 2 | Not Approved | YES | 2024-10-29 | YES | Resubmitted |  |  |  | NA | "Datat Sheet for Steel Structure and Painting" | 2024-09-09 | 2024-11-16 | 1 | 000715 | 2024-09-09, 2024-11-16 | 00, 01 | 2 | PEN | NAP | NAP
000715 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0021 | 1 | 131242-WSW41-SP-0021 | 2024-11-16 | Datat Sheet for Steel Structure and Painting | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-05 | 2024-12-08 | 1 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "Datat Sheet for Steel Structure and Painting" | 2024-09-09 | 2024-11-16 | 1 | 000715 | 2024-09-09, 2024-11-16 | 00, 01 | 2 | PEN | AWC | AWC
000716 | 00 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 0 | 131242-WSD11-DS-0023 | 2024-09-09 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-07 | 2024-10-14 | 5 | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000716 | 01 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 1 | 131242-WSD11-DS-0023 | 2024-11-13 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 2 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000716 | 02 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 2 | 131242-WSD11-DS-0023 | 2025-01-20 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 53 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | PEN | APP | APP
000717 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0045 | 0 | 131242-WST02-CD-0045 | 2024-09-09 | Submission Of BIM Coordination VCM Model (Aug-2024) | For Information. | 2024-10-07 | 2024-09-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Aug-2024)" | 2024-09-09 | 2024-09-09 | 0 | 000717 | 2024-09-09 | 00 | 1 | PEN | INF | INF
000718 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 0 | 131242-WST02-DS-0010 | 2024-09-10 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-10-29 | 15 | Approved with Comments | YES | 2024-11-19 | YES | Resubmitted |  |  |  | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000718 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 1 | 131242-WST02-DS-0010 | 2024-12-19 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-02-18 | 26 | Approved with Comments | YES | 2025-03-10 | YES | Resubmitted |  |  |  | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000718 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 2 | 131242-WST02-DS-0010 | 2025-03-07 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-04-27 | 19 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | PEN | AWC | AWC
000719 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1383 | 0 | 131242-WST02-DS-1383 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0003) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 |  | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for Lightning and Earthing System (MTF 0003)" | 2024-09-10 | 2024-09-10 | 0 | 000719 | 2024-09-10 | 00 | 1 | PEN | APP | APP
000720 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1385 | 0 | 131242-WST02-DS-1385 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0005) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 |  | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for Lightning and Earthing System (MTF 0005)" | 2024-09-10 | 2024-09-10 | 0 | 000720 | 2024-09-10 | 00 | 1 | PEN | APP | APP
000721 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5451 | 0 | 131242-WST02-DS-5451 | 2024-09-10 | Data Sheet for Side Manway | Rev 0: Rejected | 2024-10-08 | 2024-10-11 | 3 | Rejected | NO |  | YES |  |  |  |  | NA | "Data Sheet for Side Manway" | 2024-09-10 | 2024-09-10 | 0 | 000721 | 2024-09-10 | 00 | 1 | PEN | REJ | REJ
000722 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | Z | 0001 | 0 | 131242-WSW41-MS-0001 | 2024-09-11 | MSRA SWP for Operating Forklift | Approved | 2024-10-09 | 2024-10-10 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | APP | APP
000723 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0002 | 0 | 131242-WST02-RT-0002 | 2024-09-12 | Detailed Design Report – SSN PACKAGE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-11-07 | 19 | Approved with Comments | YES | 2024-11-27 | NO | Overdue | 302 | 2025-04-30 | comments received on 14 Feb | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | PEN | AWC | AWC
000724 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-0016 | 2024-09-16 | Mock-up Temperature Monitoring Test Reports (Alliance) | For Information | 2024-10-14 | 2024-09-26 |  | For Information | NO |  | YES |  |  |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | INF | INF
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5351 | 0 | 131242-WST02-CL-5351 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 |  | Approved with Comments | YES | 2024-10-24 | YES | Resubmitted |  |  |  | NA | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5361 | NA | 131242-WST02-CL-5361 | 2024-09-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-14 | 2024-10-04 |  | Approved with Comments | YES | 2024-10-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5371 | NA | 131242-WST02-CL-5371 | 2024-09-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-14 | 2024-10-04 |  | Approved with Comments | YES | 2024-10-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5381 | NA | 131242-WST02-CL-5381 | 2024-09-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-14 | 2024-10-04 |  | Approved with Comments | YES | 2024-10-24 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5351 | 1 | 131242-WST02-CL-5351 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-17 | 2024-12-08 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5361 | NA | 131242-WST02-CL-5361 | 2024-11-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-26 | 2024-12-08 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5371 | NA | 131242-WST02-CL-5371 | 2024-11-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-26 | 2024-12-08 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5381 | NA | 131242-WST02-CL-5381 | 2024-11-27 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-12-26 | 2024-12-08 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-16 | 2024-11-27 | NA | 000000 | 2024-09-16, 2024-11-27 | 00 | 2 | PEN | AWC | AWC
000726 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0016 | 0 | 131242-WSW41-RT-0016 | 2024-09-16 | C4B Monthly Progress Report Number No.16 (08 24) | Rev. 0 - Approved with comments (need to re-submit; see attached comment sheet) | 2024-10-14 | 2024-10-01 |  | Approved with Comments | YES | 2024-10-21 | NO | Overdue | 328 |  |  | NA | "C4B Monthly Progress Report Number No.16 (08 24) " | 2024-09-16 | 2024-09-16 | 0 | 000726 | 2024-09-16 | 00 | 1 | PEN | AWC | AWC
000727 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0040 | 0 | 131242-WSW41-LT-0040 | 2024-09-16 | NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA | Rejected. Please refer to S.O. Correspondence no. 258 dated 2 Dec 2024. | 2024-10-14 | 2025-02-24 | 90 | Rejected | NO |  | YES |  |  |  | SO Corres 000257. Sent to Vincent on 03 Dec 2025 | NA | "NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA" | 2024-09-16 | 2024-09-16 | 0 | 000727 | 2024-09-16 | 00 | 1 | PEN | REJ | REJ
000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 0 | 131242-WST02-DS-5301 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 |  | Not Approved | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5311 | NA | 131242-WST02-DS-5311 | 2024-09-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-16 | 2024-10-14 |  | Not Approved | YES | 2024-11-04 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-18 | 2024-12-20 | NA | 000000 | 2024-09-18, 2024-12-10, 2024-12-20 | 00 | 3 | PEN | NAP | NAP
000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 1 | 131242-WST02-DS-5301 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2024-12-31 | 2024-12-14 |  | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5311 | NA | 131242-WST02-DS-5311 | 2024-12-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-08 | 2024-12-14 |  | Not Approved | YES | 2025-01-03 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-18 | 2024-12-20 | NA | 000000 | 2024-09-18, 2024-12-10, 2024-12-20 | 00 | 3 | PEN | NAP | NAP
000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 2 | 131242-WST02-DS-5301 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-10 | 2025-01-09 |  | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5311 | NA | 131242-WST02-DS-5311 | 2024-12-20 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-20 | 2025-01-09 |  | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-18 | 2024-12-20 | NA | 000000 | 2024-09-18, 2024-12-10, 2024-12-20 | 00 | 3 | PEN | APP | APP
000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5301 | 0 | 131242-WST02-CL-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 |  | Approved with Comments | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-09-18 | 0 | 000729 | 2024-09-18 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5311 | NA | 131242-WST02-CL-5311 | 2024-09-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-16 | 2024-10-14 |  | Approved with Comments | YES | 2024-11-04 | NO | Overdue | 319 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-18 | 2024-09-18 | NA | 000000 | 2024-09-18 | 00 | 2 | PEN | AWC | AWC
000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5301 | 1 | 131242-WST02-CL-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-12-05 | 41 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 |  |  | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-09-18 | 0 | 000729 | 2024-09-18 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5311 | NA | 131242-WST02-CL-5311 | 2024-09-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-16 | 2024-12-05 | 35 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-09-18 | 2024-09-18 | NA | 000000 | 2024-09-18 | 00 | 2 | PEN | AWC | AWC
000730 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 0 | 131242-WST02-VI-0009 | 2024-09-18 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 0: Rejected. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-10 |  | Rejected | YES | 2024-10-30 | YES | Resubmitted |  |  |  | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | PEN | REJ | REJ
000730 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 1 | 131242-WST02-VI-0009 | 2024-10-14 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 1: Approved with comments. Refer to attached file for comments. | 2024-11-04 | 2024-11-07 | 3 | Approved with Comments | YES | 2024-11-27 | NO | Overdue | 302 |  | To follow-up with SKYPRO. | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | PEN | AWC | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | B | 131242-WST02-DR-6000 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  |  |  | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | NA | 131242-WST02-DR-6001 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | NA | 131242-WST02-DR-6002 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | NA | 131242-WST02-DR-6003 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | NA | 131242-WST02-DR-6004 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | NA | 131242-WST02-DR-6005 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | NA | 131242-WST02-DR-6006 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | NA | 131242-WST02-DR-6007 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | NA | 131242-WST02-DR-6008 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | NA | 131242-WST02-DR-6009 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | NA | 131242-WST02-DR-6010 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | NA | 131242-WST02-DR-6011 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | NA | 131242-WST02-DR-6012 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | NA | 131242-WST02-DR-6013 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | NA | 131242-WST02-DR-6014 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | NA | 131242-WST02-DR-6015 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Chemical Dosing Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000399 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | NA | 131242-WST02-DR-6016 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | NA | 131242-WST02-DR-6017 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | NA | 131242-WST02-DR-6018 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | NA | 131242-WST02-DR-6019 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | NA | 131242-WST02-DR-6020 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | NA | 131242-WST02-DR-6200 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Plant Water and Instrument Air" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000400 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6300 | NA | 131242-WST02-DR-6300 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | NA | 131242-WST02-DR-6600 | 2024-09-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-10-17 | 2024-11-07 | 14 | Approved with Comments | YES | 2024-11-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | C | 131242-WST02-DR-6000 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  |  |  | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | NA | 131242-WST02-DR-6001 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | NA | 131242-WST02-DR-6002 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | NA | 131242-WST02-DR-6003 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | NA | 131242-WST02-DR-6004 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | NA | 131242-WST02-DR-6005 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | NA | 131242-WST02-DR-6006 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | NA | 131242-WST02-DR-6007 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | NA | 131242-WST02-DR-6008 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | NA | 131242-WST02-DR-6009 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | NA | 131242-WST02-DR-6010 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | NA | 131242-WST02-DR-6011 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | NA | 131242-WST02-DR-6012 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | NA | 131242-WST02-DR-6013 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | NA | 131242-WST02-DR-6014 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | NA | 131242-WST02-DR-6015 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Chemical Dosing Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000399 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | NA | 131242-WST02-DR-6016 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | NA | 131242-WST02-DR-6017 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | NA | 131242-WST02-DR-6018 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | NA | 131242-WST02-DR-6019 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | NA | 131242-WST02-DR-6020 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | NA | 131242-WST02-DR-6200 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Plant Water and Instrument Air" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000400 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6300 | NA | 131242-WST02-DR-6300 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | NA | 131242-WST02-DR-6600 | 2025-01-03 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-23 | 2025-03-06 | 28 | Approved with Comments | YES | 2025-03-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-6000 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  |  |  | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | NA | 131242-WST02-DR-6001 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | NA | 131242-WST02-DR-6002 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | NA | 131242-WST02-DR-6003 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | NA | 131242-WST02-DR-6004 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | NA | 131242-WST02-DR-6005 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | NA | 131242-WST02-DR-6006 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | NA | 131242-WST02-DR-6007 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | NA | 131242-WST02-DR-6008 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | NA | 131242-WST02-DR-6009 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | NA | 131242-WST02-DR-6010 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | NA | 131242-WST02-DR-6011 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | NA | 131242-WST02-DR-6012 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | NA | 131242-WST02-DR-6013 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | NA | 131242-WST02-DR-6014 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | NA | 131242-WST02-DR-6015 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Chemical Dosing Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000399 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | NA | 131242-WST02-DR-6016 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | NA | 131242-WST02-DR-6017 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | NA | 131242-WST02-DR-6018 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | NA | 131242-WST02-DR-6019 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | NA | 131242-WST02-DR-6020 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | NA | 131242-WST02-DR-6200 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "P&ID for SSN Plant Water and Instrument Air" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000400 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6300 | NA | 131242-WST02-DR-6300 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | NA | 131242-WST02-DR-6600 | 2025-06-16 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-07-04 | 2025-08-28 | 39 | Approved with Comments | YES | 2025-09-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | AWC | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-6000 | 2026-02-24 | P&ID for SSN | NA | 2026-03-16 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | NA | 131242-WST02-DR-6001 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | NA | 131242-WST02-DR-6002 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | NA | 131242-WST02-DR-6003 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | NA | 131242-WST02-DR-6004 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | NA | 131242-WST02-DR-6005 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | NA | 131242-WST02-DR-6006 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | NA | 131242-WST02-DR-6007 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | NA | 131242-WST02-DR-6008 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | NA | 131242-WST02-DR-6009 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | NA | 131242-WST02-DR-6010 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | NA | 131242-WST02-DR-6011 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | NA | 131242-WST02-DR-6012 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | NA | 131242-WST02-DR-6013 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | NA | 131242-WST02-DR-6014 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | NA | 131242-WST02-DR-6015 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "P&ID for SSN Chemical Dosing Systems" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000399 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | NA | 131242-WST02-DR-6016 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | NA | 131242-WST02-DR-6017 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | NA | 131242-WST02-DR-6018 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | NA | 131242-WST02-DR-6019 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | NA | 131242-WST02-DR-6020 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | NA | 131242-WST02-DR-6200 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "P&ID for SSN Plant Water and Instrument Air" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | A | 000000&&000400 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6300 | NA | 131242-WST02-DR-6300 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | 2026-02-24 | B | 000000&&000187 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01 | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6301 | NA | 131242-WST02-DR-6301 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6500 | NA | 131242-WST02-DR-6500 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-15 | 2026-02-24 | NA | 000000 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 6 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | NA | 131242-WST02-DR-6600 | 2026-02-24 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2026-03-16 | 2025-08-28 |  | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-03-26 | 2026-02-24 | NA | 000000 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00 | 5 | PEN | PEN | PEN
000732 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0041 | 0 | 131242-WSW41-LT-0041 | 2024-09-20 | CV of Team member (Construction Manager) | Rev 0: Approved | 2024-10-18 | 2024-10-14 |  | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team member (Construction Manager)" | 2024-09-20 | 2024-09-20 | 0 | 000732 | 2024-09-20 | 00 | 1 | PEN | APP | APP
000733 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 0 | 131242-WSW41-QA-0017 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 11 | Approved with Comments | YES | 2024-11-25 | YES | Resubmitted |  |  |  | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | 2026-01-28 | 0 | 000000&&000733&&000747&&001056&&001342 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | PEN | AWC | AWC
000733 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 1 | 131242-WSW41-QA-0017 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-26 | 2025-03-21 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | 2026-01-28 | 0 | 000000&&000733&&000747&&001056&&001342 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | PEN | AWC | AWC
000734 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0016 | 0 | 131242-WSW41-QA-0016 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 11 | Approved with Comments | YES | 2024-11-25 | NO | Overdue | 304 |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | AWC | AWC
000735 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0042 | 0 | 131242-WSW41-LT-0042 | 2024-09-20 | Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area | Rev (0): Rejected. Please refer to S.O. correspondence no. 268 16 Dec 2024. | 2024-10-18 | 2025-11-20 | 274 | Rejected | YES | 2025-12-10 | NO | Overdue | 33 |  |  | NA | "Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area" | 2024-09-20 | 2024-09-20 | 0 | 000735 | 2024-09-20 | 00 | 1 | PEN | REJ | REJ
000736 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0032 | 0 | 131242-WSW41-MI-0032 | 2024-09-27 | Process & MEICA Meeting Minutes 0032_20240829 | For Information | 2024-10-25 | 2024-10-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0032_20240829" | 2024-09-27 | 2024-10-14 | 0 | 000000&&000736 | 2024-09-27, 2024-10-14 | 00 | 2 | PEN | INF | INF
000737 | 00 | Krishanthy | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-0008 | 2024-09-27 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-25 | 2024-10-24 |  | Approved with Comments | YES | 2024-11-14 | YES | Resubmitted |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | PEN | AWC | AWC
000737 | 01 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 1 | 131242-WSW41-RT-0008 | 2024-11-07 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.1: Approved | 2024-11-27 | 2024-11-28 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | PEN | APP | APP
000738 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0019 | 0 | 131242-WSW41-QA-0019 | 2024-09-28 | Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd) | Rev 0: Approved with comments. Refer to attached comment sheet for resubmission. | 2024-10-25 | 2024-10-29 | 2 | Approved with Comments | YES | 2024-11-19 | NO | Overdue | 308 |  |  | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | 2025-09-30 | 0 | 000000&&000738&&000814&&001343 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | PEN | AWC | AWC
000739 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0016 | 0 | 131242-WSW41-MI-0016 | 2024-10-01 | Monthly Progress Meeting Minutes 0016_20240924 | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 |  | For Information | NO |  | YES |  |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | PEN | INF | INF
000740 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-0016 | 2024-10-01 | Monthly Progress Presentation No. 16 (0924) | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | PEN | INF | INF
000741 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 0 | 131242-WSW41-QA-0014 | 2024-10-02 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-30 | 2024-11-05 | 3 | Approved with Comments | YES | 2024-11-25 | YES | Resubmitted |  |  |  | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2026-01-28 | 1 | 000000&&000741&&000971&&000998&&001336 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | AWC | AWC
000741 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 1 | 131242-WSW41-QA-0014 | 2025-03-18 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 1: Approved | 2025-04-07 | 2025-04-27 | 13 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2026-01-28 | 1 | 000000&&000741&&000971&&000998&&001336 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | APP | APP
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | C | 131242-WST00-DR-8005_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | NA | 131242-WST02-DR-0302_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | NA | 131242-WST02-DR-1200_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | NA | 131242-WST02-DR-1201_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | NA | 131242-WST02-DR-1202_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | NA | 131242-WST02-DR-1203_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | NA | 131242-WST02-DR-1204_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | NA | 131242-WST02-DR-1205_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | NA | 131242-WST02-DR-2200_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | NA | 131242-WST02-DR-2201_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | NA | 131242-WST02-DR-2202_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | NA | 131242-WST02-DR-2203_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | NA | 131242-WST02-DR-3200_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | NA | 131242-WST02-DR-3201_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | NA | 131242-WST02-DR-3202_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | NA | 131242-WST02-DR-5200_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | NA | 131242-WST02-DR-5201_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | NA | 131242-WST02-DR-5202_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | NA | 131242-WST02-DR-5203_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | NA | 131242-WST02-DR-5204_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | NA | 131242-WST02-DR-5205_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | NA | 131242-WST02-DR-5206_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | NA | 131242-WST02-DR-5207_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | NA | 131242-WST02-DR-5208_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | NA | 131242-WST02-DR-5209_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | S | 0002_ST608_BCA | NA | 131242-WST02-CL-0002_ST608_BCA | 2024-10-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-04 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-10-04 | NA | 000000 | 2024-10-04 | 00 | 1 | PEN | INF | INF
000743 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0015 | 0 | 131242-WSW41-PC-0015 | 2024-10-04 | Payment Claim No.15 | Rev(0): Approved. Please refer to S.O. correspondence no. 230 dated 4 Oct 2024 | 2024-11-04 | 2024-10-09 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.15" | 2024-10-04 | 2024-10-04 | 0 | 000743 | 2024-10-04 | 00 | 1 | PEN | APP | APP
000744 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 0 | 131242-WSW41-QA-0018 | 2024-10-04 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-04 | 2024-10-11 |  | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  |  |  | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | 2025-09-30 | 0 | 000000&&000744&&000757&&001054&&001057&&001339&&001357 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | PEN | AWC | AWC
000744 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 1 | 131242-WSW41-QA-0018 | 2024-10-30 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 1: Approved | 2024-11-20 | 2024-12-05 | 11 | Approved | NO |  | YES |  |  |  |  | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | 2025-09-30 | 0 | 000000&&000744&&000757&&001054&&001057&&001339&&001357 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | PEN | APP | APP
000745 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0043 | 0 | 131242-WSW41-LT-0043 | 2024-10-07 | Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 269 dated 17 Dec 2024. | 2024-11-05 | 2025-02-24 | 75 | Rejected | NO |  | YES |  |  |  | SO Corres 000269. Sent to Vincent on 17 Dec 2025 | NA | "Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024)" | 2024-10-07 | 2024-10-07 | 0 | 000745 | 2024-10-07 | 00 | 1 | PEN | REJ | REJ
000746 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0044 | 0 | 131242-WSW41-LT-0044 | 2024-10-07 | CV of Team member (WSHO) | Approved | 2024-11-05 | 2024-11-15 | 8 | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team member (WSHO)" | 2024-10-07 | 2024-10-07 | 0 | 000746 | 2024-10-07 | 00 | 1 | PEN | APP | APP
000747 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0017 | 0 | 131242-WSW41-QA-0017 | 2024-10-08 | Mock-up Temperature Monitoring Test Reports - G40 (Pan U) | For Information | 2024-11-06 | 2024-10-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | 2026-01-28 | 0 | 000000&&000733&&000747&&001056&&001342 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | PEN | INF | INF
000748 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0046 | 0 | 131242-WSW41-CD-0046 | 2024-10-08 | Submission Of BIM Coordination VCM Model (Sept-2024) | For Information. | 2024-11-06 | 2024-10-29 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission Of BIM Coordination VCM Model (Sept-2024)" | 2024-10-08 | 2024-10-08 | 0 | 000748 | 2024-10-08 | 00 | 1 | PEN | INF | INF
000749 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | C | 0007 | 0 | 131242-WST02-CL-0007 | 2024-10-09 | Bar chair Design for SSN Water Tanks Raft Slabs | For Information | 2024-11-07 | 2024-10-14 |  | Approved | NO |  | YES |  |  |  |  | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | PEN | APP | APP
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602_BCA | E | 131242-WST00-DR-0100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  |  |  | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 0101_ST602_BCA | NA | 131242-WST00-DR-0101_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 1100_ST602_BCA | NA | 131242-WST00-DR-1100_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 1101_ST602_BCA | NA | 131242-WST00-DR-1101_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 3100_ST602_BCA | NA | 131242-WST00-DR-3100_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 3101_ST602_BCA | NA | 131242-WST00-DR-3101_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 5101_ST602_BCA | NA | 131242-WST00-DR-5101_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | G | 8001_ST602_BCA | NA | 131242-WST00-DR-8001_ST602_BCA | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-11-08 | 1 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2024-10-09 | NA | 000000 | 2024-10-09 | 00 | 1 | PEN | INF | INF
000751 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-5451 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 |  | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  |  |  | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5451 | NA | 131242-WST02-DR-5451 | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-11 |  | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5452 | NA | 131242-WST02-DR-5452 | 2024-10-09 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-07 | 2024-10-11 |  | Approved with Comments | YES | 2024-11-01 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | AWC | AWC
000751 | 01 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5451 | NA | 131242-WST02-DR-5451 | 2024-11-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5452 | NA | 131242-WST02-DR-5452 | 2024-11-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | AWC | AWC
000751 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-5451 | 2024-12-17 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 9 | Approved | NO |  | YES |  |  |  |  | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5451 | NA | 131242-WST02-DR-5451 | 2024-11-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-07 | 2025-01-20 | 9 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5452 | NA | 131242-WST02-DR-5452 | 2024-11-08 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-07 | 2025-01-20 | 9 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-09 | 2025-10-23 | NA | 000000 | 2024-10-09, 2024-11-08, 2025-10-23 | 00 | 4 | PEN | APP | APP
000752 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 0 | 131242-WST02-RT-0003 | 2024-10-09 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-07 | 2024-11-15 | 6 | Approved with Comments | YES | 2024-12-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | 2025-07-01 | 2 | 000000&&000490&&000752 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | PEN | AWC | AWC
000752 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 1 | 131242-WST02-RT-0003 | 2024-12-10 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-31 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | 2025-07-01 | 2 | 000000&&000490&&000752 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | PEN | AWC | AWC
000752 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 2 | 131242-WST02-RT-0003 | 2025-01-20 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-13 | 24 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | 2025-07-01 | 2 | 000000&&000490&&000752 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | PEN | AWC | AWC
000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1400 | 0 | 131242-WST02-DR-1400 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 |  | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN- Biomass separator footing detail" | 2024-10-10 | 2025-12-18 | A | 000000&&000753&&001730 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 6 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5400 | NA | 131242-WST02-DR-5400 | 2024-10-10 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-08 | 2024-10-29 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Hookup Drawing -TSS Analyser" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Wall Mounted Pipe Support Design" | 2024-10-10 | 2025-12-18 | A | 000000&&000836&&001788 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00, NA | 5 | PEN | INF | INF
000754 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0045 | 0 | 131242-WSW41-LT-0045 | 2024-10-10 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025 | 2024-11-08 | 2025-11-20 | 260 | Rejected | YES | 2025-12-10 | NO | Overdue | 33 |  |  | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-10-10 | 2024-10-10 | 0 | 000754 | 2024-10-10 | 00 | 1 | PEN | REJ | REJ
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 0 | 131242-WST02-DS-5501 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | 2025-03-07 | In progress. Process (Qili) will provide updated Datasheet (some change as Pump Calculation, we just received SO cmt sheet on Pump Calc last week) -> in 2 weeks | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5511 | NA | 131242-WST02-DS-5511 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5521 | NA | 131242-WST02-DS-5521 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5531 | NA | 131242-WST02-DS-5531 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5541 | NA | 131242-WST02-DS-5541 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5551 | NA | 131242-WST02-DS-5551 | 2024-10-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-11 | 2024-11-27 | 12 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 1 | 131242-WST02-DS-5501 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5511 | NA | 131242-WST02-DS-5511 | 2025-03-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5521 | NA | 131242-WST02-DS-5521 | 2025-03-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5531 | NA | 131242-WST02-DS-5531 | 2025-03-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5541 | NA | 131242-WST02-DS-5541 | 2025-03-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5551 | NA | 131242-WST02-DS-5551 | 2025-03-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-03-24 | 2025-10-06 | 136 | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-11 | 2025-03-04 | NA | 000000 | 2024-10-11, 2025-03-04 | 00 | 2 | PEN | AWC | AWC
000756 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0020 | 0 | 131242-WSW41-QA-0020 | 2024-10-11 | Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-11 | 2024-11-19 | 6 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Monthly Concrete Cube Records for Structural works for September 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" | 2024-10-11 | 2025-09-30 | 0 | 000000&&000756&&000830 | 2024-10-11, 2024-11-21, 2025-09-30 | 00 | 3 | PEN | AWC | AWC
000757 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0018 | 0 | 131242-WSW41-QA-0018 | 2024-10-11 | Mock-up Temperature Monitoring Test Reports – G45 (Pan U) | For information. | 2024-11-11 | 2024-10-24 |  | For Information | NO |  | YES |  |  |  |  | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | 2025-09-30 | 0 | 000000&&000744&&000757&&001054&&001057&&001339&&001357 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | PEN | INF | INF
000758 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 0 | 131242-WSW41-VI-1006 | 2024-10-12 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-24 | 9 | Approved with Comments | YES | 2024-12-12 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2024-10-12 | 2025-01-16 | 1 | 000758 | 2024-10-12, 2025-01-16 | 00, 01 | 2 | PEN | AWC | AWC
000758 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 1 | 131242-WSW41-VI-1006 | 2025-01-16 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-05 | 2025-01-20 |  | Approved with Comments | NO |  | YES |  |  |  | As per SO response, Resubmission is not required. | NA | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2024-10-12 | 2025-01-16 | 1 | 000758 | 2024-10-12, 2025-01-16 | 00, 01 | 2 | PEN | AWC | AWC
000759 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0_NIL | 131242-WSW41-MS-0002 | 2024-10-14 | Delivery and Storage of Compressor Package at Biosolids Building | Rev.0: As requested by Contractor to reject the submittal. | 2024-11-12 | 2024-10-14 |  | Rejected | YES | 2024-11-04 | YES | Resubmitted |  |  |  | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | PEN | REJ | REJ
000759 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0 | 131242-WSW41-MS-0002 | 2024-10-15 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 0: Approved with comments - Revise and Resubmit | 2024-11-05 | 2024-10-24 |  | Approved with Comments | YES | 2024-11-14 | YES | Resubmitted |  |  |  | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | PEN | AWC | AWC
000759 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 1 | 131242-WSW41-MS-0002 | 2024-10-30 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 2: Approved | 2024-11-20 | 2024-12-03 | 9 | Approved | NO |  | YES |  |  |  |  | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | PEN | APP | APP
000760 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0014 | 0 | 131242-WSW41-PS-0014 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Jul 2024 | Rev 0: Scoring confirmed to be at 98/100 | 2024-11-12 | 2024-11-15 | 3 | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Jul 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-07 | 2024-10-14 | 0 | 000000&&000760 | 2024-08-07, 2024-10-14 | 00 | 2 | PEN | INF | INF
000761 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0015 | 0 | 131242-WSW41-PS-0015 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Aug 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-11-12 | 2024-11-15 | 3 | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Aug 2024" && "Monthly Progress Presentation No. 15 (0824)" | 2024-09-04 | 2024-10-14 | 0 | 000701&&000761 | 2024-09-04, 2024-10-14 | 00 | 2 | PEN | INF | INF
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0031 | 0 | 131242-WSW41-MI-0031 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | 2024-10-14 | 0 | 000000&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | C | 0032 | NA | 131242-WSW41-MI-0032 | 2024-10-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0032_20240829" | 2024-09-27 | 2024-10-14 | 0 | 000000&&000736 | 2024-09-27, 2024-10-14 | 00 | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | C | 0033 | NA | 131242-WSW41-MI-0033 | 2024-10-14 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-12 | 2024-10-24 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-14 | 2024-10-14 | NA | 000000 | 2024-10-14 | 00 | 1 | PEN | INF | INF
000763 | 00 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 0 | 131242-WST02-CD-0005 | 2024-10-15 | SSN Instrument List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-13 | 2025-02-13 | 62 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  |  |  | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | PEN | NAP | NAP
000763 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 1 | 131242-WST02-CD-0005 | 2025-10-27 | SSN Instrument List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-11-14 | 2026-01-26 | 50 | Approved with Comments | YES | 2026-02-13 | NO | Overdue | -16 |  |  | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | PEN | AWC | AWC
000764 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 0 | 131242-WSD11-QA-0004 | 2024-10-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-15 | 2025-03-25 | 88 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2026-01-28 | 1 | 000000&&000764 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, NA | 5 | PEN | AWC | AWC
000764 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 1 | 131242-WSD11-QA-0004 | 2025-05-30 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-19 | 2025-06-04 |  | Approved with Comments | YES | 2025-06-24 | NO | Overdue | 154 |  |  | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2026-01-28 | 1 | 000000&&000764 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, NA | 5 | PEN | AWC | AWC
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614 | A | 131242-WSW41-DR-0310_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  |  |  | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0311_ST614 | NA | 131242-WSW41-DR-0311_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0312_ST614 | NA | 131242-WSW41-DR-0312_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0313_ST614 | NA | 131242-WSW41-DR-0313_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0314_ST614 | NA | 131242-WSW41-DR-0314_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0315_ST614 | NA | 131242-WSW41-DR-0315_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0316_ST614 | NA | 131242-WSW41-DR-0316_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0317_ST614 | NA | 131242-WSW41-DR-0317_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1100_ST614 | NA | 131242-WSW41-DR-1100_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1101_ST614 | NA | 131242-WSW41-DR-1101_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1102_ST614 | NA | 131242-WSW41-DR-1102_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1103_ST614 | NA | 131242-WSW41-DR-1103_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1104_ST614 | NA | 131242-WSW41-DR-1104_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 2100_ST614 | NA | 131242-WSW41-DR-2100_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 2101_ST614 | NA | 131242-WSW41-DR-2101_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 3100_ST614 | NA | 131242-WSW41-DR-3100_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5100_ST614 | NA | 131242-WSW41-DR-5100_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5101_ST614 | NA | 131242-WSW41-DR-5101_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5102_ST614 | NA | 131242-WSW41-DR-5102_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5103_ST614 | NA | 131242-WSW41-DR-5103_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 8002_ST614 | NA | 131242-WSW41-DR-8002_ST614 | 2024-10-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-15 | 2024-11-08 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-17 | 2024-10-17 | NA | 000000 | 2024-10-17 | 00 | 1 | PEN | INF | INF
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | CL | M | 5461 | 0 | 131242-WST02-CL-5461 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 |  | Approved with Comments | YES | 2024-12-05 | YES | Resubmitted |  |  |  | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | 2025-04-04 | 2 | 000766 | 2024-10-18, 2025-04-04 | 00, 02 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5461 | NA | 131242-WST02-DR-5461 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-18 | 2024-11-15 |  | Approved with Comments | YES | 2024-12-05 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-10-23 | A.1 | 000000&&000766 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5463 | NA | 131242-WST02-DR-5463 | 2024-10-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-18 | 2024-11-15 |  | Approved with Comments | YES | 2024-12-05 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-04-04 | NA | 000000 | 2024-10-18, 2024-12-06, 2025-04-04 | 00 | 3 | PEN | AWC | AWC
000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | A.1 | 131242-WST02-DR-5461 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-12 |  | Approved with Comments | YES | 2025-01-02 | YES | Resubmitted |  |  | The Only comment is to get PE endorsement (Mech PE) | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-10-23 | A.1 | 000000&&000766 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01 | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5463 | NA | 131242-WST02-DR-5463 | 2024-12-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-01-06 | 2024-12-12 |  | Approved with Comments | YES | 2025-01-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-04-04 | NA | 000000 | 2024-10-18, 2024-12-06, 2025-04-04 | 00 | 3 | PEN | AWC | AWC
000766 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5461 | 2 | 131242-WST02-CL-5461 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 115 | Approved | NO |  | YES |  |  |  |  | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | 2025-04-04 | 2 | 000766 | 2024-10-18, 2025-04-04 | 00, 02 | 2 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5461 | NA | 131242-WST02-DR-5461 | 2025-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-24 | 2025-10-06 | 115 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-10-23 | A.1 | 000000&&000766 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01 | 4 | PEN | APP | APP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5463 | NA | 131242-WST02-DR-5463 | 2025-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2025-04-24 | 2025-10-06 | 115 | Approved | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-18 | 2025-04-04 | NA | 000000 | 2024-10-18, 2024-12-06, 2025-04-04 | 00 | 3 | PEN | APP | APP
000767 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0017 | 0 | 131242-WSW41-RT-0017 | 2024-10-19 | C4B Monthly Progress Report Number No.17 (09 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-11-18 | 2024-10-25 |  | Approved with Comments | YES | 2024-11-15 | NO | Overdue | 310 |  |  | NA | "C4B Monthly Progress Report Number No.17 (09 24) " | 2024-10-19 | 2024-10-19 | 0 | 000767 | 2024-10-19 | 00 | 1 | PEN | AWC | AWC
000768 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0046 | 0 | 131242-WSW41-LT-0046 | 2024-10-21 | Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings | Rev (0): Received for information. lease refer to S.O. correspondence no. 289 dated 21 Jan 2025. | 2024-11-19 | 2025-11-20 | 253 | For Information | NO |  | YES |  |  |  |  | NA | "Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings" | 2024-10-21 | 2024-10-21 | 0 | 000768 | 2024-10-21 | 00 | 1 | PEN | INF | INF
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5501 | 0 | 131242-WST02-CL-5501 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | 2025-04-30 | Pending model update, need PE endorsement | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5511 | NA | 131242-WST02-CL-5511 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-21 | 2024-10-21 | NA | 000000 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5521 | NA | 131242-WST02-CL-5521 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-21 | 2024-10-21 | NA | 000000 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5531 | NA | 131242-WST02-CL-5531 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-21 | 2024-10-21 | NA | 000000 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5541 | NA | 131242-WST02-CL-5541 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-21 | 2024-10-21 | NA | 000000 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 5551 | NA | 131242-WST02-CL-5551 | 2024-10-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-19 | 2025-01-20 | 42 | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-21 | 2024-10-21 | NA | 000000 | 2024-10-21 | 00 | 1 | PEN | AWC | AWC
000770 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | K | 0001 | 0 | 131242-WST02-CL-0001 | 2024-10-22 | SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs | Rev 0: Approved with comments. Please refer to comment sheet. | 2024-11-20 | 2024-11-21 | 1 | Approved with Comments | YES | 2024-12-11 | NO | Overdue | 292 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Cable Sizing Calculations" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2025-05-30 | 2 | 000000&&000173&&000199&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | PEN | AWC | AWC
000771 | 00 | Radha | QAQC | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-0008 | 2024-10-22 | Bored Piling Pile Eccentricity Reports (ECC 13 to 18) | For Information. Please find attached comment sheet. | 2024-11-20 | 2024-11-04 |  | For Information | NO |  | YES |  |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | PEN | INF | INF
000772 | 00 | Qili | Process | NA | 131242 | WST02 | RT | E | 0006 | 0 | 131242-WST02-RT-0006 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | 84 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "SSN Hazardous Area Assessment Report" && "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" && "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | 2025-11-20 | 0 | 000545&&000772&&001856 | 2024-07-04, 2024-10-23, 2025-11-20 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 8001 | NA | 131242-WST02-DR-8001 | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-21 | 2025-03-25 | 84 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2024-10-23 | NA | 000000 | 2024-10-23 | 00 | 1 | PEN | AWC | AWC
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | A | 131242-WSW41-DR-0310_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  |  |  | NA | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | 2025-01-03 | A | 000000&&000773 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | NA | 131242-WSW41-DR-0311_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | NA | 131242-WSW41-DR-0312_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | NA | 131242-WSW41-DR-0313_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | NA | 131242-WSW41-DR-0314_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | NA | 131242-WSW41-DR-0315_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0316_ST614_BCA | NA | 131242-WSW41-DR-0316_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2024-10-23 | NA | 000000 | 2024-10-23 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 0317_ST614_BCA | NA | 131242-WSW41-DR-0317_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2024-10-23 | NA | 000000 | 2024-10-23 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | NA | 131242-WSW41-DR-1100_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | NA | 131242-WSW41-DR-1101_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | NA | 131242-WSW41-DR-1102_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | NA | 131242-WSW41-DR-1103_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | NA | 131242-WSW41-DR-1104_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | NA | 131242-WSW41-DR-2100_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | NA | 131242-WSW41-DR-2101_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | NA | 131242-WSW41-DR-3100_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | NA | 131242-WSW41-DR-5100_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | NA | 131242-WSW41-DR-5101_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | NA | 131242-WSW41-DR-5102_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | NA | 131242-WSW41-DR-5103_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | NA | 131242-WSW41-DR-8002_ST614_BCA | 2024-10-23 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-21 | 2024-12-14 | 16 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | D | 000000&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | PEN | INF | INF
000774 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 0 | 131242-WSW41-DS-1386 | 2024-10-23 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-21 | 2024-11-21 |  | Approved with Comments | YES | 2024-12-11 | YES | Resubmitted |  |  |  | NA | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-10-23 | 2024-12-20 | 1 | 000774 | 2024-10-23, 2024-12-20 | 00, 01 | 2 | PEN | AWC | AWC
000774 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 1 | 131242-WSW41-DS-1386 | 2024-12-20 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 1: Rejected. Wrong comment reply sheet has been attached. | 2025-01-10 | 2025-02-18 | 25 | Rejected | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-10-23 | 2024-12-20 | 1 | 000774 | 2024-10-23, 2024-12-20 | 00, 01 | 2 | PEN | REJ | REJ
000775 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 0 | 131242-WSW41-MS-0019 | 2024-10-23 | MSRA for RC Wall | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-11-15 |  | Approved with Comments | YES | 2024-12-05 | YES | Resubmitted |  |  |  | NA | "MSRA for RC Wall" | 2024-10-23 | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
000775 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-0019 | 2024-11-26 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2024-12-16 | 2024-12-18 | 2 | Approved with Comments | YES | 2025-01-08 | YES | Resubmitted |  |  |  | NA | "MSRA for RC Wall" | 2024-10-23 | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
000775 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-0019 | 2024-12-19 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2025-01-09 | 2025-01-08 |  | Approved with Comments | YES | 2025-01-28 | NO | Overdue | 259 |  |  | NA | "MSRA for RC Wall" | 2024-10-23 | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
000776 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0047 | 0 | 131242-WSW41-LT-0047 | 2024-10-25 | Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works | Rejected. Please refer to S.O. correspondence no. 276 dated 7 January 2025. | 2024-11-25 | 2025-08-25 | 187 | Rejected | NO |  | YES |  |  |  |  | NA | "Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works " | 2024-10-25 | 2024-10-25 | 0 | 000776 | 2024-10-25 | 00 | 1 | PEN | REJ | REJ
000777 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 0 | 131242-WSW41-VI-0010 | 2024-10-25 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-11-25 | 2024-11-27 | 2 | Approved with Comments | YES | 2024-12-17 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | AWC | AWC
000777 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 1 | 131242-WSW41-VI-0010 | 2025-01-11 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 8 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | AWC | AWC
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-1024 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 103 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | 2026-02-04 | A | 000000&&000778 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 1025 | NA | 131242-WST02-DR-1025 | 2024-10-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-25 | 2025-04-27 | 103 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 | Tenwit in Progress |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 2000 | NA | 131242-WST02-DR-2000 | 2024-10-26 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-25 | 2025-04-27 | 103 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000779 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 0001 | A | 131242-WST02-DR-0001 | 2024-10-26 | SSN Piping Drawing Index | Rev 0: For Information | 2024-11-25 | 2024-11-27 | 2 | For Information | NO |  | YES |  |  |  |  | NA | "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | 2025-02-21 | A | 000000&&000779&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00, NA | 4 | PEN | INF | INF
000780 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0009 | 0 | 131242-WSW41-VI-0009 | 2024-10-26 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-20 |  | Approved with Comments | YES | 2024-12-10 | NO | Overdue | 293 |  |  | NA | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " && "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | 2023-08-15 | 2024-10-26 | 0 | 000071&&000780 | 2023-08-15, 2024-10-26 | 00 | 2 | PEN | AWC | AWC
000781 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-0002 | 2024-10-26 | Vendor Approval of Raised Floor – Hemsco Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-15 |  | Approved with Comments | YES | 2024-12-05 | NO | Overdue | 296 |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
000782 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 0 | 131242-WSW41-QA-0021 | 2024-10-28 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 0: Not approved - Revise and Resubmit | 2024-11-26 | 2024-11-27 | 1 | Not Approved | YES | 2024-12-17 | YES | Resubmitted |  |  |  | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | PEN | NAP | NAP
000782 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 1 | 131242-WSW41-QA-0021 | 2024-12-14 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 1: Approved | 2025-01-03 | 2025-01-20 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | PEN | APP | APP
000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0001 | A | 131242-WSD11-DR-0001 | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | 13 | For Information | NO |  | YES |  |  |  |  | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0002 | NA | 131242-WSD11-DR-0002 | 2024-10-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-26 | 2024-12-14 | 13 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-28 | 2026-01-05 | NA | 000000 | 2024-10-28, 2025-12-14, 2026-01-05 | 00, NA | 3 | PEN | INF | INF
000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | A | 131242-WSD11-DR-5150 | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | 1 | Approved with Comments | YES | 2024-12-17 | NO | Overdue | 288 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Ring Circulation Pump Drawing" | 2024-10-28 | 2025-06-12 | A | 000000&&000784 | 2024-10-28, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | NA | 131242-WSD11-DR-5160 | 2024-10-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-26 | 2024-11-27 | 1 | Approved with Comments | YES | 2024-12-17 | NO | Overdue | 288 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-28 | 2025-06-12 | NA | 000000 | 2024-10-28, 2025-06-12 | 00 | 2 | PEN | AWC | AWC
000785 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0016 | 0 | 131242-WSW41-PS-0016 | 2024-10-28 | Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024 | For Information | 2024-11-26 | 2024-11-15 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | PEN | INF | INF
000786 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0010 | 0 | 131242-WSW41-RT-0010 | 2024-10-28 | Report of DFS (GUIDE 3) for PIPE RACKS | Rev.0: Approved with comments. Revise and resubmit. | 2024-11-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "C4B Monthly Progress Report Number No.10 (02 24)" && "Report of DFS (GUIDE 3) for PIPE RACKS" | 2024-03-18 | 2024-10-28 | 0 | 000377&&000786 | 2024-03-18, 2024-10-28 | 00 | 2 | PEN | AWC | AWC
000787 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0011 | 0 | 131242-WSW41-RT-0011 | 2024-10-28 | Report of PROJECT SAFETY REVIEW for PIPE RACKS | For Information | 2024-11-26 | 2024-12-18 | 16 | For Information | NO |  | YES |  |  |  |  | NA | "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-10-28 | 2024-10-28 | 0 | 000787 | 2024-10-28 | 00 | 1 | PEN | INF | INF
000788 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0016 | 0 | 131242-WSW41-PC-0016 | 2024-10-29 | Payment Claim No.16 | Rev(0): Approved. Please refer to S.O. Correspondence no. 244 dated 1 Nov 2024. | 2024-11-27 | 2024-11-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.16" | 2024-10-29 | 2024-10-29 | 0 | 000788 | 2024-10-29 | 00 | 1 | PEN | APP | APP
000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9100 | A | 131242-WSD11-DR-9100 | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | 2025-03-05 | 2nd priority (Shall update and submit under as built drawing) | NA | "THP Underground Piping and Cast in Details" | 2024-10-30 | 2024-10-30 | A | 000789 | 2024-10-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1190 | NA | 131242-WSD11-DR-1190 | 2024-10-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-28 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-30 | 2025-08-13 | NA | 000000 | 2024-10-30, 2025-06-16, 2025-08-13 | 00, NA | 3 | PEN | AWC | AWC
000790 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0012 | 0 | 131242-WSW41-RT-0012 | 2024-10-30 | Quarterly Safety Review Follow Up on ERSS | For Information | 2024-11-28 | 2024-11-15 |  | For Information | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | PEN | INF | INF
000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0034 | 0 | 131242-WSW41-MI-0034 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | 2024-10-31 | 2024-10-31 | 0 | 000791 | 2024-10-31 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | C | 0035 | NA | 131242-WSW41-MI-0035 | 2024-10-31 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-11-28 | 2024-11-15 |  | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-31 | 2024-10-31 | NA | 000000 | 2024-10-31 | 00 | 1 | PEN | INF | INF
000792 | 00 | PCM | PCM | NA | 131242 | WSW41 | MI | PM | 0017 | 0 | 131242-WSW41-MI-0017 | 2024-10-31 | Monthly Progress Meeting Minutes 0017_20241023 | Rev. 0 - For Information | 2024-11-28 | 2024-11-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | 2024-10-31 | 0 | 000000&&000298&&000320&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | PEN | INF | INF
000793 | 00 | PCM | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-0016 | 2024-10-31 | Monthly Progress Presentation No. 17 (1024) | For Information | 2024-11-28 | 2024-11-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | PEN | INF | INF
000794 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0001 | 0 | 131242-WST02-VI-0001 | 2024-10-31 | Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-28 | 2024-11-25 |  | Approved with Comments | YES | 2024-12-13 | NO | Overdue | 290 |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | AWC | AWC
000795 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0022 | 0 | 131242-WSW41-QA-0022 | 2024-11-01 | FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver) | Rev 0: Approved | 2024-11-29 | 2024-12-05 | 4 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | PEN | APP | APP
000796 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0023 | 0 | 131242-WSW41-VI-0023 | 2024-11-02 | Vendor Approval of EICA Material and Accessories (Cable Gland) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-11-29 | 2024-11-24 |  | Approved with Comments | YES | 2024-12-12 | NO | Overdue | 291 |  |  | NA | "Vendor Approval of EICA Material and Accessories (Cable Gland)" | 2024-11-02 | 2024-11-02 | 0 | 000796 | 2024-11-02 | 00 | 1 | PEN | AWC | AWC
000797 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0022 | 0 | 131242-WSW41-VI-0022 | 2024-11-02 | Preliminary Design and Vendor Approval of Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-29 | 2024-11-24 |  | Approved with Comments | YES | 2024-12-12 | NO | Overdue | 291 |  |  | NA | "Preliminary Design and Vendor Approval of Unistrut Support" | 2024-11-02 | 2024-11-02 | 0 | 000797 | 2024-11-02 | 00 | 1 | PEN | AWC | AWC
000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | A | 131242-WST02-DR-5311 | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | 3 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  | 2025-03-28 | In Progress | NA | "GA Drawing for Centrifugal Pump" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-04 | 2025-09-24 | B | 000000&&000798 | 2024-11-04, 2025-04-17, 2025-09-24 | 00, 01 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5301 | NA | 131242-WST02-DR-5301 | 2024-11-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-02 | 2024-12-05 | 3 | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-04 | 2025-11-12 | NA | 000000 | 2024-11-04, 2025-04-17, 2025-11-12 | 00 | 3 | PEN | AWC | AWC
000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | B | 131242-WST02-DR-5311 | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | 184 | Awaiting S.O.'s response | [7 empty] | NA | "GA Drawing for Centrifugal Pump" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-04 | 2025-09-24 | B | 000000&&000798 | 2024-11-04, 2025-04-17, 2025-09-24 | 00, 01 | 3 | PEN | PEN | PEN
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5301 | NA | 131242-WST02-DR-5301 | 2025-04-17 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-05-07 | 2024-12-05 | 184 | Awaiting S.O.'s response | [5 empty] | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-04 | 2025-11-12 | NA | 000000 | 2024-11-04, 2025-04-17, 2025-11-12 | 00 | 3 | PEN | PEN | PEN
000799 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2001 | 0 | 131242-WSW41-VI-2001 | 2024-11-05 | Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package | Rev 0: Approved | 2024-12-03 | 2024-12-05 | 2 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package" | 2024-11-05 | 2024-11-05 | 0 | 000799 | 2024-11-05 | 00 | 1 | PEN | APP | APP
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618 | A | 131242-WSD11-DR-2300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3300_ST618 | NA | 131242-WSD11-DR-3300_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3301_ST618 | NA | 131242-WSD11-DR-3301_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5300_ST618 | NA | 131242-WSD11-DR-5300_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5301_ST618 | NA | 131242-WSD11-DR-5301_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5302_ST618 | NA | 131242-WSD11-DR-5302_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5303_ST618 | NA | 131242-WSD11-DR-5303_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5304_ST618 | NA | 131242-WSD11-DR-5304_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5305_ST618 | NA | 131242-WSD11-DR-5305_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5306_ST618 | NA | 131242-WSD11-DR-5306_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5307_ST618 | NA | 131242-WSD11-DR-5307_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5308_ST618 | NA | 131242-WSD11-DR-5308_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5309_ST618 | NA | 131242-WSD11-DR-5309_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5310_ST618 | NA | 131242-WSD11-DR-5310_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 8001_ST618 | NA | 131242-WSD11-DR-8001_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 0302_ST618 | NA | 131242-WSD11-DR-0302_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1300_ST618 | NA | 131242-WSD11-DR-1300_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1301_ST618 | NA | 131242-WSD11-DR-1301_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1302_ST618 | NA | 131242-WSD11-DR-1302_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1303_ST618 | NA | 131242-WSD11-DR-1303_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1304_ST618 | NA | 131242-WSD11-DR-1304_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1305_ST618 | NA | 131242-WSD11-DR-1305_ST618 | 2024-11-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-04 | 2024-12-07 | 2 | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-06 | 2024-11-06 | NA | 000000 | 2024-11-06 | 00 | 1 | PEN | AWC | AWC
000801 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0048 | 0 | 131242-WSW41-LT-0048 | 2024-11-06 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 333 dated 17 April 2025. | 2024-12-04 | 2025-11-20 | 242 | For Information | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024)" | 2024-11-06 | 2024-11-06 | 0 | 000801 | 2024-11-06 | 00 | 1 | PEN | INF | INF
000802 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 0 | 131242-WSW41-VI-0008 | 2024-11-06 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-04 | 2024-12-05 | 1 | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000802 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 1 | 131242-WSW41-VI-0008 | 2025-01-26 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-04-27 | 49 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000802 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 2 | 131242-WSW41-VI-0008 | 2025-06-16 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-11-24 | 100 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | PEN | AWC | AWC
000803 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0049 | 0 | 131242-WSW41-CD-0049 | 2024-11-08 | Submission of BIM Coordination VCM Model (Oct 2024) | For Information | 2024-12-06 | 2024-11-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission of BIM Coordination VCM Model (Oct 2024)" | 2024-11-08 | 2024-11-08 | 0 | 000803 | 2024-11-08 | 00 | 1 | PEN | INF | INF
000804 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0018 | 0 | 131242-WSW41-RT-0018 | 2024-11-09 | C4B Monthly Progress Report Number No.18 (10 24) | Rev. 0 - Approved with comments (need to re-submit / see attached comments sheet) | 2024-12-06 | 2024-12-03 |  | Approved with Comments | YES | 2024-12-23 | NO | Overdue | 284 |  |  | NA | "C4B Monthly Progress Report Number No.18 (10 24) " | 2024-11-09 | 2024-11-09 | 0 | 000804 | 2024-11-09 | 00 | 1 | PEN | AWC | AWC
000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0004 | 0 | 131242-WST02-CL-0004 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 |  | Approved with Comments | YES | 2024-12-23 | NO | Overdue | 284 |  |  | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | S | 0005 | NA | 131242-WST02-CL-0005 | 2024-11-11 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-09 | 2024-12-03 |  | Approved with Comments | YES | 2024-12-23 | NO | Overdue | 284 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" | 2024-03-28 | 2025-11-12 | 2 | 000000&&000406&&000416 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | PEN | AWC | AWC
000806 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 0 | 131242-WSW41-VI-0030 | 2024-11-11 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-09 | 2024-12-05 |  | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  | 2025-03-21 | In progress. as SO comment s/n.4, provide Vendor product presentation slides to SO on 14 Feb, will resubmit | NA | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2024-11-11 | 2025-03-20 | 1 | 000806 | 2024-11-11, 2025-03-20 | 00, 01 | 2 | PEN | AWC | AWC
000806 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 1 | 131242-WSW41-VI-0030 | 2025-03-20 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-11-24 | 159 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2024-11-11 | 2025-03-20 | 1 | 000806 | 2024-11-11, 2025-03-20 | 00, 01 | 2 | PEN | AWC | AWC
000807 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 0 | 131242-WSW41-DS-1388 | 2024-11-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-21 |  | Approved with Comments | YES | 2024-12-11 | YES | Resubmitted |  |  |  | NA | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2024-11-12 | 2025-03-12 | 1 | 000807 | 2024-11-12, 2025-03-12 | 00, 01 | 2 | PEN | AWC | AWC
000807 | 01 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 1 | 131242-WSW41-DS-1388 | 2025-03-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 1: Approved. | 2025-04-01 | 2025-05-05 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2024-11-12 | 2025-03-12 | 1 | 000807 | 2024-11-12, 2025-03-12 | 00, 01 | 2 | PEN | APP | APP
000808 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1387 | 0 | 131242-WSW41-DS-1387 | 2024-11-12 | Sample board submission for SS Cable ladder, trays & accessories (United U-Li) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-25 |  | Approved with Comments | YES | 2024-12-13 | NO | Overdue | 290 |  |  | NA | "Sample board submission for SS Cable ladder, trays & accessories (United U-Li)" | 2024-11-12 | 2024-11-12 | 0 | 000808 | 2024-11-12 | 00 | 1 | PEN | AWC | AWC
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1000 | A | 131242-WST02-DR-1000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | 2026-02-03 | A.2 | 000000&&000160&&000188&&000189&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 1001 | NA | 131242-WST02-DR-1001 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 2000 | NA | 131242-WST02-DR-2000 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 12 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 3000 | NA | 131242-WST02-DR-3000 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&000607 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, NA | 9 | PEN | INF | INF
000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1003 | A | 131242-WST02-DR-1003 | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 2002 | NA | 131242-WST02-DR-2002 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | INF | INF
000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1004 | A | 131242-WST02-DR-1004 | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 2003 | NA | 131242-WST02-DR-2003 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | INF | INF
000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1009 | A | 131242-WST02-DR-1009 | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 |  | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | 2026-02-09 | A | 000000&&000812 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 16 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 2007 | NA | 131242-WST02-DR-2007 | 2024-11-13 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-11 | 2024-12-08 |  | For Information | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-13 | 2026-02-03 | NA | 000000 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 6 | PEN | INF | INF
000813 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 0 | 131242-WSW41-QA-0023 | 2024-11-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-05 |  | Approved with Comments | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | PEN | AWC | AWC
000813 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 1 | 131242-WSW41-QA-0023 | 2025-10-23 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-12 | 2025-12-23 | 29 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | PEN | AWC | AWC
000814 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0019 | 0 | 131242-WSW41-QA-0019 | 2024-11-14 | Monthly Concrete Cube Records for Structural works for August 2024 | For Information | 2024-12-12 | 2024-12-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | 2025-09-30 | 0 | 000000&&000738&&000814&&001343 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | PEN | INF | INF
000815 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0004 | 0 | 131242-WSW41-MS-0004 | 2024-11-15 | MSRA and SWP for Installation of Manway | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-05 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | PEN | AWC | AWC
000816 | 00 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0005 | 0 | 131242-WSW41-VI-0005 | 2024-11-16 | Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech) | Rev 0: Rejected. Based on CES request. | 2024-12-13 | 2024-12-05 |  | Rejected | YES | 2024-12-26 | YES | Resubmitted |  |  | Email sent on 25 Nov 24 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | REJ | REJ
000817 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0024 | 0 | 131242-WSW41-VI-0024 | 2024-11-16 | Preliminary Design and Vendor Approval – HDMANN Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-13 | 2024-12-06 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "Preliminary Design and Vendor Approval – HDMANN Unistrut Support" | 2024-11-16 | 2024-11-16 | 0 | 000817 | 2024-11-16 | 00 | 1 | PEN | AWC | AWC
000818 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0003 | 0 | 131242-WSW41-MS-0003 | 2024-11-16 | MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-1001 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 21 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1002 | NA | 131242-WSD11-DR-1002 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2025-01-16 | 21 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 1003 | NA | 131242-WSD11-DR-1003 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2025-01-16 | 21 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 2000 | NA | 131242-WSD11-DR-2000 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2025-01-16 | 21 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-18 | 2026-01-05 | NA | 000000 | 2024-11-18, 2025-12-14, 2026-01-05 | 00, NA | 3 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 3000 | NA | 131242-WSD11-DR-3000 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2025-01-16 | 21 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | INF | INF
000820 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5000 | A | 131242-WSD11-DR-5000 | 2024-11-18 | THP Door and Finishes Schedules | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-18 | 2 | Not Approved | YES | 2025-01-08 | NO | Overdue | 273 |  |  | NA | "THP Door and Finishes Schedules" | 2024-11-18 | 2025-12-16 | A | 000000&&000820 | 2024-11-18, 2025-12-16 | 00, NA | 2 | PEN | NAP | NAP
000821 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5006 | A | 131242-WSD11-DR-5006 | 2024-11-18 | THP Corridor & Stair Compartment Waterproofing Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-21 | 4 | Not Approved | YES | 2025-01-10 | NO | Overdue | 271 |  |  | NA | "THP Corridor & Stair Compartment Waterproofing Details" | 2024-11-18 | 2024-11-18 | A | 000821 | 2024-11-18 | 00 | 1 | PEN | NAP | NAP
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5001 | A | 131242-WSD11-DR-5001 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "THP Handrail Layout and Cad Ladder Details" && "Typical Fire Alarm Installation Detail (THP)" | 2024-11-18 | 2025-12-16 | A | 000822&&001901 | 2024-11-18, 2025-12-16 | 00 | 2 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 5002 | NA | 131242-WSD11-DR-5002 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-18 | 2024-11-18 | NA | 000000 | 2024-11-18 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 5003 | NA | 131242-WSD11-DR-5003 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-18 | 2024-11-18 | NA | 000000 | 2024-11-18 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | A | 5004 | NA | 131242-WSD11-DR-5004 | 2024-11-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-16 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-18 | 2024-11-18 | NA | 000000 | 2024-11-18 | 00 | 1 | PEN | AWC | AWC
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609 | D | 131242-WST00-DR-8004_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  |  |  | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0300_ST609 | NA | 131242-WST02-DR-0300_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0301_ST609 | NA | 131242-WST02-DR-0301_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0303_ST609 | NA | 131242-WST02-DR-0303_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0304_ST609 | NA | 131242-WST02-DR-0304_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0305_ST609 | NA | 131242-WST02-DR-0305_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0306_ST609 | NA | 131242-WST02-DR-0306_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0307_ST609 | NA | 131242-WST02-DR-0307_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0308_ST609 | NA | 131242-WST02-DR-0308_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 0309_ST609 | NA | 131242-WST02-DR-0309_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1100_ST609 | NA | 131242-WST02-DR-1100_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1101_ST609 | NA | 131242-WST02-DR-1101_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1102_ST609 | NA | 131242-WST02-DR-1102_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1103_ST609 | NA | 131242-WST02-DR-1103_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2100_ST609 | NA | 131242-WST02-DR-2100_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2101_ST609 | NA | 131242-WST02-DR-2101_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 2102_ST609 | NA | 131242-WST02-DR-2102_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3100_ST609 | NA | 131242-WST02-DR-3100_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3101_ST609 | NA | 131242-WST02-DR-3101_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 3102_ST609 | NA | 131242-WST02-DR-3102_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5100_ST609 | NA | 131242-WST02-DR-5100_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5101_ST609 | NA | 131242-WST02-DR-5101_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5102_ST609 | NA | 131242-WST02-DR-5102_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5103_ST609 | NA | 131242-WST02-DR-5103_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5104_ST609 | NA | 131242-WST02-DR-5104_ST609 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2025-01-16 | 20 | For Information | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-19 | 2024-11-19 | NA | 000000 | 2024-11-19 | 00 | 1 | PEN | INF | INF
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-0300_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 0301_ST617 | NA | 131242-WSD11-DR-0301_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1000_ST617 | NA | 131242-WSD11-DR-1000_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1001_ST617 | NA | 131242-WSD11-DR-1001_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1002_ST617 | NA | 131242-WSD11-DR-1002_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1003_ST617 | NA | 131242-WSD11-DR-1003_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 2000_ST617 | NA | 131242-WSD11-DR-2000_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 2001_ST617 | NA | 131242-WSD11-DR-2001_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3000_ST617 | NA | 131242-WSD11-DR-3000_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3001_ST617 | NA | 131242-WSD11-DR-3001_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3002_ST617 | NA | 131242-WSD11-DR-3002_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5000_ST617 | NA | 131242-WSD11-DR-5000_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5001_ST617 | NA | 131242-WSD11-DR-5001_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5002_ST617 | NA | 131242-WSD11-DR-5002_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5003_ST617 | NA | 131242-WSD11-DR-5003_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5004_ST617 | NA | 131242-WSD11-DR-5004_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5005_ST617 | NA | 131242-WSD11-DR-5005_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5006_ST617 | NA | 131242-WSD11-DR-5006_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 8000_ST617 | NA | 131242-WSD11-DR-8000_ST617 | 2024-11-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-17 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-07-04 | 2024-11-19 | NA | 000000 | 2024-07-04, 2024-10-11, 2024-11-19 | 00 | 3 | PEN | AWC | AWC
000825 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-0021 | 2024-11-20 | Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm | For Information | 2024-12-18 | 2024-11-27 |  | For Information | NO |  | YES |  |  |  |  | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | PEN | INF | INF
000826 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 0 | 131242-WSD11-RT-0002 | 2024-11-20 | THP Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-02-27 |  | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
000826 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 1 | 131242-WSD11-RT-0002 | 2025-03-25 | THP Load Flow Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 14 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
000827 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 0 | 131242-WSD11-RT-0003 | 2024-11-20 | THP Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-02-27 |  | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | PEN | AWC | AWC
000827 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 1 | 131242-WSD11-RT-0003 | 2025-03-25 | THP Short Circuit Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 14 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | PEN | AWC | AWC
000828 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 0 | 131242-WSW41-MS-0005 | 2024-11-21 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-05 |  | Not Approved | YES | 2024-12-26 | YES | Resubmitted |  |  |  | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | PEN | NAP | NAP
000828 | 01 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 1 | 131242-WSW41-MS-0005 | 2024-12-11 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2024-12-30 |  | Approved with Comments | YES | 2025-01-17 | NO | Overdue | 266 |  |  | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | PEN | AWC | AWC
000829 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5006 | A | 131242-WST02-DR-5006 | 2024-11-21 | Fire Seal Detail | Rev.0: Not approved. Please revise and resubmit. | 2024-12-19 | 2024-12-06 |  | Not Approved | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "Fire Seal Detail" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | A | 000000&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00 | 4 | PEN | NAP | NAP
000830 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0020 | 0 | 131242-WSW41-QA-0020 | 2024-11-21 | Monthly Concrete Cube Records for Structural works for September 2024 | For information. | 2024-12-19 | 2024-11-27 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Concrete Cube Records for Structural works for September 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" | 2024-10-11 | 2025-09-30 | 0 | 000000&&000756&&000830 | 2024-10-11, 2024-11-21, 2025-09-30 | 00 | 3 | PEN | INF | INF
000831 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | A | 131242-WST02-DR-5003 | 2024-11-22 | SSN_CAT Ladder | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-08 |  | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | NAP | NAP
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | - | 131242-WST02-DR-5003 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 2 | Not Approved | YES | 2025-05-16 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 1007 | NA | 131242-WST02-DR-1007 | 2025-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-24 | 2025-04-28 | 2 | Not Approved | YES | 2025-05-16 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 13 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 1008 | NA | 131242-WST02-DR-1008 | 2025-04-04 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-24 | 2025-04-28 | 2 | Not Approved | YES | 2025-05-16 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000831 | 02 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | D | 131242-WST02-DR-5003 | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | 27 | Not Approved | YES | 2025-11-04 | NO | Overdue | 59 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_CAT Ladder " | 2024-05-28 | 2025-09-11 | D | 000000&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | PE report | NA | RT | A | NA | NA | PE report-NA-RT-NA | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-09-08 | 2025-10-15 | 27 | Not Approved | YES | 2025-11-04 | NO | Overdue | 59 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-08-19 | 2025-08-19 | NA | 000000 | 2025-08-19 | 00 | 1 | PEN | NAP | NAP
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1002 | A | 131242-WST02-DR-1002 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 2001 | NA | 131242-WST02-DR-2001 | 2024-11-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-20 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-03 | NA | 000000 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 5004 | NA | 131242-WST02-DR-5004 | 2024-11-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-20 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 5005 | NA | 131242-WST02-DR-5005 | 2024-11-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-20 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-05-28 | 2025-11-06 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00 | 6 | PEN | AWC | AWC
000833 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 5002 | A | 131242-WST02-DR-5002 | 2024-11-22 | SSN Door Window Schedule | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | B | 131242-WST02-DR-5002 | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | 1 | Approved with Comments | YES | 2025-03-31 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 5007 | NA | 131242-WST02-DR-5007 | 2025-02-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-10 | 2025-03-11 | 1 | Approved with Comments | YES | 2025-03-31 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00 | 4 | PEN | AWC | AWC
000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-5002 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | 12 | Approved with Comments | YES | 2025-10-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 5001 | NA | 131242-WST02-DR-5001 | 2025-08-19 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-09-08 | 2025-09-24 | 12 | Approved with Comments | YES | 2025-10-14 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-5002 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 |  | Approved with Comments | YES | 2025-12-24 | NO | Overdue | 23 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Door Window Schedule" | 2023-11-22 | 2025-11-21 | A.2 | 000000&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | A | 5001 | NA | 131242-WST02-DR-5001 | 2025-11-21 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-12-11 | 2025-12-04 |  | Approved with Comments | YES | 2025-12-24 | NO | Overdue | 23 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Process Non-Process room layout" | 2023-11-22 | 2025-11-21 | A | 000000&&000555 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00 | 13 | PEN | AWC | AWC
000834 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-1001 | 2024-11-22 | SSN Railing Layout | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-20 | 2024-12-07 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000835 | 00 | Franklin | CSA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-1025 | 2024-11-22 | SSN Pavement Plan | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-08 |  | Approved with Comments | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | AWC | AWC
000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-5400 | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 |  | Not Approved | YES | 2024-12-27 | NO | Overdue | 281 |  |  | NA | "Hookup Drawing -TSS Analyser" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Wall Mounted Pipe Support Design" | 2024-10-10 | 2025-12-18 | A | 000000&&000836&&001788 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 1400 | NA | 131242-WST02-DR-1400 | 2024-11-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-20 | 2024-12-06 |  | Not Approved | YES | 2024-12-27 | NO | Overdue | 281 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN- Biomass separator footing detail" | 2024-10-10 | 2025-12-18 | A | 000000&&000753&&001730 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 6 | PEN | NAP | NAP
000837 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 0 | 131242-WSD11-CL-0005 | 2024-11-22 | Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check | Approved | 2024-12-20 | 2024-12-06 |  | Approved | NO |  | YES |  |  |  |  | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-11-22 | 0 | 000000&&000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | PEN | APP | APP
000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0034 | 0 | 131242-WSD11-MI-0034 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | 2024-11-22 | 2024-11-22 | 0 | 000838 | 2024-11-22 | 00 | 1 | PEN | INF | INF
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0035 | NA | 131242-WSD11-MI-0035 | 2024-11-22 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-20 | 2024-12-05 |  | For Information | YES | 2024-12-26 | NO | Overdue | 282 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-22 | 2024-11-22 | NA | 000000 | 2024-11-22 | 00 | 1 | PEN | INF | INF
000839 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0020 | 0 | 131242-WSW41-MS-0020 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold | Approved | 2024-12-20 | 2024-12-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold" | 2024-11-23 | 2024-11-23 | 0 | 000839 | 2024-11-23 | 00 | 1 | PEN | APP | APP
000840 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0021 | 0 | 131242-WSW41-MS-0021 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold | Approved | 2024-12-20 | 2024-12-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold" | 2024-11-23 | 2024-11-23 | 0 | 000840 | 2024-11-23 | 00 | 1 | PEN | APP | APP
000841 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0022 | 0 | 131242-WSW41-MS-0022 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold | Approved | 2024-12-20 | 2024-12-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold" | 2024-11-23 | 2024-11-23 | 0 | 000841 | 2024-11-23 | 00 | 1 | PEN | APP | APP
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST619 | A | 131242-WSD11-DR-0304_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 0305_ST619 | NA | 131242-WSD11-DR-0305_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1100_ST619 | NA | 131242-WSD11-DR-1100_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1101_ST619 | NA | 131242-WSD11-DR-1101_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 2100_ST619 | NA | 131242-WSD11-DR-2100_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3100_ST619 | NA | 131242-WSD11-DR-3100_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5100_ST619 | NA | 131242-WSD11-DR-5100_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5101_ST619 | NA | 131242-WSD11-DR-5101_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 8002_ST619 | NA | 131242-WSD11-DR-8002_ST619 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-06 |  | Approved with Comments | NO |  | YES |  |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1500_ST611 | A | 131242-WST02-DR-1500_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | 2024-11-25 | A | 000843 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5500_ST611 | NA | 131242-WST02-DR-5500_ST611 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | S | 5501_ST611 | NA | 131242-WST02-DR-5501_ST611 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | AWC | AWC
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-1501 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | 2025-09-24 | A | 000000&&000844&&000845 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3500 | NA | 131242-WSD11-DR-3500 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2025-09-24 | NA | 000000 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00 | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1500 | NA | 131242-WSD11-DR-1500 | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-07 |  | Approved with Comments | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-11-25 | 2025-09-24 | G | 000000&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000844 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment reply | NA | 131242-WSD11-DR-comment reply | 2025-08-22 | THP Courtyard RC Plinth Detail | Rev.1: For Information | 2025-09-11 | 2025-09-17 | 4 | For Information | NO |  | YES |  |  |  |  | NA | "THP Courtyard RC Plinth Detail" | 2025-08-22 | 2025-08-22 | NA | 000844 | 2025-08-22 | 01 | 1 | PEN | INF | INF
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-1501 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 |  | Rejected | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | 2025-09-24 | A | 000000&&000844&&000845 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, NA | 7 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3500 | NA | 131242-WSD11-DR-3500 | 2024-12-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-01-06 | 2024-12-06 |  | Rejected | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2025-09-24 | NA | 000000 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00 | 5 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 1500 | NA | 131242-WSD11-DR-1500 | 2024-12-06 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-01-06 | 2024-12-06 |  | Rejected | YES | 2024-12-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-11-25 | 2025-09-24 | G | 000000&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02, NA | 7 | PEN | REJ | REJ
000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1505_Superceded | A | 131242-WSD11-DR-1505_Superceded | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-13 | 2024-12-18 | 3 | Rejected | YES | 2025-01-08 | YES | Resubmitted |  |  |  | NA | " THP Courtyard Equipment Anchor Bolt Details" | 2024-11-25 | 2024-11-25 | A | 000845 | 2024-11-25 | 01 | 1 | PEN | REJ | REJ
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3505_Superceded | NA | 131242-WSD11-DR-3505_Superceded | 2024-11-25 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-23 | 2024-12-18 |  | Rejected | YES | 2025-01-08 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-25 | 2024-11-25 | NA | 000000 | 2024-11-25 | 00 | 1 | PEN | REJ | REJ
000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1505 | A | 131242-WSD11-DR-1505 | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-08 | 2025-02-12 | 23 | Approved with Comments | YES | 2025-03-04 | NO | Overdue | 234 |  |  | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-18 | 2025-08-13 | A | 000000&&000845 | 2024-12-18, 2025-06-16, 2025-08-13 | 00, 02, NA | 3 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 3505 | NA | 131242-WSD11-DR-3505 | 2024-12-18 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-01-16 | 2025-02-12 | 17 | Approved with Comments | YES | 2025-03-04 | NO | Overdue | 234 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-18 | 2024-12-18 | NA | 000000 | 2024-12-18 | 00 | 1 | PEN | AWC | AWC
000846 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 0 | 131242-WST02-DS-5481 | 2024-11-28 | Data Sheet for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-03-07 | In progress: 1). await TVU to confirm motor area (safety zone or not, Qili checking w TUV, will discuss with SO this Friday); 2). needTenwit confirm anchor bolt detail in C&S Dwg -> in 2 weeks | NA | "Data Sheet for Hyperbolic Mixer" | 2024-11-28 | 2025-03-27 | 1 | 000846 | 2024-11-28, 2025-03-27 | 00, 01 | 2 | PEN | AWC | AWC
000846 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 1 | 131242-WST02-DS-5481 | 2025-03-27 | Data Sheet for Hyperbolic Mixer | Rev 1: Approved | 2025-04-16 | 2025-04-27 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Hyperbolic Mixer" | 2024-11-28 | 2025-03-27 | 1 | 000846 | 2024-11-28, 2025-03-27 | 00, 01 | 2 | PEN | APP | APP
000847 | 00 | Yibo/ Qili | Mech | NA | 131242 | WST02 | CL | P | 5481 | 0 | 131242-WST02-CL-5481 | 2024-11-28 | SSN Hyperbolic Mixer CFD | Rev 0: Not approved - Revise and Resubmit | 2024-12-27 | 2024-12-14 |  | Not Approved | YES | 2025-01-03 | NO | Overdue | 276 |  | To be handled by Process (QiLi), will be VO for revised CFD version | NA | "SSN Hyperbolic Mixer CFD" | 2024-11-28 | 2024-11-28 | 0 | 000847 | 2024-11-28 | 00 | 1 | PEN | NAP | NAP
000848 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0014 | 0 | 131242-WST02-VI-0014 | 2024-11-28 | Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-05 |  | Approved with Comments | YES | 2024-12-26 | NO | Overdue | 282 |  | To follow-up with HDMANN. | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | PEN | AWC | AWC
000849 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 0 | 131242-WST02-RT-0007 | 2024-11-28 | SSN Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-02-28 |  | NA | "SSN Load Flow Study Report" | 2024-11-28 | 2025-05-04 | 1 | 000849 | 2024-11-28, 2025-05-04 | 00, 01 | 2 | PEN | AWC | AWC
000849 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 1 | 131242-WST02-RT-0007 | 2025-05-04 | SSN Load Flow Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-22 | 2025-05-30 | 6 | Approved with Comments | YES | 2025-06-19 | NO | Overdue | 157 |  |  | NA | "SSN Load Flow Study Report" | 2024-11-28 | 2025-05-04 | 1 | 000849 | 2024-11-28, 2025-05-04 | 00, 01 | 2 | PEN | AWC | AWC
000850 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 0 | 131242-WST02-RT-0008 | 2024-11-28 | SSN Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | YES | Resubmitted |  | 2025-02-28 |  | NA | "SSN Short Circuit Study Report" | 2024-11-28 | 2025-05-30 | 1 | 000850 | 2024-11-28, 2025-05-30 | 00, 01 | 2 | PEN | AWC | AWC
000850 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 1 | 131242-WST02-RT-0008 | 2025-05-30 | SSN Short Circuit Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-06-19 | 2025-07-23 | 24 | Approved with Comments | YES | 2025-08-12 | NO | Overdue | 119 |  |  | NA | "SSN Short Circuit Study Report" | 2024-11-28 | 2025-05-30 | 1 | 000850 | 2024-11-28, 2025-05-30 | 00, 01 | 2 | PEN | AWC | AWC
000851 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0036 | 0 | 131242-WSW41-MI-0036 | 2024-11-28 | CSA Meeting Minutes 0036_14112024 | For Information | 2024-12-27 | 2024-12-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0036_14112024" && "Process & MEICA Meeting Minutes 0036_21112024" | 2024-11-28 | 2025-01-11 | 0 | 000851&&000965 | 2024-11-28, 2025-01-11 | 00 | 2 | PEN | INF | INF
000852 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0013 | 0 | 131242-WSW41-RT-0013 | 2024-11-28 | Quarterly Safety Review Follow Up on SSN RC Works | For Information | 2024-12-27 | 2024-12-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.13 (05 24)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Quarterly Safety Review Follow Up on SSN RC Works" | 2024-06-12 | 2025-07-01 | 0 | 000000&&000520&&000852 | 2024-06-12, 2024-11-28, 2025-07-01 | 00 | 3 | PEN | INF | INF
000853 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0022 | 0 | 131242-WST02-VI-0022 | 2024-11-28 | Vendor approval of SSN Package (Autosampler) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-27 | 2025-03-14 | 52 | Approved with Comments | YES | 2025-04-03 | NO | Overdue | 212 |  |  | NA | "Vendor approval of SSN Package (Autosampler) " | 2024-11-28 | 2024-11-28 | 0 | 000853 | 2024-11-28 | 00 | 1 | PEN | AWC | AWC
000854 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0003 | 0 | 131242-WST02-VI-0003 | 2024-11-28 | Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd. | Approved | 2024-12-27 | 2024-12-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | APP | APP
000855 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-0004 | 2024-11-28 | Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd. | Approved | 2024-12-27 | 2024-12-05 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | PEN | APP | APP
000856 | 00 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 0 | 131242-WST02-QA-0003 | 2024-11-29 | 2Hrs Fire rated AAC Blocks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2024-12-06 |  | Not Approved | YES | 2024-12-27 | YES | Resubmitted |  |  |  | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | PEN | NAP | NAP
000856 | 01 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 1 | 131242-WST02-QA-0003 | 2024-12-20 | 2Hrs Fire rated AAC Blocks | Rev.1: Approved | 2025-01-10 | 2025-01-02 |  | Approved | NO |  | YES |  |  |  |  | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | PEN | APP | APP
000857 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 0 | 131242-WSW41-DS-0001 | 2024-11-29 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-30 | 2025-03-25 | 58 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | PEN | AWC | AWC
000857 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 1 | 131242-WSW41-DS-0001 | 2025-09-15 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-10-03 | 2025-12-02 | 41 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | PEN | AWC | AWC
000858 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0008 | 0 | 131242-WSW41-QA-0008 | 2024-11-30 | FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-12-30 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | NO | Overdue | 276 |  |  | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | PEN | AWC | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5218 | A | 131242-WST02-SD-5218 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 |  |  | NA | "SSN Wall Shop Drawing" | 2024-11-30 | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5219 | NA | 131242-WST02-SD-5219 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5220 | NA | 131242-WST02-SD-5220 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5221 | NA | 131242-WST02-SD-5221 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5223 | NA | 131242-WST02-SD-5223 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5224 | NA | 131242-WST02-SD-5224 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 1201 | NA | 131242-WST02-SD-1201 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 1202 | NA | 131242-WST02-SD-1202 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 1203 | NA | 131242-WST02-SD-1203 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 1204 | NA | 131242-WST02-SD-1204 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5212 | NA | 131242-WST02-SD-5212 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5213 | NA | 131242-WST02-SD-5213 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5214 | NA | 131242-WST02-SD-5214 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5215 | NA | 131242-WST02-SD-5215 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5216 | NA | 131242-WST02-SD-5216 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SD | S | 5217 | NA | 131242-WST02-SD-5217 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-01-16 | 12 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-30 | 2024-11-30 | NA | 000000 | 2024-11-30 | 00 | 1 | PEN | AWC | AWC
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1027 | A | 131242-WST02-DR-1027 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 43 | Not Approved | YES | 2025-03-24 | NO | Overdue | 220 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | 2026-02-04 | A | 000000&&000860 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | C | 1026 | NA | 131242-WST02-DR-1026 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-03-04 | 43 | Not Approved | YES | 2025-03-24 | NO | Overdue | 220 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2026-02-04 | NA | 000000 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | C | 5008 | NA | 131242-WST02-DR-5008 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-03-04 | 43 | Not Approved | YES | 2025-03-24 | NO | Overdue | 220 | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-05-28 | 2025-02-26 | NA | 000000 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00 | 4 | PEN | NAP | NAP
000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-1210 | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | 56 | Not Approved | YES | 2025-04-10 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | 2025-12-14 | A | 000000&&000861 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00 | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-5200 | 2024-11-30 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-30 | 2025-03-21 | 56 | Not Approved | YES | 2025-04-10 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2024-11-30 | 2025-12-14 | A | 000000&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | PEN | NAP | NAP
000861 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | cmmt sheet | NA | 131242-WSD11-DR-cmmt sheet | 2025-09-15 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-25 |  | For Information | NO |  | YES |  |  |  |  | NA | "THP- Valve Pit, Sump and Kerb Detail" | 2025-09-15 | 2025-09-15 | NA | 000861 | 2025-09-15 | 01 | 1 | PEN | INF | INF
000862 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0018 | 0 | 131242-WSW41-PS-0018 | 2024-11-30 | Monthly Progress Presentation No. 18 (1124) | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Oct 2024" && "Monthly Progress Presentation No. 18 (1124)" | 2024-11-30 | 2024-12-12 | 0 | 000862&&000888 | 2024-11-30, 2024-12-12 | 00 | 2 | PEN | INF | INF
000863 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0018 | 0 | 131242-WSW41-MI-0018 | 2024-11-30 | Monthly Progress Meeting Minutes 0018_20241113 | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Meeting Minutes 0018_20241113" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | 2024-11-30 | 0 | 000000&&000313&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | PEN | INF | INF
000864 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0031 | 0 | 131242-WSW41-VI-0031 | 2024-12-02 | Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2024-06-12 |  | Approved with Comments | YES | 2024-07-03 | NO | Overdue | 405 |  |  | NA | "Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd." | 2024-12-02 | 2024-12-02 | 0 | 000864 | 2024-12-02 | 00 | 1 | PEN | AWC | AWC
000865 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 0 | 131242-WSW41-PC-0017 | 2024-12-02 | Payment Claim No.17 | As requested by C4BJV to reject this submittal and resubmit. | 2024-12-31 | 2024-12-03 |  | Rejected | YES | 2024-12-23 | YES | Resubmitted |  |  |  | NA | "Payment Claim No.17" | 2024-12-02 | 2024-12-03 | 1 | 000865 | 2024-12-02, 2024-12-03 | 00, 01 | 2 | PEN | REJ | REJ
000865 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 1 | 131242-WSW41-PC-0017 | 2024-12-03 | Payment Claim No.17 | Rev(1): Approved. Please refer to S.O. correspondence no 259 3 Dec 2024. | 2024-12-23 | 2025-01-08 | 10 | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.17" | 2024-12-02 | 2024-12-03 | 1 | 000865 | 2024-12-02, 2024-12-03 | 00, 01 | 2 | PEN | APP | APP
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | A | 131242-WST02-DR-3008 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3012 | NA | 131242-WST02-DR-3012 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3013 | NA | 131242-WST02-DR-3013 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3014 | NA | 131242-WST02-DR-3014 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3015 | NA | 131242-WST02-DR-3015 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3016 | NA | 131242-WST02-DR-3016 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3017 | NA | 131242-WST02-DR-3017 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3018 | NA | 131242-WST02-DR-3018 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3019 | NA | 131242-WST02-DR-3019 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3020 | NA | 131242-WST02-DR-3020 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3021 | NA | 131242-WST02-DR-3021 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3022 | NA | 131242-WST02-DR-3022 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3023 | NA | 131242-WST02-DR-3023 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7110 | NA | 131242-WST02-DR-7110 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7111 | NA | 131242-WST02-DR-7111 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7112 | NA | 131242-WST02-DR-7112 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7113 | NA | 131242-WST02-DR-7113 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7114 | NA | 131242-WST02-DR-7114 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7115 | NA | 131242-WST02-DR-7115 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7116 | NA | 131242-WST02-DR-7116 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7117 | NA | 131242-WST02-DR-7117 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7118 | NA | 131242-WST02-DR-7118 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7119 | NA | 131242-WST02-DR-7119 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7120 | NA | 131242-WST02-DR-7120 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7121 | NA | 131242-WST02-DR-7121 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7122 | NA | 131242-WST02-DR-7122 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7123 | NA | 131242-WST02-DR-7123 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7124 | NA | 131242-WST02-DR-7124 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7125 | NA | 131242-WST02-DR-7125 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7126 | NA | 131242-WST02-DR-7126 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7127 | NA | 131242-WST02-DR-7127 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7040 | NA | 131242-WST02-DR-7040 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | D | 000000&&000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7041 | NA | 131242-WST02-DR-7041 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7042 | NA | 131242-WST02-DR-7042 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7043 | NA | 131242-WST02-DR-7043 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7044 | NA | 131242-WST02-DR-7044 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7045 | NA | 131242-WST02-DR-7045 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7046 | NA | 131242-WST02-DR-7046 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7047 | NA | 131242-WST02-DR-7047 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7048 | NA | 131242-WST02-DR-7048 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7049 | NA | 131242-WST02-DR-7049 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7050 | NA | 131242-WST02-DR-7050 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7051 | NA | 131242-WST02-DR-7051 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7052 | NA | 131242-WST02-DR-7052 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7053 | NA | 131242-WST02-DR-7053 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7054 | NA | 131242-WST02-DR-7054 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7055 | NA | 131242-WST02-DR-7055 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7060 | NA | 131242-WST02-DR-7060 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7061 | NA | 131242-WST02-DR-7061 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7062 | NA | 131242-WST02-DR-7062 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7063 | NA | 131242-WST02-DR-7063 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7064 | NA | 131242-WST02-DR-7064 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7065 | NA | 131242-WST02-DR-7065 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7066 | NA | 131242-WST02-DR-7066 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7067 | NA | 131242-WST02-DR-7067 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7068 | NA | 131242-WST02-DR-7068 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7069 | NA | 131242-WST02-DR-7069 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7070 | NA | 131242-WST02-DR-7070 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7071 | NA | 131242-WST02-DR-7071 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7072 | NA | 131242-WST02-DR-7072 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7073 | NA | 131242-WST02-DR-7073 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7074 | NA | 131242-WST02-DR-7074 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7075 | NA | 131242-WST02-DR-7075 | 2024-12-02 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2024-12-31 | 2025-02-07 | 25 | Not Approved | YES | 2025-02-27 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | B | 131242-WST02-DR-7040 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | D | 000000&&000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7041 | NA | 131242-WST02-DR-7041 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7042 | NA | 131242-WST02-DR-7042 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7043 | NA | 131242-WST02-DR-7043 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7044 | NA | 131242-WST02-DR-7044 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7045 | NA | 131242-WST02-DR-7045 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7046 | NA | 131242-WST02-DR-7046 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7047 | NA | 131242-WST02-DR-7047 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7048 | NA | 131242-WST02-DR-7048 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7049 | NA | 131242-WST02-DR-7049 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7050 | NA | 131242-WST02-DR-7050 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7051 | NA | 131242-WST02-DR-7051 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7052 | NA | 131242-WST02-DR-7052 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7053 | NA | 131242-WST02-DR-7053 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7054 | NA | 131242-WST02-DR-7054 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7055 | NA | 131242-WST02-DR-7055 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7056 | NA | 131242-WST02-DR-7056 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7057 | NA | 131242-WST02-DR-7057 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7058 | NA | 131242-WST02-DR-7058 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7060 | NA | 131242-WST02-DR-7060 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7061 | NA | 131242-WST02-DR-7061 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7062 | NA | 131242-WST02-DR-7062 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7063 | NA | 131242-WST02-DR-7063 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7064 | NA | 131242-WST02-DR-7064 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7065 | NA | 131242-WST02-DR-7065 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7066 | NA | 131242-WST02-DR-7066 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7067 | NA | 131242-WST02-DR-7067 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7068 | NA | 131242-WST02-DR-7068 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7069 | NA | 131242-WST02-DR-7069 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7070 | NA | 131242-WST02-DR-7070 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7071 | NA | 131242-WST02-DR-7071 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7072 | NA | 131242-WST02-DR-7072 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7073 | NA | 131242-WST02-DR-7073 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7074 | NA | 131242-WST02-DR-7074 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7075 | NA | 131242-WST02-DR-7075 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7076 | NA | 131242-WST02-DR-7076 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7077 | NA | 131242-WST02-DR-7077 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7078 | NA | 131242-WST02-DR-7078 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3012 | NA | 131242-WST02-DR-3012 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3013 | NA | 131242-WST02-DR-3013 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3014 | NA | 131242-WST02-DR-3014 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3015 | NA | 131242-WST02-DR-3015 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3016 | NA | 131242-WST02-DR-3016 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3017 | NA | 131242-WST02-DR-3017 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3018 | NA | 131242-WST02-DR-3018 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3019 | NA | 131242-WST02-DR-3019 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3020 | NA | 131242-WST02-DR-3020 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3021 | NA | 131242-WST02-DR-3021 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3022 | NA | 131242-WST02-DR-3022 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 3023 | NA | 131242-WST02-DR-3023 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7110 | NA | 131242-WST02-DR-7110 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7111 | NA | 131242-WST02-DR-7111 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7112 | NA | 131242-WST02-DR-7112 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7113 | NA | 131242-WST02-DR-7113 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7114 | NA | 131242-WST02-DR-7114 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7115 | NA | 131242-WST02-DR-7115 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7116 | NA | 131242-WST02-DR-7116 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7117 | NA | 131242-WST02-DR-7117 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7118 | NA | 131242-WST02-DR-7118 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7119 | NA | 131242-WST02-DR-7119 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7120 | NA | 131242-WST02-DR-7120 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7121 | NA | 131242-WST02-DR-7121 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7122 | NA | 131242-WST02-DR-7122 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7123 | NA | 131242-WST02-DR-7123 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7124 | NA | 131242-WST02-DR-7124 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EP | 7125 | NA | 131242-WST02-DR-7125 | 2025-03-07 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-03-27 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | NAP | NAP
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | C | 131242-WST02-DR-7040 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | D | 000000&&000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7041 | NA | 131242-WST02-DR-7041 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7042 | NA | 131242-WST02-DR-7042 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7043 | NA | 131242-WST02-DR-7043 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7044 | NA | 131242-WST02-DR-7044 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7045 | NA | 131242-WST02-DR-7045 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7046 | NA | 131242-WST02-DR-7046 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7047 | NA | 131242-WST02-DR-7047 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7048 | NA | 131242-WST02-DR-7048 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7049 | NA | 131242-WST02-DR-7049 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7050 | NA | 131242-WST02-DR-7050 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7051 | NA | 131242-WST02-DR-7051 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7052 | NA | 131242-WST02-DR-7052 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7053 | NA | 131242-WST02-DR-7053 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7054 | NA | 131242-WST02-DR-7054 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7055 | NA | 131242-WST02-DR-7055 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7056 | NA | 131242-WST02-DR-7056 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7057 | NA | 131242-WST02-DR-7057 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7058 | NA | 131242-WST02-DR-7058 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7060 | NA | 131242-WST02-DR-7060 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7061 | NA | 131242-WST02-DR-7061 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7062 | NA | 131242-WST02-DR-7062 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7063 | NA | 131242-WST02-DR-7063 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7064 | NA | 131242-WST02-DR-7064 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7065 | NA | 131242-WST02-DR-7065 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7066 | NA | 131242-WST02-DR-7066 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7067 | NA | 131242-WST02-DR-7067 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7068 | NA | 131242-WST02-DR-7068 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7069 | NA | 131242-WST02-DR-7069 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7070 | NA | 131242-WST02-DR-7070 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | EI | 7071 | NA | 131242-WST02-DR-7071 | 2025-03-28 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | For information | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | Tenwit in Progress |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7072 | NA | 131242-WST02-DR-7072 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7073 | NA | 131242-WST02-DR-7073 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7074 | NA | 131242-WST02-DR-7074 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7075 | NA | 131242-WST02-DR-7075 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7076 | NA | 131242-WST02-DR-7076 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7077 | NA | 131242-WST02-DR-7077 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7078 | NA | 131242-WST02-DR-7078 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3012 | NA | 131242-WST02-DR-3012 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3013 | NA | 131242-WST02-DR-3013 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3014 | NA | 131242-WST02-DR-3014 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3015 | NA | 131242-WST02-DR-3015 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3016 | NA | 131242-WST02-DR-3016 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3017 | NA | 131242-WST02-DR-3017 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3018 | NA | 131242-WST02-DR-3018 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3019 | NA | 131242-WST02-DR-3019 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3020 | NA | 131242-WST02-DR-3020 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3021 | NA | 131242-WST02-DR-3021 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3022 | NA | 131242-WST02-DR-3022 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3023 | NA | 131242-WST02-DR-3023 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7110 | NA | 131242-WST02-DR-7110 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7111 | NA | 131242-WST02-DR-7111 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7112 | NA | 131242-WST02-DR-7112 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7113 | NA | 131242-WST02-DR-7113 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7114 | NA | 131242-WST02-DR-7114 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7115 | NA | 131242-WST02-DR-7115 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7116 | NA | 131242-WST02-DR-7116 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7117 | NA | 131242-WST02-DR-7117 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7118 | NA | 131242-WST02-DR-7118 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7119 | NA | 131242-WST02-DR-7119 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7120 | NA | 131242-WST02-DR-7120 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7121 | NA | 131242-WST02-DR-7121 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7122 | NA | 131242-WST02-DR-7122 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7123 | NA | 131242-WST02-DR-7123 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7124 | NA | 131242-WST02-DR-7124 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7125 | NA | 131242-WST02-DR-7125 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | D | 131242-WST02-DR-7040 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | D | 000000&&000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7041 | NA | 131242-WST02-DR-7041 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7042 | NA | 131242-WST02-DR-7042 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7043 | NA | 131242-WST02-DR-7043 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7044 | NA | 131242-WST02-DR-7044 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7045 | NA | 131242-WST02-DR-7045 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7046 | NA | 131242-WST02-DR-7046 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7047 | NA | 131242-WST02-DR-7047 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7048 | NA | 131242-WST02-DR-7048 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7049 | NA | 131242-WST02-DR-7049 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7050 | NA | 131242-WST02-DR-7050 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7051 | NA | 131242-WST02-DR-7051 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7052 | NA | 131242-WST02-DR-7052 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7053 | NA | 131242-WST02-DR-7053 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7054 | NA | 131242-WST02-DR-7054 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7055 | NA | 131242-WST02-DR-7055 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7056 | NA | 131242-WST02-DR-7056 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7057 | NA | 131242-WST02-DR-7057 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7058 | NA | 131242-WST02-DR-7058 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2026-02-03 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7060 | NA | 131242-WST02-DR-7060 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7061 | NA | 131242-WST02-DR-7061 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7062 | NA | 131242-WST02-DR-7062 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7063 | NA | 131242-WST02-DR-7063 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7064 | NA | 131242-WST02-DR-7064 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7065 | NA | 131242-WST02-DR-7065 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7066 | NA | 131242-WST02-DR-7066 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7067 | NA | 131242-WST02-DR-7067 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7068 | NA | 131242-WST02-DR-7068 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7069 | NA | 131242-WST02-DR-7069 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7070 | NA | 131242-WST02-DR-7070 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7071 | NA | 131242-WST02-DR-7071 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7072 | NA | 131242-WST02-DR-7072 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7073 | NA | 131242-WST02-DR-7073 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7074 | NA | 131242-WST02-DR-7074 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7075 | NA | 131242-WST02-DR-7075 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7076 | NA | 131242-WST02-DR-7076 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7077 | NA | 131242-WST02-DR-7077 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7078 | NA | 131242-WST02-DR-7078 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-07 | 2025-07-01 | NA | 000000 | 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3008 | NA | 131242-WST02-DR-3008 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3009 | NA | 131242-WST02-DR-3009 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3010 | NA | 131242-WST02-DR-3010 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3011 | NA | 131242-WST02-DR-3011 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3012 | NA | 131242-WST02-DR-3012 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3013 | NA | 131242-WST02-DR-3013 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3014 | NA | 131242-WST02-DR-3014 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3015 | NA | 131242-WST02-DR-3015 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3016 | NA | 131242-WST02-DR-3016 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3017 | NA | 131242-WST02-DR-3017 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3018 | NA | 131242-WST02-DR-3018 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3019 | NA | 131242-WST02-DR-3019 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3020 | NA | 131242-WST02-DR-3020 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3021 | NA | 131242-WST02-DR-3021 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3022 | NA | 131242-WST02-DR-3022 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3023 | NA | 131242-WST02-DR-3023 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7110 | NA | 131242-WST02-DR-7110 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7111 | NA | 131242-WST02-DR-7111 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7112 | NA | 131242-WST02-DR-7112 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7113 | NA | 131242-WST02-DR-7113 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7114 | NA | 131242-WST02-DR-7114 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7115 | NA | 131242-WST02-DR-7115 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7116 | NA | 131242-WST02-DR-7116 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7117 | NA | 131242-WST02-DR-7117 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7118 | NA | 131242-WST02-DR-7118 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7119 | NA | 131242-WST02-DR-7119 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7120 | NA | 131242-WST02-DR-7120 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7121 | NA | 131242-WST02-DR-7121 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7122 | NA | 131242-WST02-DR-7122 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7123 | NA | 131242-WST02-DR-7123 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7124 | NA | 131242-WST02-DR-7124 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7125 | NA | 131242-WST02-DR-7125 | 2025-07-01 |  | NA | 2025-07-21 | 2025-10-06 | 55 | Approved with Comments | YES | 2025-10-24 | NO | Overdue | 66 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | A | 131242-WST02-DR-3038 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3039 | NA | 131242-WST02-DR-3039 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3040 | NA | 131242-WST02-DR-3040 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3041 | NA | 131242-WST02-DR-3041 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | 2026-02-03 | A | 000000&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3042 | NA | 131242-WST02-DR-3042 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3043 | NA | 131242-WST02-DR-3043 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3044 | NA | 131242-WST02-DR-3044 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3045 | NA | 131242-WST02-DR-3045 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3046 | NA | 131242-WST02-DR-3046 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3047 | NA | 131242-WST02-DR-3047 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3048 | NA | 131242-WST02-DR-3048 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3049 | NA | 131242-WST02-DR-3049 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3050 | NA | 131242-WST02-DR-3050 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3051 | NA | 131242-WST02-DR-3051 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7136 | NA | 131242-WST02-DR-7136 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7137 | NA | 131242-WST02-DR-7137 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7138 | NA | 131242-WST02-DR-7138 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7139 | NA | 131242-WST02-DR-7139 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7140 | NA | 131242-WST02-DR-7140 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7141 | NA | 131242-WST02-DR-7141 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7120 | NA | 131242-WST02-DR-7120 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7121 | NA | 131242-WST02-DR-7121 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7122 | NA | 131242-WST02-DR-7122 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7123 | NA | 131242-WST02-DR-7123 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7124 | NA | 131242-WST02-DR-7124 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7125 | NA | 131242-WST02-DR-7125 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7126 | NA | 131242-WST02-DR-7126 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7127 | NA | 131242-WST02-DR-7127 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7128 | NA | 131242-WST02-DR-7128 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7140 | NA | 131242-WST02-DR-7140 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7141 | NA | 131242-WST02-DR-7141 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7142 | NA | 131242-WST02-DR-7142 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7143 | NA | 131242-WST02-DR-7143 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7144 | NA | 131242-WST02-DR-7144 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7145 | NA | 131242-WST02-DR-7145 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7146 | NA | 131242-WST02-DR-7146 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7147 | NA | 131242-WST02-DR-7147 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7148 | NA | 131242-WST02-DR-7148 | 2024-12-02 |  | NA | 2024-12-31 | 2025-02-07 | 25 | Approved with Comments | YES | 2025-02-27 | NO | Overdue | 237 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | B | 131242-WST02-DR-3038 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3039 | NA | 131242-WST02-DR-3039 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3040 | NA | 131242-WST02-DR-3040 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3041 | NA | 131242-WST02-DR-3041 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | 2026-02-03 | A | 000000&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3042 | NA | 131242-WST02-DR-3042 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3043 | NA | 131242-WST02-DR-3043 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3044 | NA | 131242-WST02-DR-3044 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3045 | NA | 131242-WST02-DR-3045 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3046 | NA | 131242-WST02-DR-3046 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3047 | NA | 131242-WST02-DR-3047 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3048 | NA | 131242-WST02-DR-3048 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3049 | NA | 131242-WST02-DR-3049 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3050 | NA | 131242-WST02-DR-3050 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3051 | NA | 131242-WST02-DR-3051 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7136 | NA | 131242-WST02-DR-7136 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7137 | NA | 131242-WST02-DR-7137 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7138 | NA | 131242-WST02-DR-7138 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7139 | NA | 131242-WST02-DR-7139 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7140 | NA | 131242-WST02-DR-7140 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7141 | NA | 131242-WST02-DR-7141 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7120 | NA | 131242-WST02-DR-7120 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7121 | NA | 131242-WST02-DR-7121 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7122 | NA | 131242-WST02-DR-7122 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7123 | NA | 131242-WST02-DR-7123 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7124 | NA | 131242-WST02-DR-7124 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7125 | NA | 131242-WST02-DR-7125 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7126 | NA | 131242-WST02-DR-7126 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7127 | NA | 131242-WST02-DR-7127 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7128 | NA | 131242-WST02-DR-7128 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7140 | NA | 131242-WST02-DR-7140 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7141 | NA | 131242-WST02-DR-7141 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7142 | NA | 131242-WST02-DR-7142 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7143 | NA | 131242-WST02-DR-7143 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7144 | NA | 131242-WST02-DR-7144 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7145 | NA | 131242-WST02-DR-7145 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7146 | NA | 131242-WST02-DR-7146 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7147 | NA | 131242-WST02-DR-7147 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7148 | NA | 131242-WST02-DR-7148 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7149 | NA | 131242-WST02-DR-7149 | 2025-03-28 |  | NA | 2025-04-17 | 2025-05-06 | 11 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-03-28, 2025-07-21 | NA | 4 | PEN | AWC | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | C | 131242-WST02-DR-3038 | 2025-08-21 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3039 | NA | 131242-WST02-DR-3039 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3040 | NA | 131242-WST02-DR-3040 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3041 | NA | 131242-WST02-DR-3041 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | 2026-02-03 | A | 000000&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3042 | NA | 131242-WST02-DR-3042 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3043 | NA | 131242-WST02-DR-3043 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3044 | NA | 131242-WST02-DR-3044 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3045 | NA | 131242-WST02-DR-3045 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3046 | NA | 131242-WST02-DR-3046 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3047 | NA | 131242-WST02-DR-3047 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3048 | NA | 131242-WST02-DR-3048 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3049 | NA | 131242-WST02-DR-3049 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3050 | NA | 131242-WST02-DR-3050 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2026-02-03 | NA | 000000 | 2024-12-02, 2025-03-28, 2026-02-03 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3051 | NA | 131242-WST02-DR-3051 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A | 000000&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7136 | NA | 131242-WST02-DR-7136 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7137 | NA | 131242-WST02-DR-7137 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7138 | NA | 131242-WST02-DR-7138 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7139 | NA | 131242-WST02-DR-7139 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7140 | NA | 131242-WST02-DR-7140 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7141 | NA | 131242-WST02-DR-7141 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7120 | NA | 131242-WST02-DR-7120 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7121 | NA | 131242-WST02-DR-7121 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7122 | NA | 131242-WST02-DR-7122 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7123 | NA | 131242-WST02-DR-7123 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7124 | NA | 131242-WST02-DR-7124 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7125 | NA | 131242-WST02-DR-7125 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-01 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7126 | NA | 131242-WST02-DR-7126 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7127 | NA | 131242-WST02-DR-7127 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7128 | NA | 131242-WST02-DR-7128 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7140 | NA | 131242-WST02-DR-7140 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7141 | NA | 131242-WST02-DR-7141 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-03-28 | NA | 000000 | 2024-12-02, 2025-03-28 | NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7142 | NA | 131242-WST02-DR-7142 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7143 | NA | 131242-WST02-DR-7143 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7144 | NA | 131242-WST02-DR-7144 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7145 | NA | 131242-WST02-DR-7145 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7146 | NA | 131242-WST02-DR-7146 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7147 | NA | 131242-WST02-DR-7147 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7148 | NA | 131242-WST02-DR-7148 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7149 | NA | 131242-WST02-DR-7149 | 2025-03-28 |  | NA | 2025-09-10 | 2025-10-01 | 15 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-03-28, 2025-07-21 | NA | 4 | PEN | AWC | AWC
000868 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 0 | 131242-WSW41-SP-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-31 | 2025-01-08 | 5 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  |  |  | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | PEN | NAP | NAP
000868 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 1 | 131242-WSW41-SP-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-17 | 37 | Approved with Comments | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | PEN | AWC | AWC
000868 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 2 | 131242-WSW41-SP-0022 | 2025-02-20 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R2: Approved | 2025-03-12 | 2025-03-04 |  | Approved | NO |  | YES |  |  |  |  | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | PEN | APP | APP
000869 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 0 | 131242-WSW41-SP-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R0: Not Approved. Please refer to comment sheet for resubmission | 2024-12-31 | 2025-01-08 | 5 | Not Approved | YES | 2025-01-28 | YES | Resubmitted |  |  |  | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | 2024-12-02 | 0 | 000869 | 2024-12-02 | 00, 01 | 2 | PEN | NAP | NAP
000869 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 1 | 131242-WSW41-SP-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R1:Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-03 | 27 | Approved with Comments | YES | 2025-02-21 | NO | Overdue | 241 |  |  | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | 2024-12-02 | 0 | 000869 | 2024-12-02 | 00, 01 | 2 | PEN | AWC | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | A | 131242-WST02-DR-3024 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  | TBA |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3025 | NA | 131242-WST02-DR-3025 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2026-02-03 | B | 000000&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3026 | NA | 131242-WST02-DR-3026 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3027 | NA | 131242-WST02-DR-3027 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3028 | NA | 131242-WST02-DR-3028 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3029 | NA | 131242-WST02-DR-3029 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3030 | NA | 131242-WST02-DR-3030 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | 2026-02-03 | B | 000000&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3031 | NA | 131242-WST02-DR-3031 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3032 | NA | 131242-WST02-DR-3032 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3033 | NA | 131242-WST02-DR-3033 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3034 | NA | 131242-WST02-DR-3034 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3035 | NA | 131242-WST02-DR-3035 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2025-10-31 | A | 000000&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7080 | NA | 131242-WST02-DR-7080 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7081 | NA | 131242-WST02-DR-7081 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7082 | NA | 131242-WST02-DR-7082 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7083 | NA | 131242-WST02-DR-7083 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7084 | NA | 131242-WST02-DR-7084 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7085 | NA | 131242-WST02-DR-7085 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7086 | NA | 131242-WST02-DR-7086 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7087 | NA | 131242-WST02-DR-7087 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7088 | NA | 131242-WST02-DR-7088 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7089 | NA | 131242-WST02-DR-7089 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7090 | NA | 131242-WST02-DR-7090 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7091 | NA | 131242-WST02-DR-7091 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7100 | NA | 131242-WST02-DR-7100 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7101 | NA | 131242-WST02-DR-7101 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7102 | NA | 131242-WST02-DR-7102 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7103 | NA | 131242-WST02-DR-7103 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7104 | NA | 131242-WST02-DR-7104 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7105 | NA | 131242-WST02-DR-7105 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7106 | NA | 131242-WST02-DR-7106 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7107 | NA | 131242-WST02-DR-7107 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7108 | NA | 131242-WST02-DR-7108 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7109 | NA | 131242-WST02-DR-7109 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7110 | NA | 131242-WST02-DR-7110 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7111 | NA | 131242-WST02-DR-7111 | 2024-12-03 |  | NA | 2025-01-01 | 2025-02-07 | 24 | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | B | 131242-WST02-DR-3024 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  | TBA |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3025 | NA | 131242-WST02-DR-3025 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2026-02-03 | B | 000000&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3026 | NA | 131242-WST02-DR-3026 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3027 | NA | 131242-WST02-DR-3027 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3028 | NA | 131242-WST02-DR-3028 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3029 | NA | 131242-WST02-DR-3029 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3030 | NA | 131242-WST02-DR-3030 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | 2026-02-03 | B | 000000&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3031 | NA | 131242-WST02-DR-3031 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3032 | NA | 131242-WST02-DR-3032 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3033 | NA | 131242-WST02-DR-3033 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3034 | NA | 131242-WST02-DR-3034 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3035 | NA | 131242-WST02-DR-3035 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2025-10-31 | A | 000000&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7126 | NA | 131242-WST02-DR-7126 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7127 | NA | 131242-WST02-DR-7127 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7128 | NA | 131242-WST02-DR-7128 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7129 | NA | 131242-WST02-DR-7129 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7130 | NA | 131242-WST02-DR-7130 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7131 | NA | 131242-WST02-DR-7131 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7132 | NA | 131242-WST02-DR-7132 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7133 | NA | 131242-WST02-DR-7133 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7134 | NA | 131242-WST02-DR-7134 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7135 | NA | 131242-WST02-DR-7135 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7080 | NA | 131242-WST02-DR-7080 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7081 | NA | 131242-WST02-DR-7081 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7082 | NA | 131242-WST02-DR-7082 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7083 | NA | 131242-WST02-DR-7083 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7084 | NA | 131242-WST02-DR-7084 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7085 | NA | 131242-WST02-DR-7085 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7086 | NA | 131242-WST02-DR-7086 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7087 | NA | 131242-WST02-DR-7087 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7088 | NA | 131242-WST02-DR-7088 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7089 | NA | 131242-WST02-DR-7089 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7090 | NA | 131242-WST02-DR-7090 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7091 | NA | 131242-WST02-DR-7091 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7092 | NA | 131242-WST02-DR-7092 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7100 | NA | 131242-WST02-DR-7100 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7101 | NA | 131242-WST02-DR-7101 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7102 | NA | 131242-WST02-DR-7102 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7103 | NA | 131242-WST02-DR-7103 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7104 | NA | 131242-WST02-DR-7104 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7105 | NA | 131242-WST02-DR-7105 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7106 | NA | 131242-WST02-DR-7106 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7107 | NA | 131242-WST02-DR-7107 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7108 | NA | 131242-WST02-DR-7108 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7109 | NA | 131242-WST02-DR-7109 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7110 | NA | 131242-WST02-DR-7110 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7111 | NA | 131242-WST02-DR-7111 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7112 | NA | 131242-WST02-DR-7112 | 2025-04-08 |  | NA | 2025-04-28 | 2025-05-06 | 5 | Approved with Comments | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | C | 131242-WST02-DR-3024 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3025 | NA | 131242-WST02-DR-3025 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2026-02-03 | B | 000000&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3026 | NA | 131242-WST02-DR-3026 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3027 | NA | 131242-WST02-DR-3027 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3028 | NA | 131242-WST02-DR-3028 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3029 | NA | 131242-WST02-DR-3029 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3030 | NA | 131242-WST02-DR-3030 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | 2026-02-03 | B | 000000&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3031 | NA | 131242-WST02-DR-3031 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2026-02-03 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3032 | NA | 131242-WST02-DR-3032 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3033 | NA | 131242-WST02-DR-3033 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3034 | NA | 131242-WST02-DR-3034 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-03 | 2025-09-29 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3035 | NA | 131242-WST02-DR-3035 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | 2025-10-31 | A | 000000&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7126 | NA | 131242-WST02-DR-7126 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7127 | NA | 131242-WST02-DR-7127 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7128 | NA | 131242-WST02-DR-7128 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7129 | NA | 131242-WST02-DR-7129 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7130 | NA | 131242-WST02-DR-7130 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7131 | NA | 131242-WST02-DR-7131 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7132 | NA | 131242-WST02-DR-7132 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7133 | NA | 131242-WST02-DR-7133 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7134 | NA | 131242-WST02-DR-7134 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7135 | NA | 131242-WST02-DR-7135 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7080 | NA | 131242-WST02-DR-7080 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7081 | NA | 131242-WST02-DR-7081 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7082 | NA | 131242-WST02-DR-7082 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7083 | NA | 131242-WST02-DR-7083 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7084 | NA | 131242-WST02-DR-7084 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7085 | NA | 131242-WST02-DR-7085 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7086 | NA | 131242-WST02-DR-7086 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7087 | NA | 131242-WST02-DR-7087 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7088 | NA | 131242-WST02-DR-7088 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7089 | NA | 131242-WST02-DR-7089 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7090 | NA | 131242-WST02-DR-7090 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7091 | NA | 131242-WST02-DR-7091 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2024-12-03 | 2025-07-24 | NA | 000000 | 2024-12-03, 2025-04-08, 2025-07-24 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7092 | NA | 131242-WST02-DR-7092 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA |  | 2025-04-08 | 2025-07-24 | NA | 000000 | 2025-04-08, 2025-07-24 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7100 | NA | 131242-WST02-DR-7100 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2025-07-24 | A | 000000&&000605 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7101 | NA | 131242-WST02-DR-7101 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7102 | NA | 131242-WST02-DR-7102 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7103 | NA | 131242-WST02-DR-7103 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2025-07-24 | NA | 000000 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7104 | NA | 131242-WST02-DR-7104 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7105 | NA | 131242-WST02-DR-7105 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7106 | NA | 131242-WST02-DR-7106 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7107 | NA | 131242-WST02-DR-7107 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7108 | NA | 131242-WST02-DR-7108 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7109 | NA | 131242-WST02-DR-7109 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-07-24 | NA | 000000 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7110 | NA | 131242-WST02-DR-7110 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7111 | NA | 131242-WST02-DR-7111 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7112 | NA | 131242-WST02-DR-7112 | 2025-07-24 |  | NA | 2025-08-13 | 2026-01-02 | 100 | Approved with Comments | YES | 2026-01-22 | NO | Overdue | 2 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-07-24 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, NA | 6 | PEN | AWC | AWC
000871 | 00 | Thet Myo | QAQC | NA | 131242 | WSD11 | MM | S | 0001 | 0 | 131242-WSD11-MM-0001 | 2024-12-03 | THP Courtyard SCDF Consultation Letter | For Information | 2025-01-01 | 2024-11-14 |  | For Information | NO |  | YES |  |  |  |  | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" && "THP Courtyard SCDF Consultation Letter" | 2024-12-03 | 2025-11-20 | 0 | 000871&&001859 | 2024-12-03, 2025-11-20 | 00 | 2 | PEN | INF | INF
000872 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0026 | 0 | 131242-WSW41-QA-0026 | 2024-12-04 | Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-02 | 2024-12-14 |  | Approved with Comments | YES | 2025-01-03 | NO | Overdue | 276 |  |  | NA | "Factory Acceptance Test Report for pH Analyser" && "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | 2024-12-04 | 2025-07-08 | 0 | 000872&&001241&&001447 | 2024-12-04, 2025-04-21, 2025-07-08 | 00 | 3 | PEN | AWC | AWC
000873 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0009 | 0 | 131242-WST02-QA-0009 | 2024-12-04 | FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-02 | 2024-12-23 |  | Approved with Comments | YES | 2025-01-13 | NO | Overdue | 270 |  |  | NA | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " && "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-04 | 2025-09-15 | 0 | 000873&&000901&&001679 | 2024-12-04, 2024-12-13, 2025-09-15 | 00 | 3 | PEN | AWC | AWC
000874 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 0 | 131242-WST02-CL-5431 | 2024-12-04 | SSN Catchpot Sizing Calculation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-02 | 2025-01-08 | 4 | Approved with Comments | YES | 2025-01-28 | YES | Resubmitted |  | 2025-02-28 | comments received on 14 Feb | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | PEN | AWC | AWC
000874 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 1 | 131242-WST02-CL-5431 | 2025-03-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-28 | 16 | Approved with Comments | YES | 2025-05-16 | YES | Resubmitted |  |  |  | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | PEN | AWC | AWC
000874 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 2 | 131242-WST02-CL-5431 | 2025-07-14 | SSN Catchpot Sizing Calculation | NA | 2025-08-01 | 2025-09-17 | 33 | Approved with Comments | YES | 2025-10-07 | NO | Overdue | 79 |  |  | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | PEN | AWC | AWC
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | E | 131242-WST00-DR-8005_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | NA | 131242-WST02-DR-0302_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0310_ST608_BCA | NA | 131242-WST02-DR-0310_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA |  | 2024-12-05 | 2024-12-05 | NA | 000000 | 2024-12-05 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0311_ST608_BCA | NA | 131242-WST02-DR-0311_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA |  | 2024-12-05 | 2024-12-05 | NA | 000000 | 2024-12-05 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0312_ST608_BCA | NA | 131242-WST02-DR-0312_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA |  | 2024-12-05 | 2024-12-05 | NA | 000000 | 2024-12-05 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | NA | 131242-WST02-DR-1200_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | NA | 131242-WST02-DR-1201_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | NA | 131242-WST02-DR-1202_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | NA | 131242-WST02-DR-1203_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | NA | 131242-WST02-DR-1204_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | NA | 131242-WST02-DR-1205_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | NA | 131242-WST02-DR-2200_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | NA | 131242-WST02-DR-2201_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | NA | 131242-WST02-DR-2202_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | NA | 131242-WST02-DR-2203_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | NA | 131242-WST02-DR-3200_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | NA | 131242-WST02-DR-3201_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | NA | 131242-WST02-DR-3202_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | NA | 131242-WST02-DR-5200_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | NA | 131242-WST02-DR-5201_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | NA | 131242-WST02-DR-5202_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | NA | 131242-WST02-DR-5203_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | NA | 131242-WST02-DR-5204_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | NA | 131242-WST02-DR-5205_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | NA | 131242-WST02-DR-5206_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | NA | 131242-WST02-DR-5207_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | NA | 131242-WST02-DR-5208_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | NA | 131242-WST02-DR-5209_ST608_BCA | 2024-12-05 |  | NA | 2025-01-03 | 2025-01-16 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-04 | 2024-12-05 | NA | 000000 | 2024-10-04, 2024-12-05 | 00, NA | 2 | PEN | INF | INF
000876 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 0 | 131242-WST02-QA-0001 | 2024-12-05 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-03 | 2024-12-23 |  | Approved with Comments | YES | 2025-01-13 | YES | Resubmitted |  |  |  | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000876 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 1 | 131242-WST02-QA-0001 | 2025-04-11 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Approved with Comments | 2025-05-01 | 2025-06-09 | 25 | Approved with Comments | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000877 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0051 | 0 | 131242-WSW41-LT-0051 | 2024-12-07 | CV of Team Member (CSEM) | Rev 0: Accepted for Information. | 2025-01-06 | 2025-03-25 | 54 | For Information | NO |  | YES |  |  |  |  | NA | "CV of Team Member (CSEM)" | 2024-12-07 | 2024-12-07 | 0 | 000877 | 2024-12-07 | 00 | 1 | PEN | INF | INF
000878 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0052 | 0 | 131242-WSW41-LT-0052 | 2024-12-07 | Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3) | Rev (0): Rejected. Please refer to S.O. correspondence no. 397 dated 10 Sep 25. | 2025-01-06 | 2025-09-23 | 180 | Rejected | NO |  | YES |  |  |  |  | NA | "Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3)" | 2024-12-07 | 2024-12-07 | 0 | 000878 | 2024-12-07 | 00 | 1 | PEN | REJ | REJ
000879 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-NA | 2024-12-09 | VCM Model Submission | For Information. | 2025-01-07 | 2024-12-23 |  | For Information | NO |  | YES |  |  |  |  | NA | " VCM Submission for 2025-11" && "VCM Model Submission" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | 2026-02-09 | 0 | 000879&&001888&&001941&&002009 | 2024-12-09, 2025-12-08, 2026-01-08, 2026-02-09 | 00 | 4 | PEN | INF | INF
000880 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5391 | 0 | 131242-WST02-CL-5391 | 2024-12-10 | Sampling Pump Calculation | Rev 0: Approved | 2025-01-08 | 2025-04-27 | 73 | Approved | NO |  | YES |  |  |  |  | NA | "Sampling Pump Calculation" | 2024-12-10 | 2024-12-10 | 0 | 000880 | 2024-12-10 | 00 | 1 | PEN | APP | APP
000881 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 0 | 131242-WSW41-QA-0025 | 2024-12-10 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-08 | 2025-01-20 | 8 | Approved with Comments | YES | 2025-02-07 | YES | Resubmitted |  |  |  | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | PEN | AWC | AWC
000881 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 1 | 131242-WSW41-QA-0025 | 2025-03-13 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Approved | 2025-04-02 | 2025-05-19 | 30 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | PEN | APP | APP
000882 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0005 | 0 | 131242-WST02-VI-0005 | 2024-12-10 | Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-08 | 2024-12-23 |  | Approved with Comments | YES | 2025-01-13 | NO | Overdue | 270 |  | To follow-up with Jebsen and Jessen. | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | PEN | AWC | AWC
000883 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0008 | 0 | 131242-WST02-QA-0008 | 2024-12-10 | Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-08 | 2024-12-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" && "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " && "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2024-12-10 | 2025-09-04 | 0 | 000883&&001268&&001654 | 2024-12-10, 2025-05-04, 2025-07-05, 2025-09-04 | 00, 01 | 4 | PEN | APP | APP
000884 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0007 | 0 | 131242-WST02-QA-0007 | 2024-12-11 | Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-09 | 2024-12-23 |  | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " && "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " && "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2024-12-11 | 2025-08-27 | 0 | 000884&&001263&&001629 | 2024-12-11, 2025-05-02, 2025-07-07, 2025-08-27 | 00, 01 | 4 | PEN | APP | APP
000885 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 0 | 131242-WSW41-QA-0010 | 2024-12-11 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.0: As requested by CES to reject this submission. | 2025-01-09 | 2024-12-14 |  | Rejected | YES | 2025-01-03 | YES | Resubmitted |  |  |  | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | PEN | REJ | REJ
000885 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 1 | 131242-WSW41-QA-0010 | 2024-12-18 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.1: Approved with comments. Please refer comment sheet for resubmission. | 2025-01-08 | 2024-12-23 |  | Approved with Comments | YES | 2025-01-13 | NO | Overdue | 270 |  |  | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | PEN | AWC | AWC
000886 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | I | 0006 | 0 | 131242-WSW41-VI-0006 | 2024-12-11 | Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-09 | 2025-01-08 |  | Approved with Comments | YES | 2025-01-28 | NO | Overdue | 259 |  |  | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | PEN | AWC | AWC
000887 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0017 | 0 | 131242-WSW41-PS-0017 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Sept 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2025-01-10 | 2024-12-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Sept 2024" | 2024-12-12 | 2024-12-12 | 0 | 000887 | 2024-12-12 | 00 | 1 | PEN | INF | INF
000888 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0018 | 0 | 131242-WSW41-PS-0018 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Oct 2024 | Rev 0: Scoring confirmed to be at 60/100 | 2025-01-10 | 2024-12-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Oct 2024" && "Monthly Progress Presentation No. 18 (1124)" | 2024-11-30 | 2024-12-12 | 0 | 000862&&000888 | 2024-11-30, 2024-12-12 | 00 | 2 | PEN | INF | INF
000889 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-01-20 | 6 | Approved with Comments | YES | 2025-02-07 | YES | Resubmitted |  |  |  | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | PEN | AWC | AWC
000889 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 1: Approved. | 2025-01-02 | 2025-12-23 | 246 | Approved | NO |  | YES |  |  |  |  | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | PEN | APP | APP
000890 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 19 | 0 | 131242-WSW41-RT-19 | 2024-12-13 | C4B Monthly Progress Report Number No.19 (11 24) | Rev. 0 - Approved with comments (see attached comment sheet / need to re-submit) | 2025-01-13 | 2025-01-16 | 3 | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 |  |  | NA | "C4B Monthly Progress Report Number No.19 (11 24) " | 2024-12-13 | 2024-12-13 | 0 | 000890 | 2024-12-13 | 00 | 1 | PEN | AWC | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | A | 131242-WSW41-DR-5201 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | YES | Resubmitted |  | 2025-02-25 | Pending vendor resubmission - Jash | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-03-13 | B | 000891 | 2024-12-13, 2025-03-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5202 | NA | 131242-WSW41-DR-5202 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5203 | NA | 131242-WSW41-DR-5203 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5204 | NA | 131242-WSW41-DR-5204 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5205 | NA | 131242-WSW41-DR-5205 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5206 | NA | 131242-WSW41-DR-5206 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5207 | NA | 131242-WSW41-DR-5207 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5208 | NA | 131242-WSW41-DR-5208 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5209 | NA | 131242-WSW41-DR-5209 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5210 | NA | 131242-WSW41-DR-5210 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5211 | NA | 131242-WSW41-DR-5211 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5212 | NA | 131242-WSW41-DR-5212 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5213 | NA | 131242-WSW41-DR-5213 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5214 | NA | 131242-WSW41-DR-5214 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5215 | NA | 131242-WSW41-DR-5215 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5216 | NA | 131242-WSW41-DR-5216 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5217 | NA | 131242-WSW41-DR-5217 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5218 | NA | 131242-WSW41-DR-5218 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5219 | NA | 131242-WSW41-DR-5219 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5220 | NA | 131242-WSW41-DR-5220 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5221 | NA | 131242-WSW41-DR-5221 | 2024-12-13 |  | NA | 2025-01-13 | 2025-01-12 |  | Approved with Comments | YES | 2025-01-30 | NO | Overdue | 257 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | B | 131242-WSW41-DR-5201 | 2025-03-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 | 2025-02-25 | Pending vendor resubmission - Jash | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-03-13 | B | 000891 | 2024-12-13, 2025-03-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5202 | NA | 131242-WSW41-DR-5202 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5203 | NA | 131242-WSW41-DR-5203 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5204 | NA | 131242-WSW41-DR-5204 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5205 | NA | 131242-WSW41-DR-5205 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5206 | NA | 131242-WSW41-DR-5206 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5207 | NA | 131242-WSW41-DR-5207 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5208 | NA | 131242-WSW41-DR-5208 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5209 | NA | 131242-WSW41-DR-5209 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5210 | NA | 131242-WSW41-DR-5210 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5211 | NA | 131242-WSW41-DR-5211 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5212 | NA | 131242-WSW41-DR-5212 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5213 | NA | 131242-WSW41-DR-5213 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5214 | NA | 131242-WSW41-DR-5214 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5215 | NA | 131242-WSW41-DR-5215 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5216 | NA | 131242-WSW41-DR-5216 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5217 | NA | 131242-WSW41-DR-5217 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5218 | NA | 131242-WSW41-DR-5218 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5219 | NA | 131242-WSW41-DR-5219 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5220 | NA | 131242-WSW41-DR-5220 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5221 | NA | 131242-WSW41-DR-5221 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2024-12-13 | 2025-01-13 | NA | 000000 | 2024-12-13, 2025-01-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5222 | NA | 131242-WSW41-DR-5222 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5223 | NA | 131242-WSW41-DR-5223 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5224 | NA | 131242-WSW41-DR-5224 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5225 | NA | 131242-WSW41-DR-5225 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5226 | NA | 131242-WSW41-DR-5226 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5227 | NA | 131242-WSW41-DR-5227 | 2025-01-13 |  | NA | 2025-04-02 | 2025-04-08 | 4 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA |  | 2025-01-13 | 2025-01-13 | NA | 000000 | 2025-01-13 | NA | 1 | PEN | AWC | AWC
000892 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0037 | 0 | 131242-WSW41-MI-0037 | 2024-12-13 | CSA Meeting Minutes 0037_28112024 | For Information | 2025-01-13 | 2024-12-30 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0037_28112024" && "Process & MEICA Meeting Minutes 0037_05122024" | 2024-12-13 | 2025-01-11 | 0 | 000892&&000966 | 2024-12-13, 2025-01-11 | 00 | 2 | PEN | INF | INF
000893 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0023 | 0 | 131242-WST02-VI-0023 | 2024-12-13 | Vendor Approval of SSN Package (Rotameter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-14 | 42 | Approved with Comments | YES | 2025-04-03 | NO | Overdue | 212 |  |  | NA | "Vendor Approval of SSN Package (Rotameter)" | 2024-12-13 | 2024-12-13 | 0 | 000893 | 2024-12-13 | 00 | 1 | PEN | AWC | AWC
000894 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0050 | 0 | 131242-WSW41-LT-0050 | 2024-12-13 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025. | 2025-01-13 | 2025-08-25 | 154 | Rejected | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-12-13 | 2024-12-13 | 0 | 000894 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000895 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 0 | 131242-WSW41-DS-1390 | 2024-12-13 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2024-12-23 |  | Approved with Comments | YES | 2025-01-13 | YES | Resubmitted |  |  |  | NA | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2024-12-13 | 2025-02-14 | 1 | 000895 | 2024-12-13, 2025-02-14 | 00, 01 | 2 | PEN | AWC | AWC
000895 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 1 | 131242-WSW41-DS-1390 | 2025-02-14 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 1: Approved. | 2025-03-06 | 2025-04-27 | 34 | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2024-12-13 | 2025-02-14 | 1 | 000895 | 2024-12-13, 2025-02-14 | 00, 01 | 2 | PEN | APP | APP
000896 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 0 | 131242-WSW41-DS-1389 | 2024-12-13 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 3 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2024-12-13 | 2025-03-06 | 1 | 000896 | 2024-12-13, 2025-03-06 | 00, 01 | 2 | PEN | AWC | AWC
000896 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 1 | 131242-WSW41-DS-1389 | 2025-03-06 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-26 | 2025-04-27 | 20 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2024-12-13 | 2025-03-06 | 1 | 000896 | 2024-12-13, 2025-03-06 | 00, 01 | 2 | PEN | AWC | AWC
000897 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-1391 | 2024-12-13 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 3 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2024-12-13 | 2025-03-11 | 0 | 000897 | 2024-12-13, 2025-03-11 | 00, 01 | 2 | PEN | AWC | AWC
000897 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-1391 | 2025-03-11 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 1: Approved. | 2025-03-31 | 2025-05-05 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2024-12-13 | 2025-03-11 | 0 | 000897 | 2024-12-13, 2025-03-11 | 00, 01 | 2 | PEN | APP | APP
000898 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-0023 | 2024-12-13 | MSRA and SWP for Installation of AAC Block Wall | Approved | 2025-01-13 | 2025-01-08 |  | Approved | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2024-12-13 | 2025-02-16 | 0 | 000898&&001044 | 2024-12-13, 2025-02-16 | 00 | 2 | PEN | APP | APP
000899 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0030 | 0 | 131242-WST02-DS-0030 | 2024-12-13 | Data Sheet for Blower Discharge Sliencer | Rev 0: Approved | 2025-01-13 | 2025-03-04 | 34 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Blower Discharge Sliencer" | 2024-12-13 | 2024-12-13 | 0 | 000899 | 2024-12-13 | 00 | 1 | PEN | APP | APP
000900 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 0 | 131242-WST02-DS-0002 | 2024-12-13 | Datasheet for Electromagnetic Flowmeter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-25 | 49 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2025-06-26 | 1 | 000000&&000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | PEN | NAP | NAP
000900 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 1 | 131242-WST02-DS-0002 | 2025-06-26 | Datasheet for Electromagnetic Flowmeter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-16 | 2025-07-28 | 8 | Approved with Comments | YES | 2025-08-15 | NO | Overdue | 116 |  |  | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2025-06-26 | 1 | 000000&&000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | PEN | AWC | AWC
000901 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0009 | 0 | 131242-WST02-QA-0009 | 2024-12-13 | Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh | For Information | 2025-01-13 | 2024-12-23 |  | For Information | NO |  | YES |  |  |  |  | NA | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " && "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-04 | 2025-09-15 | 0 | 000873&&000901&&001679 | 2024-12-04, 2024-12-13, 2025-09-15 | 00 | 3 | PEN | INF | INF
000902 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004_Withdraw | 0 | 131242-WSD11-QA-0004_Withdraw | 2024-12-13 | Instrument Differential Pressure Switch SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 17 | Rejected | NO |  | YES |  |  |  |  | NA | "Instrument Differential Pressure Switch SAT" | 2024-12-13 | 2024-12-13 | 0 | 000902 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000903 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005_Withdraw | 0 | 131242-WSD11-QA-0005_Withdraw | 2024-12-13 | Instrument Pressure Transmitter SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 17 | Rejected | NO |  | YES |  |  |  |  | NA | "Instrument Pressure Transmitter SAT" | 2024-12-13 | 2024-12-13 | 0 | 000903 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000904 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006_Withdraw | 0 | 131242-WSD11-QA-0006_Withdraw | 2024-12-13 | Penumatic on/ off Valve SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 17 | Rejected | NO |  | YES |  |  |  |  | NA | "Penumatic on/ off Valve SAT" | 2024-12-13 | 2024-12-13 | 0 | 000904 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000905 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002_Withdraw | 0 | 131242-WSD11-QA-0002_Withdraw | 2024-12-13 | Air Compresspor SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 17 | Rejected | NO |  | YES |  |  |  |  | NA | "Air Compresspor SAT" | 2024-12-13 | 2024-12-13 | 0 | 000905 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000906 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003_Withdraw | 0 | 131242-WSD11-QA-0003_Withdraw | 2024-12-13 | Air Dryer SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 17 | Rejected | NO |  | YES |  |  |  |  | NA | "Air Dryer SAT" | 2024-12-13 | 2024-12-13 | 0 | 000906 | 2024-12-13 | 00 | 1 | PEN | REJ | REJ
000907 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 0 | 131242-WST02-RT-0009 | 2024-12-16 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 23 | Approved with Comments | YES | 2025-03-10 | YES | Resubmitted |  |  |  | NA | "SSN Harmonics Study Report" | 2024-12-16 | 2026-01-20 | 1 | 000907 | 2024-12-16, 2026-01-20 | 00, 01 | 2 | PEN | AWC | AWC
000907 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 1 | 131242-WST02-RT-0009 | 2026-01-20 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-09 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "SSN Harmonics Study Report" | 2024-12-16 | 2026-01-20 | 1 | 000907 | 2024-12-16, 2026-01-20 | 00, 01 | 2 | PEN | PEN | PEN
000908 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0004 | 0 | 131242-WSD11-RT-0004 | 2024-12-16 | THP Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 23 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | PEN | AWC | AWC
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A | 131242-WSW41-DR-5128 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 2 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | 2025-02-27 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5129 | NA | 131242-WSW41-DR-5129 | 2024-12-16 |  | NA | 2025-01-14 | 2025-01-16 | 2 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-06-25 | A.2 | 000000&&000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 02, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5130 | NA | 131242-WSW41-DR-5130 | 2024-12-16 |  | NA | 2025-01-14 | 2025-01-16 | 2 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-16 | 2025-03-13 | NA | 000000 | 2024-12-16, 2025-03-13 | NA | 2 | PEN | AWC | AWC
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A.1 | 131242-WSW41-DR-5128 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | 2025-02-27 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5129 | NA | 131242-WSW41-DR-5129 | 2025-03-13 |  | NA | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-06-25 | A.2 | 000000&&000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 02, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5130 | NA | 131242-WSW41-DR-5130 | 2025-03-13 |  | NA | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  |  |  | NA |  | 2024-12-16 | 2025-03-13 | NA | 000000 | 2024-12-16, 2025-03-13 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | M | 5100 | NA | 131242-WSW41-DR-5100 | 2025-03-13 |  | NA | 2025-04-02 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2026-01-19 | A.1 | 000000&&000297 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01, NA | 5 | PEN | AWC | AWC
000909 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.2 | 131242-WSW41-DR-5129 | 2025-06-25 | Pipe Support Standard- SWPR | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 59 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-06-25 | A.2 | 000000&&000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 02, NA | 3 | PEN | AWC | AWC
000910 | 00 | David | Mech | NA | 131242 | WSW41 | DS | M | 5341 | 0 | 131242-WSW41-DS-5341 | 2024-12-17 | Data Sheet of Auto Lubrication Unit for centrifugal pump | Rev 0: Not approved - Revise and Resubmit | 2025-01-15 | 2025-01-20 | 3 | Not Approved | YES | 2025-02-07 | NO | Overdue | 251 | 2025-03-28 | In Progress | NA | "Data Sheet of Auto Lubrication Unit for centrifugal pump" | 2024-12-17 | 2024-12-17 | 0 | 000910 | 2024-12-17 | 00 | 1 | PEN | NAP | NAP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A | 131242-WST02-DR-5401 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  | 2025-03-28 | In Progress | NA | "GA Drawing for FRP Tank" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-17 | 2025-10-23 | A.1 | 000000&&000911 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5402 | NA | 131242-WST02-DR-5402 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-12-05 | NA | 000000 | 2024-12-17, 2025-04-01, 2025-12-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5403 | NA | 131242-WST02-DR-5403 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5404 | NA | 131242-WST02-DR-5404 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5405 | NA | 131242-WST02-DR-5405 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5416 | NA | 131242-WST02-DR-5416 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5417 | NA | 131242-WST02-DR-5417 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5419 | NA | 131242-WST02-DR-5419 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5420 | NA | 131242-WST02-DR-5420 | 2024-12-17 |  | NA | 2025-01-15 | 2025-01-16 | 1 | Approved with Comments | YES | 2025-02-05 | YES | Resubmitted |  |  |  | NA | "Hookup Drawing - DO Analyser" | 2024-12-17 | 2025-10-23 | A | 000000&&001786 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, NA | 3 | PEN | AWC | AWC
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A.1 | 131242-WST02-DR-5401 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "GA Drawing for FRP Tank" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-17 | 2025-10-23 | A.1 | 000000&&000911 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5402 | NA | 131242-WST02-DR-5402 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-12-05 | NA | 000000 | 2024-12-17, 2025-04-01, 2025-12-05 | NA | 3 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5403 | NA | 131242-WST02-DR-5403 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5404 | NA | 131242-WST02-DR-5404 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5405 | NA | 131242-WST02-DR-5405 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5406 | NA | 131242-WST02-DR-5406 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2025-04-01 | 2025-12-18 | NA | 000000 | 2025-04-01, 2025-12-18 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5407 | NA | 131242-WST02-DR-5407 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2025-04-01 | 2025-04-01 | NA | 000000 | 2025-04-01 | NA | 1 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5408 | NA | 131242-WST02-DR-5408 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2025-04-01 | 2025-04-01 | NA | 000000 | 2025-04-01 | NA | 1 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5416 | NA | 131242-WST02-DR-5416 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5417 | NA | 131242-WST02-DR-5417 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5418 | NA | 131242-WST02-DR-5418 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2025-04-01 | 2025-04-01 | NA | 000000 | 2025-04-01 | NA | 1 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5419 | NA | 131242-WST02-DR-5419 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2024-12-17 | 2025-04-01 | NA | 000000 | 2024-12-17, 2025-04-01 | NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5420 | NA | 131242-WST02-DR-5420 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Hookup Drawing - DO Analyser" | 2024-12-17 | 2025-10-23 | A | 000000&&001786 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, NA | 3 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5421 | NA | 131242-WST02-DR-5421 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-04-01 | 2025-10-23 | NA | 000000 | 2025-04-01, 2025-10-23 | 00, NA | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5422 | NA | 131242-WST02-DR-5422 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA |  | 2025-04-01 | 2025-04-01 | NA | 000000 | 2025-04-01 | NA | 1 | PEN | APP | APP
000912 | 00 | Max | Project | NA | 131242 | WST02 | RT | S | 0001 | 0 | 131242-WST02-RT-0001 | 2024-12-18 | Safety Review Report for SSN Structures | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-16 | 2025-01-16 |  | Approved with Comments | YES | 2025-02-05 | NO | Overdue | 253 |  |  | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
000913 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0010 | 0 | 131242-WST02-QA-0010 | 2024-12-18 | FAT report for Earth cable, LV Power cable (Unwitnessed) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-02-18 | 21 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | PEN | AWC | AWC
000914 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0028 | 0 | 131242-WSD11-QA-0028 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 41 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | "Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI)" | 2024-12-18 | 2024-12-18 | 0 | 000914 | 2024-12-18 | 00 | 1 | PEN | AWC | AWC
000915 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0024 | 0 | 131242-WSD11-QA-0024 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 41 | Approved with Comments | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
000916 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0013 | 0 | 131242-WSD11-CL-0013 | 2024-12-18 | THP G2D Plant Hydraulic Network Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-04-27 | 67 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "THP G2D Plant Hydraulic Network Calculation" | 2024-12-18 | 2024-12-18 | 0 | 000916 | 2024-12-18 | 00 | 1 | PEN | AWC | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | A | 131242-WST02-DR-5501 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "GA Drawing for Dosing Pump" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | 2026-01-20 | B | 000000&&000573&&000917 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5511 | NA | 131242-WST02-DR-5511 | 2024-12-18 |  | NA | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5521 | NA | 131242-WST02-DR-5521 | 2024-12-18 |  | NA | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5531 | NA | 131242-WST02-DR-5531 | 2024-12-18 |  | NA | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5541 | NA | 131242-WST02-DR-5541 | 2024-12-18 |  | NA | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5551 | NA | 131242-WST02-DR-5551 | 2024-12-18 |  | NA | 2025-01-16 | 2025-03-04 | 31 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | AWC | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | B | 131242-WST02-DR-5501 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-03 |  | 144 | Awaiting S.O.'s response | [7 empty] | NA | "GA Drawing for Dosing Pump" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | 2026-01-20 | B | 000000&&000573&&000917 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01, NA | 4 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5511 | NA | 131242-WST02-DR-5511 | 2025-06-15 |  | NA | 2025-07-11 | 2025-03-04 | 138 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5521 | NA | 131242-WST02-DR-5521 | 2025-06-15 |  | NA | 2025-07-11 | 2025-03-04 | 138 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5531 | NA | 131242-WST02-DR-5531 | 2025-06-15 |  | NA | 2025-07-11 | 2025-03-04 | 138 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5541 | NA | 131242-WST02-DR-5541 | 2025-06-15 |  | NA | 2025-07-11 | 2025-03-04 | 138 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5551 | NA | 131242-WST02-DR-5551 | 2025-06-15 |  | NA | 2025-07-11 | 2025-03-04 | 138 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-18 | 2025-06-15 | NA | 000000 | 2024-12-18, 2025-06-15 | NA | 2 | PEN | PEN | PEN
000918 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 0 | 131242-WST02-CL-8000 | 2024-12-18 | Hydraulic Calculation (HOSEREEL) | Rev 0: Not approved - Revise and Resubmit | 2025-01-16 | 2025-01-24 | 6 | Not Approved | YES | 2025-02-13 | YES | Resubmitted |  |  |  | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
000918 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 1 | 131242-WST02-CL-8000 | 2025-02-19 | Hydraulic Calculation (HOSEREEL) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-11 | 2025-03-18 | 5 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
000919 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 0 | 131242-WSW41-LT-0053 | 2024-12-19 | CV of Team Member (T&C Manager) | Rejected as requested by Contractor | 2025-01-17 | 2024-12-27 |  | Rejected | YES | 2025-01-16 | YES | Resubmitted |  |  |  | NA | "CV of Team Member (T&C Manager)" | 2024-12-19 | 2024-12-27 | 1 | 000919 | 2024-12-19, 2024-12-27 | 00, 01 | 2 | PEN | REJ | REJ
000919 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 1 | 131242-WSW41-LT-0053 | 2024-12-27 | CV of Team Member (T&C Manager) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-21 | 44 | Approved with Comments | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "CV of Team Member (T&C Manager)" | 2024-12-19 | 2024-12-27 | 1 | 000919 | 2024-12-19, 2024-12-27 | 00, 01 | 2 | PEN | AWC | AWC
000920 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0006 | 0 | 131242-WSW41-MS-0006 | 2024-12-18 | Installation of Cable Container Support System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the attached file for comments. | 2025-01-16 | 2025-12-17 | 232 | Approved with Comments | YES | 2026-01-06 | NO | Overdue | 14 |  |  | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | PEN | AWC | AWC
000921 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 0 | 131242-WSW41-VI-2004 | 2024-12-19 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-17 | 2025-03-10 | 34 | Approved with Comments | YES | 2025-03-28 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2024-12-19 | 2025-04-01 | 1 | 000921 | 2024-12-19, 2025-04-01 | 00, 01 | 2 | PEN | AWC | AWC
000921 | 01 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 1 | 131242-WSW41-VI-2004 | 2025-04-01 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2024-12-19 | 2025-04-01 | 1 | 000921 | 2024-12-19, 2025-04-01 | 00, 01 | 2 | PEN | APP | APP
000922 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1393 | 0 | 131242-WST02-DS-1393 | 2024-12-19 | Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 20 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) " | 2024-12-19 | 2024-12-19 | 0 | 000922 | 2024-12-19 | 00 | 1 | PEN | AWC | AWC
000923 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1392 | 0 | 131242-WST02-DS-1392 | 2024-12-19 | Sample Board Submission for SS Cable Ladder, Accessories (United U-LI) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 20 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for SS Cable Ladder, Accessories (United U-LI)" | 2024-12-19 | 2024-12-19 | 0 | 000923 | 2024-12-19 | 00 | 1 | PEN | AWC | AWC
000924 | 00 | Yuen Fatt | Project | NA | 131242 | WSD11 | VI | M | 0032 | 0 | 131242-WSD11-VI-0032 | 2024-12-20 | Vendor Approval of Ducting - CES_Salcon Sdn Bhd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-20 | 2025-01-09 |  | Approved with Comments | YES | 2025-01-29 | NO | Overdue | 258 |  |  | NA | "Vendor Approval of Ducting - CES_Salcon Sdn Bhd" | 2024-12-20 | 2024-12-20 | 0 | 000924 | 2024-12-20 | 00 | 1 | PEN | AWC | AWC
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5351 | A | 131242-WST02-DR-5351 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 64 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "PC Pump GA Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-23 | 2025-10-23 | A | 000000&&000925 | 2024-12-23, 2025-10-23 | 00 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5361 | NA | 131242-WST02-DR-5361 | 2024-12-23 |  | NA | 2025-01-21 | 2025-03-04 | 255 | Awaiting S.O.'s response | [7 empty] | NA |  | 2024-12-23 | 2024-12-23 | NA | 000000 | 2024-12-23 | NA | 1 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5371 | NA | 131242-WST02-DR-5371 | 2024-12-23 |  | NA | 2025-01-21 | 2025-03-04 | 255 | Awaiting S.O.'s response | [7 empty] | NA | "SSN Instrument Hookup Drawing for Temperature Transmitter" | 2024-12-23 | 2025-09-10 | A | 000000&&001674 | 2024-12-23, 2025-09-10 | 00, NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5381 | NA | 131242-WST02-DR-5381 | 2024-12-23 |  | NA | 2025-01-21 | 2025-03-04 | 255 | Awaiting S.O.'s response | [7 empty] | NA | "Hookup Drawing - Autosampler" | 2024-12-23 | 2025-11-05 | 0 | 000000&&001822 | 2024-12-23, 2025-11-05 | 00, NA | 2 | PEN | PEN | PEN
000926 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0012 | 0 | 131242-WST02-VI-0012 | 2024-12-23 | Vendor Approval - Passive Harmonic Filter | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-01-21 | 2025-01-19 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | PEN | REJ | REJ
000927 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-0011 | 2024-12-23 | FAT Report for Cable Ladder 1st Batch (United ULI) | Rev 0: Approved. | 2025-01-21 | 2025-02-18 | 18 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | PEN | APP | APP
000928 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0018 | 0 | 131242-WSW41-PC-0018 | 2024-12-24 | Payment Claim No.18 | Rev(0): Approved. Please refer to S.O. correspondence no. 273 dated 26 Dec 2024. | 2025-01-22 | 2025-01-08 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.18" | 2024-12-24 | 2024-12-24 | 0 | 000928 | 2024-12-24 | 00 | 1 | PEN | APP | APP
000929 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0030 | 0 | 131242-WSW41-QA-0030 | 2024-12-24 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-22 | 2025-03-11 | 32 | Approved with Comments | YES | 2025-03-31 | NO | Overdue | 215 |  |  | NA | "FAT Report for Control Cable and Power Cables" && "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" && "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | 2024-12-24 | 2025-04-25 | 0 | 000929&&001237&&001253 | 2024-12-24, 2025-04-21, 2025-04-25 | 00 | 3 | PEN | AWC | AWC
000930 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0031 | 0 | 131242-WSD11-QA-0031 | 2024-12-26 | Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) | Rev 0: Approved | 2025-01-23 | 2025-03-11 | 31 | Approved | NO |  | YES |  |  |  |  | NA | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " && "SAT Report for WSD11-MCC-0101A&B" | 2024-12-26 | 2025-05-23 | 0 | 000930&&001317 | 2024-12-26, 2025-05-23 | 00 | 2 | PEN | APP | APP
000931 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | A | 131242-WST02-DR-5601 | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-24 | 2025-03-04 | 25 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Screen General Arrangement Drawing" | 2024-12-27 | 2025-07-24 | B | 000000&&000931 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01, NA | 4 | PEN | AWC | AWC
000931 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | B | 131242-WST02-DR-5601 | 2025-05-26 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 |  | 158 | Awaiting S.O.'s response | [7 empty] | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Screen General Arrangement Drawing" | 2024-12-27 | 2025-07-24 | B | 000000&&000931 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01, NA | 4 | PEN | PEN | PEN
000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0011 | 0 | 131242-WSD11-OM-0011 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | 29 | For Information | NO |  | YES |  |  |  |  | NA | "O&M manual for Air Dryer and Air Compressor" | 2024-12-27 | 2024-12-27 | 0 | 000932 | 2024-12-27 | 00 | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | OM | M | 0010 | NA | 131242-WSD11-OM-0010 | 2024-12-27 |  | NA | 2025-01-24 | 2025-03-10 | 29 | For Information | NO |  | YES |  |  |  |  | NA |  | 2024-12-27 | 2024-12-27 | NA | 000000 | 2024-12-27 | NA | 1 | PEN | INF | INF
000933 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601_WITHDRAW | A | 131242-WST02-DR-5601_WITHDRAW | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Rejected Submittal 931 include the same content and is already reviewed. | 2025-01-24 | 2025-03-04 | 25 | Rejected | NO |  | YES |  |  |  |  | NA | "Screen General Arrangement Drawing" | 2024-12-27 | 2024-12-27 | A | 000933 | 2024-12-27 | 00 | 1 | PEN | REJ | REJ
000934 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5136 | 0 | 131242-WST02-DR-5136 | 2024-12-31 | Blower Name Plate Drawing | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 47 | Approved | NO |  | YES |  |  |  |  | NA | "Blower Name Plate Drawing " | 2024-12-31 | 2024-12-31 | 0 | 000934 | 2024-12-31 | 00 | 1 | PEN | APP | APP
000935 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0010 | 0 | 131242-WST02-QA-0010 | 2024-12-31 | Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-01-28 | 2025-02-24 | 17 | Approved with Comments | YES | 2025-03-14 | NO | Overdue | 226 |  |  | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | PEN | AWC | AWC
000936 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0012 | 0 | 131242-WSW41-QA-0012 | 2024-12-31 | FAT Report for Power Cable, Control Cable, MV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-28 | 2025-01-20 |  | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 |  |  | NA | "FAT Report for Power Cable, Control Cable, MV Cable" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2024-12-31 | 2026-01-28 | 0 | 000000&&000936&&001304 | 2024-12-31, 2025-05-18, 2025-09-30, 2026-01-28 | 00 | 4 | PEN | AWC | AWC
000937 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0034 | 0 | 131242-WSW41-QA-0034 | 2024-12-31 | Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 47 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" && "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" && "Site Acceptance Test Procedure for 22KV HV Cable" | 2024-12-31 | 2025-07-08 | 0 | 000937&&001280&&001449 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | PEN | APP | APP
000938 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0035 | 0 | 131242-WSW41-QA-0035 | 2024-12-31 | Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 47 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " && "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " && "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | 2025-07-08 | 0 | 000938&&001292&&001450 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | PEN | APP | APP
000939 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0032 | 0 | 131242-WSW41-QA-0032 | 2025-01-02 | QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details) | Rev 0: Approved | 2025-01-30 | 2025-04-27 | 58 | Approved | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" && "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" | 2025-01-02 | 2025-05-13 | 0 | 000939&&001278 | 2025-01-02, 2025-05-13 | 00 | 2 | PEN | APP | APP
000940 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0029 | 0 | 131242-WSW41-QA-0029 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating | Rev 0: Approved | 2025-01-30 | 2025-04-08 | 46 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" && "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" && "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" && "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | 2025-10-13 | 0 | 000940&&001217&&001238&&001745 | 2025-01-02, 2025-04-10, 2025-04-21, 2025-10-13 | 00 | 4 | PEN | APP | APP
000941 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 0 | 131242-WSW41-QA-0033 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Rev 0: Not approved - Revise and Resubmit | 2025-01-30 | 2025-03-18 | 32 | Not Approved | YES | 2025-04-07 | YES | Resubmitted |  |  |  | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | PEN | NAP | NAP
000941 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 1 | 131242-WSW41-QA-0033 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Approved | 2025-05-09 | 2025-05-19 | 5 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | PEN | APP | APP
000942 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 0 | 131242-WSW41-SH-1004 | 2025-01-02 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 8 | Approved with Comments | YES | 2025-03-04 | YES | Resubmitted |  | TBC | SO comment: Please furnish GA drawings in TWRP format. (vendor not able to provide) | NA | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-01-02 | 2025-06-16 | 1 | 000942 | 2025-01-02, 2025-06-16 | 00, 01 | 2 | PEN | AWC | AWC
000942 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 1 | 131242-WSW41-SH-1004 | 2025-06-16 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2025-09-04 | 44 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-01-02 | 2025-06-16 | 1 | 000942 | 2025-01-02, 2025-06-16 | 00, 01 | 2 | PEN | AWC | AWC
000943 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | E | 0001 | 0 | 131242-WSW41-DS-0001 | 2025-01-03 | Datasheet for Unistrut Supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | PEN | AWC | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1300 | A | 131242-WSW41-DR-1300 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1301 | NA | 131242-WSW41-DR-1301 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1302 | NA | 131242-WSW41-DR-1302 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1303 | NA | 131242-WSW41-DR-1303 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1304 | NA | 131242-WSW41-DR-1304 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1305 | NA | 131242-WSW41-DR-1305 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1306 | NA | 131242-WSW41-DR-1306 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1307 | NA | 131242-WSW41-DR-1307 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1308 | NA | 131242-WSW41-DR-1308 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | E | 1309 | NA | 131242-WSW41-DR-1309 | 2025-01-03 |  | NA | 2025-01-31 | 2025-03-13 | 29 | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | AWC | AWC
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-1600_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | 2025-01-11 | D | 000000&&000945 | 2025-01-03, 2025-01-11 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | NA | 131242-WST02-DR-1601_ST611_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-08 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | NA | 131242-WST02-DR-5600_ST611_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-08 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-5601_ST611_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-08 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-11 | D | 000000&&000963 | 2025-01-03, 2025-01-11 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | NA | 131242-WST02-DR-5602_ST611_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-08 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609_BCA | E | 131242-WST00-DR-8004_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1100__ST609_BCA | NA | 131242-WST02-DR-1100__ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0300__ST609_BCA | NA | 131242-WST02-DR-0300__ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0301_ST609_BCA | NA | 131242-WST02-DR-0301_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0303_ST609_BCA | NA | 131242-WST02-DR-0303_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0304_ST609_BCA | NA | 131242-WST02-DR-0304_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0305_ST609_BCA | NA | 131242-WST02-DR-0305_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0306_ST609_BCA | NA | 131242-WST02-DR-0306_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0307_ST609_BCA | NA | 131242-WST02-DR-0307_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0308_ST609_BCA | NA | 131242-WST02-DR-0308_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 0309_ST609_BCA | NA | 131242-WST02-DR-0309_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1101_ST609_BCA | NA | 131242-WST02-DR-1101_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1102_ST609_BCA | NA | 131242-WST02-DR-1102_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1103_ST609_BCA | NA | 131242-WST02-DR-1103_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2100_ST609_BCA | NA | 131242-WST02-DR-2100_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2101_ST609_BCA | NA | 131242-WST02-DR-2101_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 2102_ST609_BCA | NA | 131242-WST02-DR-2102_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3100_ST609_BCA | NA | 131242-WST02-DR-3100_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3101_ST609_BCA | NA | 131242-WST02-DR-3101_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 3102_ST609_BCA | NA | 131242-WST02-DR-3102_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5100_ST609_BCA | NA | 131242-WST02-DR-5100_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5101_ST609_BCA | NA | 131242-WST02-DR-5101_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5102_ST609_BCA | NA | 131242-WST02-DR-5102_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5103_ST609_BCA | NA | 131242-WST02-DR-5103_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5104_ST609_BCA | NA | 131242-WST02-DR-5104_ST609_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | D | 131242-WSW41-DR-8002_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | D | 000000&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | NA | 131242-WSW41-DR-1100_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | NA | 131242-WSW41-DR-0310_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | 2025-01-03 | A | 000000&&000773 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | NA | 131242-WSW41-DR-0311_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | NA | 131242-WSW41-DR-0312_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | NA | 131242-WSW41-DR-0313_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | NA | 131242-WSW41-DR-0314_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | NA | 131242-WSW41-DR-0315_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | NA | 131242-WSW41-DR-1101_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | NA | 131242-WSW41-DR-1102_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | NA | 131242-WSW41-DR-1103_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | NA | 131242-WSW41-DR-1104_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1105_ST614_BCA | NA | 131242-WSW41-DR-1105_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 1106_ST614_BCA | NA | 131242-WSW41-DR-1106_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-03 | NA | 000000 | 2025-01-03 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | NA | 131242-WSW41-DR-2100_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | NA | 131242-WSW41-DR-2101_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | NA | 131242-WSW41-DR-3100_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | NA | 131242-WSW41-DR-5100_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | NA | 131242-WSW41-DR-5101_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | NA | 131242-WSW41-DR-5102_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | NA | 131242-WSW41-DR-5103_ST614_BCA | 2025-01-03 |  | NA | 2025-01-31 | 2025-02-12 | 8 | For Information | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-10-23 | 2025-01-03 | NA | 000000 | 2024-10-23, 2025-01-03 | 00, NA | 2 | PEN | INF | INF
000948 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0014 | 0 | 131242-WSW41-RT-0014 | 2025-01-03 | Bored Piling Pile Eccentricity Reports (ECC 19 & 20) | For Information. Please refer comment sheet. | 2025-01-31 | 2025-01-12 |  | For Information | NO |  | YES |  |  |  |  | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | PEN | INF | INF
000949 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 0 | 131242-WSW41-MS-0007 | 2025-01-03 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-01-31 | 2025-01-24 |  | Not Approved | YES | 2025-02-13 | YES | Resubmitted |  |  |  | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | PEN | NAP | NAP
000949 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 1 | 131242-WSW41-MS-0007 | 2025-02-27 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-27 | 25 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | PEN | AWC | AWC
000950 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0005 | 0 | 131242-WST02-VI-0005 | 2025-01-03 | Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd. | Approved | 2025-01-31 | 2025-01-16 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | PEN | APP | APP
000951 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0011 | 0 | 131242-WST02-QA-0011 | 2025-01-04 | Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-01-31 | 2025-02-03 | 1 | Approved with Comments | YES | 2025-02-21 | NO | Overdue | 241 |  |  | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | PEN | AWC | AWC
000952 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-0021 | 2025-01-04 | Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024 | For information. | 2025-01-31 | 2025-01-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | PEN | INF | INF
000953 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1003 | 0 | 131242-WSW41-SH-1003 | 2025-01-07 | C4B Knife Gate Valve List & Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-04 | 2025-04-08 | 44 | Approved with Comments | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA | "C4B Knife Gate Valve List & Datasheet" | 2025-01-07 | 2025-01-07 | 0 | 000953 | 2025-01-07 | 00 | 1 | PEN | AWC | AWC
000954 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 0 | 131242-WSW41-VI-1013 | 2025-01-07 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 0: Not approved - Revise and Resubmit | 2025-02-04 | 2025-02-12 | 6 | Rejected | YES | 2025-03-04 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | PEN | REJ | REJ
000954 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 1 | 131242-WSW41-VI-1013 | 2025-03-27 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-04-11 |  | Approved with Comments | YES | 2025-05-01 | YES | Resubmitted |  | 2025-02-28 | Pending vendor clarification - Breen | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | PEN | AWC | AWC
000954 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 2 | 131242-WSW41-VI-1013 | 2025-06-17 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 2: Approved | 2025-07-07 | 2025-07-28 | 15 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | PEN | APP | APP
000955 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0036 | 0 | 131242-WSW41-QA-0036 | 2025-01-07 | FAT/MDR Report for Side Manway (9 no;) | Rev 0: Approved | 2025-02-04 | 2025-03-25 | 35 | Approved | NO |  | YES |  |  |  |  | NA | "FAT/MDR Report for Side Manway (9 no;)" && "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" | 2025-01-07 | 2025-05-13 | 0 | 000955&&001293 | 2025-01-07, 2025-05-13 | 00 | 2 | PEN | APP | APP
000956 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0051 | 0 | 131242-WSW41-CD-0051 | 2025-01-08 | Submission of BIM Coordination VCM Model (Dec 2024) | For Information. Score= 71/100 | 2025-02-05 | 2025-01-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Submission of BIM Coordination VCM Model (Dec 2024)" | 2025-01-08 | 2025-01-08 | 0 | 000956 | 2025-01-08 | 00 | 1 | PEN | INF | INF
000957 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0038 | 0 | 131242-WSW41-MI-0038 | 2025-01-09 | CSA Meeting Minutes 0038_12122024 | For information. | 2025-02-06 | 2025-01-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0038_12122024" | 2025-01-09 | 2025-01-09 | 0 | 000957 | 2025-01-09 | 00 | 1 | PEN | INF | INF
000958 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0038 | 0 | 131242-WST02-QA-0038 | 2025-01-09 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch) | Rev 0: Approved | 2025-02-06 | 2025-03-25 | 33 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" && "Factory Acceptance Test Report for TSS Analyser - Optical" && "Inspection Test Plan for Low Voltage Switchgear" | 2025-01-09 | 2025-07-22 | 0 | 000958&&001490&&001521 | 2025-01-09, 2025-07-21, 2025-07-22 | 00 | 3 | PEN | APP | APP
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0006 | A | 131242-WSD11-CL-0006 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1602 | NA | 131242-WSD11-DR-1602 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5602 | NA | 131242-WSD11-DR-5602 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007 | A | 131242-WSD11-CL-0007 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | 2026-01-12 | 1 | 000000&&000664&&000960 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5600 | NA | 131242-WSD11-DR-5600 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5601 | NA | 131242-WSD11-DR-5601 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1600 | NA | 131242-WSD11-DR-1600 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1601 | NA | 131242-WSD11-DR-1601 | 2025-01-10 |  | NA | 2025-02-07 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA |  | 2025-01-10 | 2025-01-10 | NA | 000000 | 2025-01-10 | NA | 1 | PEN | AWC | AWC
000961 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 0 | 131242-WSD11-DS-0004 | 2025-01-10 | Datasheet for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 4 | Approved with Comments | YES | 2025-03-05 | YES | Resubmitted |  | 2025-03-05 |  | NA | "Datasheet for Pressure Transmitter" | 2025-01-10 | 2025-03-17 | 1 | 000961 | 2025-01-10, 2025-03-17 | 00, 01 | 2 | PEN | AWC | AWC
000961 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 1 | 131242-WSD11-DS-0004 | 2025-03-17 | Datasheet for Pressure Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 21 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "Datasheet for Pressure Transmitter" | 2025-01-10 | 2025-03-17 | 1 | 000961 | 2025-01-10, 2025-03-17 | 00, 01 | 2 | PEN | AWC | AWC
000962 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 0 | 131242-WSD11-QA-0039 | 2025-01-10 | FAT report for THP Train 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-20 | 9 | Approved with Comments | YES | 2025-03-12 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000962 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 1 | 131242-WSD11-QA-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rejected, as requested by contractor via email dated 8 Dec 2025. They will resubmit ZIP files with clear descriptive folder names instead of individual file | 2025-12-26 | 2025-12-08 |  | Rejected | YES | 2025-12-26 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | PEN | REJ | REJ
000962 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 2 | 131242-WSD11-QA-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2025-12-23 |  | Approved with Comments | YES | 2026-01-12 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000962 | 03 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 3 | 131242-WSD11-QA-0039 | 2026-01-06 | FAT report for THP Train 1 (Part-1) | Rejected, as requested by contractor via email dated 8 Dec 2025. They will resubmit ZIP files with clear descriptive folder names instead of individual file | 2026-01-26 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | PEN | PEN | PEN
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-5601_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-11 | D | 000000&&000963 | 2025-01-03, 2025-01-11 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | NA | 131242-WST02-DR-5602_ST611_BCA | 2025-01-11 |  | NA | 2025-02-07 | 2025-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | NA | 131242-WST02-DR-1600_ST611_BCA | 2025-01-11 |  | NA | 2025-02-07 | 2025-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | 2025-01-11 | D | 000000&&000945 | 2025-01-03, 2025-01-11 | 00, NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | NA | 131242-WST02-DR-1601_ST611_BCA | 2025-01-11 |  | NA | 2025-02-07 | 2025-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | NA | 131242-WST02-DR-5600_ST611_BCA | 2025-01-11 |  | NA | 2025-02-07 | 2025-02-07 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-03 | 2025-01-11 | NA | 000000 | 2025-01-03, 2025-01-11 | NA | 2 | PEN | INF | INF
000964 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 0 | 131242-WSD11-SP-0004 | 2025-01-11 | Functional Design Specification (Air Compressor System) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-04 | 17 | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | PEN | AWC | AWC
000964 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 1 | 131242-WSD11-SP-0004 | 2025-06-04 | Functional Design Specification (Air Compressor System) | R1: Approved with comments. No resubmittal is required at this moment. The resubmittal is required only if any changes during the detailing. | 2025-06-24 | 2025-07-02 | 6 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | PEN | AWC | AWC
000964 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 2 | 131242-WSD11-SP-0004 | 2025-08-12 | Functional Design Specification (Air Compressor System) | R2: Approved with comments. However, no resubmission at this stage unless there is a change to the document. | 2025-09-01 | 2025-10-08 | 27 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | PEN | AWC | AWC
000965 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0036 | 0 | 131242-WSW41-MI-0036 | 2025-01-11 | Process & MEICA Meeting Minutes 0036_21112024 | For Information | 2025-02-07 | 2025-01-16 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0036_14112024" && "Process & MEICA Meeting Minutes 0036_21112024" | 2024-11-28 | 2025-01-11 | 0 | 000851&&000965 | 2024-11-28, 2025-01-11 | 00 | 2 | PEN | INF | INF
000966 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0037 | 0 | 131242-WSW41-MI-0037 | 2025-01-11 | Process & MEICA Meeting Minutes 0037_05122024 | For Information | 2025-02-07 | 2025-01-16 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0037_28112024" && "Process & MEICA Meeting Minutes 0037_05122024" | 2024-12-13 | 2025-01-11 | 0 | 000892&&000966 | 2024-12-13, 2025-01-11 | 00 | 2 | PEN | INF | INF
000967 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 0 | 131242-WST02-DS-0005 | 2025-01-11 | Datasheet for pH Transmitter & Sensor | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 4 | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  |  |  | NA | "Datasheet for pH Transmitter & Sensor " | 2025-01-11 | 2025-08-15 | 1 | 000967 | 2025-01-11, 2025-08-15 | 00, 01 | 2 | PEN | NAP | NAP
000967 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 1 | 131242-WST02-DS-0005 | 2025-08-15 | Datasheet for pH Transmitter & Sensor | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-11-26 | 58 | Approved with Comments | YES | 2025-12-16 | NO | Overdue | 29 |  |  | NA | "Datasheet for pH Transmitter & Sensor " | 2025-01-11 | 2025-08-15 | 1 | 000967 | 2025-01-11, 2025-08-15 | 00, 01 | 2 | PEN | AWC | AWC
000968 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 0 | 131242-WST02-QA-0012 | 2025-01-11 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-02-24 | 11 | Not Approved | YES | 2025-03-14 | YES | Resubmitted |  |  |  | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | PEN | NAP | NAP
000968 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-0012 | 2025-03-10 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-14 | 10 | Not Approved | YES | 2025-05-02 | YES | Resubmitted |  |  |  | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | PEN | NAP | NAP
000968 | 02 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-0012 | 2025-04-23 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.2: Not Approved. Please refer to comment sheet for resubmission | 2025-05-13 | 2025-04-28 |  | Not Approved | YES | 2025-05-16 | NO | Overdue | 181 |  |  | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | PEN | NAP | NAP
000969 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | I | 0005 | 0 | 131242-WSW41-QA-0005 | 2025-01-13 | FAT report for Power cable, Control Cable, Instrument Cable (Witness) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-02-10 | 2025-01-20 |  | Approved with Comments | YES | 2025-02-07 | NO | Overdue | 251 |  |  | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | PEN | AWC | AWC
000970 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0013 | 0 | 131242-WSW41-QA-0013 | 2025-01-13 | FAT report for SS Unistrut Support, Accessories (HDMANN) | Rev 0: Approved with comments. Resubmission not required. Please refer to attached file for comments as noted. | 2025-02-10 | 2025-03-02 | 14 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | AWC | AWC
000971 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0014 | 0 | 131242-WSW41-QA-0014 | 2025-01-13 | FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2026-01-28 | 1 | 000000&&000741&&000971&&000998&&001336 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | APP | APP
000972 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0015 | 0 | 131242-WST02-QA-0015 | 2025-01-13 | FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | PEN | APP | APP
000973 | 00 | Franklin | CSA | NA | 131242 | WSW41 | CN | S | 0002 | 0 | 131242-WSW41-CN-0002 | 2025-01-13 | Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-10 | 2025-02-24 | 10 | Approved with Comments | YES | 2025-03-14 | NO | Overdue | 226 |  |  | NA | "Proposed change of Manufacturer for SSN Aeration blowers" && "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | 2023-10-06 | 2025-01-13 | 0 | 000116&&000973 | 2023-10-06, 2025-01-13 | 00 | 2 | PEN | AWC | AWC
000974 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0040 | 0 | 131242-WSW41-QA-0040 | 2025-01-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) | Rev 0: Approved | 2025-02-11 | 2025-03-18 | 25 | Approved | NO |  | YES |  |  |  |  | NA | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " && "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | 2025-08-18 | 1 | 000974&&001454&&001491 | 2025-01-14, 2025-07-09, 2025-07-21, 2025-08-18 | 00, 01 | 4 | PEN | APP | APP
000975 | 00 | K. Balaji | Mech | NA | 131242 | WSW41 | MS | M | 0006 | 0 | 131242-WSW41-MS-0006 | 2025-01-14 | Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 | Rev 0: Approved | 2025-02-11 | 2025-04-11 | 42 | Approved | NO |  | YES |  |  |  |  | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | PEN | APP | APP
000976 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 0 | 131242-WSD11-QA-0041 | 2025-01-15 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-12 | 2025-02-20 | 6 | Approved with Comments | YES | 2025-03-12 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | PEN | AWC | AWC
000976 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 1 | 131242-WSD11-QA-0041 | 2025-12-09 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-29 | 2025-12-23 |  | Approved with Comments | YES | 2026-01-12 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | PEN | AWC | AWC
000976 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 2 | 131242-WSD11-QA-0041 | 2026-01-06 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | PEN | PEN | PEN
000977 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0024 | 0 | 131242-WSW41-SP-0024 | 2025-01-15 | Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-12 | 2025-03-04 | 14 | Approved with Comments | YES | 2025-03-24 | NO | Overdue | 220 |  |  | NA | "Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd)" | 2025-01-15 | 2025-01-15 | 0 | 000977 | 2025-01-15 | 00 | 1 | PEN | AWC | AWC
000978 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0043 | 0 | 131242-WST02-QA-0043 | 2025-01-16 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch) | Rev 0: Approved | 2025-02-13 | 2025-03-25 | 28 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" && "Factory Acceptance Test Report for PH Analyser" | 2025-01-16 | 2025-07-30 | 0 | 000978&&001540 | 2025-01-16, 2025-07-30 | 00 | 2 | PEN | APP | APP
000979 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0019 | 0 | 131242-WSW41-PS-0019 | 2025-01-16 | Monthly Progress Presentation No. 19 (1224) | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 |  | For Information | YES | 2025-02-06 | YES | Resubmitted |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Nov 2024" && "Monthly Progress Presentation No. 19 (1224)" | 2025-01-16 | 2025-03-17 | 0 | 000979&&001128 | 2025-01-16, 2025-03-17 | 00 | 2 | PEN | INF | INF
000980 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0019 | 0 | 131242-WSW41-MI-0019 | 2025-01-16 | Monthly Progress Meeting Minutes 0019_20241217 | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 |  | For Information | YES | 2025-02-06 | YES | Resubmitted |  |  |  | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | PEN | INF | INF
000981 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0002 | 0 | 131242-WSW41-RT-0002 | 2025-01-16 | Final Investigation Report (Incident on Leg Injury) | For Information | 2025-02-13 | 2025-12-23 | 218 | For Information | NO |  | YES |  |  |  |  | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | PEN | INF | INF
000982 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0022 | 0 | 131242-WSW41-QA-0022 | 2025-01-16 | Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-02-13 | 2025-02-24 | 7 | Approved with Comments | YES | 2025-03-14 | NO | Overdue | 226 |  |  | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | PEN | AWC | AWC
000983 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 0 | 131242-WSD11-QA-0042 | 2025-01-16 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-02-20 | 5 | Approved with Comments | YES | 2025-03-12 | YES | Resubmitted |  |  |  | NA | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-01-16 | 2025-12-02 | 1 | 000983 | 2025-01-16, 2025-12-02 | 00, 01 | 2 | PEN | AWC | AWC
000983 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 1 | 131242-WSD11-QA-0042 | 2025-12-02 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-01-16 | 2025-12-02 | 1 | 000983 | 2025-01-16, 2025-12-02 | 00, 01 | 2 | PEN | APP | APP
000984 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 0 | 131242-WSW41-VI-1014 | 2025-01-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-01-20 |  | Approved with Comments | YES | 2025-02-07 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-01-16 | 2025-06-16 | 1 | 000984 | 2025-01-16, 2025-06-16 | 00, 01 | 2 | PEN | AWC | AWC
000984 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 1 | 131242-WSW41-VI-1014 | 2025-06-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-06-23 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-01-16 | 2025-06-16 | 1 | 000984 | 2025-01-16, 2025-06-16 | 00, 01 | 2 | PEN | AWC | AWC
000985 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0044 | 0 | 131242-WSW41-QA-0044 | 2025-01-17 | Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-14 | 2025-04-27 | 48 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | " Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025" && "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " | 2025-01-17 | 2025-09-30 | 0 | 000985&&001708 | 2025-01-17, 2025-09-30 | 00 | 2 | PEN | AWC | AWC
000986 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0020 | 0 | 131242-WSW41-RT-0020 | 2025-01-19 | C4B Monthly Progress Report Number No.20 (12 24) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-02-14 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | NO | Overdue | 241 |  |  | NA | "C4B Monthly Progress Report Number No.20 (12 24) " | 2025-01-19 | 2025-01-19 | 0 | 000986 | 2025-01-19 | 00 | 1 | PEN | AWC | AWC
000987 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0024 | 0 | 131242-WSW41-MS-0024 | 2025-01-20 | MSRA and SWP for Waterproofing Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-17 | 2025-02-17 |  | Approved with Comments | YES | 2025-03-07 | NO | Overdue | 231 |  |  | NA | "MSRA and SWP for Waterproofing Work" | 2025-01-20 | 2025-01-20 | 0 | 000987 | 2025-01-20 | 00 | 1 | PEN | AWC | AWC
000988 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 0 | 131242-WSW41-VI-2005 | 2025-01-20 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 |  | Approved with Comments | YES | 2025-03-04 | YES | Resubmitted |  | 2025-02-28 |  | NA | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-01-20 | 2025-06-18 | 1 | 000988 | 2025-01-20, 2025-06-18 | 00, 01 | 2 | PEN | AWC | AWC
000988 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 1 | 131242-WSW41-VI-2005 | 2025-06-18 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-08 | 2026-01-07 | 129 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-01-20 | 2025-06-18 | 1 | 000988 | 2025-01-20, 2025-06-18 | 00, 01 | 2 | PEN | AWC | AWC
000989 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 0 | 131242-WSW41-VI-2002 | 2025-01-20 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-01-24 |  | Approved with Comments | YES | 2025-02-13 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000989 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-2002 | 2025-02-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-04-02 | 11 | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000989 | 02 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-2002 | 2025-04-17 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-05-07 | 2025-05-21 | 9 | Approved with Comments | YES | 2025-06-10 | YES | Resubmitted |  | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
000989 | 03 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-2002 | 2025-08-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-09-12 |  | 93 | Awaiting S.O.'s response | [5 empty] | 2025-02-21 |  | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | PEN | PEN | PEN
000990 | 00 | Prachi | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-0014 | 2025-01-20 | THP Steam Pressure Loss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 161 | Approved | NO |  | YES |  |  |  |  | NA | "Process Gas Hydraulic Calculation" && "THP Steam Pressure Loss Calculation" | 2025-01-20 | 2025-01-26 | 0 | 000990&&001007 | 2025-01-20, 2025-01-26 | 00 | 2 | PEN | APP | APP
000991 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0011 | 0 | 131242-WST02-CL-0011 | 2025-01-20 | SSN Compressed Air Headloss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 161 | Approved | NO |  | YES |  |  |  |  | NA | "SSN Compressed Air Headloss Calculation" | 2025-01-20 | 2025-01-20 | 0 | 000991 | 2025-01-20 | 00 | 1 | PEN | APP | APP
000992 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-0025 | 2025-01-20 | Air Compressor On Off Valve Data sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 |  | Approved with Comments | YES | 2025-03-04 | YES | Resubmitted |  |  |  | NA | "Air Compressor On Off Valve Data sheet" | 2025-01-20 | 2025-03-07 | 0 | 000992 | 2025-01-20, 2025-03-07 | 00, 01 | 2 | PEN | AWC | AWC
000992 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-0025 | 2025-03-07 | Air Compressor On Off Valve Data sheet | Rev 1: Approved | 2025-03-27 | 2025-07-08 | 69 | Approved | NO |  | YES |  |  |  |  | NA | "Air Compressor On Off Valve Data sheet" | 2025-01-20 | 2025-03-07 | 0 | 000992 | 2025-01-20, 2025-03-07 | 00, 01 | 2 | PEN | APP | APP
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-0002 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0003 | NA | 131242-WSD11-QA-0003 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0004 | NA | 131242-WSD11-QA-0004 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2026-01-28 | 1 | 000000&&000764 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0005 | NA | 131242-WSD11-QA-0005 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 1 | 000000&&000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0006 | NA | 131242-WSD11-QA-0006 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-01-20 | 2026-01-28 | 0 | 000000&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0009 | NA | 131242-WSD11-QA-0009 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " | 2025-01-20 | 2026-01-28 | 0 | 000000&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0010 | NA | 131242-WSD11-QA-0010 | 2025-01-20 |  | NA | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | AWC | AWC
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-0005 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 |  | Approved with Comments | YES | 2025-04-07 | YES | Resubmitted |  |  |  | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 1 | 000000&&000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0006 | NA | 131242-WSD11-QA-0006 | 2025-03-06 |  | NA | 2025-03-26 | 2025-03-18 |  | Approved with Comments | YES | 2025-04-07 | YES | Resubmitted |  |  |  | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-01-20 | 2026-01-28 | 0 | 000000&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0009 | NA | 131242-WSD11-QA-0009 | 2025-03-06 |  | NA | 2025-03-26 | 2025-03-18 |  | Approved with Comments | YES | 2025-04-07 | YES | Resubmitted |  |  |  | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " | 2025-01-20 | 2026-01-28 | 0 | 000000&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, NA | 5 | PEN | AWC | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-0002 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0003 | NA | 131242-WSD11-QA-0003 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0004 | NA | 131242-WSD11-QA-0004 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2026-01-28 | 1 | 000000&&000764 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0005 | NA | 131242-WSD11-QA-0005 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 1 | 000000&&000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0006 | NA | 131242-WSD11-QA-0006 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-01-20 | 2026-01-28 | 0 | 000000&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0009 | NA | 131242-WSD11-QA-0009 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " | 2025-01-20 | 2026-01-28 | 0 | 000000&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0010 | NA | 131242-WSD11-QA-0010 | 2025-04-08 |  | NA | 2025-04-28 | 2025-04-22 |  | Approved with Comments | YES | 2025-05-12 | NO | Overdue | 185 |  |  | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | AWC | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-0002 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0003 | NA | 131242-WSD11-QA-0003 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0004 | NA | 131242-WSD11-QA-0004 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2026-01-28 | 1 | 000000&&000764 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, NA | 5 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0005 | NA | 131242-WSD11-QA-0005 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2026-01-28 | 1 | 000000&&000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 01, NA | 4 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0006 | NA | 131242-WSD11-QA-0006 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-01-20 | 2026-01-28 | 0 | 000000&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, NA | 6 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0009 | NA | 131242-WSD11-QA-0009 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " | 2025-01-20 | 2026-01-28 | 0 | 000000&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, NA | 5 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WSD11 | QA | N | 0010 | NA | 131242-WSD11-QA-0010 | 2026-01-28 |  | NA | 2026-02-17 | 2025-04-22 |  | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-01-20 | 2026-01-28 | NA | 000000 | 2025-01-20, 2025-04-08, 2026-01-28 | NA | 3 | PEN | PEN | PEN
000994 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 0 | 131242-WSD11-QA-0001 | 2025-01-20 | Commissioning Plan for THP Air Compressor System | Rev.0: Approved with Comments. Revise and resubmit. | 2025-02-17 | 2025-02-03 |  | Approved with Comments | YES | 2025-02-21 | YES | Resubmitted |  |  |  | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000994 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 1 | 131242-WSD11-QA-0001 | 2025-03-06 | Commissioning Plan for THP Air Compressor System | Rev.1: Approved with Comments. Resubmittal is required | 2025-03-26 | 2025-03-18 |  | Approved with Comments | YES | 2025-04-07 | YES | Resubmitted |  |  |  | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000994 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 2 | 131242-WSD11-QA-0001 | 2025-05-10 | Commissioning Plan for THP Air Compressor System | Rev.2: Approved with Comments. Resubmittal is required | 2025-05-29 | 2025-06-04 | 4 | Approved with Comments | YES | 2025-06-24 | NO | Overdue | 154 |  |  | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | PEN | AWC | AWC
000995 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 0 | 131242-WSD11-DR-7209 | 2025-01-21 | THP Biosolids PMS Network Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-18 | 2025-03-31 | 28 | Not Approved | YES | 2025-04-18 | YES | Resubmitted |  |  |  | NA | "THP Biosolids PMS Network Architecture Drawing" | 2025-01-21 | 2025-04-09 | 1 | 000995 | 2025-01-21, 2025-04-09 | 00, 01 | 2 | PEN | NAP | NAP
000995 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 1 | 131242-WSD11-DR-7209 | 2025-04-09 | THP Biosolids PMS Network Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-29 | 2025-05-07 | 5 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "THP Biosolids PMS Network Architecture Drawing" | 2025-01-21 | 2025-04-09 | 1 | 000995 | 2025-01-21, 2025-04-09 | 00, 01 | 2 | PEN | AWC | AWC
000996 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 0001 | A | 131242-WSD11-DR-0001 | 2025-01-21 | THP Drawing Index for Cable Raceway and Room Layout | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2025-02-18 | 2025-03-13 | 17 | Not Approved | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | PEN | NAP | NAP
000997 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0020 | 0 | 131242-WSD11-QA-0020 | 2025-01-22 | Electrical Documents for THP Train 1 & Train 2 (CAMBI) | Rev 0: Rejected. Please refer to attached file for comments. | 2025-02-19 | 2025-03-13 | 16 | Not Approved | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Electrical Documents for THP Train 1 & Train 2 (CAMBI)" | 2025-01-22 | 2025-01-22 | 0 | 000997 | 2025-01-22 | 00 | 1 | PEN | NAP | NAP
000998 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 0 | 131242-WSW41-QA-0014 | 2025-01-22 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-19 | 2025-02-24 | 3 | Not Approved | YES | 2025-03-14 | YES | Resubmitted |  |  |  | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2026-01-28 | 1 | 000000&&000741&&000971&&000998&&001336 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | NAP | NAP
000998 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 1 | 131242-WSW41-QA-0014 | 2025-03-10 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-11 | 9 | Not Approved | YES | 2025-05-01 | NO | Overdue | 192 |  |  | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2026-01-28 | 1 | 000000&&000741&&000971&&000998&&001336 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | NAP | NAP
000999 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0013 | 0 | 131242-WSW41-QA-0013 | 2025-01-24 | Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd) | Approved | 2025-02-21 | 2025-02-24 | 1 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | 2026-01-28 | 0 | 000000&&000670&&000691&&000970&&000999&&001313 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | PEN | APP | APP
001000 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 0 | 131242-WSW41-SP-0025 | 2025-01-24 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-13 |  | Not Approved | YES | 2025-03-05 | YES | Resubmitted |  |  |  | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
001000 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 1 | 131242-WSW41-SP-0025 | 2025-03-14 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-06 | 1 | Not Approved | YES | 2025-04-24 | YES | Resubmitted |  |  |  | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | PEN | NAP | NAP
001000 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 2 | 131242-WSW41-SP-0025 | 2025-04-08 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Approved with Comments | 2025-04-28 | 2025-05-16 | 12 | Approved with Comments | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | PEN | AWC | AWC
001000 | 03 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 3 | 131242-WSW41-SP-0025 | 2025-06-06 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.3: Approved | 2025-06-26 | 2025-07-04 | 6 | Approved | NO |  | YES |  |  |  |  | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | PEN | APP | APP
001001 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0026 | 0 | 131242-WSW41-SP-0026 | 2025-01-24 | Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information. | 2025-02-21 | 2025-02-20 |  | For Information | NO |  | YES |  |  |  |  | NA | "Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32)" | 2025-01-24 | 2025-01-24 | 0 | 001001 | 2025-01-24 | 00 | 1 | PEN | INF | INF
001002 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 0001 | A | 131242-WSD11-DR-0001 | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | 43 | For Information | NO |  | YES |  |  |  |  | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | B | 0001 | NA | 131242-WST02-DR-0001 | 2025-01-26 |  | NA | 2025-02-21 | 2025-04-22 | 234 | Awaiting S.O.'s response | [7 empty] | NA | "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | 2025-02-21 | A | 000000&&000779&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00, NA | 4 | PEN | PEN | PEN
001003 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0054 | 0 | 131242-WSW41-LT-0054 | 2025-01-26 | CV of Team member (Senior Planning Engineer) | Rev. 0 - Approved | 2025-02-21 | 2025-02-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "CV of Team member (Senior Planning Engineer)" | 2025-01-26 | 2025-01-26 | 0 | 001003 | 2025-01-26 | 00 | 1 | PEN | APP | APP
001004 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0021 | 0 | 131242-WST02-QA-0021 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI)" | 2025-01-26 | 2025-01-26 | 0 | 001004 | 2025-01-26 | 00 | 1 | PEN | APP | APP
001005 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1394 | 0 | 131242-WST02-DS-1394 | 2025-01-26 | Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-03-02 | 5 | Approved with Comments | YES | 2025-03-20 | NO | Overdue | 222 |  |  | NA | "Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd)" | 2025-01-26 | 2025-01-26 | 0 | 001005 | 2025-01-26 | 00 | 1 | PEN | AWC | AWC
001006 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 0 | 131242-WSD11-MS-0001 | 2025-01-26 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-21 | 2025-02-07 |  | Approved with Comments | YES | 2025-02-27 | YES | Resubmitted |  |  |  | NA | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-01-26 | 2025-05-19 | 1 | 001006 | 2025-01-26, 2025-05-19 | 00, 01 | 2 | PEN | AWC | AWC
001006 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 1 | 131242-WSD11-MS-0001 | 2025-05-19 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-06 | 2025-07-02 | 18 | Approved with Comments | YES | 2025-07-22 | NO | Overdue | 134 |  |  | NA | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-01-26 | 2025-05-19 | 1 | 001006 | 2025-01-26, 2025-05-19 | 00, 01 | 2 | PEN | AWC | AWC
001007 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-0014 | 2025-01-26 | Process Gas Hydraulic Calculation | Rev 0: Approved. Please furnish PE Endorsement. | 2025-02-21 | 2025-10-06 | 157 | Approved | NO |  | YES |  |  |  |  | NA | "Process Gas Hydraulic Calculation" && "THP Steam Pressure Loss Calculation" | 2025-01-20 | 2025-01-26 | 0 | 000990&&001007 | 2025-01-20, 2025-01-26 | 00 | 2 | PEN | APP | APP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | A | 131242-WST02-SD-1010 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | 2025-08-22 | C | 000000&&001008 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1011 | NA | 131242-WST02-SD-1011 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-01-26 | 2025-11-27 | A | 000000&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1012 | NA | 131242-WST02-SD-1012 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1013 | NA | 131242-WST02-SD-1013 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3006 | NA | 131242-WST02-SD-3006 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-08-13 | B | 000000&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3007 | NA | 131242-WST02-SD-3007 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3008 | NA | 131242-WST02-SD-3008 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3009 | NA | 131242-WST02-SD-3009 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3010 | NA | 131242-WST02-SD-3010 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3011 | NA | 131242-WST02-SD-3011 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3012 | NA | 131242-WST02-SD-3012 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3013 | NA | 131242-WST02-SD-3013 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST00 | DR | S | 0001 | NA | 131242-WST00-DR-0001 | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-17 |  | Not Approved | YES | 2025-03-07 | YES | Resubmitted |  |  |  | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "SITE OFFICE LAYOUT (Rev1)" | 2023-05-31 | 2025-01-26 | 3 | 000000&&000018 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03, NA | 6 | PEN | NAP | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-1010 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-10 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | 2025-08-22 | C | 000000&&001008 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1011 | NA | 131242-WST02-SD-1011 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-01-26 | 2025-11-27 | A | 000000&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1012 | NA | 131242-WST02-SD-1012 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1013 | NA | 131242-WST02-SD-1013 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3006 | NA | 131242-WST02-SD-3006 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-08-13 | B | 000000&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3007 | NA | 131242-WST02-SD-3007 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3008 | NA | 131242-WST02-SD-3008 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3009 | NA | 131242-WST02-SD-3009 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3010 | NA | 131242-WST02-SD-3010 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3011 | NA | 131242-WST02-SD-3011 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3012 | NA | 131242-WST02-SD-3012 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3013 | NA | 131242-WST02-SD-3013 | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | QA | A | 0001_supporting docs | NA | 131242-WSW41-QA-0001_supporting docs | 2025-03-21 |  | NA | 2025-04-18 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-03-21 | NA | 000000 | 2025-03-21 | NA | 1 | PEN | NAP | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | C | 131242-WST02-SD-1010 | 2025-08-13 | Shop Drawings for Block Wall | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | 2025-08-22 | C | 000000&&001008 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1011 | NA | 131242-WST02-SD-1011 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-01-26 | 2025-11-27 | A | 000000&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1012 | NA | 131242-WST02-SD-1012 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1013 | NA | 131242-WST02-SD-1013 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3006 | NA | 131242-WST02-SD-3006 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-08-13 | B | 000000&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3007 | NA | 131242-WST02-SD-3007 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3008 | NA | 131242-WST02-SD-3008 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3009 | NA | 131242-WST02-SD-3009 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3010 | NA | 131242-WST02-SD-3010 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-03-21, 2025-08-13 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3011 | NA | 131242-WST02-SD-3011 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3012 | NA | 131242-WST02-SD-3012 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3013 | NA | 131242-WST02-SD-3013 | 2025-08-13 |  | NA | 2025-09-02 | 2025-09-15 | 9 | Not Approved | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617_BCA | B | 131242-WSD11-DR-0300_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0301_ST617_BCA | NA | 131242-WSD11-DR-0301_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0302_ST617_BCA | NA | 131242-WSD11-DR-0302_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0303_ST617_BCA | NA | 131242-WSD11-DR-0303_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0304_ST617_BCA | NA | 131242-WSD11-DR-0304_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0305_ST617_BCA | NA | 131242-WSD11-DR-0305_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1000_ST617_BCA | NA | 131242-WSD11-DR-1000_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1001_ST617_BCA | NA | 131242-WSD11-DR-1001_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1002_ST617_BCA | NA | 131242-WSD11-DR-1002_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1003_ST617_BCA | NA | 131242-WSD11-DR-1003_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2000_ST617_BCA | NA | 131242-WSD11-DR-2000_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2001_ST617_BCA | NA | 131242-WSD11-DR-2001_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3000_ST617_BCA | NA | 131242-WSD11-DR-3000_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3001_ST617_BCA | NA | 131242-WSD11-DR-3001_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3002_ST617_BCA | NA | 131242-WSD11-DR-3002_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5000_ST617_BCA | NA | 131242-WSD11-DR-5000_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5001_ST617_BCA | NA | 131242-WSD11-DR-5001_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5002_ST617_BCA | NA | 131242-WSD11-DR-5002_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5003_ST617_BCA | NA | 131242-WSD11-DR-5003_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5004_ST617_BCA | NA | 131242-WSD11-DR-5004_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5005_ST617_BCA | NA | 131242-WSD11-DR-5005_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5006_ST617_BCA | NA | 131242-WSD11-DR-5006_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 8000_ST617_BCA | NA | 131242-WSD11-DR-8000_ST617_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-01-26 | NA | 000000 | 2025-01-26 | NA | 1 | PEN | AWC | AWC
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-0306_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | NA | 131242-WSD11-DR-0307_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | NA | 131242-WSD11-DR-0308_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | NA | 131242-WSD11-DR-1100_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | NA | 131242-WSD11-DR-1101_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | NA | 131242-WSD11-DR-2100_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | NA | 131242-WSD11-DR-3100_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | NA | 131242-WSD11-DR-5100_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | NA | 131242-WSD11-DR-5101_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | NA | 131242-WSD11-DR-8002_ST619_BCA | 2025-01-26 |  | NA | 2025-02-21 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | AWC | AWC
001011 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0006 | 0 | 131242-WSD11-QA-0006 | 2025-01-26 | Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-21 | 2025-04-11 | 34 | Not Approved | YES | 2025-05-01 | NO | Overdue | 192 |  |  | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-01-20 | 2026-01-28 | 0 | 000000&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, NA | 6 | PEN | NAP | NAP
001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7001 | A | 131242-WSD11-DR-7001 | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | 27 | Rejected | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" | 2023-10-26 | 2025-10-23 | A | 000000&&000143&&000198&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02 | 12 | PEN | REJ | REJ
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EL | 1005 | NA | 131242-WSD11-DR-1005 | 2025-01-26 |  | NA | 2025-02-21 | 2025-04-02 | 27 | Rejected | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-10-28 | NA | 000000 | 2025-01-26, 2025-05-28, 2025-10-28 | 00, NA | 3 | PEN | REJ | REJ
001013 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0019 | 0 | 131242-WST02-QA-0019 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 |  | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | PEN | APP | APP
001014 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 0 | 131242-WSW41-QA-0016 | 2025-01-26 | ITP for Lightning Protection System Installation | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file and incorporate minor comments. | 2025-02-21 | 2025-03-13 | 14 | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | AWC | AWC
001014 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 1 | 131242-WSW41-QA-0016 | 2025-03-14 | ITP for Lightning Protection System Installation | Rev 1: Approved. | 2025-04-03 | 2025-05-07 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | APP | APP
001015 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0010 | 0 | 131242-WSW41-VI-0010 | 2025-02-03 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-03 | 2025-02-20 |  | Approved with Comments | YES | 2025-03-12 | NO | Overdue | 228 |  |  | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | PEN | AWC | AWC
001016 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0019 | 0 | 131242-WSW41-PC-0019 | 2025-02-03 | Payment Claim No.19 | Rev (0): Approved. Please refer to S.O. Correspondence no. 291 dated 5 Feb 2025. | 2025-03-03 | 2025-02-17 |  | Approved | NO |  | YES |  |  |  |  | NA | "Payment Claim No.19" | 2025-02-03 | 2025-02-03 | 0 | 001016 | 2025-02-03 | 00 | 1 | PEN | APP | APP
001017 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BH | 7000 | A | 131242-WSD11-DR-7000 | 2025-02-03 | THP Protected Corridor Fan Control Circuit Diagram | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-03-03 | 2025-04-27 | 37 | Rejected | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | REJ | REJ
001018 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 0 | 131242-WSD11-QA-0047 | 2025-02-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-03 | 2025-03-25 | 16 | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-02-03 | 2025-07-03 | 1 | 001018 | 2025-02-03, 2025-07-03 | 00, 01 | 2 | PEN | AWC | AWC
001018 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 1 | 131242-WSD11-QA-0047 | 2025-07-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 1: Approved | 2025-07-23 | 2025-12-23 | 108 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-02-03 | 2025-07-03 | 1 | 001018 | 2025-02-03, 2025-07-03 | 00, 01 | 2 | PEN | APP | APP
001019 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0045 | 0 | 131242-WSW41-QA-0045 | 2025-02-03 | WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd | Rev 0: For Information | 2025-03-03 | 2025-04-27 | 37 | For Information | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" && "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | 2026-01-15 | 1 | 001019&&001545&&001830 | 2025-02-03, 2025-07-31, 2025-11-07, 2026-01-15 | 00, 01 | 4 | PEN | INF | INF
001020 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 0 | 131242-WST02-DS-1395 | 2025-02-04 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-04 | 2025-03-02 |  | Approved with Comments | YES | 2025-03-20 | YES | Resubmitted |  |  |  | NA | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-02-04 | 2025-03-14 | 1 | 001020 | 2025-02-04, 2025-03-14 | 00, 01 | 2 | PEN | AWC | AWC
001020 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 1 | 131242-WST02-DS-1395 | 2025-03-14 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 20 | Approved with Comments | YES | 2025-05-23 | NO | Overdue | 176 |  |  | NA | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-02-04 | 2025-03-14 | 1 | 001020 | 2025-02-04, 2025-03-14 | 00, 01 | 2 | PEN | AWC | AWC
001021 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0048 | 0 | 131242-WST02-QA-0048 | 2025-02-05 | FAT Report for Air Blowers (Aerzen) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 14 | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "FAT Report for Air Blowers (Aerzen)" && "Factory Acceptance Test Report for Thermal Flow Switch" | 2025-02-05 | 2025-08-17 | 0 | 001021&&001598 | 2025-02-05, 2025-08-17 | 00 | 2 | PEN | AWC | AWC
001022 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0016 | 0 | 131242-WSW41-QA-0016 | 2025-02-06 | Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-06 | 2025-02-18 |  | Approved with Comments | YES | 2025-03-10 | NO | Overdue | 230 |  |  | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | 2026-01-28 | 1 | 000000&&000693&&000724&&000734&&001014&&001022&&001340 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | PEN | AWC | AWC
001023 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-0025 | 2025-02-07 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-03-02 |  | Not Approved | YES | 2025-03-20 | YES | Resubmitted |  |  |  | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | PEN | NAP | NAP
001023 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-0025 | 2025-03-10 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Approved with Comments | 2025-03-28 | 2025-06-11 | 49 | Approved with Comments | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | PEN | AWC | AWC
001024 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0023 | 0 | 131242-WSW41-QA-0023 | 2025-02-07 | Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024 | For information. | 2025-03-07 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | PEN | INF | INF
001025 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0015 | 0 | 131242-WST02-QA-0015 | 2025-02-07 | Sample Board Submission for Roof Waterproofing (G-Concept) | For information. Please provide technical data sheet for the proposed system and submit shop drawings for approval. | 2025-03-07 | 2025-02-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | PEN | INF | INF
001026 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1014 | 0 | 131242-WST02-SD-1014 | 2025-02-07 | Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-02-24 |  | Not Approved | YES | 2025-03-14 | NO | Overdue | 226 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | 2025-08-27 | C | 000000&&001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | PEN | NAP | NAP
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | A | 131242-WSD11-DR-7040 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7041 | NA | 131242-WSD11-DR-7041 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7042 | NA | 131242-WSD11-DR-7042 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7043 | NA | 131242-WSD11-DR-7043 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7044 | NA | 131242-WSD11-DR-7044 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7045 | NA | 131242-WSD11-DR-7045 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7046 | NA | 131242-WSD11-DR-7046 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7047 | NA | 131242-WSD11-DR-7047 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7048 | NA | 131242-WSD11-DR-7048 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7049 | NA | 131242-WSD11-DR-7049 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7050 | NA | 131242-WSD11-DR-7050 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7060 | NA | 131242-WSD11-DR-7060 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7061 | NA | 131242-WSD11-DR-7061 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7062 | NA | 131242-WSD11-DR-7062 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7063 | NA | 131242-WSD11-DR-7063 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7064 | NA | 131242-WSD11-DR-7064 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7065 | NA | 131242-WSD11-DR-7065 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7066 | NA | 131242-WSD11-DR-7066 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7067 | NA | 131242-WSD11-DR-7067 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7068 | NA | 131242-WSD11-DR-7068 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7069 | NA | 131242-WSD11-DR-7069 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7070 | NA | 131242-WSD11-DR-7070 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3014 | NA | 131242-WSD11-DR-3014 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3015 | NA | 131242-WSD11-DR-3015 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3016 | NA | 131242-WSD11-DR-3016 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002B SLD, Schematic and GA Drawing" | 2025-02-07 | 2026-02-03 | A | 000000&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3017 | NA | 131242-WSD11-DR-3017 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3018 | NA | 131242-WSD11-DR-3018 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3019 | NA | 131242-WSD11-DR-3019 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3020 | NA | 131242-WSD11-DR-3020 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3021 | NA | 131242-WSD11-DR-3021 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3022 | NA | 131242-WSD11-DR-3022 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3023 | NA | 131242-WSD11-DR-3023 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3024 | NA | 131242-WSD11-DR-3024 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3025 | NA | 131242-WSD11-DR-3025 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3026 | NA | 131242-WSD11-DR-3026 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3027 | NA | 131242-WSD11-DR-3027 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7110 | NA | 131242-WSD11-DR-7110 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7111 | NA | 131242-WSD11-DR-7111 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7112 | NA | 131242-WSD11-DR-7112 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7113 | NA | 131242-WSD11-DR-7113 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7114 | NA | 131242-WSD11-DR-7114 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7115 | NA | 131242-WSD11-DR-7115 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7116 | NA | 131242-WSD11-DR-7116 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7117 | NA | 131242-WSD11-DR-7117 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7118 | NA | 131242-WSD11-DR-7118 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7119 | NA | 131242-WSD11-DR-7119 | 2025-02-07 |  | NA | 2025-03-07 | 2025-04-08 | 21 | Not Approved | YES | 2025-04-28 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | B | 131242-WSD11-DR-7040 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7041 | NA | 131242-WSD11-DR-7041 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7042 | NA | 131242-WSD11-DR-7042 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7043 | NA | 131242-WSD11-DR-7043 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7044 | NA | 131242-WSD11-DR-7044 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7045 | NA | 131242-WSD11-DR-7045 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7046 | NA | 131242-WSD11-DR-7046 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7047 | NA | 131242-WSD11-DR-7047 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7048 | NA | 131242-WSD11-DR-7048 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7049 | NA | 131242-WSD11-DR-7049 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7050 | NA | 131242-WSD11-DR-7050 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7060 | NA | 131242-WSD11-DR-7060 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7061 | NA | 131242-WSD11-DR-7061 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7062 | NA | 131242-WSD11-DR-7062 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7063 | NA | 131242-WSD11-DR-7063 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7064 | NA | 131242-WSD11-DR-7064 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7065 | NA | 131242-WSD11-DR-7065 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7066 | NA | 131242-WSD11-DR-7066 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7067 | NA | 131242-WSD11-DR-7067 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7068 | NA | 131242-WSD11-DR-7068 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7069 | NA | 131242-WSD11-DR-7069 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7070 | NA | 131242-WSD11-DR-7070 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3014 | NA | 131242-WSD11-DR-3014 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3015 | NA | 131242-WSD11-DR-3015 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3016 | NA | 131242-WSD11-DR-3016 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002B SLD, Schematic and GA Drawing" | 2025-02-07 | 2026-02-03 | A | 000000&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3017 | NA | 131242-WSD11-DR-3017 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3018 | NA | 131242-WSD11-DR-3018 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3019 | NA | 131242-WSD11-DR-3019 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3020 | NA | 131242-WSD11-DR-3020 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3021 | NA | 131242-WSD11-DR-3021 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3022 | NA | 131242-WSD11-DR-3022 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3023 | NA | 131242-WSD11-DR-3023 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3024 | NA | 131242-WSD11-DR-3024 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3025 | NA | 131242-WSD11-DR-3025 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3026 | NA | 131242-WSD11-DR-3026 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3027 | NA | 131242-WSD11-DR-3027 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7110 | NA | 131242-WSD11-DR-7110 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7111 | NA | 131242-WSD11-DR-7111 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7112 | NA | 131242-WSD11-DR-7112 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7113 | NA | 131242-WSD11-DR-7113 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7114 | NA | 131242-WSD11-DR-7114 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7115 | NA | 131242-WSD11-DR-7115 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7116 | NA | 131242-WSD11-DR-7116 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7117 | NA | 131242-WSD11-DR-7117 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7118 | NA | 131242-WSD11-DR-7118 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7119 | NA | 131242-WSD11-DR-7119 | 2025-05-30 |  | NA | 2025-06-19 | 2025-06-30 | 7 | Not Approved | YES | 2025-07-18 | YES | Resubmitted |  |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | NAP | NAP
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | C | 131242-WSD11-DR-7040 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7041 | NA | 131242-WSD11-DR-7041 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7042 | NA | 131242-WSD11-DR-7042 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7043 | NA | 131242-WSD11-DR-7043 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7044 | NA | 131242-WSD11-DR-7044 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7045 | NA | 131242-WSD11-DR-7045 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7046 | NA | 131242-WSD11-DR-7046 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7047 | NA | 131242-WSD11-DR-7047 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7048 | NA | 131242-WSD11-DR-7048 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7049 | NA | 131242-WSD11-DR-7049 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7050 | NA | 131242-WSD11-DR-7050 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7060 | NA | 131242-WSD11-DR-7060 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7061 | NA | 131242-WSD11-DR-7061 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7062 | NA | 131242-WSD11-DR-7062 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7063 | NA | 131242-WSD11-DR-7063 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7064 | NA | 131242-WSD11-DR-7064 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7065 | NA | 131242-WSD11-DR-7065 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7066 | NA | 131242-WSD11-DR-7066 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7067 | NA | 131242-WSD11-DR-7067 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7068 | NA | 131242-WSD11-DR-7068 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7069 | NA | 131242-WSD11-DR-7069 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EI | 7070 | NA | 131242-WSD11-DR-7070 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3014 | NA | 131242-WSD11-DR-3014 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3015 | NA | 131242-WSD11-DR-3015 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3016 | NA | 131242-WSD11-DR-3016 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0002B SLD, Schematic and GA Drawing" | 2025-02-07 | 2026-02-03 | A | 000000&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3017 | NA | 131242-WSD11-DR-3017 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-07 | 2025-11-11 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3018 | NA | 131242-WSD11-DR-3018 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3019 | NA | 131242-WSD11-DR-3019 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3020 | NA | 131242-WSD11-DR-3020 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2026-02-03 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, NA | 10 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3021 | NA | 131242-WSD11-DR-3021 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3022 | NA | 131242-WSD11-DR-3022 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3023 | NA | 131242-WSD11-DR-3023 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3024 | NA | 131242-WSD11-DR-3024 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3025 | NA | 131242-WSD11-DR-3025 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3026 | NA | 131242-WSD11-DR-3026 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 3027 | NA | 131242-WSD11-DR-3027 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-02-07 | 2025-11-28 | NA | 000000 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7110 | NA | 131242-WSD11-DR-7110 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7111 | NA | 131242-WSD11-DR-7111 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7112 | NA | 131242-WSD11-DR-7112 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7113 | NA | 131242-WSD11-DR-7113 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7114 | NA | 131242-WSD11-DR-7114 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7115 | NA | 131242-WSD11-DR-7115 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7116 | NA | 131242-WSD11-DR-7116 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7117 | NA | 131242-WSD11-DR-7117 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7118 | NA | 131242-WSD11-DR-7118 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | EP | 7119 | NA | 131242-WSD11-DR-7119 | 2025-08-05 |  | NA | 2025-08-25 | 2025-08-20 |  | Approved with Comments | YES | 2025-09-09 | NO | Overdue | 99 |  |  | NA |  | 2025-02-07 | 2025-08-05 | NA | 000000 | 2025-02-07, 2025-05-30, 2025-08-05 | NA | 3 | PEN | AWC | AWC
001028 | 00 | Zora | CSA | NA | 131242 | NA | NA | NA | FOR INFORMATION | NA | 131242-NA-NA-FOR INFORMATION | 2025-02-07 | BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters | For information. | 2025-03-07 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters " | 2025-02-07 | 2025-02-07 | NA | 001028 | 2025-02-07 | 00 | 1 | PEN | INF | INF
001029 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 0 | 131242-WSW41-QA-0037 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Rev 0: Not approved - Revise and Resubmit | 2025-03-07 | 2025-03-25 | 12 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | 2025-05-14 | 0 | 001029&&001294 | 2025-02-07, 2025-04-21, 2025-05-14 | 00, 01 | 3 | PEN | NAP | NAP
001029 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 1 | 131242-WSW41-QA-0037 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Approved | 2025-05-09 | 2025-05-12 | 0 | Approved | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | 2025-05-14 | 0 | 001029&&001294 | 2025-02-07, 2025-04-21, 2025-05-14 | 00, 01 | 3 | PEN | APP | APP
001030 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 0 | 131242-WSW41-QA-0046 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-27 | 33 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | PEN | AWC | AWC
001030 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 1 | 131242-WSW41-QA-0046 | 2025-06-18 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-08 | 2025-09-08 | 44 | Approved | NO |  | YES |  |  |  |  | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | PEN | APP | APP
001031 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0009 | 0 | 131242-WST02-CL-0009 | 2025-02-07 | SSN Energy Consumption Computation | Rev 0: For Information | 2025-03-07 | 2025-10-06 | 147 | For Information | NO |  | YES |  |  |  |  | NA | " SSN Energy Consumption Computation" | 2025-02-07 | 2025-02-07 | 0 | 001031 | 2025-02-07 | 00 | 1 | PEN | INF | INF
001032 | 00 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 0 | 131242-WST02-SP-0002 | 2025-02-07 | SSN Aeration Blower Control Philosophy | Rev0: approved with comments, resubmission is required. | 2025-03-07 | 2025-03-13 | 4 | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | PEN | AWC | AWC
001032 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 1 | 131242-WST02-SP-0002 | 2025-06-04 | SSN Aeration Blower Control Philosophy | Rev1: approved with comments, resubmission is required. | 2025-06-24 | 2025-07-02 | 6 | Approved with Comments | YES | 2025-07-22 | NO | Overdue | 134 |  |  | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | PEN | AWC | AWC
001033 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 0 | 131242-WSD11-VI-0004 | 2025-02-10 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-10 | 2025-02-13 |  | Approved with Comments | YES | 2025-03-05 | YES | Resubmitted |  | 2025-03-05 |  | NA | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" && "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | 2025-05-10 | 0 | 001033&&001274 | 2025-02-10, 2025-03-17, 2025-05-10 | 00, 01 | 3 | PEN | AWC | AWC
001033 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 1 | 131242-WSD11-VI-0004 | 2025-03-17 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 21 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" && "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | 2025-05-10 | 0 | 001033&&001274 | 2025-02-10, 2025-03-17, 2025-05-10 | 00, 01 | 3 | PEN | AWC | AWC
001034 | 00 | Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-0052 | 2025-02-10 | Submission of BIM Coordination VCM Model (Jan 2025) | For Information. Score= 70/100 | 2025-03-10 | 2025-02-20 |  | For Information | NO |  | YES |  |  |  |  | NA | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-02-10 | 2025-12-16 | 0 | 000163&&001034 | 2025-02-10, 2025-12-16 | 00, 03 | 2 | PEN | INF | INF
001035 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0049 | 0 | 131242-WSD11-QA-0049 | 2025-02-10 | FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch) | Rev 0: Approved | 2025-03-10 | 2025-03-25 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch)" | 2025-02-10 | 2025-02-10 | 0 | 001035 | 2025-02-10 | 00 | 1 | PEN | APP | APP
001036 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | A | 0017 | 0 | 131242-WST02-QA-0017 | 2025-02-11 | Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | For information. | 2025-03-11 | 2025-02-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "QA/QC Report for Mechanical Ventilation Fan" && "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-11 | 2025-10-13 | 1 | 001036&&001601 | 2025-02-11, 2025-08-19, 2025-10-13 | 00, 01 | 3 | PEN | INF | INF
001037 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0055 | 0 | 131242-WSW41-LT-0055 | 2025-02-11 | EOT Notice Letter for ST617 & ST619 | Rev (0): For Information. Please refer to S.O. correspondence no. 327 dated 14 April 2025. | 2025-03-11 | 2025-04-27 | 31 | For Information | NO |  | YES |  |  |  |  | NA | "EOT Notice Letter for ST617 & ST619" | 2025-02-11 | 2025-02-11 | 0 | 001037 | 2025-02-11 | 00 | 1 | PEN | INF | INF
001038 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0004 | 0 | 131242-WSW41-PO-0004 | 2025-02-11 | Unppriced PO for YHW | Rev 0: For Information. | 2025-03-11 | 2025-03-13 | 2 | For Information | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Unppriced PO for YHW" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | 2025-02-11 | 2025-08-01 | 0 | 001038&&001503&&001515 | 2025-02-11, 2025-07-22, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A | 131242-WSD11-DR-1003 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 3000 | NA | 131242-WSD11-DR-3000 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1000 | NA | 131242-WSD11-DR-1000 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1001 | NA | 131242-WSD11-DR-1001 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1002 | NA | 131242-WSD11-DR-1002 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 1002 | NA | 131242-WSD11-DR-1002 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 3001 | NA | 131242-WSD11-DR-3001 | 2025-02-12 |  | NA | 2025-03-12 | 2025-03-25 | 9 | Not Approved | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | NAP | NAP
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | CL | BH | 8000 | 0 | 131242-WSD11-CL-8000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-06-04 | 0 | 001039 | 2025-06-04 | 01 | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | B | 1003 | NA | 131242-WSD11-DR-1003 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP Fire Alarm System Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" | 2023-11-30 | 2026-01-20 | A | 000000&&001039&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, NA | 24 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 3000 | NA | 131242-WSD11-DR-3000 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1000 | NA | 131242-WSD11-DR-1000 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1001 | NA | 131242-WSD11-DR-1001 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BH | 1002 | NA | 131242-WSD11-DR-1002 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 1002 | NA | 131242-WSD11-DR-1002 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-30 | 2026-01-05 | NA | 000000 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, NA | 25 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 3001 | NA | 131242-WSD11-DR-3001 | 2025-06-04 |  | NA | 2025-06-24 | 2025-07-17 | 17 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | 2026-02-03 | B | 000000&&001230&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, NA | 17 | PEN | AWC | AWC
001040 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 0 | 131242-WSD11-QA-0023 | 2025-02-12 | FAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. | 2025-03-12 | 2025-03-13 | 1 | Approved with Comments | YES | 2025-04-02 | YES | Resubmitted |  |  |  | NA | "FAT Report for WSD11-MCC-0101A&B" | 2025-02-12 | 2025-03-27 | 1 | 001040 | 2025-02-12, 2025-03-27 | 00, 01 | 2 | PEN | AWC | AWC
001040 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 1 | 131242-WSD11-QA-0023 | 2025-03-27 | FAT Report for WSD11-MCC-0101A&B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-05-07 | 13 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "FAT Report for WSD11-MCC-0101A&B" | 2025-02-12 | 2025-03-27 | 1 | 001040 | 2025-02-12, 2025-03-27 | 00, 01 | 2 | PEN | AWC | AWC
001041 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 0 | 131242-WSW41-QA-0051 | 2025-02-13 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Rev 0: Not approved - Revise and Resubmit | 2025-03-13 | 2025-02-18 |  | Not Approved | YES | 2025-03-10 | YES | Resubmitted |  |  |  | NA | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-02-13 | 2025-03-24 | 1 | 001041 | 2025-02-13, 2025-03-24 | 00, 01 | 2 | PEN | NAP | NAP
001041 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 1 | 131242-WSW41-QA-0051 | 2025-03-24 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Approved | 2025-04-11 | 2025-05-19 | 23 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-02-13 | 2025-03-24 | 1 | 001041 | 2025-02-13, 2025-03-24 | 00, 01 | 2 | PEN | APP | APP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-3006 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-08-13 | B | 000000&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3011 | NA | 131242-WST02-SD-3011 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3012 | NA | 131242-WST02-SD-3012 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3013 | NA | 131242-WST02-SD-3013 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA |  | 2025-01-26 | 2025-08-13 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-1010 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | 2025-08-22 | C | 000000&&001008 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1011 | NA | 131242-WST02-SD-1011 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-01-26 | 2025-11-27 | A | 000000&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1012 | NA | 131242-WST02-SD-1012 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1013 | NA | 131242-WST02-SD-1013 | 2025-02-14 |  | NA | 2025-03-14 | 2025-03-21 | 5 | Not Approved | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-01-26 | 2025-11-27 | NA | 000000 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, NA | 5 | PEN | NAP | NAP
001043 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 0 | 131242-WSW41-VI-1007 | 2025-02-14 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-04-05 | 14 | Approved with Comments | YES | 2025-04-24 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-02-14 | 2025-06-09 | 1 | 001043 | 2025-02-14, 2025-06-09 | 00, 01 | 2 | PEN | AWC | AWC
001043 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 1 | 131242-WSW41-VI-1007 | 2025-06-09 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 |  | Approved with Comments | YES | 2025-07-10 | NO | Overdue | 142 |  |  | NA | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-02-14 | 2025-06-09 | 1 | 001043 | 2025-02-14, 2025-06-09 | 00, 01 | 2 | PEN | AWC | AWC
001044 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-0023 | 2025-02-16 | MSRA, SWP for Site Wide Pipe Rack Installation | Approved | 2025-03-14 | 2025-12-17 | 193 | Approved | NO |  | YES |  |  |  |  | NA | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2024-12-13 | 2025-02-16 | 0 | 000898&&001044 | 2024-12-13, 2025-02-16 | 00 | 2 | PEN | APP | APP
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-0306_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | NA | 131242-WSD11-DR-0307_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | NA | 131242-WSD11-DR-0308_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | NA | 131242-WSD11-DR-1100_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | NA | 131242-WSD11-DR-1101_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | NA | 131242-WSD11-DR-2100_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | NA | 131242-WSD11-DR-3100_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | NA | 131242-WSD11-DR-5100_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | NA | 131242-WSD11-DR-5101_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | NA | 131242-WSD11-DR-8002_ST619_BCA | 2025-02-17 |  | NA | 2025-03-17 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-01-26 | 2025-02-17 | NA | 000000 | 2025-01-26, 2025-02-17 | NA | 2 | PEN | INF | INF
001046 | 00 | Jun | HSE | NA | 131242 | WSW41 | MS | E | 0008 | 0 | 131242-WSW41-MS-0008 | 2025-02-17 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-03-17 |  | Approved with Comments | YES | 2025-04-04 | NO | Overdue | 211 |  |  | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | PEN | AWC | AWC
001047 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0021 | 0 | 131242-WSW41-RT-0021 | 2025-02-17 | C4B Monthly Progress Report Number No.21 (01 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-03-17 | 2025-03-13 |  | Approved with Comments | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "C4B Monthly Progress Report Number No.21 (01 25) " | 2025-02-17 | 2025-02-17 | 0 | 001047 | 2025-02-17 | 00 | 1 | PEN | AWC | AWC
001048 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0020 | 0 | 131242-WSW41-PS-0020 | 2025-02-18 | Monthly Progress Presentation No. 20 (0125) | Rev. 0 - For Information | 2025-03-18 | 2025-02-18 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 20 (0125)" && "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | 2025-02-18 | 2025-03-18 | 0 | 001048&&001130 | 2025-02-18, 2025-03-18 | 00 | 2 | PEN | INF | INF
001049 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0020 | 0 | 131242-WSW41-MI-0020 | 2025-02-18 | Monthly Progress Meeting Minutes 0020_20250122 | Rev. 0 - For Information | 2025-03-18 | 2025-02-24 |  | For Information | NO |  | YES |  |  |  |  | NA | "Monthly Progress Meeting Minutes 0020_20250122" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | 2025-02-18 | 0 | 000000&&000353&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | PEN | INF | INF
001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-1014 | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | 2025-08-27 | C | 000000&&001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 3014 | NA | 131242-WST02-SD-3014 | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-13 |  | Not Approved | YES | 2025-04-02 | NO | Overdue | 213 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | 2025-08-27 | B | 000000&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, NA | 5 | PEN | NAP | NAP
001051 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 0 | 131242-WST02-DS-5601 | 2025-02-18 | Data Sheet for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-03-04 |  | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Parabolic Screen" | 2025-02-18 | 2025-04-01 | 1 | 001051 | 2025-02-18, 2025-04-01 | 00, 01 | 2 | PEN | AWC | AWC
001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 1 | 131242-WST02-DS-5601 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Data Sheet for Parabolic Screen" | 2025-02-18 | 2025-04-01 | 1 | 001051 | 2025-02-18, 2025-04-01 | 00, 01 | 2 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5601 | NA | 131242-WST02-DR-5601 | 2025-04-01 |  | NA | 2025-04-21 | 2025-10-06 | 118 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Screen General Arrangement Drawing" | 2024-12-27 | 2025-07-24 | B | 000000&&000931 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01, NA | 4 | PEN | APP | APP
001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3203 | A | 131242-WST02-DR-3203 | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | 14 | Not Approved | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-18 | 2025-03-06 | A | 000000&&001052 | 2025-02-18, 2025-03-06 | 00 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | E | 3204 | NA | 131242-WST02-DR-3204 | 2025-02-18 |  | NA | 2025-03-18 | 2025-04-08 | 14 | Not Approved | YES | 2025-04-28 | NO | Overdue | 195 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-02-18 | 2025-03-06 | NA | 000000 | 2025-02-18, 2025-03-06 | 00, NA | 2 | PEN | NAP | NAP
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_BCA | B | 131242-WSD11-DR-0300_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0301_BCA | NA | 131242-WSD11-DR-0301_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0302_BCA | NA | 131242-WSD11-DR-0302_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0303_BCA | NA | 131242-WSD11-DR-0303_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0304_BCA | NA | 131242-WSD11-DR-0304_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 0305_BCA | NA | 131242-WSD11-DR-0305_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1000_BCA | NA | 131242-WSD11-DR-1000_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1001_BCA | NA | 131242-WSD11-DR-1001_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1002_BCA | NA | 131242-WSD11-DR-1002_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1003_BCA | NA | 131242-WSD11-DR-1003_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2000_BCA | NA | 131242-WSD11-DR-2000_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 2001_BCA | NA | 131242-WSD11-DR-2001_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3000_BCA | NA | 131242-WSD11-DR-3000_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3001_BCA | NA | 131242-WSD11-DR-3001_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 3002_BCA | NA | 131242-WSD11-DR-3002_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5000_BCA | NA | 131242-WSD11-DR-5000_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5001_BCA | NA | 131242-WSD11-DR-5001_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5002_BCA | NA | 131242-WSD11-DR-5002_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5003_BCA | NA | 131242-WSD11-DR-5003_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5004_BCA | NA | 131242-WSD11-DR-5004_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5005_BCA | NA | 131242-WSD11-DR-5005_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5006_BCA | NA | 131242-WSD11-DR-5006_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 8000_BCA | NA | 131242-WSD11-DR-8000_BCA | 2025-02-18 |  | NA | 2025-03-18 | 2025-03-10 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-18 | 2025-02-18 | NA | 000000 | 2025-02-18 | NA | 1 | PEN | INF | INF
001054 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0018 | 0 | 131242-WSW41-QA-0018 | 2025-02-18 | Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works | Rev.0:Approved. Please submit MSRA. | 2025-03-18 | 2025-02-24 |  | Approved | NO |  | YES |  |  |  |  | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | 2025-09-30 | 0 | 000000&&000744&&000757&&001054&&001057&&001339&&001357 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | PEN | APP | APP
001055 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0022 | 0 | 131242-WSW41-QA-0022 | 2025-02-18 | Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 32 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | PEN | AWC | AWC
001056 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0017 | 0 | 131242-WSW41-QA-0017 | 2025-02-18 | Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 32 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | 2026-01-28 | 0 | 000000&&000733&&000747&&001056&&001342 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | PEN | AWC | AWC
001057 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0018 | 0 | 131242-WSW41-QA-0018 | 2025-02-18 | Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 32 | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | 2025-09-30 | 0 | 000000&&000744&&000757&&001054&&001057&&001339&&001357 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | PEN | AWC | AWC
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-1600_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | NA | 131242-WSD11-DR-1601_ST620_BCA | 2025-02-19 |  | NA | 2025-03-19 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | NA | 131242-WSD11-DR-5600_ST620_BCA | 2025-02-19 |  | NA | 2025-03-19 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | NA | 131242-WSD11-DR-5601_ST620_BCA | 2025-02-19 |  | NA | 2025-03-19 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | CL | S | 0007_ST620_BCA | NA | 131242-WSD11-CL-0007_ST620_BCA | 2025-02-19 |  | NA | 2025-03-19 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-19 | NA | 000000 | 2025-02-19 | NA | 1 | PEN | INF | INF
001059 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0050 | 0 | 131242-WST02-QA-0050 | 2025-02-19 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch) | Rev 0: Approved | 2025-03-19 | 2025-04-27 | 25 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" && "Factory Acceptance Test Report for Conductive Probe Level Switches" | 2025-02-19 | 2025-08-29 | 0 | 001059&&001639 | 2025-02-19, 2025-08-29 | 00 | 2 | PEN | APP | APP
001060 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0052 | 0 | 131242-WSD11-QA-0052 | 2025-02-19 | Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-02 | 9 | Approved with Comments | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | "Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system" | 2025-02-19 | 2025-02-19 | 0 | 001060 | 2025-02-19 | 00 | 1 | PEN | AWC | AWC
001061 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 0 | 131242-WSD11-QA-0024 | 2025-02-20 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-20 | 2025-02-25 |  | Not Approved | YES | 2025-03-17 | YES | Resubmitted |  |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | NAP | NAP
001061 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 1 | 131242-WSD11-QA-0024 | 2025-03-10 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-02 | 2 | Approved with Comments | YES | 2025-04-22 | YES | Resubmitted |  |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
001061 | 02 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 2 | 131242-WSD11-QA-0024 | 2025-04-11 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-05-01 | 2025-05-12 | 5 | Approved with Comments | YES | 2025-05-30 | YES | Resubmitted |  |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
001061 | 03 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 3 | 131242-WSD11-QA-0024 | 2025-05-02 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-05-12 |  | Approved with Comments | YES | 2025-05-30 | YES | Resubmitted |  |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
001061 | 04 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 4 | 131242-WSD11-QA-0024 | 2025-06-28 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 4: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-07-17 | 2025-07-23 | 4 | Rejected | YES | 2025-08-12 | NO | Overdue | 119 |  |  | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | PEN | REJ | REJ
001062 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0007 | 0 | 131242-WSD11-QA-0007 | 2025-02-20 | Inspection and Test plan for THP air Compressor System Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-03-20 | 2025-05-30 | 47 | Approved with Comments | YES | 2025-06-19 | NO | Overdue | 157 |  |  | NA | "Inspection and Test plan for THP air Compressor System Pressure Transmitter " | 2025-02-20 | 2025-02-20 | 0 | 001062 | 2025-02-20 | 00 | 1 | PEN | AWC | AWC
001063 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | E | 0001 | A | 131242-WST02-DR-0001 | 2025-02-21 | SSN Drawing Index (Cable Tray Layout) | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-03-21 | 2025-05-06 | 29 | Rejected | NO |  | YES |  |  |  |  | NA | "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | 2025-02-21 | A | 000000&&000779&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00, NA | 4 | PEN | REJ | REJ
001064 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 0001 | A | 131242-WST02-DR-0001 | 2025-02-21 | SSN Drawing Index (Instrument Layout) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-21 | 2025-05-07 | 30 | Not Approved | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | 2025-02-21 | A | 000000&&000779&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00, NA | 4 | PEN | NAP | NAP
001065 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0053 | 0 | 131242-WSD11-QA-0053 | 2025-02-21 | Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton) | Rev 0: Approved | 2025-03-21 | 2025-04-02 | 7 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton)" | 2025-02-21 | 2025-02-21 | 0 | 001065 | 2025-02-21 | 00 | 1 | PEN | APP | APP
001066 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0026 | 0 | 131242-WSW41-VI-0026 | 2025-02-21 | Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-21 | 2025-04-02 | 7 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks)" | 2025-02-21 | 2025-02-21 | 0 | 001066 | 2025-02-21 | 00 | 1 | PEN | AWC | AWC
001067 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0026 | 0 | 131242-WSD11-DS-0026 | 2025-02-21 | Data Sheet for Steam Sparger G2D Inlet Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-21 | 2025-04-28 | 24 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 |  |  | NA | "Data Sheet for Steam Sparger G2D Inlet Control Valve" | 2025-02-21 | 2025-02-21 | 0 | 001067 | 2025-02-21 | 00 | 1 | PEN | AWC | AWC
001068 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-0025 | 2025-02-24 | MSRA, SWP for Box Out Concreting | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-24 | 2025-03-18 |  | Not Approved | YES | 2025-04-07 | NO | Overdue | 210 |  |  | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | PEN | NAP | NAP
001068 | 01 | Kumar | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-0025 | 2025-03-28 | MSRA, SWP for Box Out Concreting | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-04-15 |  | Not Approved | YES | 2025-05-05 | NO | Overdue | 190 |  |  | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | PEN | NAP | NAP
001069 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0013 | 0 | 131242-WSW41-PO-0013 | 2025-02-24 | Unpriced PO for CSEL Pipes (MUSG) | Rev 0: For Information. | 2025-03-24 | 2025-03-27 | 3 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for CSEL Pipes (MUSG)" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | 2025-02-24 | 2025-08-22 | 0 | 001069&&001503&&001611 | 2025-02-24, 2025-07-22, 2025-08-22 | 00 | 3 | PEN | INF | INF
001070 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0005 | 0 | 131242-WSW41-PO-0005 | 2025-02-24 | Unpriced PO for Cable Raceway (United-U Li) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | PEN | INF | INF
001071 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0006 | 0 | 131242-WSW41-PO-0006 | 2025-02-24 | Unpriced PO for Cable Raceway (Jebsen & Jessen) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | PEN | INF | INF
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0039 | 0 | 131242-WSW41-MI-0039 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 |  | For Information | NO |  | YES |  |  |  |  | NA | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | 2025-02-25 | 0 | 001072 | 2025-02-25 | 00 | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | MI | C | 0040 | NA | 131242-WSW41-MI-0040 | 2025-02-25 |  | NA | 2025-03-25 | 2025-03-11 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-25 | 2025-02-25 | NA | 000000 | 2025-02-25 | NA | 1 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSW41 | MI | C | 0041 | NA | 131242-WSW41-MI-0041 | 2025-02-25 |  | NA | 2025-03-25 | 2025-03-11 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-25 | 2025-02-25 | NA | 000000 | 2025-02-25 | NA | 1 | PEN | INF | INF
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A | 131242-WSD11-DR-7000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | 2025-12-16 | E | 000000&&000171&&000197&&000570&&000571&&001017&&001073&&001526 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05, NA | 15 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 3000 | NA | 131242-WSD11-DR-3000 | 2025-02-25 |  | NA | 2025-03-25 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "Dry Riser Installation Details" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP MCC Outline Drawing" | 2024-02-13 | 2026-01-05 | A1 | 000000&&000575&&001902 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, NA | 22 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 1001 | NA | 131242-WSD11-DR-1001 | 2025-02-25 |  | NA | 2025-03-25 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" | 2023-11-30 | 2026-01-05 | A | 000000&&000819&&001328 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, NA | 26 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | BF | 1000 | NA | 131242-WSD11-DR-1000 | 2025-02-25 |  | NA | 2025-03-25 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "SITE OFFICE LAYOUT (Rev1)" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" | 2023-11-30 | 2026-01-05 | C | 000000&&000217&&000218&&000311&&000390&&000414&&000446 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04, NA | 25 | PEN | AWC | AWC
001074 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0025 | 0 | 131242-WSD11-QA-0025 | 2025-02-26 | FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch | Rev 0: Approved. | 2025-03-26 | 2025-05-06 | 26 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch" | 2025-02-26 | 2025-02-26 | 0 | 001074 | 2025-02-26 | 00 | 1 | PEN | APP | APP
001075 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0020 | 0 | 131242-WST02-QA-0020 | 2025-02-27 | Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd) | For Information | 2025-03-27 | 2025-04-11 | 10 | Approved | NO |  | YES |  |  |  |  | NA | "SAT Procedure for Public Address System" && "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" | 2025-02-27 | 2025-12-18 | 0 | 001075&&001909 | 2025-02-27, 2025-12-18 | 00 | 2 | PEN | APP | APP
001076 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8000 | 0 | 131242-WST02-CL-8000 | 2025-02-27 | Fan Static Load Calculation (SSN Electrical Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | NO | Overdue | 205 |  |  | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-1600_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | NA | 131242-WSD11-DR-1601_ST620_BCA | 2025-02-28 |  | NA | 2025-03-28 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | NA | 131242-WSD11-DR-5600_ST620_BCA | 2025-02-28 |  | NA | 2025-03-28 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | NA | 131242-WSD11-DR-5601_ST620_BCA | 2025-02-28 |  | NA | 2025-03-28 | 2025-03-13 |  | For Information | NO |  | YES |  |  |  |  | NA |  | 2025-02-19 | 2025-02-28 | NA | 000000 | 2025-02-19, 2025-02-28 | NA | 2 | PEN | INF | INF
001078 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 0 | 131242-WST02-QA-0019 | 2025-02-28 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-06 | 4 | Not Approved | YES | 2025-04-24 | YES | Resubmitted |  |  |  | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | PEN | NAP | NAP
001078 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 1 | 131242-WST02-QA-0019 | 2025-04-09 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-29 | 2025-05-27 | 18 | Not Approved | YES | 2025-06-16 | NO | Overdue | 160 |  |  | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | PEN | NAP | NAP
001079 | 00 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5751 | 0 | 131242-WST02-CL-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Calculations | Rev 0: Approved | 2025-03-28 | 2025-04-28 | 19 | Approved | NO |  | YES |  |  |  |  | NA | "C4B SSN Pressure Reducing Valve Calculations" | 2025-02-28 | 2025-02-28 | 0 | 001079 | 2025-02-28 | 00 | 1 | PEN | APP | APP
001080 | 00 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 0 | 131242-WST02-DS-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-28 | 19 | Approved with Comments | YES | 2025-05-16 | NO | Overdue | 181 |  |  | NA | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-02-28 | 2025-07-07 | 1 | 001080 | 2025-02-28, 2025-07-07 | 00, 01 | 2 | PEN | AWC | AWC
001080 | 01 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 1 | 131242-WST02-DS-5751 | 2025-07-07 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | 128 | Awaiting S.O.'s response | [7 empty] | NA | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-02-28 | 2025-07-07 | 1 | 001080 | 2025-02-28, 2025-07-07 | 00, 01 | 2 | PEN | PEN | PEN
001081 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 0 | 131242-WSD11-VI-0003 | 2025-03-03 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-31 | 2025-03-04 |  | Approved with Comments | YES | 2025-03-24 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-03 | 2025-03-14 | 1 | 001081 | 2025-03-03, 2025-03-14 | 00, 01 | 2 | PEN | AWC | AWC
001081 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 1 | 131242-WSD11-VI-0003 | 2025-03-14 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-02 |  | Approved with Comments | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-03 | 2025-03-14 | 1 | 001081 | 2025-03-03, 2025-03-14 | 00, 01 | 2 | PEN | AWC | AWC
001082 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | S | 0010 | 0 | 131242-WST02-VI-0010 | 2025-03-03 | Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-31 | 2025-04-02 | 1 | Not Approved | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | PEN | NAP | NAP
001083 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0024 | 0 | 131242-WSD11-DS-0024 | 2025-03-04 | Ring Circulation Pump Data Sheet | Rev 0: Approved | 2025-04-01 | 2025-10-06 | 131 | Approved | NO |  | YES |  |  |  |  | NA | "Ring Circulation Pump Data Sheet" | 2025-03-04 | 2025-03-04 | 0 | 001083 | 2025-03-04 | 00 | 1 | PEN | APP | APP
001084 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0028 | 0 | 131242-WSD11-CL-0028 | 2025-03-04 | Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-07-08 | 67 | Approved with Comments | YES | 2025-07-28 | NO | Overdue | 130 |  |  | NA | "Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation" | 2025-03-04 | 2025-03-04 | 0 | 001084 | 2025-03-04 | 00 | 1 | PEN | AWC | AWC
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 0301 | A1 | 131242-WSW41-SD-0301 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1101 | NA | 131242-WSW41-SD-1101 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1102 | NA | 131242-WSW41-SD-1102 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1103 | NA | 131242-WSW41-SD-1103 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1104 | NA | 131242-WSW41-SD-1104 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1105 | NA | 131242-WSW41-SD-1105 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1106 | NA | 131242-WSW41-SD-1106 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1107 | NA | 131242-WSW41-SD-1107 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 1108 | NA | 131242-WSW41-SD-1108 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 2100 | NA | 131242-WSW41-SD-2100 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 2101 | NA | 131242-WSW41-SD-2101 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 2102 | NA | 131242-WSW41-SD-2102 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 3100 | NA | 131242-WSW41-SD-3100 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" | 2024-07-23 | 2025-12-17 | A.1 | 000000&&000581 | 2024-07-23, 2025-03-04, 2025-12-17 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 3101 | NA | 131242-WSW41-SD-3101 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5100 | NA | 131242-WSW41-SD-5100 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5101 | NA | 131242-WSW41-SD-5101 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5102 | NA | 131242-WSW41-SD-5102 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5103 | NA | 131242-WSW41-SD-5103 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5104 | NA | 131242-WSW41-SD-5104 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5105 | NA | 131242-WSW41-SD-5105 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 5106 | NA | 131242-WSW41-SD-5106 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-03-04 | NA | 000000 | 2025-03-04 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSW41 | SD | S | 8002 | NA | 131242-WSW41-SD-8002 | 2025-03-04 |  | NA | 2025-04-01 | 2025-06-09 | 46 | Not Approved | YES | 2025-06-27 | NO | Overdue | 151 |  |  | NA |  | 2025-03-04 | 2025-12-17 | NA | 000000 | 2025-03-04, 2025-12-17 | NA | 2 | PEN | NAP | NAP
001086 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0055 | 0 | 131242-WST02-QA-0055 | 2025-03-04 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch) | Rev 0: Approved | 2025-04-01 | 2025-04-30 | 20 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" && "Factory Acceptance Test Report for Rotameter" | 2025-03-04 | 2025-09-09 | 0 | 001086&&001662 | 2025-03-04, 2025-09-09 | 00 | 2 | PEN | APP | APP
001087 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-0011 | 2025-03-05 | FAT report for Cable Ladder 1st batch (United ULI) | For information | 2025-04-02 | 2025-05-05 | 21 | Approved | NO |  | YES |  |  |  |  | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | PEN | APP | APP
001088 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0033 | 0 | 131242-WSD11-VI-0033 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED | Rev 0: Rejected | 2025-04-02 | 2025-03-18 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED" | 2025-03-05 | 2025-03-05 | 0 | 001088 | 2025-03-05 | 00 | 1 | PEN | REJ | REJ
001089 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0034 | 0 | 131242-WSD11-VI-0034 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD | Rev 0: Rejected | 2025-04-02 | 2025-03-18 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD " | 2025-03-05 | 2025-03-05 | 0 | 001089 | 2025-03-05 | 00 | 1 | PEN | REJ | REJ
001090 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0035 | 0 | 131242-WSD11-VI-0035 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES | Rev 0: Rejected | 2025-04-02 | 2025-03-18 |  | Rejected | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES" | 2025-03-05 | 2025-03-05 | 0 | 001090 | 2025-03-05 | 00 | 1 | PEN | REJ | REJ
001091 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0054 | 0 | 131242-WSW41-QA-0054 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-03-25 |  | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL)" | 2025-03-06 | 2025-03-06 | 0 | 001091 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
001092 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0028 | 0 | 131242-WSD11-DS-0028 | 2025-03-06 | Manual Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 129 | Approved | NO |  | YES |  |  |  |  | NA | "Manual Gate Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-03-06 | 0 | 001092 | 2025-03-06 | 00 | 1 | PEN | APP | APP
001093 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0029 | 0 | 131242-WSD11-DS-0029 | 2025-03-06 | Manual Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 129 | Approved | NO |  | YES |  |  |  |  | NA | "Manual Ball Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-03-06 | 0 | 001093 | 2025-03-06 | 00 | 1 | PEN | APP | APP
001094 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0030 | 0 | 131242-WSD11-DS-0030 | 2025-03-06 | Manual Globe Valve Data Sheet (Cambi Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 65 | Approved with Comments | YES | 2025-07-28 | NO | Overdue | 130 |  |  | NA | "Manual Globe Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-03-06 | 0 | 001094 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
001095 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1395 | 0 | 131242-WSW41-DS-1395 | 2025-03-06 | Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) | Rev 0: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 20 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) " | 2025-03-06 | 2025-03-06 | 0 | 001095 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
001096 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0056 | 0 | 131242-WST02-QA-0056 | 2025-03-06 | FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved | 2025-04-03 | 2025-03-21 |  | Approved | NO |  | YES |  |  |  |  | NA | " Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN)" && "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-03-06 | 2025-09-30 | 0 | 001096&&001705 | 2025-03-06, 2025-09-30 | 00 | 2 | PEN | APP | APP
001097 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0026 | 0 | 131242-WSD11-QA-0026 | 2025-03-06 | FAT report for Pressure transmitter (Air compressor) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-05-30 | 38 | Approved with Comments | YES | 2025-06-19 | NO | Overdue | 157 |  |  | NA | "FAT report for Pressure transmitter (Air compressor)" | 2025-03-06 | 2025-03-06 | 0 | 001097 | 2025-03-06 | 00 | 1 | PEN | AWC | AWC
001098 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0014 | 0 | 131242-WSW41-PO-0014 | 2025-03-06 | Unpriced PO for HDPE Pipes (AGRU) | Rev 0 for information | 2025-04-03 | 2025-03-27 |  | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for HDPE Pipes (AGRU) " && "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | 2025-03-06 | 2025-08-22 | 0 | 001098&&001504&&001612 | 2025-03-06, 2025-07-22, 2025-08-22 | 00 | 3 | PEN | INF | INF
001099 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 0 | 131242-WST02-CD-0009 | 2025-03-06 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 12 | Approved with Comments | YES | 2025-05-12 | YES | Resubmitted |  |  |  | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
001099 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 1 | 131242-WST02-CD-0009 | 2025-06-16 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 4 | Approved with Comments | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
001099 | 02 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 2 | 131242-WST02-CD-0009 | 2025-08-19 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-23 | 11 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | PEN | AWC | AWC
001100 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 0 | 131242-WST02-CD-0008 | 2025-03-06 | SSN Aeration Blowers I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 12 | Not Approved | YES | 2025-05-12 | YES | Resubmitted |  |  |  | NA | "SSN Aeration Blowers I/O List" | 2025-03-06 | 2025-07-11 | 1 | 001100 | 2025-03-06, 2025-07-11 | 00, 01 | 2 | PEN | NAP | NAP
001100 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 1 | 131242-WST02-CD-0008 | 2025-07-11 | SSN Aeration Blowers I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 38 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "SSN Aeration Blowers I/O List" | 2025-03-06 | 2025-07-11 | 1 | 001100 | 2025-03-06, 2025-07-11 | 00, 01 | 2 | PEN | AWC | AWC
001101 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0011 | 0 | 131242-WST02-RT-0011 | 2025-03-07 | SSN Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 21 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "SSN Motor Starting Study Report " | 2025-03-07 | 2025-03-07 | 0 | 001101 | 2025-03-07 | 00 | 1 | PEN | AWC | AWC
001102 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0006 | 0 | 131242-WSD11-RT-0006 | 2025-03-07 | THP Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 21 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "THP Motor Starting Study Report " | 2025-03-07 | 2025-03-07 | 0 | 001102 | 2025-03-07 | 00 | 1 | PEN | AWC | AWC
001103 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0032 | 0 | 131242-WSD11-DS-0032 | 2025-03-07 | ON OFF Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 128 | Approved | NO |  | YES |  |  |  |  | NA | "ON OFF Gate Valve Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-03-07 | 0 | 001103 | 2025-03-07 | 00 | 1 | PEN | APP | APP
001104 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0033 | 0 | 131242-WSD11-DS-0033 | 2025-03-07 | ON OFF Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 128 | Approved | NO |  | YES |  |  |  |  | NA | "ON OFF Ball Valve Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-03-07 | 0 | 001104 | 2025-03-07 | 00 | 1 | PEN | APP | APP
001105 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0034 | 0 | 131242-WSD11-DS-0034 | 2025-03-07 | ON OFF Ball Valve PN25 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 128 | Approved | NO |  | YES |  |  |  |  | NA | "ON OFF Ball Valve PN25 Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-03-07 | 0 | 001105 | 2025-03-07 | 00 | 1 | PEN | APP | APP
001106 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0035 | 0 | 131242-WSD11-DS-0035 | 2025-03-07 | ON OFF Ball Valve PN40 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 128 | Approved | NO |  | YES |  |  |  |  | NA | "ON OFF Ball Valve PN40 Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-03-07 | 0 | 001106 | 2025-03-07 | 00 | 1 | PEN | APP | APP
001107 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0022 | 0 | 131242-WSW41-RT-0022 | 2025-03-10 | C4B Monthly Progress Report Number No.22 (02 25) | Rev. 0 - Approved with comments (need to re-submit / see attached comment sheet) | 2025-04-07 | 2025-03-27 |  | Approved with Comments | YES | 2025-04-16 | NO | Overdue | 203 |  |  | NA | "C4B Monthly Progress Report Number No.22 (02 25) " | 2025-03-10 | 2025-03-10 | 0 | 001107 | 2025-03-10 | 00 | 1 | PEN | AWC | AWC
001108 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 0 | 131242-WST02-VI-0003 | 2025-03-10 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | AWC | AWC
001108 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 1 | 131242-WST02-VI-0003 | 2025-08-22 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-11 |  | 94 | Awaiting S.O.'s response | [7 empty] | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | PEN | PEN | PEN
001109 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 0 | 131242-WST02-VI-0002 | 2025-03-10 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
001109 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 1 | 131242-WST02-VI-0002 | 2025-04-18 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-08 | 2025-05-06 |  | Approved with Comments | YES | 2025-05-26 | NO | Overdue | 175 |  |  | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | PEN | AWC | AWC
001110 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0053 | 0 | 131242-WSW41-CD-0053 | 2025-03-10 | Submission of BIM Coordination VCM Model (Feb 2025) | For information. | 2025-04-07 | 2025-03-25 |  | For Information | NO |  | YES |  |  |  |  | NA | " Submission of BIM Coordination VCM Model (Feb 2025) " | 2025-03-10 | 2025-03-10 | 0 | 001110 | 2025-03-10 | 00 | 1 | PEN | INF | INF
001111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0020 | 0 | 131242-WSW41-PC-0020 | 2025-03-10 | Payment Claim No.20 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-04-07 | 2025-04-27 | 13 | For Information | NO |  | YES |  |  |  |  | NA | "Payment Claim No.20" | 2025-03-10 | 2025-03-10 | 0 | 001111 | 2025-03-10 | 00 | 1 | PEN | INF | INF
001112 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 0 | 131242-WST02-DR-7209 | 2025-03-10 | SSN PMS Network Architecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-07 | 2025-05-07 | 20 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "SSN PMS Network Architecture Drawings" | 2025-03-10 | 2025-08-07 | 1 | 000000&&001112 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01, NA | 4 | PEN | NAP | NAP
001112 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 1 | 131242-WST02-DR-7209 | 2025-08-07 | SSN PMS Network Architecture Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | 40 | Approved with Comments | YES | 2025-11-12 | NO | Overdue | 53 |  |  | NA | "SSN PMS Network Architecture Drawings" | 2025-03-10 | 2025-08-07 | 1 | 000000&&001112 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01, NA | 4 | PEN | AWC | AWC
001113 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 0 | 131242-WST02-VI-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-04-07 | 2025-03-28 |  | Not Approved | YES | 2025-04-17 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
001113 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 1 | 131242-WST02-VI-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-03-28 | 2025-05-29 | 40 | Not Approved | YES | 2025-06-18 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
001113 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 2 | 131242-WST02-VI-0001 | 2026-02-05 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | NA | 2026-02-25 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | PEN | PEN
001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-3015 | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 |  | Not Approved | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Shop Drawings for Siphonic System (Fast Flow)" | 2025-03-11 | 2025-06-12 | A | 000000&&001114 | 2025-03-11, 2025-06-12 | 00 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | SD | A | 1015 | NA | 131242-WST02-SD-1015 | 2025-03-11 |  | NA | 2025-04-08 | 2025-04-02 |  | Not Approved | YES | 2025-04-22 | NO | Overdue | 199 |  |  | NA |  | 2025-03-11 | 2025-03-11 | NA | 000000 | 2025-03-11 | NA | 1 | PEN | NAP | NAP
001115 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0007 | 0 | 131242-WSW41-PO-0007 | 2025-03-11 | Unpriced PO for Cable Support System (Jiangsu HDMann) | Rev 0: For Information. | 2025-04-08 | 2025-04-27 | 12 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Support System (Jiangsu HDMann) " && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | 2025-08-01 | 0 | 000595&&001115&&001506 | 2024-07-30, 2025-03-11, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
001116 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0057 | 0 | 131242-WSD11-QA-0057 | 2025-03-12 | FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-09 | 2025-03-21 |  | Approved with Comments | YES | 2025-04-10 | NO | Overdue | 207 |  |  | NA | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " && "Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP)" | 2025-03-12 | 2025-10-06 | 0 | 001116&&001726 | 2025-03-12, 2025-10-06 | 00 | 2 | PEN | AWC | AWC
001117 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 0 | 131242-WST02-CD-0010 | 2025-03-12 | SSN -RIO PANEL 0202- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-09 | 2025-04-22 | 8 | Not Approved | YES | 2025-05-12 | YES | Resubmitted |  |  |  | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | PEN | NAP | NAP
001117 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 1 | 131242-WST02-CD-0010 | 2025-06-18 | SSN -RIO PANEL 0202- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-02 | 40 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | PEN | AWC | AWC
001118 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2007 | 0 | 131242-WSW41-VI-2007 | 2025-03-12 | Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-07-08 | 61 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain" | 2025-03-12 | 2025-03-12 | 0 | 001118 | 2025-03-12 | 00 | 1 | PEN | AWC | AWC
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_LTA_NPKS | A | 131242-WSD11-DR-1002_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA | "THP LTA Submission" | 2025-03-12 | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1003_LTA_NPKS | NA | 131242-WSD11-DR-1003_LTA_NPKS | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1004_LTA_NPKS | NA | 131242-WSD11-DR-1004_LTA_NPKS | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 2000_LTA_NPKS | NA | 131242-WSD11-DR-2000_LTA_NPKS | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 3000_LTA_NPKS | NA | 131242-WSD11-DR-3000_LTA_NPKS | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_PUB | A | 131242-WSD11-DR-1002_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA | "THP PUB Submission" | 2025-03-12 | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1003_PUB | NA | 131242-WSD11-DR-1003_PUB | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1004_PUB | NA | 131242-WSD11-DR-1004_PUB | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 2000_PUB | NA | 131242-WSD11-DR-2000_PUB | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 3000_PUB | NA | 131242-WSD11-DR-3000_PUB | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_NEA | A | 131242-WSD11-DR-1002_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA | "THP NEA Submission" | 2025-03-12 | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1003_NEA | NA | 131242-WSD11-DR-1003_NEA | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 1004_NEA | NA | 131242-WSD11-DR-1004_NEA | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 2000_NEA | NA | 131242-WSD11-DR-2000_NEA | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | A | 3000_NEA | NA | 131242-WSD11-DR-3000_NEA | 2025-03-12 |  | NA | 2025-04-09 | 2025-06-11 | 42 | Not Approved | YES | 2025-07-01 | NO | Overdue | 149 |  |  | NA |  | 2025-03-12 | 2025-03-12 | NA | 000000 | 2025-03-12 | NA | 1 | PEN | NAP | NAP
001122 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0056 | 0 | 131242-WSW41-LT-0056 | 2025-03-13 | NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings | For Information. Please refer to S.O. correspondence no. 353 dated 28 May 2025. | 2025-04-10 | 2025-08-25 | 94 | For Information | NO |  | YES |  |  |  |  | NA | "NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings" | 2025-03-13 | 2025-03-13 | 0 | 001122 | 2025-03-13 | 00 | 1 | PEN | INF | INF
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | A | 131242-WST02-DR-5484 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 10 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5481 | NA | 131242-WST02-DR-5481 | 2025-03-13 |  | NA | 2025-04-10 | 2025-04-27 | 10 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-09-24 | NA | 000000 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5482 | NA | 131242-WST02-DR-5482 | 2025-03-13 |  | NA | 2025-04-10 | 2025-04-27 | 10 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-09-24 | NA | 000000 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5483 | NA | 131242-WST02-DR-5483 | 2025-03-13 |  | NA | 2025-04-10 | 2025-04-27 | 10 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-13 | 2025-07-07 | NA | 000000 | 2025-03-13, 2025-07-07 | NA | 2 | PEN | AWC | AWC
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | B | 131242-WST02-DR-5484 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 133 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5481 | NA | 131242-WST02-DR-5481 | 2025-07-07 |  | NA | 2025-07-25 | 2026-01-30 | 133 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-09-24 | NA | 000000 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5482 | NA | 131242-WST02-DR-5482 | 2025-07-07 |  | NA | 2025-07-25 | 2026-01-30 | 133 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-13 | 2025-09-24 | NA | 000000 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5483 | NA | 131242-WST02-DR-5483 | 2025-07-07 |  | NA | 2025-07-25 | 2026-01-30 | 133 | Approved with Comments | YES | 2026-02-19 | NO | Overdue | -20 |  |  | NA |  | 2025-03-13 | 2025-07-07 | NA | 000000 | 2025-03-13, 2025-07-07 | NA | 2 | PEN | AWC | AWC
001124 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 5483 | 0 | 131242-WSD11-QA-5483 | 2025-03-14 | Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON) | Rev 0: Approved | 2025-04-11 | 2025-07-08 | 59 | Approved | NO |  | YES |  |  |  |  | NA | "Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON)" | 2025-03-14 | 2025-03-14 | 0 | 001124 | 2025-03-14 | 00 | 1 | PEN | APP | APP
001125 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2003 | 0 | 131242-WSW41-VI-2003 | 2025-03-14 | Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-11 | 2025-04-27 | 9 | Approved with Comments | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen)" | 2025-03-14 | 2025-03-14 | 0 | 001125 | 2025-03-14 | 00 | 1 | PEN | AWC | AWC
001126 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0026 | 0 | 131242-WSW41-MS-0026 | 2025-03-14 | SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd. | R0: As communicated, CES would like to withdraw the submittal as CES has no intention to use the proposed materials for grouting. Hence, this submittal is rejected and no resubmission is required. | 2025-04-11 | 2025-06-04 | 35 | Rejected | NO |  | YES |  |  |  |  | NA | "SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd." | 2025-03-14 | 2025-03-14 | 0 | 001126 | 2025-03-14 | 00 | 1 | PEN | REJ | REJ
001127 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0005 | 0 | 131242-WSD11-DS-0005 | 2025-03-17 | Datasheet for Differential Pressure Switch (Compressed Air System) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-14 | 2025-07-10 | 60 | Approved with Comments | YES | 2025-07-30 | NO | Overdue | 128 |  |  | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | PEN | AWC | AWC
001128 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0019 | 0 | 131242-WSW41-PS-0019 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Nov 2024 | Rev 0: Scoring confirmed to be at 70/100 | 2025-04-14 | 2025-03-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Incentive/ Disincentive Audit Scheme for Nov 2024" && "Monthly Progress Presentation No. 19 (1224)" | 2025-01-16 | 2025-03-17 | 0 | 000979&&001128 | 2025-01-16, 2025-03-17 | 00 | 2 | PEN | APP | APP
001129 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0005 | 0 | 131242-WST02-VI-0005 | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-03-25 |  | Approved with Comments | YES | 2025-04-14 | YES | Resubmitted |  |  |  | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | PEN | AWC | AWC
001129 | 01 | Yuen Fatt | Project | NA | 131242 | NA | NA | NA | Cmt reply sheet | NA | 131242-NA-NA-Cmt reply sheet | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 1: Approved | 2025-04-07 | 2025-05-06 | 19 | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | 2025-03-18 | 2025-03-18 | NA | 001129 | 2025-03-18 | 01 | 1 | PEN | APP | APP
001130 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0020 | 0 | 131242-WSW41-PS-0020 | 2025-03-18 | Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025 | Rev 0: Noted for information | 2025-04-15 | 2025-03-25 |  | Approved | NO |  | YES |  |  |  |  | NA | "Monthly Progress Presentation No. 20 (0125)" && "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | 2025-02-18 | 2025-03-18 | 0 | 001048&&001130 | 2025-02-18, 2025-03-18 | 00 | 2 | PEN | APP | APP
001131 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 0 | 131242-WST02-RT-0002 | 2025-03-18 | Safety Review Report for Sitewide Pipe Rack | Approved with Comments | 2025-04-15 | 2025-05-13 | 17 | Approved with Comments | YES | 2025-06-02 | YES | Resubmitted |  |  |  | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | PEN | AWC | AWC
001131 | 01 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 1 | 131242-WST02-RT-0002 | 2025-06-18 | Safety Review Report for Sitewide Pipe Rack | R1: Approved | 2025-07-08 | 2025-07-07 |  | Approved | NO |  | YES |  |  |  |  | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | PEN | APP | APP
001132 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 0 | 131242-WST02-QA-0026 | 2025-03-18 | FAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-05-07 | 14 | Approved with Comments | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | PEN | AWC | AWC
001132 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 1 | 131242-WST02-QA-0026 | 2025-05-23 | FAT Procedure for LVSG Panels (Sunlight) | Rev 1: Approved. | 2025-06-12 | 2025-07-14 | 22 | Approved | NO |  | YES |  |  |  |  | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | PEN | APP | APP
001133 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0027 | 0 | 131242-WST02-QA-0027 | 2025-03-18 | FAT Procedure for MDB Panels (Sunlight) | Approved with Comments | 2025-04-15 | 2025-05-21 | 23 | Approved with Comments | YES | 2025-06-10 | NO | Overdue | 164 |  |  | NA | " FAT Procedure for MDB Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Gauges" && "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" | 2025-03-18 | 2025-07-14 | 0 | 001133&&001463&&001476 | 2025-03-18, 2025-07-11, 2025-07-14 | 00 | 3 | PEN | AWC | AWC
001134 | 00 | Max | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 0 | 131242-WSD11-RT-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-12 | 16 | Not Approved | YES | 2025-05-30 | YES | Resubmitted |  |  |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | NAP | NAP
001134 | 01 | Htet Nu | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 1 | 131242-WSD11-RT-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-07 | 2025-07-17 | 70 | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | PEN | AWC | AWC
001135 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5801 | A | 131242-WST02-DS-5801 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | 59 | Approved with Comments | YES | 2025-08-01 | NO | Overdue | 126 |  |  | NA | "SSN Spray Nozzle datasheet and drawing" | 2025-03-20 | 2025-03-20 | A | 001135 | 2025-03-20 | 00 | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5801 | NA | 131242-WST02-DR-5801 | 2025-03-20 |  | NA | 2025-04-17 | 2025-07-14 | 59 | Approved with Comments | YES | 2025-08-01 | NO | Overdue | 126 |  |  | NA |  | 2025-03-20 | 2025-03-20 | NA | 000000 | 2025-03-20 | NA | 1 | PEN | AWC | AWC
001136 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | A | 5000 | A | 131242-WSW41-DR-5000 | 2025-03-20 | Sitewide Piperack Handrail and Cad Ladder Layout and Details | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 12 | Not Approved | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2024-01-23 | 2026-01-19 | A | 000000&&001136 | 2024-01-23, 2025-03-20, 2026-01-19 | 00, NA | 3 | PEN | NAP | NAP
001137 | 00 | Radha | QAQC | NA | 131101 | WSW41 | MM | C | 0002 | 0 | 131101-WSW41-MM-0002 | 2025-03-20 | Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 12 | Approved with Comments | YES | 2025-05-27 | NO | Overdue | 174 |  |  | NA | "Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall)" | 2025-03-20 | 2025-03-20 | 0 | 001137 | 2025-03-20 | 00 | 1 | PEN | AWC | AWC
001138 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0028 | 0 | 131242-WSW41-QA-0028 | 2025-03-20 | FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI) | Approved | 2025-04-17 | 2025-05-06 | 11 | Approved | NO |  | YES |  |  |  |  | NA | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" && "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" && "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | 2025-03-20 | 2025-10-06 | 0 | 001138&&001239&&001723 | 2025-03-20, 2025-04-21, 2025-10-06 | 00 | 3 | PEN | APP | APP
001139 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 0 | 131242-WSW41-VI-2006 | 2025-03-20 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-04-05 |  | Approved with Comments | YES | 2025-04-24 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-03-20 | 2025-05-05 | 1 | 001139 | 2025-03-20, 2025-05-05 | 00, 01 | 2 | PEN | AWC | AWC
001139 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 1 | 131242-WSW41-VI-2006 | 2025-05-05 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | NA | 2025-05-23 |  | 173 | Awaiting S.O.'s response | [7 empty] | NA | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-03-20 | 2025-05-05 | 1 | 001139 | 2025-03-20, 2025-05-05 | 00, 01 | 2 | PEN | PEN | PEN
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | A | 131242-WST02-DR-7160 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7161 | NA | 131242-WST02-DR-7161 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7162 | NA | 131242-WST02-DR-7162 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7163 | NA | 131242-WST02-DR-7163 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7164 | NA | 131242-WST02-DR-7164 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7165 | NA | 131242-WST02-DR-7165 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7166 | NA | 131242-WST02-DR-7166 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7167 | NA | 131242-WST02-DR-7167 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7180 | NA | 131242-WST02-DR-7180 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7181 | NA | 131242-WST02-DR-7181 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7182 | NA | 131242-WST02-DR-7182 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7183 | NA | 131242-WST02-DR-7183 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7184 | NA | 131242-WST02-DR-7184 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7185 | NA | 131242-WST02-DR-7185 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7186 | NA | 131242-WST02-DR-7186 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7187 | NA | 131242-WST02-DR-7187 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3052 | NA | 131242-WST02-DR-3052 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3053 | NA | 131242-WST02-DR-3053 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3054 | NA | 131242-WST02-DR-3054 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3055 | NA | 131242-WST02-DR-3055 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2026-02-03 | NA | 000000 | 2025-03-21, 2025-07-21, 2026-02-03 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3056 | NA | 131242-WST02-DR-3056 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-03-21 | 2026-02-03 | A | 000000&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3057 | NA | 131242-WST02-DR-3057 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3058 | NA | 131242-WST02-DR-3058 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3059 | NA | 131242-WST02-DR-3059 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3060 | NA | 131242-WST02-DR-3060 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2026-02-03 | NA | 000000 | 2025-03-21, 2025-07-21, 2026-02-03 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3061 | NA | 131242-WST02-DR-3061 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3062 | NA | 131242-WST02-DR-3062 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3063 | NA | 131242-WST02-DR-3063 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3064 | NA | 131242-WST02-DR-3064 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3065 | NA | 131242-WST02-DR-3065 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7142 | NA | 131242-WST02-DR-7142 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7143 | NA | 131242-WST02-DR-7143 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7144 | NA | 131242-WST02-DR-7144 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7145 | NA | 131242-WST02-DR-7145 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7146 | NA | 131242-WST02-DR-7146 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7147 | NA | 131242-WST02-DR-7147 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-20 | 19 | Approved with Comments | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | B | 131242-WST02-DR-7160 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7161 | NA | 131242-WST02-DR-7161 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7162 | NA | 131242-WST02-DR-7162 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7163 | NA | 131242-WST02-DR-7163 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7164 | NA | 131242-WST02-DR-7164 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7165 | NA | 131242-WST02-DR-7165 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7166 | NA | 131242-WST02-DR-7166 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7167 | NA | 131242-WST02-DR-7167 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7180 | NA | 131242-WST02-DR-7180 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7181 | NA | 131242-WST02-DR-7181 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7182 | NA | 131242-WST02-DR-7182 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7183 | NA | 131242-WST02-DR-7183 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-10-08 | NA | 000000 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7184 | NA | 131242-WST02-DR-7184 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7185 | NA | 131242-WST02-DR-7185 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7186 | NA | 131242-WST02-DR-7186 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7187 | NA | 131242-WST02-DR-7187 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3052 | NA | 131242-WST02-DR-3052 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3053 | NA | 131242-WST02-DR-3053 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3054 | NA | 131242-WST02-DR-3054 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3055 | NA | 131242-WST02-DR-3055 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2026-02-03 | NA | 000000 | 2025-03-21, 2025-07-21, 2026-02-03 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3056 | NA | 131242-WST02-DR-3056 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-03-21 | 2026-02-03 | A | 000000&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3057 | NA | 131242-WST02-DR-3057 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3058 | NA | 131242-WST02-DR-3058 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3059 | NA | 131242-WST02-DR-3059 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3060 | NA | 131242-WST02-DR-3060 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2026-02-03 | NA | 000000 | 2025-03-21, 2025-07-21, 2026-02-03 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3061 | NA | 131242-WST02-DR-3061 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3062 | NA | 131242-WST02-DR-3062 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3063 | NA | 131242-WST02-DR-3063 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3064 | NA | 131242-WST02-DR-3064 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3065 | NA | 131242-WST02-DR-3065 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-21 | 2025-07-21 | NA | 000000 | 2025-03-21, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7142 | NA | 131242-WST02-DR-7142 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7143 | NA | 131242-WST02-DR-7143 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7144 | NA | 131242-WST02-DR-7144 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7145 | NA | 131242-WST02-DR-7145 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7146 | NA | 131242-WST02-DR-7146 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7147 | NA | 131242-WST02-DR-7147 | 2025-07-21 |  | NA | 2025-08-08 | 2025-09-23 | 32 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
001141 | 00 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 0 | 131242-WST02-VI-0024 | 2025-03-21 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-03-21 | 2025-04-30 | 1 | 001141 | 2025-03-21, 2025-04-30 | 00, 01 | 2 | PEN | NAP | NAP
001141 | 01 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 1 | 131242-WST02-VI-0024 | 2025-04-30 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-04 | 11 | Approved with Comments | YES | 2025-06-24 | NO | Overdue | 154 |  |  | NA | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-03-21 | 2025-04-30 | 1 | 001141 | 2025-03-21, 2025-04-30 | 00, 01 | 2 | PEN | AWC | AWC
001142 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 0 | 131242-WST02-CD-0011 | 2025-03-21 | SSN -RIO PANEL 0401- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-22 | 1 | Not Approved | YES | 2025-05-12 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0401- I/O List" | 2023-11-10 | 2025-06-25 | 1 | 000000&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | PEN | NAP | NAP
001142 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 1 | 131242-WST02-CD-0011 | 2025-06-25 | SSN -RIO PANEL 0401- I/O List | Rev 1: Approved with Comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-15 | 44 | Approved with Comments | YES | 2025-10-03 | NO | Overdue | 81 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0401- I/O List" | 2023-11-10 | 2025-06-25 | 1 | 000000&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | PEN | AWC | AWC
001143 | 00 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 0 | 131242-WSD11-MS-0007 | 2025-03-21 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Not approved - Revise and Resubmit. Refer to comments provided during MSRA briefing meeting dated 28th March 2025 and 4 April 2025. | 2025-04-18 | 2025-04-05 |  | Not Approved | YES | 2025-04-24 | YES | Resubmitted |  |  |  | NA | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " && "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | 2025-05-30 | 0 | 001143&&001334 | 2025-03-21, 2025-04-10, 2025-05-30 | 00, 01 | 3 | PEN | NAP | NAP
001143 | 01 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 1 | 131242-WSD11-MS-0007 | 2025-04-10 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Approved | 2025-04-30 | 2025-05-21 | 13 | Approved | NO |  | YES |  |  |  |  | NA | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " && "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | 2025-05-30 | 0 | 001143&&001334 | 2025-03-21, 2025-04-10, 2025-05-30 | 00, 01 | 3 | PEN | APP | APP
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-1001 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1002 | NA | 131242-WST02-DR-1002 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1003 | NA | 131242-WST02-DR-1003 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1004 | NA | 131242-WST02-DR-1004 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1005 | NA | 131242-WST02-DR-1005 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1006 | NA | 131242-WST02-DR-1006 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1007 | NA | 131242-WST02-DR-1007 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 13 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1008 | NA | 131242-WST02-DR-1008 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1009 | NA | 131242-WST02-DR-1009 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | 2026-02-09 | A | 000000&&000812 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 16 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1010 | NA | 131242-WST02-DR-1010 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1011 | NA | 131242-WST02-DR-1011 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1012 | NA | 131242-WST02-DR-1012 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1013 | NA | 131242-WST02-DR-1013 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1014 | NA | 131242-WST02-DR-1014 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1015 | NA | 131242-WST02-DR-1015 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1016 | NA | 131242-WST02-DR-1016 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1017 | NA | 131242-WST02-DR-1017 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1018 | NA | 131242-WST02-DR-1018 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1019 | NA | 131242-WST02-DR-1019 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1020 | NA | 131242-WST02-DR-1020 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1021 | NA | 131242-WST02-DR-1021 | 2025-03-21 |  | NA | 2025-04-18 | 2025-05-16 | 17 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | NAP | NAP
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-1001 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "BMS Panel GA & Wiring Drawing " && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" | 2023-11-03 | 2026-02-03 | A | 000000&&000834&&001144&&001625&&001793 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, NA | 33 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1002 | NA | 131242-WST02-DR-1002 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "ACMV LCP GA & Wiring Drawing" && "Hose Reel (SSN Area)" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Electrical Building Archi Drawing" | 2023-11-03 | 2026-02-04 | 1 | 000000&&000190&&000832&&001402 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03, NA | 28 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1003 | NA | 131242-WST02-DR-1003 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | 2026-02-04 | A | 000000&&000418&&000810 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, NA | 29 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1004 | NA | 131242-WST02-DR-1004 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | 2026-02-09 | A.6 | 000000&&000811&&001528 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, NA | 33 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1005 | NA | 131242-WST02-DR-1005 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2023-11-22 | 2026-02-09 | NA | 000000 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 23 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1006 | NA | 131242-WST02-DR-1006 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 17 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1007 | NA | 131242-WST02-DR-1007 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-09 | NA | 000000 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 13 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1008 | NA | 131242-WST02-DR-1008 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 12 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1009 | NA | 131242-WST02-DR-1009 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | 2026-02-09 | A | 000000&&000812 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, NA | 16 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1010 | NA | 131242-WST02-DR-1010 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-09 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1011 | NA | 131242-WST02-DR-1011 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2024-04-04 | 2026-02-04 | E | 000000&&000419&&001284 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, NA | 14 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1012 | NA | 131242-WST02-DR-1012 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1013 | NA | 131242-WST02-DR-1013 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-04 | 2026-02-04 | NA | 000000 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1014 | NA | 131242-WST02-DR-1014 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1015 | NA | 131242-WST02-DR-1015 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1016 | NA | 131242-WST02-DR-1016 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1017 | NA | 131242-WST02-DR-1017 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1018 | NA | 131242-WST02-DR-1018 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1019 | NA | 131242-WST02-DR-1019 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1020 | NA | 131242-WST02-DR-1020 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1021 | NA | 131242-WST02-DR-1021 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-02-04 | NA | 000000 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 7 | PEN | AWC | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | B | 131242-WST02-DR-1051 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2026-01-28 | C | 000000&&001145 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1052 | NA | 131242-WST02-DR-1052 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1053 | NA | 131242-WST02-DR-1053 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1054 | NA | 131242-WST02-DR-1054 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1055 | NA | 131242-WST02-DR-1055 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1056 | NA | 131242-WST02-DR-1056 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1057 | NA | 131242-WST02-DR-1057 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1058 | NA | 131242-WST02-DR-1058 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1059 | NA | 131242-WST02-DR-1059 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1060 | NA | 131242-WST02-DR-1060 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1061 | NA | 131242-WST02-DR-1061 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1062 | NA | 131242-WST02-DR-1062 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1063 | NA | 131242-WST02-DR-1063 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1064 | NA | 131242-WST02-DR-1064 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1065 | NA | 131242-WST02-DR-1065 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1066 | NA | 131242-WST02-DR-1066 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1067 | NA | 131242-WST02-DR-1067 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1068 | NA | 131242-WST02-DR-1068 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1069 | NA | 131242-WST02-DR-1069 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1070 | NA | 131242-WST02-DR-1070 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1071 | NA | 131242-WST02-DR-1071 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1072 | NA | 131242-WST02-DR-1072 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1073 | NA | 131242-WST02-DR-1073 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1074 | NA | 131242-WST02-DR-1074 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1075 | NA | 131242-WST02-DR-1075 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | NAP | NAP
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | C | 131242-WST02-DR-1051 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2026-01-28 | C | 000000&&001145 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1052 | NA | 131242-WST02-DR-1052 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1053 | NA | 131242-WST02-DR-1053 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1054 | NA | 131242-WST02-DR-1054 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1055 | NA | 131242-WST02-DR-1055 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1056 | NA | 131242-WST02-DR-1056 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1057 | NA | 131242-WST02-DR-1057 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1058 | NA | 131242-WST02-DR-1058 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1059 | NA | 131242-WST02-DR-1059 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1060 | NA | 131242-WST02-DR-1060 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1061 | NA | 131242-WST02-DR-1061 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1062 | NA | 131242-WST02-DR-1062 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1063 | NA | 131242-WST02-DR-1063 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1064 | NA | 131242-WST02-DR-1064 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1065 | NA | 131242-WST02-DR-1065 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1066 | NA | 131242-WST02-DR-1066 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1067 | NA | 131242-WST02-DR-1067 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1068 | NA | 131242-WST02-DR-1068 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1069 | NA | 131242-WST02-DR-1069 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1070 | NA | 131242-WST02-DR-1070 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1071 | NA | 131242-WST02-DR-1071 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1072 | NA | 131242-WST02-DR-1072 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1073 | NA | 131242-WST02-DR-1073 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1074 | NA | 131242-WST02-DR-1074 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1075 | NA | 131242-WST02-DR-1075 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-01 | 17 | Approved with Comments | YES | 2025-10-21 | NO | Overdue | 69 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2026-01-28 | NA | 000000 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, NA | 3 | PEN | AWC | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-1101 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1102 | NA | 131242-WST02-DR-1102 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1103 | NA | 131242-WST02-DR-1103 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1104 | NA | 131242-WST02-DR-1104 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1105 | NA | 131242-WST02-DR-1105 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1106 | NA | 131242-WST02-DR-1106 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1107 | NA | 131242-WST02-DR-1107 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1108 | NA | 131242-WST02-DR-1108 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1109 | NA | 131242-WST02-DR-1109 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1110 | NA | 131242-WST02-DR-1110 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1111 | NA | 131242-WST02-DR-1111 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1112 | NA | 131242-WST02-DR-1112 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1113 | NA | 131242-WST02-DR-1113 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1114 | NA | 131242-WST02-DR-1114 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1115 | NA | 131242-WST02-DR-1115 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1116 | NA | 131242-WST02-DR-1116 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1117 | NA | 131242-WST02-DR-1117 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1118 | NA | 131242-WST02-DR-1118 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1119 | NA | 131242-WST02-DR-1119 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1120 | NA | 131242-WST02-DR-1120 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1121 | NA | 131242-WST02-DR-1121 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1122 | NA | 131242-WST02-DR-1122 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1123 | NA | 131242-WST02-DR-1123 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1124 | NA | 131242-WST02-DR-1124 | 2025-03-21 |  | NA | 2025-04-18 | 2025-04-30 | 7 | Not Approved | YES | 2025-05-20 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | NAP | NAP
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-1101 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | 2025-08-19 | B | 000000&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01 | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1102 | NA | 131242-WST02-DR-1102 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1103 | NA | 131242-WST02-DR-1103 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2023-12-18 | 2025-08-19 | NA | 000000 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1104 | NA | 131242-WST02-DR-1104 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1105 | NA | 131242-WST02-DR-1105 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1106 | NA | 131242-WST02-DR-1106 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1107 | NA | 131242-WST02-DR-1107 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1108 | NA | 131242-WST02-DR-1108 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1109 | NA | 131242-WST02-DR-1109 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1110 | NA | 131242-WST02-DR-1110 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1111 | NA | 131242-WST02-DR-1111 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-31 | NA | 000000 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1112 | NA | 131242-WST02-DR-1112 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1113 | NA | 131242-WST02-DR-1113 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1114 | NA | 131242-WST02-DR-1114 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1115 | NA | 131242-WST02-DR-1115 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1116 | NA | 131242-WST02-DR-1116 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1117 | NA | 131242-WST02-DR-1117 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" | 2025-03-21 | 2025-10-27 | NA | 000000 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1118 | NA | 131242-WST02-DR-1118 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1119 | NA | 131242-WST02-DR-1119 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1120 | NA | 131242-WST02-DR-1120 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1121 | NA | 131242-WST02-DR-1121 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1122 | NA | 131242-WST02-DR-1122 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1123 | NA | 131242-WST02-DR-1123 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1124 | NA | 131242-WST02-DR-1124 | 2025-08-19 |  | NA | 2025-09-08 | 2025-10-08 | 22 | Approved with Comments | YES | 2025-10-28 | NO | Overdue | 64 |  |  | NA |  | 2025-03-21 | 2025-08-19 | NA | 000000 | 2025-03-21, 2025-08-19 | NA | 2 | PEN | AWC | AWC
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | B | 131242-WST02-DR-1151 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1152 | NA | 131242-WST02-DR-1152 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1153 | NA | 131242-WST02-DR-1153 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "SSN Electrical building L2, Column C2A PE Endorsement" | 2025-03-21 | 2025-07-29 | A | 000000&&001525 | 2025-03-21, 2025-07-24, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1154 | NA | 131242-WST02-DR-1154 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1155 | NA | 131242-WST02-DR-1155 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1156 | NA | 131242-WST02-DR-1156 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1157 | NA | 131242-WST02-DR-1157 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1158 | NA | 131242-WST02-DR-1158 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1159 | NA | 131242-WST02-DR-1159 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1160 | NA | 131242-WST02-DR-1160 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1161 | NA | 131242-WST02-DR-1161 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1162 | NA | 131242-WST02-DR-1162 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1163 | NA | 131242-WST02-DR-1163 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1164 | NA | 131242-WST02-DR-1164 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1165 | NA | 131242-WST02-DR-1165 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1166 | NA | 131242-WST02-DR-1166 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1167 | NA | 131242-WST02-DR-1167 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1168 | NA | 131242-WST02-DR-1168 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1169 | NA | 131242-WST02-DR-1169 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1170 | NA | 131242-WST02-DR-1170 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1171 | NA | 131242-WST02-DR-1171 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1172 | NA | 131242-WST02-DR-1172 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1173 | NA | 131242-WST02-DR-1173 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1174 | NA | 131242-WST02-DR-1174 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1175 | NA | 131242-WST02-DR-1175 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1176 | NA | 131242-WST02-DR-1176 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1177 | NA | 131242-WST02-DR-1177 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1178 | NA | 131242-WST02-DR-1178 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1179 | NA | 131242-WST02-DR-1179 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1180 | NA | 131242-WST02-DR-1180 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1181 | NA | 131242-WST02-DR-1181 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1182 | NA | 131242-WST02-DR-1182 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1183 | NA | 131242-WST02-DR-1183 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1184 | NA | 131242-WST02-DR-1184 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1185 | NA | 131242-WST02-DR-1185 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1186 | NA | 131242-WST02-DR-1186 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1187 | NA | 131242-WST02-DR-1187 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1188 | NA | 131242-WST02-DR-1188 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1189 | NA | 131242-WST02-DR-1189 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1190 | NA | 131242-WST02-DR-1190 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1191 | NA | 131242-WST02-DR-1191 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1192 | NA | 131242-WST02-DR-1192 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1193 | NA | 131242-WST02-DR-1193 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1194 | NA | 131242-WST02-DR-1194 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1195 | NA | 131242-WST02-DR-1195 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1196 | NA | 131242-WST02-DR-1196 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1197 | NA | 131242-WST02-DR-1197 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1198 | NA | 131242-WST02-DR-1198 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1199 | NA | 131242-WST02-DR-1199 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1200 | NA | 131242-WST02-DR-1200 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1201 | NA | 131242-WST02-DR-1201 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1202 | NA | 131242-WST02-DR-1202 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1203 | NA | 131242-WST02-DR-1203 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST608 drawings Connection Details" | 2025-03-06 | 2025-07-29 | F | 000000&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1204 | NA | 131242-WST02-DR-1204 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1205 | NA | 131242-WST02-DR-1205 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1206 | NA | 131242-WST02-DR-1206 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1207 | NA | 131242-WST02-DR-1207 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1208 | NA | 131242-WST02-DR-1208 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1209 | NA | 131242-WST02-DR-1209 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1210 | NA | 131242-WST02-DR-1210 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1211 | NA | 131242-WST02-DR-1211 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1212 | NA | 131242-WST02-DR-1212 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1213 | NA | 131242-WST02-DR-1213 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1214 | NA | 131242-WST02-DR-1214 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1215 | NA | 131242-WST02-DR-1215 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1216 | NA | 131242-WST02-DR-1216 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1217 | NA | 131242-WST02-DR-1217 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1218 | NA | 131242-WST02-DR-1218 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1219 | NA | 131242-WST02-DR-1219 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1220 | NA | 131242-WST02-DR-1220 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1221 | NA | 131242-WST02-DR-1221 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1222 | NA | 131242-WST02-DR-1222 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1223 | NA | 131242-WST02-DR-1223 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1224 | NA | 131242-WST02-DR-1224 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1225 | NA | 131242-WST02-DR-1225 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1226 | NA | 131242-WST02-DR-1226 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1227 | NA | 131242-WST02-DR-1227 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1228 | NA | 131242-WST02-DR-1228 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1229 | NA | 131242-WST02-DR-1229 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1230 | NA | 131242-WST02-DR-1230 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1231 | NA | 131242-WST02-DR-1231 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1232 | NA | 131242-WST02-DR-1232 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1233 | NA | 131242-WST02-DR-1233 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1234 | NA | 131242-WST02-DR-1234 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1235 | NA | 131242-WST02-DR-1235 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1236 | NA | 131242-WST02-DR-1236 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1237 | NA | 131242-WST02-DR-1237 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1238 | NA | 131242-WST02-DR-1238 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1239 | NA | 131242-WST02-DR-1239 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1240 | NA | 131242-WST02-DR-1240 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1241 | NA | 131242-WST02-DR-1241 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1242 | NA | 131242-WST02-DR-1242 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1243 | NA | 131242-WST02-DR-1243 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1244 | NA | 131242-WST02-DR-1244 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1245 | NA | 131242-WST02-DR-1245 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1246 | NA | 131242-WST02-DR-1246 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1247 | NA | 131242-WST02-DR-1247 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1248 | NA | 131242-WST02-DR-1248 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1249 | NA | 131242-WST02-DR-1249 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1250 | NA | 131242-WST02-DR-1250 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1251 | NA | 131242-WST02-DR-1251 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1252 | NA | 131242-WST02-DR-1252 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1253 | NA | 131242-WST02-DR-1253 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1254 | NA | 131242-WST02-DR-1254 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1255 | NA | 131242-WST02-DR-1255 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1256 | NA | 131242-WST02-DR-1256 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1257 | NA | 131242-WST02-DR-1257 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1258 | NA | 131242-WST02-DR-1258 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1259 | NA | 131242-WST02-DR-1259 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1260 | NA | 131242-WST02-DR-1260 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1261 | NA | 131242-WST02-DR-1261 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1262 | NA | 131242-WST02-DR-1262 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1263 | NA | 131242-WST02-DR-1263 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1264 | NA | 131242-WST02-DR-1264 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1265 | NA | 131242-WST02-DR-1265 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1266 | NA | 131242-WST02-DR-1266 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1267 | NA | 131242-WST02-DR-1267 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1268 | NA | 131242-WST02-DR-1268 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1269 | NA | 131242-WST02-DR-1269 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1270 | NA | 131242-WST02-DR-1270 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1271 | NA | 131242-WST02-DR-1271 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1272 | NA | 131242-WST02-DR-1272 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1273 | NA | 131242-WST02-DR-1273 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1274 | NA | 131242-WST02-DR-1274 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1275 | NA | 131242-WST02-DR-1275 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1276 | NA | 131242-WST02-DR-1276 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1277 | NA | 131242-WST02-DR-1277 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1278 | NA | 131242-WST02-DR-1278 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1279 | NA | 131242-WST02-DR-1279 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1280 | NA | 131242-WST02-DR-1280 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1281 | NA | 131242-WST02-DR-1281 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1282 | NA | 131242-WST02-DR-1282 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1283 | NA | 131242-WST02-DR-1283 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1284 | NA | 131242-WST02-DR-1284 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1285 | NA | 131242-WST02-DR-1285 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1286 | NA | 131242-WST02-DR-1286 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1287 | NA | 131242-WST02-DR-1287 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1288 | NA | 131242-WST02-DR-1288 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1289 | NA | 131242-WST02-DR-1289 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1290 | NA | 131242-WST02-DR-1290 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1291 | NA | 131242-WST02-DR-1291 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1292 | NA | 131242-WST02-DR-1292 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1293 | NA | 131242-WST02-DR-1293 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1294 | NA | 131242-WST02-DR-1294 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1295 | NA | 131242-WST02-DR-1295 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1296 | NA | 131242-WST02-DR-1296 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1297 | NA | 131242-WST02-DR-1297 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1298 | NA | 131242-WST02-DR-1298 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1299 | NA | 131242-WST02-DR-1299 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | C | 131242-WST02-DR-1151 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1152 | NA | 131242-WST02-DR-1152 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1153 | NA | 131242-WST02-DR-1153 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "SSN Electrical building L2, Column C2A PE Endorsement" | 2025-03-21 | 2025-07-29 | A | 000000&&001525 | 2025-03-21, 2025-07-24, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1154 | NA | 131242-WST02-DR-1154 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1155 | NA | 131242-WST02-DR-1155 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1156 | NA | 131242-WST02-DR-1156 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1157 | NA | 131242-WST02-DR-1157 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1158 | NA | 131242-WST02-DR-1158 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1159 | NA | 131242-WST02-DR-1159 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1160 | NA | 131242-WST02-DR-1160 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1161 | NA | 131242-WST02-DR-1161 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1162 | NA | 131242-WST02-DR-1162 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1163 | NA | 131242-WST02-DR-1163 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1164 | NA | 131242-WST02-DR-1164 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1165 | NA | 131242-WST02-DR-1165 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1166 | NA | 131242-WST02-DR-1166 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1167 | NA | 131242-WST02-DR-1167 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1168 | NA | 131242-WST02-DR-1168 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1169 | NA | 131242-WST02-DR-1169 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1170 | NA | 131242-WST02-DR-1170 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1171 | NA | 131242-WST02-DR-1171 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1172 | NA | 131242-WST02-DR-1172 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1173 | NA | 131242-WST02-DR-1173 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1174 | NA | 131242-WST02-DR-1174 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1175 | NA | 131242-WST02-DR-1175 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1176 | NA | 131242-WST02-DR-1176 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1177 | NA | 131242-WST02-DR-1177 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1178 | NA | 131242-WST02-DR-1178 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1179 | NA | 131242-WST02-DR-1179 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1180 | NA | 131242-WST02-DR-1180 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1181 | NA | 131242-WST02-DR-1181 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1182 | NA | 131242-WST02-DR-1182 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1183 | NA | 131242-WST02-DR-1183 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1184 | NA | 131242-WST02-DR-1184 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1185 | NA | 131242-WST02-DR-1185 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1186 | NA | 131242-WST02-DR-1186 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1187 | NA | 131242-WST02-DR-1187 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1188 | NA | 131242-WST02-DR-1188 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1189 | NA | 131242-WST02-DR-1189 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1190 | NA | 131242-WST02-DR-1190 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1191 | NA | 131242-WST02-DR-1191 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1192 | NA | 131242-WST02-DR-1192 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1193 | NA | 131242-WST02-DR-1193 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1194 | NA | 131242-WST02-DR-1194 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1195 | NA | 131242-WST02-DR-1195 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1196 | NA | 131242-WST02-DR-1196 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1197 | NA | 131242-WST02-DR-1197 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1198 | NA | 131242-WST02-DR-1198 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1199 | NA | 131242-WST02-DR-1199 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1200 | NA | 131242-WST02-DR-1200 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1201 | NA | 131242-WST02-DR-1201 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1202 | NA | 131242-WST02-DR-1202 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1203 | NA | 131242-WST02-DR-1203 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "ST608 drawings Connection Details" | 2025-03-06 | 2025-07-29 | F | 000000&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1204 | NA | 131242-WST02-DR-1204 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1205 | NA | 131242-WST02-DR-1205 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1206 | NA | 131242-WST02-DR-1206 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1207 | NA | 131242-WST02-DR-1207 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1208 | NA | 131242-WST02-DR-1208 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1209 | NA | 131242-WST02-DR-1209 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1210 | NA | 131242-WST02-DR-1210 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-06 | 2025-07-29 | NA | 000000 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1211 | NA | 131242-WST02-DR-1211 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1212 | NA | 131242-WST02-DR-1212 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1213 | NA | 131242-WST02-DR-1213 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1214 | NA | 131242-WST02-DR-1214 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1215 | NA | 131242-WST02-DR-1215 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1216 | NA | 131242-WST02-DR-1216 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1217 | NA | 131242-WST02-DR-1217 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1218 | NA | 131242-WST02-DR-1218 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1219 | NA | 131242-WST02-DR-1219 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1220 | NA | 131242-WST02-DR-1220 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1221 | NA | 131242-WST02-DR-1221 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1222 | NA | 131242-WST02-DR-1222 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1223 | NA | 131242-WST02-DR-1223 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1224 | NA | 131242-WST02-DR-1224 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1225 | NA | 131242-WST02-DR-1225 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1226 | NA | 131242-WST02-DR-1226 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1227 | NA | 131242-WST02-DR-1227 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1228 | NA | 131242-WST02-DR-1228 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1229 | NA | 131242-WST02-DR-1229 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1230 | NA | 131242-WST02-DR-1230 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1231 | NA | 131242-WST02-DR-1231 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1232 | NA | 131242-WST02-DR-1232 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1233 | NA | 131242-WST02-DR-1233 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1234 | NA | 131242-WST02-DR-1234 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1235 | NA | 131242-WST02-DR-1235 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1236 | NA | 131242-WST02-DR-1236 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1237 | NA | 131242-WST02-DR-1237 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1238 | NA | 131242-WST02-DR-1238 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1239 | NA | 131242-WST02-DR-1239 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1240 | NA | 131242-WST02-DR-1240 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1241 | NA | 131242-WST02-DR-1241 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1242 | NA | 131242-WST02-DR-1242 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1243 | NA | 131242-WST02-DR-1243 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1244 | NA | 131242-WST02-DR-1244 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1245 | NA | 131242-WST02-DR-1245 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1246 | NA | 131242-WST02-DR-1246 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1247 | NA | 131242-WST02-DR-1247 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1248 | NA | 131242-WST02-DR-1248 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1249 | NA | 131242-WST02-DR-1249 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1250 | NA | 131242-WST02-DR-1250 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1251 | NA | 131242-WST02-DR-1251 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1252 | NA | 131242-WST02-DR-1252 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1253 | NA | 131242-WST02-DR-1253 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1254 | NA | 131242-WST02-DR-1254 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1255 | NA | 131242-WST02-DR-1255 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1256 | NA | 131242-WST02-DR-1256 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1257 | NA | 131242-WST02-DR-1257 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1258 | NA | 131242-WST02-DR-1258 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1259 | NA | 131242-WST02-DR-1259 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1260 | NA | 131242-WST02-DR-1260 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1261 | NA | 131242-WST02-DR-1261 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1262 | NA | 131242-WST02-DR-1262 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1263 | NA | 131242-WST02-DR-1263 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1264 | NA | 131242-WST02-DR-1264 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1265 | NA | 131242-WST02-DR-1265 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1266 | NA | 131242-WST02-DR-1266 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1267 | NA | 131242-WST02-DR-1267 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1268 | NA | 131242-WST02-DR-1268 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1269 | NA | 131242-WST02-DR-1269 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1270 | NA | 131242-WST02-DR-1270 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1271 | NA | 131242-WST02-DR-1271 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1272 | NA | 131242-WST02-DR-1272 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1273 | NA | 131242-WST02-DR-1273 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1274 | NA | 131242-WST02-DR-1274 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1275 | NA | 131242-WST02-DR-1275 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1276 | NA | 131242-WST02-DR-1276 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1277 | NA | 131242-WST02-DR-1277 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1278 | NA | 131242-WST02-DR-1278 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1279 | NA | 131242-WST02-DR-1279 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1280 | NA | 131242-WST02-DR-1280 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1281 | NA | 131242-WST02-DR-1281 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1282 | NA | 131242-WST02-DR-1282 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1283 | NA | 131242-WST02-DR-1283 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1284 | NA | 131242-WST02-DR-1284 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1285 | NA | 131242-WST02-DR-1285 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1286 | NA | 131242-WST02-DR-1286 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1287 | NA | 131242-WST02-DR-1287 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1288 | NA | 131242-WST02-DR-1288 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1289 | NA | 131242-WST02-DR-1289 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1290 | NA | 131242-WST02-DR-1290 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1291 | NA | 131242-WST02-DR-1291 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1292 | NA | 131242-WST02-DR-1292 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1293 | NA | 131242-WST02-DR-1293 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1294 | NA | 131242-WST02-DR-1294 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1295 | NA | 131242-WST02-DR-1295 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1296 | NA | 131242-WST02-DR-1296 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1297 | NA | 131242-WST02-DR-1297 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1298 | NA | 131242-WST02-DR-1298 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1299 | NA | 131242-WST02-DR-1299 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-1351 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1352 | NA | 131242-WST02-DR-1352 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1353 | NA | 131242-WST02-DR-1353 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1354 | NA | 131242-WST02-DR-1354 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1355 | NA | 131242-WST02-DR-1355 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1356 | NA | 131242-WST02-DR-1356 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1357 | NA | 131242-WST02-DR-1357 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1358 | NA | 131242-WST02-DR-1358 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1359 | NA | 131242-WST02-DR-1359 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1360 | NA | 131242-WST02-DR-1360 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1361 | NA | 131242-WST02-DR-1361 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1362 | NA | 131242-WST02-DR-1362 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1363 | NA | 131242-WST02-DR-1363 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1364 | NA | 131242-WST02-DR-1364 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1365 | NA | 131242-WST02-DR-1365 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1366 | NA | 131242-WST02-DR-1366 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1367 | NA | 131242-WST02-DR-1367 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1368 | NA | 131242-WST02-DR-1368 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1369 | NA | 131242-WST02-DR-1369 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1370 | NA | 131242-WST02-DR-1370 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1371 | NA | 131242-WST02-DR-1371 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1372 | NA | 131242-WST02-DR-1372 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1373 | NA | 131242-WST02-DR-1373 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1374 | NA | 131242-WST02-DR-1374 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1375 | NA | 131242-WST02-DR-1375 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1376 | NA | 131242-WST02-DR-1376 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1377 | NA | 131242-WST02-DR-1377 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1378 | NA | 131242-WST02-DR-1378 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1379 | NA | 131242-WST02-DR-1379 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1380 | NA | 131242-WST02-DR-1380 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1381 | NA | 131242-WST02-DR-1381 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1382 | NA | 131242-WST02-DR-1382 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1383 | NA | 131242-WST02-DR-1383 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1384 | NA | 131242-WST02-DR-1384 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1385 | NA | 131242-WST02-DR-1385 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1386 | NA | 131242-WST02-DR-1386 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1387 | NA | 131242-WST02-DR-1387 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1388 | NA | 131242-WST02-DR-1388 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1389 | NA | 131242-WST02-DR-1389 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1390 | NA | 131242-WST02-DR-1390 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1391 | NA | 131242-WST02-DR-1391 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1392 | NA | 131242-WST02-DR-1392 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1393 | NA | 131242-WST02-DR-1393 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1394 | NA | 131242-WST02-DR-1394 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1395 | NA | 131242-WST02-DR-1395 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1396 | NA | 131242-WST02-DR-1396 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1397 | NA | 131242-WST02-DR-1397 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1398 | NA | 131242-WST02-DR-1398 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1399 | NA | 131242-WST02-DR-1399 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1400 | NA | 131242-WST02-DR-1400 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN- Biomass separator footing detail" | 2024-10-10 | 2025-12-18 | A | 000000&&000753&&001730 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1401 | NA | 131242-WST02-DR-1401 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1402 | NA | 131242-WST02-DR-1402 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-12-18 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1403 | NA | 131242-WST02-DR-1403 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-12-18 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1404 | NA | 131242-WST02-DR-1404 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1405 | NA | 131242-WST02-DR-1405 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1406 | NA | 131242-WST02-DR-1406 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1407 | NA | 131242-WST02-DR-1407 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1408 | NA | 131242-WST02-DR-1408 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1409 | NA | 131242-WST02-DR-1409 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1410 | NA | 131242-WST02-DR-1410 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1411 | NA | 131242-WST02-DR-1411 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1412 | NA | 131242-WST02-DR-1412 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1413 | NA | 131242-WST02-DR-1413 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1414 | NA | 131242-WST02-DR-1414 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1415 | NA | 131242-WST02-DR-1415 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1416 | NA | 131242-WST02-DR-1416 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1417 | NA | 131242-WST02-DR-1417 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1418 | NA | 131242-WST02-DR-1418 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1419 | NA | 131242-WST02-DR-1419 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1420 | NA | 131242-WST02-DR-1420 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1421 | NA | 131242-WST02-DR-1421 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1422 | NA | 131242-WST02-DR-1422 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1423 | NA | 131242-WST02-DR-1423 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1424 | NA | 131242-WST02-DR-1424 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1425 | NA | 131242-WST02-DR-1425 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1426 | NA | 131242-WST02-DR-1426 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1427 | NA | 131242-WST02-DR-1427 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1428 | NA | 131242-WST02-DR-1428 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1429 | NA | 131242-WST02-DR-1429 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1430 | NA | 131242-WST02-DR-1430 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1431 | NA | 131242-WST02-DR-1431 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1432 | NA | 131242-WST02-DR-1432 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1433 | NA | 131242-WST02-DR-1433 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1434 | NA | 131242-WST02-DR-1434 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1435 | NA | 131242-WST02-DR-1435 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1436 | NA | 131242-WST02-DR-1436 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1437 | NA | 131242-WST02-DR-1437 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1438 | NA | 131242-WST02-DR-1438 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1439 | NA | 131242-WST02-DR-1439 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1440 | NA | 131242-WST02-DR-1440 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1441 | NA | 131242-WST02-DR-1441 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1442 | NA | 131242-WST02-DR-1442 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1443 | NA | 131242-WST02-DR-1443 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1444 | NA | 131242-WST02-DR-1444 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1445 | NA | 131242-WST02-DR-1445 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1446 | NA | 131242-WST02-DR-1446 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1447 | NA | 131242-WST02-DR-1447 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1448 | NA | 131242-WST02-DR-1448 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1449 | NA | 131242-WST02-DR-1449 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1450 | NA | 131242-WST02-DR-1450 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1451 | NA | 131242-WST02-DR-1451 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1452 | NA | 131242-WST02-DR-1452 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1453 | NA | 131242-WST02-DR-1453 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1454 | NA | 131242-WST02-DR-1454 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1455 | NA | 131242-WST02-DR-1455 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1456 | NA | 131242-WST02-DR-1456 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1457 | NA | 131242-WST02-DR-1457 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1458 | NA | 131242-WST02-DR-1458 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1459 | NA | 131242-WST02-DR-1459 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1460 | NA | 131242-WST02-DR-1460 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1461 | NA | 131242-WST02-DR-1461 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1462 | NA | 131242-WST02-DR-1462 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1463 | NA | 131242-WST02-DR-1463 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1464 | NA | 131242-WST02-DR-1464 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1465 | NA | 131242-WST02-DR-1465 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1466 | NA | 131242-WST02-DR-1466 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1467 | NA | 131242-WST02-DR-1467 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1468 | NA | 131242-WST02-DR-1468 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1469 | NA | 131242-WST02-DR-1469 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1470 | NA | 131242-WST02-DR-1470 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1471 | NA | 131242-WST02-DR-1471 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1472 | NA | 131242-WST02-DR-1472 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1473 | NA | 131242-WST02-DR-1473 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1474 | NA | 131242-WST02-DR-1474 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1475 | NA | 131242-WST02-DR-1475 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1476 | NA | 131242-WST02-DR-1476 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1477 | NA | 131242-WST02-DR-1477 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1478 | NA | 131242-WST02-DR-1478 | 2025-03-21 |  | NA | 2025-04-18 | 2025-07-10 | 56 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-1351 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1352 | NA | 131242-WST02-DR-1352 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1353 | NA | 131242-WST02-DR-1353 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1354 | NA | 131242-WST02-DR-1354 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1355 | NA | 131242-WST02-DR-1355 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1356 | NA | 131242-WST02-DR-1356 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1357 | NA | 131242-WST02-DR-1357 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1358 | NA | 131242-WST02-DR-1358 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1359 | NA | 131242-WST02-DR-1359 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1360 | NA | 131242-WST02-DR-1360 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1361 | NA | 131242-WST02-DR-1361 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1362 | NA | 131242-WST02-DR-1362 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1363 | NA | 131242-WST02-DR-1363 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1364 | NA | 131242-WST02-DR-1364 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1365 | NA | 131242-WST02-DR-1365 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1366 | NA | 131242-WST02-DR-1366 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1367 | NA | 131242-WST02-DR-1367 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1368 | NA | 131242-WST02-DR-1368 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1369 | NA | 131242-WST02-DR-1369 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1370 | NA | 131242-WST02-DR-1370 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1371 | NA | 131242-WST02-DR-1371 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1372 | NA | 131242-WST02-DR-1372 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1373 | NA | 131242-WST02-DR-1373 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1374 | NA | 131242-WST02-DR-1374 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1375 | NA | 131242-WST02-DR-1375 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1376 | NA | 131242-WST02-DR-1376 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1377 | NA | 131242-WST02-DR-1377 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1378 | NA | 131242-WST02-DR-1378 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1379 | NA | 131242-WST02-DR-1379 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1380 | NA | 131242-WST02-DR-1380 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1381 | NA | 131242-WST02-DR-1381 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1382 | NA | 131242-WST02-DR-1382 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1383 | NA | 131242-WST02-DR-1383 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1384 | NA | 131242-WST02-DR-1384 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1385 | NA | 131242-WST02-DR-1385 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1386 | NA | 131242-WST02-DR-1386 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1387 | NA | 131242-WST02-DR-1387 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1388 | NA | 131242-WST02-DR-1388 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1389 | NA | 131242-WST02-DR-1389 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1390 | NA | 131242-WST02-DR-1390 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1391 | NA | 131242-WST02-DR-1391 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1392 | NA | 131242-WST02-DR-1392 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1393 | NA | 131242-WST02-DR-1393 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1394 | NA | 131242-WST02-DR-1394 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1395 | NA | 131242-WST02-DR-1395 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1396 | NA | 131242-WST02-DR-1396 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1397 | NA | 131242-WST02-DR-1397 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1398 | NA | 131242-WST02-DR-1398 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1399 | NA | 131242-WST02-DR-1399 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1400 | NA | 131242-WST02-DR-1400 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN- Biomass separator footing detail" | 2024-10-10 | 2025-12-18 | A | 000000&&000753&&001730 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1401 | NA | 131242-WST02-DR-1401 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1402 | NA | 131242-WST02-DR-1402 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-12-18 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1403 | NA | 131242-WST02-DR-1403 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-12-18 | NA | 000000 | 2025-03-21, 2025-07-29, 2025-12-18 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1404 | NA | 131242-WST02-DR-1404 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1405 | NA | 131242-WST02-DR-1405 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1406 | NA | 131242-WST02-DR-1406 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1407 | NA | 131242-WST02-DR-1407 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1408 | NA | 131242-WST02-DR-1408 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1409 | NA | 131242-WST02-DR-1409 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1410 | NA | 131242-WST02-DR-1410 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1411 | NA | 131242-WST02-DR-1411 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1412 | NA | 131242-WST02-DR-1412 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1413 | NA | 131242-WST02-DR-1413 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1414 | NA | 131242-WST02-DR-1414 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1415 | NA | 131242-WST02-DR-1415 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1416 | NA | 131242-WST02-DR-1416 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1417 | NA | 131242-WST02-DR-1417 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1418 | NA | 131242-WST02-DR-1418 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1419 | NA | 131242-WST02-DR-1419 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1420 | NA | 131242-WST02-DR-1420 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1421 | NA | 131242-WST02-DR-1421 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1422 | NA | 131242-WST02-DR-1422 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1423 | NA | 131242-WST02-DR-1423 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1424 | NA | 131242-WST02-DR-1424 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1425 | NA | 131242-WST02-DR-1425 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1426 | NA | 131242-WST02-DR-1426 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1427 | NA | 131242-WST02-DR-1427 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1428 | NA | 131242-WST02-DR-1428 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1429 | NA | 131242-WST02-DR-1429 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1430 | NA | 131242-WST02-DR-1430 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1431 | NA | 131242-WST02-DR-1431 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1432 | NA | 131242-WST02-DR-1432 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1433 | NA | 131242-WST02-DR-1433 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1434 | NA | 131242-WST02-DR-1434 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1435 | NA | 131242-WST02-DR-1435 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1436 | NA | 131242-WST02-DR-1436 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1437 | NA | 131242-WST02-DR-1437 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1438 | NA | 131242-WST02-DR-1438 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1439 | NA | 131242-WST02-DR-1439 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1440 | NA | 131242-WST02-DR-1440 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1441 | NA | 131242-WST02-DR-1441 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1442 | NA | 131242-WST02-DR-1442 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1443 | NA | 131242-WST02-DR-1443 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1444 | NA | 131242-WST02-DR-1444 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1445 | NA | 131242-WST02-DR-1445 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1446 | NA | 131242-WST02-DR-1446 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1447 | NA | 131242-WST02-DR-1447 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1448 | NA | 131242-WST02-DR-1448 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1449 | NA | 131242-WST02-DR-1449 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1450 | NA | 131242-WST02-DR-1450 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1451 | NA | 131242-WST02-DR-1451 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1452 | NA | 131242-WST02-DR-1452 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1453 | NA | 131242-WST02-DR-1453 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1454 | NA | 131242-WST02-DR-1454 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1455 | NA | 131242-WST02-DR-1455 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1456 | NA | 131242-WST02-DR-1456 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1457 | NA | 131242-WST02-DR-1457 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1458 | NA | 131242-WST02-DR-1458 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1459 | NA | 131242-WST02-DR-1459 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1460 | NA | 131242-WST02-DR-1460 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1461 | NA | 131242-WST02-DR-1461 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1462 | NA | 131242-WST02-DR-1462 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1463 | NA | 131242-WST02-DR-1463 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1464 | NA | 131242-WST02-DR-1464 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1465 | NA | 131242-WST02-DR-1465 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1466 | NA | 131242-WST02-DR-1466 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1467 | NA | 131242-WST02-DR-1467 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1468 | NA | 131242-WST02-DR-1468 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1469 | NA | 131242-WST02-DR-1469 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1470 | NA | 131242-WST02-DR-1470 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1471 | NA | 131242-WST02-DR-1471 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1472 | NA | 131242-WST02-DR-1472 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1473 | NA | 131242-WST02-DR-1473 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1474 | NA | 131242-WST02-DR-1474 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1475 | NA | 131242-WST02-DR-1475 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1476 | NA | 131242-WST02-DR-1476 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1477 | NA | 131242-WST02-DR-1477 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1478 | NA | 131242-WST02-DR-1478 | 2025-07-29 |  | NA | 2025-08-18 | 2025-12-11 | 82 | Not Approved | YES | 2025-12-31 | NO | Overdue | 18 |  |  | NA |  | 2025-03-21 | 2025-07-29 | NA | 000000 | 2025-03-21, 2025-07-29 | NA | 2 | PEN | NAP | NAP
001149 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | B | 1397 | 0 | 131242-WSW41-DS-1397 | 2025-03-21 | Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance) | Approved | 2025-04-18 | 2025-05-25 | 22 | Approved | NO |  | YES |  |  |  |  | NA | "Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance)" | 2025-03-21 | 2025-03-21 | 0 | 001149 | 2025-03-21 | 00 | 1 | PEN | APP | APP
001150 | 00 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 0 | 131242-WSD11-RT-0002 | 2025-03-24 | Report of Project Safety Review for THP Trains Installation | Approved with Comments | 2025-04-21 | 2025-05-13 | 14 | Approved with Comments | YES | 2025-06-02 | YES | Resubmitted |  |  |  | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
001150 | 01 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 1 | 131242-WSD11-RT-0002 | 2025-06-18 | Report of Project Safety Review for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-08 | 2025-07-04 |  | Approved with Comments | YES | 2025-07-24 | YES | Resubmitted |  |  |  | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
001150 | 02 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 2 | 131242-WSD11-RT-0002 | 2025-09-03 | Report of Project Safety Review for THP Trains Installation | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-10-14 | 15 | Approved with Comments | YES | 2025-11-03 | NO | Overdue | 60 |  |  | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | PEN | AWC | AWC
001151 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0059 | 0 | 131242-WSW41-QA-0059 | 2025-03-24 | FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch) | NA | 2025-04-21 | 2025-09-02 | 94 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" && "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-03-24 | 2025-12-18 | 1 | 001151&&001799&&001860 | 2025-03-24, 2025-10-29, 2025-11-24, 2025-12-18 | 00, 01 | 4 | PEN | AWC | AWC
001152 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0028 | 0 | 131242-WSW41-SP-0028 | 2025-03-24 | Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) | Approved | 2025-04-21 | 2025-05-09 | 13 | Approved | NO |  | YES |  |  |  |  | NA | "Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) " | 2025-03-24 | 2025-03-24 | 0 | 001152 | 2025-03-24 | 00 | 1 | PEN | APP | APP
001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | CL | S | 0003 | 0 | 131242-WST02-CL-0003 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | 5 | Approved | NO |  | YES |  |  |  |  | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | PEN | APP | APP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | S | 5603 | NA | 131242-WST02-DR-5603 | 2025-03-24 |  | NA | 2025-04-21 | 2025-04-28 | 5 | Approved | NO |  | YES |  |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-24 | 2025-07-24 | NA | 000000 | 2025-03-24, 2025-07-24 | 00, NA | 2 | PEN | APP | APP
001154 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 0 | 131242-WST02-VI-0001 | 2025-03-24 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-04-21 | 2025-05-06 | 10 | Not Approved | YES | 2025-05-26 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
001154 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 1 | 131242-WST02-VI-0001 | 2025-06-04 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-06-24 | 2025-07-08 | 10 | Not Approved | YES | 2025-07-28 | YES | Resubmitted |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | NAP | NAP
001154 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 2 | 131242-WST02-VI-0001 | 2025-08-12 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-09-01 | 2026-01-05 | 88 | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | PEN | APP | APP
001155 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 0 | 131242-WST02-CD-0012 | 2025-03-24 | SSN -RIO PANEL 0203- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-21 | 2025-04-27 | 4 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0203- I/O List " | 2023-11-10 | 2025-06-25 | 1 | 000000&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | PEN | NAP | NAP
001155 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 1 | 131242-WST02-CD-0012 | 2025-06-25 | SSN -RIO PANEL 0203- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-02 | 35 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | "SITE OFFICE LAYOUT (Rev1)" && "SSN -RIO PANEL 0203- I/O List " | 2023-11-10 | 2025-06-25 | 1 | 000000&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | PEN | AWC | AWC
001156 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | A | 0005 | 0 | 131242-WSW41-MS-0005 | 2025-03-24 | MSRA for Waterproofing Works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-21 | 2025-04-15 |  | Not Approved | YES | 2025-05-05 | NO | Overdue | 190 |  |  | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | PEN | NAP | NAP
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | A | 131242-WST02-DR-7200 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2026-02-03 | B | 000000&&001157 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7201 | NA | 131242-WST02-DR-7201 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN UPSDB SLD " | 2025-03-25 | 2026-02-03 | A | 000000&&001190 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7202 | NA | 131242-WST02-DR-7202 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7203 | NA | 131242-WST02-DR-7203 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7204 | NA | 131242-WST02-DR-7204 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7205 | NA | 131242-WST02-DR-7205 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7206 | NA | 131242-WST02-DR-7206 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7207 | NA | 131242-WST02-DR-7207 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7208 | NA | 131242-WST02-DR-7208 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7209 | NA | 131242-WST02-DR-7209 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "SSN PMS Network Architecture Drawings" | 2025-03-10 | 2025-08-07 | 1 | 000000&&001112 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7220 | NA | 131242-WST02-DR-7220 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7221 | NA | 131242-WST02-DR-7221 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7222 | NA | 131242-WST02-DR-7222 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7223 | NA | 131242-WST02-DR-7223 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7224 | NA | 131242-WST02-DR-7224 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7225 | NA | 131242-WST02-DR-7225 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7226 | NA | 131242-WST02-DR-7226 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7227 | NA | 131242-WST02-DR-7227 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7228 | NA | 131242-WST02-DR-7228 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7229 | NA | 131242-WST02-DR-7229 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3066 | NA | 131242-WST02-DR-3066 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3067 | NA | 131242-WST02-DR-3067 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3068 | NA | 131242-WST02-DR-3068 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3069 | NA | 131242-WST02-DR-3069 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3070 | NA | 131242-WST02-DR-3070 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3071 | NA | 131242-WST02-DR-3071 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3072 | NA | 131242-WST02-DR-3072 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3073 | NA | 131242-WST02-DR-3073 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3074 | NA | 131242-WST02-DR-3074 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3075 | NA | 131242-WST02-DR-3075 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3076 | NA | 131242-WST02-DR-3076 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3077 | NA | 131242-WST02-DR-3077 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3078 | NA | 131242-WST02-DR-3078 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3079 | NA | 131242-WST02-DR-3079 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7148 | NA | 131242-WST02-DR-7148 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7149 | NA | 131242-WST02-DR-7149 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-03-28, 2025-07-21 | NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7150 | NA | 131242-WST02-DR-7150 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7151 | NA | 131242-WST02-DR-7151 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7152 | NA | 131242-WST02-DR-7152 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7153 | NA | 131242-WST02-DR-7153 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7154 | NA | 131242-WST02-DR-7154 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7155 | NA | 131242-WST02-DR-7155 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-20 | 18 | Not Approved | YES | 2025-06-09 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | NAP | NAP
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | B | 131242-WST02-DR-7200 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-04 | 19 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2026-02-03 | B | 000000&&001157 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7201 | NA | 131242-WST02-DR-7201 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN UPSDB SLD " | 2025-03-25 | 2026-02-03 | A | 000000&&001190 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7202 | NA | 131242-WST02-DR-7202 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7203 | NA | 131242-WST02-DR-7203 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7204 | NA | 131242-WST02-DR-7204 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7205 | NA | 131242-WST02-DR-7205 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7206 | NA | 131242-WST02-DR-7206 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7207 | NA | 131242-WST02-DR-7207 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7208 | NA | 131242-WST02-DR-7208 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-04-03, 2025-07-21 | NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7209 | NA | 131242-WST02-DR-7209 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "SSN PMS Network Architecture Drawings" | 2025-03-10 | 2025-08-07 | 1 | 000000&&001112 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7220 | NA | 131242-WST02-DR-7220 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7221 | NA | 131242-WST02-DR-7221 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7222 | NA | 131242-WST02-DR-7222 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7223 | NA | 131242-WST02-DR-7223 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7224 | NA | 131242-WST02-DR-7224 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7225 | NA | 131242-WST02-DR-7225 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7226 | NA | 131242-WST02-DR-7226 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7227 | NA | 131242-WST02-DR-7227 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-02-03 | NA | 000000 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, NA | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7228 | NA | 131242-WST02-DR-7228 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EI | 7229 | NA | 131242-WST02-DR-7229 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3066 | NA | 131242-WST02-DR-3066 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3067 | NA | 131242-WST02-DR-3067 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3068 | NA | 131242-WST02-DR-3068 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3069 | NA | 131242-WST02-DR-3069 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3070 | NA | 131242-WST02-DR-3070 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3071 | NA | 131242-WST02-DR-3071 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3072 | NA | 131242-WST02-DR-3072 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3073 | NA | 131242-WST02-DR-3073 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3074 | NA | 131242-WST02-DR-3074 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3075 | NA | 131242-WST02-DR-3075 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3076 | NA | 131242-WST02-DR-3076 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3077 | NA | 131242-WST02-DR-3077 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3078 | NA | 131242-WST02-DR-3078 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 3079 | NA | 131242-WST02-DR-3079 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7148 | NA | 131242-WST02-DR-7148 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2024-12-02 | 2025-07-21 | NA | 000000 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7149 | NA | 131242-WST02-DR-7149 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-03-28, 2025-07-21 | NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7150 | NA | 131242-WST02-DR-7150 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7151 | NA | 131242-WST02-DR-7151 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7152 | NA | 131242-WST02-DR-7152 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7153 | NA | 131242-WST02-DR-7153 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7154 | NA | 131242-WST02-DR-7154 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | EP | 7155 | NA | 131242-WST02-DR-7155 | 2025-07-21 |  | NA | 2025-08-18 | 2025-09-04 | 13 | Approved with Comments | YES | 2025-09-24 | NO | Overdue | 88 |  |  | NA |  | 2025-03-25 | 2025-07-21 | NA | 000000 | 2025-03-25, 2025-07-21 | NA | 2 | PEN | AWC | AWC
001158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0010 | 0 | 131242-WST02-RT-0010 | 2025-03-25 | SSN Protection Coordination Study Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-22 | 2025-05-27 | 23 | Approved with Comments | YES | 2025-06-16 | NO | Overdue | 160 |  |  | NA | "SSN Protection Coordination Study Report" | 2025-03-25 | 2025-03-25 | 0 | 001158 | 2025-03-25 | 00 | 1 | PEN | AWC | AWC
001159 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0005 | 0 | 131242-WSD11-RT-0005 | 2025-03-25 | THP Protection Coordination Study Report | : Rev 0: Approved with comments. To revise and resubmit | 2025-04-22 | 2025-05-27 | 23 | Approved with Comments | YES | 2025-06-16 | NO | Overdue | 160 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP Protection Coordination Study Report" | 2025-03-25 | 2025-07-01 | 0 | 000000&&001159 | 2025-03-25, 2025-07-01 | 00 | 2 | PEN | AWC | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7201 | A | 131242-WSD11-DR-7201 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 15 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "THP UPS DB SLD Drawing " | 2025-03-25 | 2026-01-27 | A | 000000&&001160 | 2025-03-25, 2025-10-22, 2026-01-27 | 00 | 3 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | I | 7202 | NA | 131242-WSD11-DR-7202 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-15 | 15 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-01-27 | NA | 000000 | 2025-03-25, 2026-01-27 | 00, NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | I | 7203 | NA | 131242-WSD11-DR-7203 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-15 | 15 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA |  | 2025-03-25 | 2025-03-25 | NA | 000000 | 2025-03-25 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | I | 7204 | NA | 131242-WSD11-DR-7204 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-15 | 15 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA |  | 2025-03-25 | 2025-03-25 | NA | 000000 | 2025-03-25 | NA | 1 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WSD11 | DR | I | 7205 | NA | 131242-WSD11-DR-7205 | 2025-03-25 |  | NA | 2025-04-22 | 2025-05-15 | 15 | Approved with Comments | YES | 2025-06-04 | NO | Overdue | 168 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-25 | 2026-01-27 | NA | 000000 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, NA | 3 | PEN | AWC | AWC
001161 | 00 | Charles | CSA | NA | 131242 | WSW41 | MS | A | 0001 | 0 | 131242-WSW41-MS-0001 | 2025-03-25 | MSRA and SWP for MEICA OPENING on Block-wall | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 |  | Approved with Comments | YES | 2025-05-05 | NO | Overdue | 190 |  |  | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | PEN | AWC | AWC
001162 | 00 | N.Kumar | CSA | NA | 131242 | WSW41 | MS | C | 0027 | 0 | 131242-WSW41-MS-0027 | 2025-03-25 | Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 |  | Not Approved | YES | 2025-05-05 | NO | Overdue | 190 |  |  | NA | "Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) " | 2025-03-25 | 2025-03-25 | 0 | 001162 | 2025-03-25 | 00 | 1 | PEN | NAP | NAP
001163 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0008 | 0 | 131242-WSW41-PO-0008 | 2025-03-25 | Unpriced PO for Cable Raceway (Jiangsu HDMann) | Rev 0: For information. | 2025-04-22 | 2025-05-06 | 9 | For Information | NO |  | YES |  |  |  |  | NA | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" && "Unpriced PO for Centrifugal Pump (KSB)" && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2024-08-01 | 2025-08-01 | 0 | 000608&&001163&&001507 | 2024-08-01, 2025-03-25, 2025-08-01 | 00, 01 | 3 | PEN | INF | INF
001164 | 00 | Aaron | CSA | NA | 131242 | WSW41 | VI | A | 0005 | 0 | 131242-WSW41-VI-0005 | 2025-03-25 | Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd) | R0: Approved | 2025-04-22 | 2025-04-15 |  | Approved | NO |  | YES |  |  |  |  | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | PEN | APP | APP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | A | 131242-WST02-DR-3001 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3002 | NA | 131242-WST02-DR-3002 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3003 | NA | 131242-WST02-DR-3003 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3004 | NA | 131242-WST02-DR-3004 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3005 | NA | 131242-WST02-DR-3005 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3006 | NA | 131242-WST02-DR-3006 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3007 | NA | 131242-WST02-DR-3007 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3008 | NA | 131242-WST02-DR-3008 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3009 | NA | 131242-WST02-DR-3009 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3010 | NA | 131242-WST02-DR-3010 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3011 | NA | 131242-WST02-DR-3011 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3012 | NA | 131242-WST02-DR-3012 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3013 | NA | 131242-WST02-DR-3013 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3014 | NA | 131242-WST02-DR-3014 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3015 | NA | 131242-WST02-DR-3015 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3016 | NA | 131242-WST02-DR-3016 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3017 | NA | 131242-WST02-DR-3017 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3018 | NA | 131242-WST02-DR-3018 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3019 | NA | 131242-WST02-DR-3019 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3020 | NA | 131242-WST02-DR-3020 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3021 | NA | 131242-WST02-DR-3021 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3022 | NA | 131242-WST02-DR-3022 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3023 | NA | 131242-WST02-DR-3023 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3024 | NA | 131242-WST02-DR-3024 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-18 |  | Not Approved | YES | 2025-05-08 | YES | Resubmitted |  |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | NAP | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | B | 131242-WST02-DR-3001 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-12-09 | 62 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | 2026-02-03 | B | 000000&&001165&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01 | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3002 | NA | 131242-WST02-DR-3002 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | 2026-02-09 | E | 000000&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3003 | NA | 131242-WST02-DR-3003 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3004 | NA | 131242-WST02-DR-3004 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2026-02-09 | A_To withdraw | 000000&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3005 | NA | 131242-WST02-DR-3005 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-08-01 | 2026-02-09 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3006 | NA | 131242-WST02-DR-3006 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-01 | 2026-02-03 | A | 000000&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3007 | NA | 131242-WST02-DR-3007 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-08-01 | 2025-08-22 | NA | 000000 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3008 | NA | 131242-WST02-DR-3008 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | A | 000000&&000866 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3009 | NA | 131242-WST02-DR-3009 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2025-08-22 | NA | 000000 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 10 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3010 | NA | 131242-WST02-DR-3010 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-11-21 | 2026-02-03 | A_To withdraw | 000000&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3011 | NA | 131242-WST02-DR-3011 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | 2026-02-03 | A | 000000&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3012 | NA | 131242-WST02-DR-3012 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3013 | NA | 131242-WST02-DR-3013 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3014 | NA | 131242-WST02-DR-3014 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3015 | NA | 131242-WST02-DR-3015 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | 2026-02-03 | A_To withdraw | 000000&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3016 | NA | 131242-WST02-DR-3016 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-03 | B | 000000&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3017 | NA | 131242-WST02-DR-3017 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-12-02 | 2025-08-22 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, NA | 7 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3018 | NA | 131242-WST02-DR-3018 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3019 | NA | 131242-WST02-DR-3019 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2025-10-31 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3020 | NA | 131242-WST02-DR-3020 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | 2026-02-04 | A | 000000&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, NA | 12 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3021 | NA | 131242-WST02-DR-3021 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | 2026-02-04 | B | 000000&&001809 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, NA | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3022 | NA | 131242-WST02-DR-3022 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3023 | NA | 131242-WST02-DR-3023 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-02 | 2026-02-04 | NA | 000000 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IC | 3024 | NA | 131242-WST02-DR-3024 | 2025-08-22 |  | NA | 2025-09-19 | 2025-12-09 | 56 | Not Approved | YES | 2025-12-29 | NO | Overdue | 20 |  |  | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SITE OFFICE LAYOUT (Rev1)" | 2024-12-03 | 2025-10-31 | C | 000000&&000870 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, NA | 7 | PEN | NAP | NAP
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | A | 131242-WST02-DR-2101 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2102 | NA | 131242-WST02-DR-2102 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2103 | NA | 131242-WST02-DR-2103 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2104 | NA | 131242-WST02-DR-2104 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2105 | NA | 131242-WST02-DR-2105 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2106 | NA | 131242-WST02-DR-2106 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2107 | NA | 131242-WST02-DR-2107 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2108 | NA | 131242-WST02-DR-2108 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2109 | NA | 131242-WST02-DR-2109 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2110 | NA | 131242-WST02-DR-2110 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2111 | NA | 131242-WST02-DR-2111 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2112 | NA | 131242-WST02-DR-2112 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2113 | NA | 131242-WST02-DR-2113 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2114 | NA | 131242-WST02-DR-2114 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2115 | NA | 131242-WST02-DR-2115 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2116 | NA | 131242-WST02-DR-2116 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2117 | NA | 131242-WST02-DR-2117 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2118 | NA | 131242-WST02-DR-2118 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2119 | NA | 131242-WST02-DR-2119 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-03-25 | NA | 000000 | 2025-03-25 | NA | 1 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2120 | NA | 131242-WST02-DR-2120 | 2025-03-25 |  | NA | 2025-04-22 | 2025-04-27 | 3 | Not Approved | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA |  | 2025-03-25 | 2025-03-25 | NA | 000000 | 2025-03-25 | NA | 1 | PEN | NAP | NAP
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | D | 131242-WST02-DR-2101 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-02 | 2026-01-27 | 17 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2102 | NA | 131242-WST02-DR-2102 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2103 | NA | 131242-WST02-DR-2103 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2104 | NA | 131242-WST02-DR-2104 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2105 | NA | 131242-WST02-DR-2105 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2106 | NA | 131242-WST02-DR-2106 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2107 | NA | 131242-WST02-DR-2107 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2108 | NA | 131242-WST02-DR-2108 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2109 | NA | 131242-WST02-DR-2109 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2110 | NA | 131242-WST02-DR-2110 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2111 | NA | 131242-WST02-DR-2111 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2112 | NA | 131242-WST02-DR-2112 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2113 | NA | 131242-WST02-DR-2113 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2114 | NA | 131242-WST02-DR-2114 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2115 | NA | 131242-WST02-DR-2115 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2116 | NA | 131242-WST02-DR-2116 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2117 | NA | 131242-WST02-DR-2117 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 2118 | NA | 131242-WST02-DR-2118 | 2025-12-15 |  | NA | 2026-01-12 | 2026-01-27 | 11 | Approved with Comments | YES | 2026-02-16 | NO | Overdue | -17 |  |  | NA |  | 2025-03-25 | 2025-12-15 | NA | 000000 | 2025-03-25, 2025-12-15 | NA | 2 | PEN | AWC | AWC
001167 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 0 | 131242-WSD11-DS-0006 | 2025-03-25 | Datasheet for Electromagnetic Flow Meter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-07-10 | 55 | Not Approved | YES | 2025-07-30 | YES | Resubmitted |  |  |  | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | PEN | NAP | NAP
001167 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 1 | 131242-WSD11-DS-0006 | 2025-10-16 | Datasheet for Electromagnetic Flow Meter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-27 | 16 | Approved with Comments | YES | 2025-12-17 | NO | Overdue | 28 |  |  | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | PEN | AWC | AWC
001168 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0006 | 0 | 131242-WST02-VI-0006 | 2025-03-26 | Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd. | Approved | 2025-04-23 | 2025-04-11 |  | Approved | NO |  | YES |  |  |  |  | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | PEN | APP | APP
001169 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0058 | 0 | 131242-WSW41-LT-0058 | 2025-03-26 | Consent to Potential Acquisition of CES Construction by OKH | For Information | 2025-04-23 | 2025-04-05 |  | For Information | NO |  | YES |  |  |  |  | NA | "Consent to Potential Acquisition of CES Construction by OKH " | 2025-03-26 | 2025-03-26 | 0 | 001169 | 2025-03-26 | 00 | 1 | PEN | INF | INF
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 0 | 131242-WST02-CL-5701 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | YES | Resubmitted |  |  |  | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | CL | P | 5702 | NA | 131242-WST02-CL-5702 | 2025-03-27 |  | NA | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | CL | P | 5703 | NA | 131242-WST02-CL-5703 | 2025-03-27 |  | NA | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5701 | NA | 131242-WST02-DS-5701 | 2025-03-27 |  | NA | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5702 | NA | 131242-WST02-DS-5702 | 2025-03-27 |  | NA | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5703 | NA | 131242-WST02-DS-5703 | 2025-03-27 |  | NA | 2025-04-24 | 2025-04-27 | 1 | Approved with Comments | YES | 2025-05-15 | NO | Overdue | 182 |  |  | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | AWC | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 1 | 131242-WST02-CL-5701 | 2025-07-07 | SSN FCV Calculation and Datasheet | NA | 2025-07-25 |  | 128 | Awaiting S.O.'s response | [7 empty] | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | CL | P | 5702 | NA | 131242-WST02-CL-5702 | 2025-07-07 |  | NA | 2025-08-04 | 2025-04-27 | 122 | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | CL | P | 5703 | NA | 131242-WST02-CL-5703 | 2025-07-07 |  | NA | 2025-08-04 | 2025-04-27 | 122 | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5701 | NA | 131242-WST02-DS-5701 | 2025-07-07 |  | NA | 2025-08-04 | 2025-04-27 | 122 | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5702 | NA | 131242-WST02-DS-5702 | 2025-07-07 |  | NA | 2025-08-04 | 2025-04-27 | 122 | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DS | M | 5703 | NA | 131242-WST02-DS-5703 | 2025-07-07 |  | NA | 2025-08-04 | 2025-04-27 | 122 | Awaiting S.O.'s response | [7 empty] | NA |  | 2025-03-27 | 2025-07-07 | NA | 000000 | 2025-03-27, 2025-07-07 | NA | 2 | PEN | PEN | PEN
001171 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 0 | 131242-WSD11-DS-0007 | 2025-03-27 | Datasheet for Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 55 | Not Approved | YES | 2025-08-01 | YES | Resubmitted |  |  |  | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | NAP | NAP
001171 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 1 | 131242-WSD11-DS-0007 | 2025-10-16 | Datasheet for Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-05 |  | Approved with Comments | YES | 2025-11-25 | NO | Overdue | 44 |  |  | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | PEN | AWC | AWC
001172 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 0 | 131242-WST02-DS-5391 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | 17 | Approved with Comments | YES | 2025-06-10 | YES | Resubmitted |  |  |  | NA | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | 2025-10-18 | 1 | 001172 | 2025-03-27, 2025-10-18 | 00, 01 | 2 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5391 | NA | 131242-WST02-DR-5391 | 2025-03-27 |  | NA | 2025-04-24 | 2025-05-21 | 17 | Approved with Comments | YES | 2025-06-10 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-27 | 2025-10-18 | NA | 000000 | 2025-03-27, 2025-08-27, 2025-10-18 | 00, NA | 3 | PEN | AWC | AWC
001172 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 1 | 131242-WST02-DS-5391 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-06 |  | 55 | Awaiting S.O.'s response | [7 empty] | NA | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | 2025-10-18 | 1 | 001172 | 2025-03-27, 2025-10-18 | 00, 01 | 2 | PEN | PEN | PEN
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | M | 5391 | NA | 131242-WST02-DR-5391 | 2025-10-18 |  | NA | 2025-11-14 | 2025-05-21 | 49 | Awaiting S.O.'s response | [7 empty] | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-27 | 2025-10-18 | NA | 000000 | 2025-03-27, 2025-08-27, 2025-10-18 | 00, NA | 3 | PEN | PEN | PEN
001173 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 0 | 131242-WSD11-DS-0011 | 2025-03-27 | Datasheet for Temperature Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 55 | Not Approved | YES | 2025-08-01 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | PEN | NAP | NAP
001173 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1_Superceded | 131242-WSD11-DS-0011 | 2025-10-27 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2025-11-14 | 2025-12-09 | 17 | Not Approved | YES | 2025-12-29 | YES | Resubmitted |  |  |  | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | PEN | NAP | NAP
001173 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1 | 131242-WSD11-DS-0011 | 2026-01-21 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2026-02-10 |  |  | Awaiting S.O.'s response | [7 empty] | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | PEN | PEN | PEN
001174 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-0029 | 2025-03-27 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-24 | 2025-06-17 | 36 | Approved with Comments | YES | 2025-07-07 | YES | Resubmitted |  |  |  | NA | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " && "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-03-27 | 2025-07-11 | 0 | 001174&&001465 | 2025-03-27, 2025-07-10, 2025-07-11 | 00, 01 | 3 | PEN | AWC | AWC
001174 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-0029 | 2025-07-10 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached filed for comments. | 2025-07-30 | 2025-07-17 |  | Approved with Comments | YES | 2025-08-06 | NO | Overdue | 123 |  |  | NA | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " && "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-03-27 | 2025-07-11 | 0 | 001174&&001465 | 2025-03-27, 2025-07-10, 2025-07-11 | 00, 01 | 3 | PEN | AWC | AWC
001175 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0060 | 0 | 131242-WSW41-QA-0060 | 2025-03-27 | FAT Report for Compressor Pipe support in Bio solid building | NA | 2025-04-24 | 2025-09-02 | 91 | Approved with Comments | YES | 2025-09-22 | NO | Overdue | 90 |  |  | NA | " FAT Report for Compressor Pipe support in Bio solid building" && "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" && "Factory Acceptance Test Report for Pressure Switch" | 2025-03-27 | 2026-01-13 | 1 | 001175&&001823&&001861 | 2025-03-27, 2025-11-05, 2025-11-24, 2026-01-13 | 00, 01 | 4 | PEN | AWC | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | A | 131242-WST02-DR-1025 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1026 | NA | 131242-WST02-DR-1026 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2026-02-04 | NA | 000000 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1027 | NA | 131242-WST02-DR-1027 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | 2026-02-04 | A | 000000&&000860 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1028 | NA | 131242-WST02-DR-1028 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1029 | NA | 131242-WST02-DR-1029 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1030 | NA | 131242-WST02-DR-1030 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1031 | NA | 131242-WST02-DR-1031 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1032 | NA | 131242-WST02-DR-1032 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1033 | NA | 131242-WST02-DR-1033 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1034 | NA | 131242-WST02-DR-1034 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1035 | NA | 131242-WST02-DR-1035 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1036 | NA | 131242-WST02-DR-1036 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1037 | NA | 131242-WST02-DR-1037 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1038 | NA | 131242-WST02-DR-1038 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1039 | NA | 131242-WST02-DR-1039 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1040 | NA | 131242-WST02-DR-1040 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1041 | NA | 131242-WST02-DR-1041 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1042 | NA | 131242-WST02-DR-1042 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1043 | NA | 131242-WST02-DR-1043 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1044 | NA | 131242-WST02-DR-1044 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1045 | NA | 131242-WST02-DR-1045 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1046 | NA | 131242-WST02-DR-1046 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-07 | 7 | Not Approved | YES | 2025-05-27 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | NAP | NAP
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-1025 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1026 | NA | 131242-WST02-DR-1026 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2026-02-04 | NA | 000000 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1027 | NA | 131242-WST02-DR-1027 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | 2026-02-04 | A | 000000&&000860 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1028 | NA | 131242-WST02-DR-1028 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1029 | NA | 131242-WST02-DR-1029 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1030 | NA | 131242-WST02-DR-1030 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1031 | NA | 131242-WST02-DR-1031 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1032 | NA | 131242-WST02-DR-1032 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1033 | NA | 131242-WST02-DR-1033 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1034 | NA | 131242-WST02-DR-1034 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1035 | NA | 131242-WST02-DR-1035 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1036 | NA | 131242-WST02-DR-1036 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1037 | NA | 131242-WST02-DR-1037 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1038 | NA | 131242-WST02-DR-1038 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1039 | NA | 131242-WST02-DR-1039 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1040 | NA | 131242-WST02-DR-1040 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1041 | NA | 131242-WST02-DR-1041 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1042 | NA | 131242-WST02-DR-1042 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1043 | NA | 131242-WST02-DR-1043 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1044 | NA | 131242-WST02-DR-1044 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1045 | NA | 131242-WST02-DR-1045 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1046 | NA | 131242-WST02-DR-1046 | 2025-07-11 |  | NA | 2025-07-31 | 2025-10-01 | 44 | Approved with Comments | YES | 2025-10-21 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-1025 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "C4B SSN Drain Hydraulic Calculation" && "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" | 2024-04-09 | 2026-02-24 | A | 000000&&000835&&001176&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, NA | 11 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1026 | NA | 131242-WST02-DR-1026 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-04-09 | 2026-02-04 | NA | 000000 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, NA | 9 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1027 | NA | 131242-WST02-DR-1027 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | 2026-02-04 | A | 000000&&000860 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 8 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1028 | NA | 131242-WST02-DR-1028 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1029 | NA | 131242-WST02-DR-1029 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1030 | NA | 131242-WST02-DR-1030 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, NA | 5 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1031 | NA | 131242-WST02-DR-1031 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1032 | NA | 131242-WST02-DR-1032 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1033 | NA | 131242-WST02-DR-1033 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1034 | NA | 131242-WST02-DR-1034 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-02-04 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, NA | 6 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1035 | NA | 131242-WST02-DR-1035 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1036 | NA | 131242-WST02-DR-1036 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1037 | NA | 131242-WST02-DR-1037 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1038 | NA | 131242-WST02-DR-1038 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1039 | NA | 131242-WST02-DR-1039 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1040 | NA | 131242-WST02-DR-1040 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1041 | NA | 131242-WST02-DR-1041 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1042 | NA | 131242-WST02-DR-1042 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1043 | NA | 131242-WST02-DR-1043 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1044 | NA | 131242-WST02-DR-1044 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1045 | NA | 131242-WST02-DR-1045 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1046 | NA | 131242-WST02-DR-1046 | 2025-11-17 |  | NA | 2025-12-05 | 2025-12-16 | 7 | Approved with Comments | YES | 2026-01-05 | NO | Overdue | 15 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2026-01-28 | NA | 000000 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, NA | 4 | PEN | AWC | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | A | 131242-WST02-DR-1901 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-11-17 | B | 000000&&001177 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1902 | NA | 131242-WST02-DR-1902 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1903 | NA | 131242-WST02-DR-1903 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1904 | NA | 131242-WST02-DR-1904 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1905 | NA | 131242-WST02-DR-1905 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1906 | NA | 131242-WST02-DR-1906 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1907 | NA | 131242-WST02-DR-1907 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1908 | NA | 131242-WST02-DR-1908 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1909 | NA | 131242-WST02-DR-1909 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1910 | NA | 131242-WST02-DR-1910 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1911 | NA | 131242-WST02-DR-1911 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1912 | NA | 131242-WST02-DR-1912 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1913 | NA | 131242-WST02-DR-1913 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1914 | NA | 131242-WST02-DR-1914 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1915 | NA | 131242-WST02-DR-1915 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1916 | NA | 131242-WST02-DR-1916 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1917 | NA | 131242-WST02-DR-1917 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1918 | NA | 131242-WST02-DR-1918 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1919 | NA | 131242-WST02-DR-1919 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1920 | NA | 131242-WST02-DR-1920 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1921 | NA | 131242-WST02-DR-1921 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1922 | NA | 131242-WST02-DR-1922 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1923 | NA | 131242-WST02-DR-1923 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1924 | NA | 131242-WST02-DR-1924 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1925 | NA | 131242-WST02-DR-1925 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1926 | NA | 131242-WST02-DR-1926 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1927 | NA | 131242-WST02-DR-1927 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1928 | NA | 131242-WST02-DR-1928 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1929 | NA | 131242-WST02-DR-1929 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1930 | NA | 131242-WST02-DR-1930 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1931 | NA | 131242-WST02-DR-1931 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1932 | NA | 131242-WST02-DR-1932 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1933 | NA | 131242-WST02-DR-1933 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1934 | NA | 131242-WST02-DR-1934 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1935 | NA | 131242-WST02-DR-1935 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1936 | NA | 131242-WST02-DR-1936 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1937 | NA | 131242-WST02-DR-1937 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1938 | NA | 131242-WST02-DR-1938 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1939 | NA | 131242-WST02-DR-1939 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1940 | NA | 131242-WST02-DR-1940 | 2025-03-28 |  | NA | 2025-04-25 | 2025-05-16 | 13 | Not Approved | YES | 2025-06-05 | YES | Resubmitted |  |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | NAP | NAP
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-1901 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | YES | Resubmitted |  |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" && "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-11-17 | B | 000000&&001177 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1902 | NA | 131242-WST02-DR-1902 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1903 | NA | 131242-WST02-DR-1903 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1904 | NA | 131242-WST02-DR-1904 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1905 | NA | 131242-WST02-DR-1905 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1906 | NA | 131242-WST02-DR-1906 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1907 | NA | 131242-WST02-DR-1907 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1908 | NA | 131242-WST02-DR-1908 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1909 | NA | 131242-WST02-DR-1909 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1910 | NA | 131242-WST02-DR-1910 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1911 | NA | 131242-WST02-DR-1911 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1912 | NA | 131242-WST02-DR-1912 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1913 | NA | 131242-WST02-DR-1913 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1914 | NA | 131242-WST02-DR-1914 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1915 | NA | 131242-WST02-DR-1915 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1916 | NA | 131242-WST02-DR-1916 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, NA | 4 | PEN | AWC | AWC
000000 | NA | NA | NA | NA | 131242 | WST02 | DR | IP | 1917 | NA | 131242-WST02-DR-1917 | 2025-07-10 |  | NA | 2025-07-30 | 2025-09-23 | 39 | Approved with Comments | YES | 2025-10-13 | NO | Overdue | 75 |  |  | NA |  | 2025-03-28 | 2025-11-17 | NA | 000000 | 2025-03-28, 2025-07-10, 2025-11-17 | NA | 3 | PEN | AWC | AWC