## Sheet1
Submission_Session | Submission_Session_Revision | Submitted_By | Department | Transmittal_Number | Project_Code | Facility_Code | Document_Type | Discipline | Document_Sequence_Number | Document_Revision | Document_ID | Submission_Date | Submission_Session_Subject | Review_Comments | Review_Return_Plan_Date | Review_Return_Actual_Date | Duration_of_Review | Review_Status | Resubmission_Required | Resubmission_Plan_Date | Submission_Closed | Resubmission_Overdue_Status | Delay_of_Resubmission | Resubmission_Forecast_Date | Notes | All_Submission_Sessions | First_Submittion_Date | Latest_Submittion_Date | Latest_Revision | Review_Status_Code | Latest_Approval_Status | Count_of_Submissions | Consolidated_Submission_Session_Subject | Latest_Approval_Code
000001 | 00 | Soe Myat | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 0 | 131242-WST00-PP-PM-0001 | 2023-05-15 | Project Quality Plan | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-13 | 2023-12-05 | 146 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000001 | 2023-05-15 | 2024-05-13 | 1 | AWC | Approved with Comments | 2 | "Project Quality Plan" | AWC
000001 | 01 | Radha | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 1 | 131242-WST00-PP-PM-0001 | 2024-05-13 | Project Quality Plan | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-03 | 2024-09-10 | 86 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000001 | 2023-05-15 | 2024-05-13 | 1 | AWC | Approved with Comments | 2 | "Project Quality Plan" | AWC
000002 | 00 | Shena | PMT | NA | 131242 | WST00 | PP | PC | 0001 | 0 | 131242-WST00-PP-PC-0001 | 2023-05-15 | Project Risk Management Plan | Rev 0: Approved with Comments. Refer to comment sheet and resubmit. | 2023-06-13 | 2023-06-14 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-05-15 | 2023-05-15 | 0 | AWC | Approved with Comments | 1 | "Project Risk Management Plan" | AWC
000002 | 01 | Max/Edwin | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 1 | 131242-WSW41-PP-PC-0001 | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-09-25 | 2023-09-13 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-10-30 | 2 | AWC | Approved | 2 | "Project Risk Management Plan" | APP
000002 | 01 | Max/Edwin | PMT | NA | #000002.0_ Reply_2023 08 31 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 08 31-NA-NA-NA-NA | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-10-03 | 2023-09-13 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-09-05 | NA | AWC | Approved with Comments | 1 | "Project Risk Management Plan" | AWC
000002 | 02 | Max | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 2 | 131242-WSW41-PP-PC-0001 | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-20 | 2023-11-07 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-10-30 | 2 | APP | Approved | 2 | "Project Risk Management Plan" | APP
000002 | 02 | Max | PMT | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025-NA-NA-NA-NA | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-28 | 2023-11-07 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-10-30 | 2023-10-30 | NA | APP | Approved | 1 | "Project Risk Management Plan" | APP
000003 | 00 | Heng Peng | BIM | NA | 131242 | WST00 | PP | IM | 0001 | 0 | 131242-WST00-PP-IM-0001 | 2023-05-16 | BIM Execution Plan (BEP) | R0- Not Approved, please refer to comment sheet | 2023-06-14 | 2023-07-03 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-05-16 | 2023-05-16 | 0 | NAP | Not Approved | 1 | "BIM Execution Plan (BEP)" | NAP
000003 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 1 | 131242-WSW41-PP-IM-0001 | 2023-08-21 | BIM Execution Plan (BEP) | R1- Not Approved. Please refer to "Comment Sheet_Submittal-0003-1". | 2023-09-08 | 2023-10-20 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | NAP | Approved | 5 | "BIM Execution Plan (BEP)" | APP
000003 | 02 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 2 | 131242-WSW41-PP-IM-0001 | 2023-12-12 | BIM Execution Plan (BEP) | R2- Not Approved, revise and resubmit. Please refer to "Comment Sheet_Submittal-0003-2". | 2024-01-03 | 2024-03-14 | 67 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | NAP | Approved | 5 | "BIM Execution Plan (BEP)" | APP
000003 | 03 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 3 | 131242-WSW41-PP-IM-0001 | 2024-03-15 | BIM Execution Plan (BEP) | R3- Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet | 2024-04-05 | 2024-03-20 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | AWC | Approved | 5 | "BIM Execution Plan (BEP)" | APP
000003 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 4 | 131242-WSW41-PP-IM-0001 | 2024-06-28 | BIM Execution Plan (BEP) | Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet. | 2024-07-18 | 2024-08-07 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R3_AWC | 000003 | 2023-08-21 | 2024-09-18 | 5 | AWC | Approved | 5 | "BIM Execution Plan (BEP)" | APP
000003 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 5 | 131242-WSW41-PP-IM-0001 | 2024-09-18 | BIM Execution Plan (BEP) | Approved | 2024-10-08 | 2024-10-02 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | APP | Approved | 5 | "BIM Execution Plan (BEP)" | APP
000004 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 0 | 131242-WST00-PP-HS-0001 | 2023-05-16 | Project HSE Plan | Names are not as proposed. Signatory also not as proposed for HSEM. Review and resubmit. | 2023-06-14 | 2023-07-24 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000004 | 2023-05-16 | 2023-09-27 | 1 | NAP | Approved | 2 | "Project HSE Plan" | APP
000004 | 01 | Dharmen | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 1 | 131242-WST00-PP-HS-0001 | 2023-09-27 | Project HSE Plan | Approved from HSE standpoint. | 2023-10-17 | 2023-10-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000004 | 2023-05-16 | 2023-09-27 | 1 | APP | Approved | 2 | "Project HSE Plan" | APP
000005 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 0 | 131242-WST00-PG-PC-0001 | 2023-05-17 | PROGRAMME OF THE WORKS | Rev. 0 - Not Approved, need to re-submit (see comments sheet) | 2023-06-15 | 2023-06-14 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-05-17 | 2023-07-13 | 1 | NAP | Not Approved | 2 | "PROGRAMME OF THE WORKS" | NAP
000005 | 01 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 1 | 131242-WST00-PG-PC-0001 | 2023-07-13 | PROGRAMME OF THE WORKS | Rev. 1 - Not Approved, need to re-submit (see attached comments sheet R1) | 2023-08-02 | 2023-07-31 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-05-17 | 2023-07-13 | 1 | NAP | Not Approved | 2 | "PROGRAMME OF THE WORKS" | NAP
000005 | 02 | Thomas | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 2 | 131242-WSW41-PG-PC-0001 | 2023-09-07 | PROGRAMME OF THE WORKS | Rev. 2 Approved with comments. Need to re-submit (see attached comment sheet) | 2023-09-27 | 2023-09-18 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" | AWC
000005 | 03 | Thomas | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-PM-0003 | 2023-09-26 | PROGRAMME OF THE WORKS | For Information | 2023-10-16 | 2023-10-03 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  | 000040 | 000005&&000040 | 2023-07-06 | 2023-09-26 | 0 | INF | For Information | 2 | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | INF
000005 | 04 | Krishanthy | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 3 | 131242-WSW41-PG-PC-0001 | 2023-10-27 | PROGRAMME OF THE WORKS | Rev. 4 Approved with comments. | 2023-11-17 | 2023-11-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To be resubmitted when there is a major change in the program of works. Thomas checked with S.O. in the meeting on 18 Jan. | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" | AWC
000005 | 05 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 4 | 131242-WSW41-PG-PC-0001 | 2024-10-19 | PROGRAMME OF THE WORKS | Rev. 5. Not-Approved need to re-submit (see attached comment sheet) - new Rebaseline of the Programme Rev.1 need to re-submit with a new Prolog Submittal Number | 2024-11-08 | 2024-11-04 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | NAP | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" | AWC
000005 | 06 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5 | 131242-WSW41-PG-PC-0001 | 2025-03-14 | PROGRAMME OF THE WORKS | Rev. 6 - Approved with comments (need to re-submit - see attached comments sheet rev.1) | 2025-04-03 | 2025-04-15 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" | AWC
000005 | 07 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5.1 | 131242-WSW41-PG-PC-0001 | 2025-04-16 | PROGRAMME OF THE WORKS | Rev. 7 - Approved with comments (No resubmission needed - See attached comments sheet rev.7) | 2025-05-06 | 2025-04-27 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" | AWC
000006 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 0 | 131242-WST00-VI-C-0001 | 2023-05-17 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-15 | 2023-06-12 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000006 | 2023-05-17 | 2023-06-23 | 1 | AWC | Approved | 2 | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" | APP
000006 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 1 | 131242-WST00-VI-C-0001 | 2023-06-23 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Approved | 2023-07-14 | 2023-06-30 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000006 | 2023-05-17 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" | APP
000007 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0002 | 0 | 131242-WST00-PG-PC-0002 | 2023-05-18 | MOBILIZATION PROGRAMME | Rev. 0 - Not Approved need to re-submit Refer Comment sheet) | 2023-06-16 | 2023-06-13 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  | Reply to S.O. Comment Sheet Only | 000007 | 2023-05-18 | 2023-05-18 | 0 | NAP | Not Approved | 1 | "MOBILIZATION PROGRAMME " | NAP
000007 | 01 | Thomas | PCM | NA | Reply to Comment Sheet_#000007 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000007-NA-NA-NA-NA | 2023-09-13 | MOBILIZATION PROGRAMME | Approved | 2023-10-03 | 2023-09-20 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000007 | 2023-09-13 | 2023-09-13 | NA | APP | Approved | 1 | "MOBILIZATION PROGRAMME " | APP
000008 | 00 | Frank/ Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 0 | 131242-WST00-RG-Z-0001 | 2023-05-18 | Engineering Deliverable Lists | Rev 0: Not approved - Revise and Resubmit | 2023-06-16 | 2023-11-21 | 133 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000008 | 2023-05-18 | 2024-01-15 | 1 | NAP | For Information | 2 | "Engineering Deliverable Lists" | INF
000008 | 01 | Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 1 | 131242-WST00-RG-Z-0001 | 2024-01-15 | Engineering Deliverable Lists | For Information To revise and resubmit. Refer to attached file for comments. | 2024-02-02 | 2024-08-29 | 163 | For Information | NO |  | YES | Resubmitted | 0 |  | R1_Not APP | 000008 | 2023-05-18 | 2024-01-15 | 1 | INF | For Information | 2 | "Engineering Deliverable Lists" | INF
000009 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 0 | 131242-WST00-VI-C-0002 | 2023-05-19 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-12 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000009 | 2023-05-19 | 2023-07-03 | 1 | NAP | Approved | 2 | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | APP
000009 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 1 | 131242-WST00-VI-C-0002 | 2023-07-03 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Approved | 2023-07-21 | 2023-07-12 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000009 | 2023-05-19 | 2023-07-03 | 1 | APP | Approved | 2 | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | APP
000010 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | S | 0001 | 0 | 131242-WST00-VI-S-0001 | 2023-05-19 | Vendor Approval for CSA Consultant QP (Tenwit) | Approved | 2023-06-19 | 2023-06-12 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000010 | 2023-05-19 | 2023-05-19 | 0 | APP | Approved | 1 | "Vendor Approval for CSA Consultant QP (Tenwit)" | APP
000011 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | G | 0001 | 0 | 131242-WST00-VI-G-0001 | 2023-05-19 | Vendor Approval for Temp ERSS QPD,QPS (Tenwit ) | Approved | 2023-06-19 | 2023-06-12 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000011 | 2023-05-19 | 2023-05-19 | 0 | APP | Approved | 1 | "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | APP
000012 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 0 | 131242-WST00-VI-HS-0001 | 2023-05-19 | Vendor Approval for QECP Consultant (Tenwit ) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000012 | 2023-05-19 | 2023-06-23 | 1 | NAP | Approved | 2 | "Vendor Approval for QECP Consultant (Tenwit )" | APP
000012 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 1 | 131242-WST00-VI-HS-0001 | 2023-06-23 | Vendor Approval for QECP Consultant (Tenwit ) | Approved | 2023-07-14 | 2023-07-24 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000012 | 2023-05-19 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for QECP Consultant (Tenwit )" | APP
000013 | 00 | Freedomer | EICA | NA | 131242 | WST00 | VI | B | 0001 | 0 | 131242-WST00-VI-B-0001 | 2023-05-21 | Vendor Approval for M&E QP (C2D Solutions Pte. LTD ) | Approved | 2023-06-19 | 2024-03-18 | 215 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000013 | 2023-05-21 | 2023-05-21 | 0 | APP | Approved | 1 | "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" | APP
000014 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 0 | 131242-WST00-VI-C-0003 | 2023-05-22 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-20 | 2023-06-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | NAP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | APP
000014 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 1 | 131242-WST00-VI-C-0003 | 2023-06-23 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.1: Not Approved. Please refer to attached comment sheet for resubmission. | 2023-07-14 | 2023-07-12 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | NAP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | APP
000014 | 02 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 2 | 131242-WST00-VI-C-0003 | 2023-07-31 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Approved | 2023-08-21 | 2023-08-11 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | APP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | APP
000015 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0001 | 0 | 131242-WST00-MI-C-0001 | 2023-05-23 | CSA Meeting Minutes 0001 | For Information | 2023-06-21 | 2023-06-12 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000015 | 2023-05-23 | 2023-05-23 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0001" | INF
000016 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 0001 | 0 | 131242-WST02-DS-M-0001 | 2023-05-26 | FRP TANK DATA SHEET | Not approved - Revise and Resubmit | 2023-06-26 | 2023-10-16 | 101 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2023-05-26 | 2023-05-26 | 0 | NAP | Not Approved | 1 | "FRP TANK DATA SHEET" | NAP
000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 0 | 131242-WST02-DS-M-5401 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-14 | In Progress | 000016 | 2024-09-20 | 2025-04-01 | 1 | AWC | Approved | 2 | "FRP TANK DATA SHEET" | APP
000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 0 | 131242-WST02-DS-M-5416 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | AWC | Approved | 2 | "FRP TANK DATA SHEET" | APP
000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 1 | 131242-WST02-DS-M-5401 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | APP | Approved | 2 | "FRP TANK DATA SHEET" | APP
000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 1 | 131242-WST02-DS-M-5416 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | APP | Approved | 2 | "FRP TANK DATA SHEET" | APP
000017 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 0 | 131242-WST00-LT-PM-0001 | 2023-05-27 | CVs of Team Member | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-26 | 2023-06-27 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000017 | 2023-05-27 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | AWC
000017 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 1 | 131242-WST00-LT-PM-0001 | 2023-07-12 | CVs of Team Member Part 1 (14 Members) | Rev.1: Approved with comments. Please refer to attached comment sheet. | 2023-08-01 | 2023-07-25 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000017 | 2023-05-27 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | AWC
000017 | 02 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000017 | 2 | 131242-WSW41-LT-PM- Reply to Comment Sheet_#000017 | 2023-09-04 | CVs of Team Member Part 1 (14 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-22 | 2023-10-10 | 26 | Approved with Comments | YES | 2023-10-30 | NO | Resubmitted | 0 |  | To obtain S.O. evaluation & final approval based on the probation period. To check with S.O during CSA bi-weekly meeting | 000017 | 2023-09-04 | 2023-09-04 | 2 | AWC | Approved with Comments | 1 | "CVs of Team Member Part 1 (14 Members)" | AWC
000018 | 00 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001 | 2023-05-31 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-30 | 2023-06-06 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | NAP
000018 | 01 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 1 | 131242-WST00-DR-Z-0001 | 2023-06-06 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-26 | 2023-06-23 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | NAP
000018 | 02 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 2 | 131242-WST00-DR-Z-0001 | 2023-06-27 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-07-18 | 2023-07-03 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | NAP
000018 | 03 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 3 | 131242-WST00-DR-Z-0001 | 2023-07-04 | Title Block Template (CAD) | Approved | 2023-07-24 | 2023-07-03 | 0 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | APP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | NAP
000019 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 0 | 131242-WST00-VI-C-0004 | 2023-05-31 | Vendor Approval for Cable Dectector (JLCD) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-30 | 2023-06-16 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000019 | 2023-05-31 | 2023-06-23 | 1 | AWC | Approved | 2 | "Vendor Approval for Cable Dectector (JLCD)" | APP
000019 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 1 | 131242-WST00-VI-C-0004 | 2023-06-23 | Vendor Approval for Cable Dectector (JLCD) | Approved | 2023-07-14 | 2023-06-30 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000019 | 2023-05-31 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for Cable Dectector (JLCD)" | APP
000020 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | FM | HS | 0001 | 0 | 131242-WST00-FM-HS-0001 | 2023-06-05 | HSE Stickers for Machineries and SIC Induction | Approved | 2023-07-04 | 2023-06-14 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000020 | 2023-06-05 | 2023-06-05 | 0 | APP | Approved | 1 | "HSE Stickers for Machineries and SIC Induction" | APP
000021 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0001 | 0 | 131242-WST00-MI-P-0001 | 2023-06-11 | Process & MEICA Meeting Minutes 0001 | For Information | 2023-07-10 | 2023-10-18 | 92 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000021 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0001" | INF
000022 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0002 | 0 | 131242-WST00-MI-P-0002 | 2023-06-11 | Process & MEICA Meeting Minutes 0002 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000022 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0002" | INF
000023 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0003 | 0 | 131242-WST00-MI-P-0003 | 2023-06-11 | Process & MEICA Meeting Minutes 0003 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000023 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0003" | INF
000024 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0004 | 0 | 131242-WST00-MI-P-0004 | 2023-06-11 | Process & MEICA Meeting Minutes 0004 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000024 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0004" | INF
000025 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 0 | 131242-WST00-LT-PM-0002 | 2023-06-12 | CVs of Team Member | Approved with comments. Please refer to comment sheet for resubmission. | 2023-07-11 | 2023-06-20 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000025 | 2023-06-12 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | AWC
000025 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 1 | 131242-WST00-LT-PM-0002 | 2023-07-12 | CVs of Team Member Part 2 (7 Members) | Rev.1: Approved with comments. Please refer to S.O. comment sheet. | 2023-08-01 | 2023-07-25 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Reply to S.O. Comment Sheet Only | 000025 | 2023-06-12 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | AWC
000025 | 02 | Shena/ Htet | PMT | NA | 131242 | NA | LT | PM | Reply to Comment Sheet_#000025 | NA | 131242-NA-LT-PM-Reply to Comment Sheet_#000025 | 2023-09-11 | CVs of Team Member Part 2 (7 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-29 | 2024-09-10 | 261 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000025 | 2023-09-11 | 2023-09-11 | NA | AWC | Approved with Comments | 1 | "CVs of Team Member Part 2 (7 Members)" | AWC
000026 | 00 | Bryan | HSE | NA | 131242 | WST00 | MS | C | 0001 | 0 | 131242-WST00-MS-C-0001 | 2023-06-13 | Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-29 | 12 | Not Approved | YES | 2023-07-19 | NO | Resubmitted | 0 | 2024-01-10 | In Progress | 000026 | 2023-06-13 | 2023-06-13 | 0 | NAP | Not Approved | 1 | "Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD)" | NAP
000027 | 00 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 0 | 131242-WST00-RT-PM-0001 | 2023-06-13 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-16 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | NAP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" | APP
000027 | 01 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 1 | 131242-WST00-RT-PM-0001 | 2023-07-04 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-24 | 2023-07-13 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | NAP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" | APP
000027 | 02 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 2 | 131242-WST00-RT-PM-0001 | 2023-07-14 | C4B Monthly Progress Report Number No.01 (05/23) | Approved | 2023-08-03 | 2023-10-18 | 68 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | APP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" | APP
000028 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 0 | 131242-WSD11-VI-M-0001 | 2023-06-14 | Vendor Approval for THP Package | Rev 0: Not approved - Revise and Resubmit | 2023-07-13 | 2023-07-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | NAP | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | AWC
000028 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 1 | 131242-WSD11-VI-M-0001 | 2023-07-28 | Vendor Approval for THP Package | Rev 1: Rejected as per contractor requested email dated on 31-Jul-2023 as there has few changes and will resubmit to include the comment sheet in next revision. | 2023-08-18 | 2023-08-01 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | NAP | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | AWC
000028 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 2 | 131242-WSD11-VI-M-0001 | 2023-08-02 | Preliminary design and Vendor Approval | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-08-23 | 2023-08-31 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | AWC
000028 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 3 | 131242-WSD11-VI-M-0001 | 2023-11-10 | Preliminary design and Vendor Approval - THP Package | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-01 | 2023-12-20 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | AWC
000028 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 4 | 131242-WSD11-VI-M-0001 | 2024-03-01 | Preliminary design and Vendor Approval - THP Package | Rev 4: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-03-21 | 2024-04-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev3: AWC | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | AWC
000029 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0002 | 0 | 131242-WST00-MI-C-0002 | 2023-06-16 | CSA Meeting Minutes 0002 | For information | 2023-07-17 | 2023-06-28 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000029 | 2023-06-16 | 2023-06-16 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0002" | INF
000030 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0003 | 0 | 131242-WST00-MI-C-0003 | 2023-06-16 | CSA Meeting Minutes 0003 | For information | 2023-07-17 | 2023-06-28 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000030 | 2023-06-16 | 2023-06-16 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0003" | INF
000031 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | Z | 0001 | 0 | 131242-WST00-MI-Z-0001 | 2023-06-19 | Engineering Kick Off Meeting Minutes 0001 | For Information | 2023-07-18 | 2024-03-18 | 195 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000031 | 2023-06-19 | 2023-06-19 | 0 | INF | For Information | 1 | "Engineering Kick Off Meeting Minutes 0001" | INF
000032 | 00 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 0 | 131242-WST00-MS-C-0002 | 2023-06-19 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-18 | 2023-06-29 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-01-10 | In Progress | 000032 | 2023-06-19 | 2024-04-12 | 1 | NAP | Approved | 2 | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | APP
000032 | 01 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 1 | 131242-WST00-MS-C-0002 | 2024-04-12 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000032 | 2023-06-19 | 2024-04-12 | 1 | APP | Approved | 2 | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | APP
000033 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PS | HS | 0001 | 0 | 131242-WST00-PS-HS-0001 | 2023-06-20 | C4B HSE Induction Course | Noted for information | 2023-07-19 | 2023-07-24 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000033 | 2023-06-20 | 2023-06-20 | 0 | INF | For Information | 1 | "C4B HSE Induction Course" | INF
000034 | 00 | Kristnnan | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 0 | 131242-WSW41-PP-HS-0003 | 2023-06-21 | Emergency Response Plan | Reporting timeline is not in sequence with what we have. Please use information in your KOM slides when preparing. Review and resubmit. | 2023-07-20 | 2023-08-02 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000034 | 2023-06-21 | 2023-09-07 | 1 | NAP | Approved | 2 | "Emergency Response Plan" | APP
000034 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 1 | 131242-WSW41-PP-HS-0003 | 2023-09-07 | Emergency Response Plan | Approved | 2023-09-27 | 2023-09-25 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000034 | 2023-06-21 | 2023-09-07 | 1 | APP | Approved | 2 | "Emergency Response Plan" | APP
000035 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0002 | 0 | 131242-WST00-PP-HS-0002 | 2023-06-22 | Project Accident Statistic Board and BCA Board | Rev.0: Not Approved. Please find attached comment sheet for resubmission. | 2023-07-21 | 2023-08-18 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000035 | 2023-06-22 | 2023-06-22 | 0 | NAP | Not Approved | 1 | "Project Accident Statistic Board and BCA Board" | NAP
000035 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0002 | 1 | 131242-WSW41-PP-HS-0002 | 2023-10-13 | Project Accident Statistic Board and BCA Board | Approved | 2023-11-02 | 2023-10-23 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000035 | 2023-10-13 | 2023-10-13 | 1 | APP | Approved | 1 | "Project Accident Statistic Board and BCA Board" | APP
000036 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0004 | 0 | 131242-WST00-MI-C-0004 | 2023-06-28 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-07-27 | 2023-07-12 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000036 | 2023-06-28 | 2023-06-28 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230614" | INF
000037 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0001 | 0 | 131242-WSW41-MI-IM-0001 | 2023-06-28 | BIM Bi-Weekly Meeting Minutes 0001_20230614 | For Information | 2023-07-27 | 2023-07-04 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000037 | 2023-06-28 | 2023-06-28 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0001_20230614" | INF
000038 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | B | 0001 | 0 | 131242-WSW41-CL-B-0001 | 2023-07-05 | Temporary Utilities for Contractor’s Site Office | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-02 | 2023-07-21 | 12 | Approved with Comments | YES | 2023-08-10 | NO | Resubmitted | 0 |  |  | 000038 | 2023-07-05 | 2023-07-05 | 0 | AWC | Approved with Comments | 1 | "Temporary Utilities for Contractor’s Site Office" | AWC
000039 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0001 | 0 | 131242-WSD11-MI-P-0001 | 2023-07-05 | MI-Process & MEICA Meeting Minutes with THP (CAMBI) | For Information | 2023-08-02 | 2024-03-18 | 183 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000039 | 2023-07-05 | 2023-07-05 | 0 | INF | For Information | 1 | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" | INF
000040 | 00 | Stanley | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-PM-0003 | 2023-07-06 | Request for time extension_Programme of works resubmission | The Prolog Submittals number 000040 (need to void) should not be created as new submission, this submission should under Prologs number 000005 because this extension request is referring from Rev. 0 to Rev. 1 - Programme of the Works | 2023-08-03 | 2023-09-22 | 56 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000005&&000040 | 2023-07-06 | 2023-09-26 | 0 | VOID | For Information | 2 | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | INF
000041 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0005 | 0 | 131242-WSW41-MI-C-0005 | 2023-07-06 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-08-03 | 2023-10-18 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000041 | 2023-07-06 | 2023-07-06 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230614" | INF
000042 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0004 | 0 | 131242-WSW41-LT-PM-0004 | 2023-07-06 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-08-03 | 2023-08-21 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000042 | 2023-07-06 | 2023-07-06 | 0 | AWC | Approved with Comments | 1 | "CVs of Team Members (Part 3)" | AWC
000042 | 01 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000042 | NA | 131242-WSW41-LT-PM-Reply to Comment Sheet_#000042 | 2023-09-04 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-09-22 | 2024-02-01 | 108 | Approved with Comments | YES | 2024-02-21 | NO | Resubmitted | 0 |  |  | 000042 | 2023-09-04 | 2023-09-04 | NA | AWC | Approved with Comments | 1 | "CVs of Team Members (Part 3)" | AWC
000043 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0001 | 0 | 131242-WSW41-PS-PM-0001 | 2023-07-07 | Presentation Slide for Monthly Progress Meeting No. 01(0523) | For information only | 2023-08-04 | 2023-07-13 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000043 | 2023-07-07 | 2023-07-07 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 01(0523)" | INF
000044 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0005 | 0 | 131242-WSW41-LT-PM-0005 | 2023-07-07 | CVs of Team Members (Part 4) | Approved | 2023-08-04 | 2023-07-24 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000044 | 2023-07-07 | 2023-07-07 | 0 | APP | Approved | 1 | "CVs of Team Members (Part 4)" | APP
000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0002 | 0 | 131242-WSW41-DR-Z-0002 | 2023-07-10 | SITE UTILIZATION PLAN | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-10 | 0 | AWC | Approved with Comments | 1 | "SITE UTILIZATION PLAN" | AWC
000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 0 | 131242-WSW41-DR-Z-0003 | 2023-07-10 | SITE OFFICE LAYOUT (Rev1) | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-26 | 1 | AWC | Approved | 2 | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | APP
000045 | 01 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 1 | 131242-WSW41-DR-Z-0003 | 2023-07-26 | SITE OFFICE LAYOUT (Rev2) | Approved | 2023-08-16 | 2023-08-02 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-26 | 1 | APP | Approved | 2 | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | APP
000046 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 0 | 131242-WSW41-RT-PM-0002 | 2023-07-12 | C4B Monthly Progress Report Number No.02 (06/23) | Rejected as informed by contractor email dated 12-Jul-2023 there has few changes/ corrections in the attached file. | 2023-08-10 | 2023-07-14 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-07-12 | 2023-07-14 | 1 | REJ | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.02 (06/23)" | AWC
000046 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 1 | 131242-WSW41-RT-PM-0002 | 2023-07-14 | C4B Monthly Progress Report Number No.02 (06/23) | Rev. 1 - Approved with comments (see the comment sheet) Resubmission required | 2023-08-03 | 2023-10-18 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-07-12 | 2023-07-14 | 1 | AWC | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.02 (06/23)" | AWC
000046 | 02 | Thomas | PCM | NA | Comment Reply Sheet 08112023 | NA | NA | NA | NA | NA | Comment Reply Sheet 08112023-NA-NA-NA-NA | 2023-11-09 | C4B Monthly Progress Report Number No.02 (06/23) | Approved | 2023-11-30 | 2023-11-15 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-11-09 | 2023-11-09 | NA | APP | Approved | 1 | "C4B Monthly Progress Report Number No.02 (06/23)" | APP
000047 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0002 | 0 | 131242-WSW41-MI-IM-0002 | 2023-07-13 | BIM Bi-Weekly Meeting Minutes 0002_20230628 | For Information | 2023-08-11 | 2023-07-24 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000047 | 2023-07-13 | 2023-07-13 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0002_20230628" | INF
000048 | 00 | Matthew | Piping/ BS | NA | 131242 | WSW41 | MI | B | 0001 | 0 | 131242-WSW41-MI-B-0001 | 2023-07-14 | BS Meeting Minutes 0001_20230706 | For Information | 2023-08-14 | 2024-02-15 | 154 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000048 | 2023-07-14 | 2023-07-14 | 0 | INF | For Information | 1 | "BS Meeting Minutes 0001_20230706" | INF
000049 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PP | PM | 0002 | 0 | 131242-WSW41-PP-PM-0002 | 2023-07-14 | C4B Manpower Deployment Plan | Approved as noted. Please note that acceptable of the manpower deployment plan shall not relieve the Contractor's responsibility to engage key personnel whenever is required or employ additional manpower to complete and successfully deliver the project timely and safely. | 2023-08-14 | 2023-07-24 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000049 | 2023-07-14 | 2023-07-14 | 0 | APP | Approved | 1 | "C4B Manpower Deployment Plan" | APP
000050 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0006 | 0 | 131242-WSW41-MI-C-0006 | 2023-07-14 | CSA Meeting Minutes 0004_20230705 | For Information | 2023-08-14 | 2023-07-24 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000050 | 2023-07-14 | 2023-07-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230705" | INF
000051 | 00 | REY | PMT | NA | 131242 | WSW41 | DR | C | 1000 | 0 | 131242-WSW41-DR-C-1000 | 2023-07-18 | Drawing of Pre-Con Topographical Survey | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-08-16 | 2023-08-11 | 18 | Approved with Comments | YES | 2023-08-31 | NO | Resubmitted | 0 |  | Heng Peng: To clear BIM comments | 000051 | 2023-07-18 | 2023-07-18 | 0 | AWC | Approved with Comments | 1 | "Drawing of Pre-Con Topographical Survey" | AWC
000052 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0003 | 0 | 131242-WSW41-MI-IM-0003 | 2023-07-18 | BIM Bi-Weekly Meeting Minutes 0003_20230712 | For Information | 2023-08-16 | 2023-07-25 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000052 | 2023-07-18 | 2023-07-18 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0003_20230712" | INF
000053 | 00 | Heng Peng | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 0 | 131242-WSW41-LT-PM-0006 | 2023-07-19 | CV of Team Member (BIM Authoring Lead) | R0- Proposed candidate doesn’t meet the requirement. Please refer to "Comment sheet - Submittal 000053.0" | 2023-08-17 | 2023-10-23 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000053 | 2023-07-19 | 2023-12-11 | 1 | NAP | Not Approved | 2 | "CV of Team Member (BIM Authoring Lead)" | NAP
000053 | 01 | Leon | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 1 | 131242-WSW41-LT-PM-0006 | 2023-12-11 | CV of Team Member (BIM Authoring Lead) | R1- Subject to 6 months' probation period. Please refer to "Comment sheet - Submittal 000053.1" | 2024-01-02 | 2023-12-22 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000053 | 2023-07-19 | 2023-12-11 | 1 | NAP | Not Approved | 2 | "CV of Team Member (BIM Authoring Lead)" | NAP
000054 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0007 | 0 | 131242-WSW41-MI-C-0007 | 2023-07-24 | CSA Meeting Minutes 0007_20230712 | For Information | 2023-08-22 | 2023-08-10 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000054 | 2023-07-24 | 2023-07-24 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0007_20230712" | INF
000055 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0001 | 0 | 131242-WSW41-PC-W-0001 | 2023-07-24 | PROGRESS CLAIM NO.1 | Accepted. Please refer to S.O. Correspondence no. 25 dated 25 July 2023. | 2023-08-22 | 2023-08-30 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000055 | 2023-07-24 | 2023-07-24 | 0 | APP | Approved | 1 | "PROGRESS CLAIM NO.1" | APP
000056 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0004 | 0 | 131242-WSW41-PP-HS-0004 | 2023-07-27 | Signboard Sticker for TWRP Main Gate route 3 entrance | For information | 2023-08-25 | 2023-08-02 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000056 | 2023-07-27 | 2023-07-27 | 0 | INF | For Information | 1 | "Signboard Sticker for TWRP Main Gate route 3 entrance" | INF
000057 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0002 | 0 | 131242-WSW41-PS-PM-0002 | 2023-07-28 | Presentation Slide for Monthly Progress Meeting No. 02(0623) | For information | 2023-08-28 | 2023-08-01 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000057 | 2023-07-28 | 2023-07-28 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" | INF
000058 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 0 | 131242-WSW41-MS-C-0003 | 2023-07-28 | MSRA, SWP for General Civil Works | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-28 | 2023-08-14 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | AWC | Approved | 4 | "MSRA, SWP for General Civil Works" | APP
000058 | 01 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 1 | 131242-WSW41-MS-C-0003 | 2024-01-22 | MSRA, SWP for General Civil Works | Rev.1: Approved with comments. Please refer to attached comment sheet for resubmission. | 2024-02-09 | 2024-02-21 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | AWC | Approved | 4 | "MSRA, SWP for General Civil Works" | APP
000058 | 02 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 2 | 131242-WSW41-MS-C-0003 | 2024-04-12 | MSRA, SWP for General Civil Works | Rev.2: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | APP | Approved | 4 | "MSRA, SWP for General Civil Works" | APP
000058 | 03 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 3 | 131242-WSW41-MS-C-0003 | 2025-03-20 | MSRA, SWP for General Civil Works | R3: Approved | 2025-04-09 | 2025-05-07 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | APP | Approved | 4 | "MSRA, SWP for General Civil Works" | APP
000059 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0005 | 0 | 131242-WSW41-VI-C-0005 | 2023-08-01 | Vendor Approval of Concrete Supplier-Alliance | Rev.0: Approved | 2023-08-30 | 2023-08-10 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000059 | 2023-08-01 | 2023-08-01 | 0 | APP | Approved | 1 | "Vendor Approval of Concrete Supplier-Alliance" | APP
000060 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-W-0002 | 2023-08-01 | Adjustment of Stage Payment | Rejected as contractor would like to resubmit with the correct reference. | 2023-08-30 | 2023-08-02 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000060&&000080 | 2023-08-01 | 2023-08-25 | 0 | REJ | Approved | 2 | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | APP
000060 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0008 | 0 | 131242-WSW41-LT-PM-0008 | 2023-08-02 | Adjustment of Stage Payment | Rejected. Contractor to re-submit. Please refer to S.O. correspondence no. 55 dated 13 Sep 2023. | 2023-08-23 | 2023-09-15 | 32 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000060 | 2023-08-02 | 2023-08-02 | 0 | REJ | Rejected | 1 | "Adjustment of Stage Payment" | REJ
000060 | 02 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0014 | 0 | 131242-WSW41-LT-PM-0014 | 2023-10-18 | Adjustment of Stage Payment | For Information | 2023-11-07 | 2023-12-18 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000060 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "Adjustment of Stage Payment" | INF
000061 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0009 | 0 | 131242-WSW41-LT-PM-0009 | 2023-08-03 | CV of Team Member (CM) | Approved | 2023-09-01 | 2023-08-11 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000061 | 2023-08-03 | 2023-08-03 | 0 | APP | Approved | 1 | "CV of Team Member (CM)" | APP
000062 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0007 | 0 | 131242-WSW41-LT-PM-0007 | 2023-08-03 | Request for Variable Site Management Team Payment | Rev(0) Accepted. Please refer to S.O. correspondence no. 84 dated 22 Nov 2023. | 2023-09-01 | 2024-01-30 | 128 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000062 | 2023-08-03 | 2023-08-03 | 0 | INF | For Information | 1 | "Request for Variable Site Management Team Payment" | INF
000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0008 | 0 | 131242-WSW41-MI-C-0008 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000063 | 2023-08-07 | 2023-08-07 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" | INF
000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0009 | 0 | 131242-WSW41-MI-C-0009 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000063 | 2023-08-07 | 2023-08-07 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" | INF
000064 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 0 | 131242-WSW41-VI-C-0006 | 2023-08-08 | Vendor Approval of Concrete Supplier-Pan United | Rev.0: Approved with comment. Please refer to attached comment sheet for resubmission. | 2023-09-06 | 2023-08-30 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000064 | 2023-08-08 | 2023-09-22 | 1 | AWC | Approved | 2 | "Vendor Approval of Concrete Supplier-Pan United" | APP
000064 | 01 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 1 | 131242-WSW41-VI-C-0006 | 2023-09-22 | Vendor Approval of Concrete Supplier-Pan United | Approved | 2023-10-12 | 2023-09-25 | 1 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000064 | 2023-08-08 | 2023-09-22 | 1 | APP | Approved | 2 | "Vendor Approval of Concrete Supplier-Pan United" | APP
000065 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CN | E | 0001 | 0 | 131242-WSW41-CN-E-0001 | 2023-08-08 | RFC For HV Routing (from C3B1) to SSN Transformer Room | Approved. Refer comment sheet for more details. | 2023-09-06 | 2024-02-15 | 137 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000065 | 2023-08-08 | 2023-08-08 | 0 | APP | Approved | 1 | "RFC For HV Routing (from C3B1) to SSN Transformer Room" | APP
000066 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0001 | 0 | 131242-WSW41-CD-IM-0001 | 2023-08-08 | Submission Of BIM Coordination VCM Model (July – 2023) | Approved with Comments. Please refer to "Comments Sheet_Sub-0066-0" | 2023-09-06 | 2023-08-24 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000066 | 2023-08-08 | 2023-08-08 | 0 | AWC | Approved with Comments | 1 | "Submission Of BIM Coordination VCM Model (July – 2023)" | AWC
000067 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0007 | 0 | 131242-WSW41-VI-C-0007 | 2023-08-11 | Vendor Approval of Rebar Supplier-BRC ASIA LIMITED | Approved | 2023-09-08 | 2023-08-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000067 | 2023-08-11 | 2023-08-11 | 0 | APP | Approved | 1 | "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" | APP
000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0005 | 0 | 131242-WSW41-MI-P-0005 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000068 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | INF
000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0006 | 0 | 131242-WSW41-MI-P-0006 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000068 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | INF
000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0001 | 0 | 131242-WST02-MI-P-0001 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000069 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | INF
000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0002 | 0 | 131242-WST02-MI-P-0002 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000069 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | INF
000070 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 0 | 131242-WSW41-RT-PM-0003 | 2023-08-14 | C4B Monthly Progress Report Number No.03 (07/23) | Rev. 0 - Approved with Comments . Refer to Comments sheet to re-submit. | 2023-09-11 | 2023-08-29 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000070 | 2023-08-14 | 2023-09-25 | 1 | AWC | Approved | 2 | "C4B Monthly Progress Report Number No.03 (07/23)" | APP
000070 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 1 | 131242-WSW41-RT-PM-0003 | 2023-09-25 | C4B Monthly Progress Report Number No.03 (07/23) | Approved | 2023-10-13 | 2023-09-27 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000070 | 2023-08-14 | 2023-09-25 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.03 (07/23)" | APP
000071 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0009 | 0 | 131242-WSW41-VI-C-0009 | 2023-08-15 | Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000071 | 2023-08-15 | 2023-08-15 | 0 | APP | Approved | 1 | "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | APP
000072 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0010 | 0 | 131242-WSW41-VI-C-0010 | 2023-08-15 | Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000072 | 2023-08-15 | 2023-08-15 | 0 | APP | Approved | 1 | "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | APP
000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0004 | 0 | 131242-WSW41-MI-IM-0004 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000073 | 2023-08-15 | 2023-08-15 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" | INF
000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0005 | 0 | 131242-WSW41-MI-IM-0005 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000073 | 2023-08-15 | 2023-08-15 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" | INF
000074 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0008 | 0 | 131242-WSW41-VI-C-0008 | 2023-08-16 | Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd | Approved | 2023-09-13 | 2023-08-30 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000074 | 2023-08-16 | 2023-08-16 | 0 | APP | Approved | 1 | "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" | APP
000075 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0011 | 0 | 131242-WSW41-LT-PM-0011 | 2023-08-22 | CV of Team Member (WSHC) | Approved | 2023-09-19 | 2023-09-25 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000075 | 2023-08-22 | 2023-08-22 | 0 | APP | Approved | 1 | "CV of Team Member (WSHC)" | APP
000076 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0010 | 0 | 131242-WSW41-LT-PM-0010 | 2023-08-22 | Delegation of Signing Authorities | For Information | 2023-09-19 | 2023-09-25 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000076 | 2023-08-22 | 2023-08-22 | 0 | INF | For Information | 1 | "Delegation of Signing Authorities" | INF
000077 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0003 | 0 | 131242-WSW41-PS-PM-0003 | 2023-08-28 | Presentation Slide for Monthly Progress Meeting No. 03(0723) | For Information | 2023-09-25 | 2023-08-24 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000077 | 2023-08-28 | 2023-08-28 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" | INF
000078 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0001 | 0 | 131242-WSW41-RT-Z-0001 | 2023-08-24 | Photographic Survey Report for C4B | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-09-21 | 2023-08-30 | 4 | Not Approved | YES | 2023-09-19 | NO | Resubmitted | 0 |  |  | 000078 | 2023-08-24 | 2023-08-24 | 0 | NAP | Not Approved | 1 | "Photographic Survey Report for C4B" | NAP
000079 | 00 | Zora | CSA | NA | 1.0 Design Brief | NA | NA | NA | NA | NA | 1.0 Design Brief-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-08-31 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" | NAP
000079 | 00 | Zora | CSA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003 | NA | NA | NA | NA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" | APP
000079 | 00 | Zora | CSA | NA | 3.0 Overall SSN area Loading Plan Marked up | NA | NA | NA | NA | NA | 3.0 Overall SSN area Loading Plan Marked up-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" | APP
000079 | 00 | Zora | CSA | NA | 4.0 SSN Overall Area Layout and Elevations | NA | NA | NA | NA | NA | 4.0 SSN Overall Area Layout and Elevations-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" | APP
000079 | 00 | Zora | CSA | NA | 5.0 Soil Report | NA | NA | NA | NA | NA | 5.0 Soil Report-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" | APP
000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A | 131242-WST00-DR-C-8000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | APP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A | 131242-WST00-DR-S-1000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | APP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A | 131242-WST02-DR-C-1001_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | APP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A | 131242-WST02-DR-C-5001_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | APP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | NAP
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A | 131242-WST02-DR-C-7000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | APP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 01 | Zora | CSA | NA | 1. C4B SSN Overall Piling Design Brief | NA | NA | NA | NA | NA | 1. C4B SSN Overall Piling Design Brief-NA-NA-NA-NA | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-16 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-09-26 | 2023-09-26 | NA | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" | NAP
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | C | 0001_ST604 | 0 | 131242-WST02-CL-C-0001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-09-26 | 2023-09-26 | 0 | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" | NAP
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | NAP
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 | 2024-08-16 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 000079 | 2023-08-24 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | NAP
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" | AWC
000080 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-W-0002 | 2023-08-25 | PAYMENT CLAIM NO.2 | Accepted. Please refer to S.O. Correspondence no. 48 dated 29 August 2023. | 2023-09-22 | 2023-08-30 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000060&&000080 | 2023-08-01 | 2023-08-25 | 0 | APP | Approved | 2 | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | APP
000081 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 0 | 131242-WSW41-SP-C-0001 | 2023-08-28 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-09-25 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000081 | 2023-08-28 | 2023-10-05 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | APP
000081 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 1 | 131242-WSW41-SP-C-0001 | 2023-10-05 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.1: Approved | 2023-10-25 | 2023-10-18 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000081 | 2023-08-28 | 2023-10-05 | 1 | APP | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | APP
000082 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0006 | 0 | 131242-WSW41-MI-IM-0006 | 2023-08-28 | BIM Bi-Weekly Meeting Minutes 0006_20230823 | For Information | 2023-09-25 | 2023-09-06 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000082 | 2023-08-28 | 2023-08-28 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0006_20230823" | INF
000083 | 00 | Zora | CSA | NA | 131242 | WSW41 | SK | S | 0001 | 0 | 131242-WSW41-SK-S-0001 | 2023-08-28 | Sidewide Pipe Rack GA and Reactions | Not Approved. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-10-06 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2023-08-28 | 2023-08-28 | 0 | NAP | Not Approved | 1 | "Sidewide Pipe Rack GA and Reactions" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A | 131242-WSW41-DR-S-1000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-01 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A | 131242-WSW41-DR-S-1004_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A | 131242-WSW41-DR-S-1007_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A | 131242-WSW41-DR-S-1008_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A | 131242-WSW41-DR-S-1009_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A | 131242-WSW41-DR-S-1010_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A | 131242-WSW41-DR-S-2000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A | 131242-WSW41-DR-S-2001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A | 131242-WSW41-DR-S-2002_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A | 131242-WSW41-DR-S-3000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A | 131242-WSW41-DR-S-3001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A | 131242-WSW41-DR-S-5000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A | 131242-WSW41-DR-S-5001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A | 131242-WSW41-DR-S-5002_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A | 131242-WSW41-DR-S-8001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 01 | Zora | CSA | NA | Site wide PR Reactions for information | NA | NA | NA | NA | NA | Site wide PR Reactions for information-NA-NA-NA-NA | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-01-13 | NA | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.1 | 131242-WSW41-DR-S-1000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-01 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  | Rev 1 : Not Approved. | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.1 | 131242-WSW41-DR-S-1004_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.1 | 131242-WSW41-DR-S-1007_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.1 | 131242-WSW41-DR-S-1008_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.1 | 131242-WSW41-DR-S-1009_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.1 | 131242-WSW41-DR-S-1010_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.1 | 131242-WSW41-DR-S-2000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.1 | 131242-WSW41-DR-S-2002_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.1 | 131242-WSW41-DR-S-3001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.1 | 131242-WSW41-DR-S-5001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.1 | 131242-WSW41-DR-S-5002_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.1 | 131242-WSW41-DR-S-5003_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A | 131242-WSW41-DR-S-5004_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.1 | 131242-WSW41-DR-S-8001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.1 | 131242-WSW41-DR-S-0301_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | CL | S | 1000_ST603 | 2 | 131242-WSW41-CL-S-1000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  | To clear technical comments first and Heng Peng to clear BIM comments. | 000083 | 2024-06-08 | 2024-06-08 | 2 | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.2 | 131242-WSW41-DR-S-1000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.2 | 131242-WSW41-DR-S-1004_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.2 | 131242-WSW41-DR-S-1007_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.2 | 131242-WSW41-DR-S-1008_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.2 | 131242-WSW41-DR-S-1009_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.2 | 131242-WSW41-DR-S-1010_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.2 | 131242-WSW41-DR-S-2000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.2 | 131242-WSW41-DR-S-2002_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.2 | 131242-WSW41-DR-S-3001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.2 | 131242-WSW41-DR-S-5001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.2 | 131242-WSW41-DR-S-5002_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.2 | 131242-WSW41-DR-S-5003_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A.2 | 131242-WSW41-DR-S-5004_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.2 | 131242-WSW41-DR-S-8001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.2 | 131242-WSW41-DR-S-0301_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" | NAP
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0302_ST603 | A | 131242-WSW41-DR-S-0302_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-06-08 | 2024-06-08 | A | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" | NAP
000084 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | S | 0002 | 0 | 131242-WSW41-VI-S-0002 | 2023-08-28 | Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd. | Approved | 2023-09-25 | 2023-09-25 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000084 | 2023-08-28 | 2023-08-28 | 0 | APP | Approved | 1 | "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | APP
000085 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0002 | 0 | 131242-WSW41-SP-C-0002 | 2023-08-31 | Concrete Design Mix for ULT Test Pile C50/60 (Alliance) | Approved | 2023-09-28 | 2023-09-25 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000085 | 2023-08-31 | 2023-08-31 | 0 | APP | Approved | 1 | "Concrete Design Mix for ULT Test Pile C50/60 (Alliance) " | APP
000086 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | Z | 0001 | 0 | 131242-WSW41-CL-Z-0001 | 2023-08-31 | ECM Plan and Calculation | Approved | 2023-09-28 | 2023-10-04 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000086 | 2023-08-31 | 2023-08-31 | 0 | APP | Approved | 1 | "ECM Plan and Calculation" | APP
000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0001 | 0 | 131242-WSW41-MI-PM-0001 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000087 | 2023-09-04 | 2023-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | INF
000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0002 | 0 | 131242-WSW41-MI-PM-0002 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000087 | 2023-09-04 | 2023-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | INF
000088 | 00 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 0 | 131242-WST02-VI-M-0001 | 2023-09-05 | Preliminary design and Vendor Approval for SSN Package | Rev 0: Not approved - Revise and Resubmit | 2023-10-03 | 2023-09-25 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | NAP | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" | AWC
000088 | 01 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 1 | 131242-WST02-VI-M-0001 | 2023-10-05 | Preliminary design and Vendor Approval for SSN Package | Rev 1: Not approved - Revise and Resubmit Document not approved as requested by Contractor. | 2023-10-25 | 2023-10-23 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | NAP | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" | AWC
000088 | 02 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 2 | 131242-WST02-VI-M-0001 | 2023-10-31 | Preliminary design and Vendor Approval for SSN Package | Rev 2: Approved with Comments, subject to clarification of comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-21 | 2023-11-08 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | AWC | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" | AWC
000088 | 03 | Joo kwan | Process | NA | 131242 | WST02 | VI | M | 0001 | 3 | 131242-WST02-VI-M-0001 | 2024-02-03 | Preliminary design and Vendor Approval for SSN Package | Rev 3: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-02-23 | 2024-04-29 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev 2: AWC | 000088 | 2023-09-05 | 2024-02-03 | 3 | AWC | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" | AWC
000089 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0007 | 0 | 131242-WSW41-MI-P-0007 | 2023-09-05 | Process & MEICA Meeting Minutes 0007_20230718 | For Information | 2023-10-03 | 2024-03-18 | 139 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000089 | 2023-09-05 | 2023-09-05 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0007_20230718" | INF
000090 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | D | 0001 | 0 | 131242-WSW41-VI-D-0001 | 2023-09-07 | Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq) | Approved | 2023-10-05 | 2023-09-25 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000090 | 2023-09-07 | 2023-09-07 | 0 | APP | Approved | 1 | "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | APP
000091 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0002 | 0 | 131242-WSW41-RT-Z-0002 | 2023-09-07 | Cable Detection Report | Approved with comments. Please refer to comment sheet for resubmission. | 2023-10-05 | 2023-09-25 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000091 | 2023-09-07 | 2023-09-07 | 0 | AWC | Approved with Comments | 1 | "Cable Detection Report" | AWC
000091 | 01 | Eng Bee | PMT | NA | Reply to Comment Sheet_#000091 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000091-NA-NA-NA-NA | 2023-10-06 | Cable Detection Report | Approved | 2023-10-26 | 2023-10-18 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000091 | 2023-10-06 | 2023-10-06 | NA | APP | Approved | 1 | "Cable Detection Report" | APP
000092 | 00 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 0 | 131242-WSW41-SP-M-8001 | 2023-09-08 | Piping Material Specification | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-10-06 | 2023-09-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | AWC | Approved | 4 | "Piping Material Specification" | APP
000092 | 01 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 1 | 131242-WSW41-SP-M-8001 | 2024-02-22 | Piping Material Specification | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-13 | 2024-04-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev 0: AWC | 000092 | 2023-09-08 | 2024-12-13 | 3 | AWC | Approved | 4 | "Piping Material Specification" | APP
000092 | 02 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 2 | 131242-WSW41-SP-M-8001 | 2024-08-07 | Piping Material Specification | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | APP | Approved | 4 | "Piping Material Specification" | APP
000092 | 03 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 3 | 131242-WSW41-SP-M-8001 | 2024-12-13 | Piping Material Specification | Rev 3: Approved | 2025-01-03 | 2025-01-20 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | APP | Approved | 4 | "Piping Material Specification" | APP
000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | 0 | 131242-WSW41-DR-P-6000 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | 0 | 131242-WSW41-DR-P-6001 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 00 | Qili | Process | NA | Pipeline - All_Data Report | NA | NA | NA | NA | NA | Pipeline - All_Data Report-NA-NA-NA-NA | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2023-09-08 | NA | AWC | Approved with Comments | 1 | "Piperack P&IDs" | AWC
000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6000 | B | 131242-WSW41-DR-P-6000 | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | Rev 0: AWC | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6001 | B | 131242-WSW41-DR-P-6001 | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | C | 131242-WSW41-DR-P-6000 | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | C | 131242-WSW41-DR-P-6001 | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | D | 131242-WSW41-DR-P-6000 | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | comments received on 14 Feb | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | D | 131242-WSW41-DR-P-6001 | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000 | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001 | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000 | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | 0 | Awaiting S.O.'s response | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | PEN | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001 | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | 0 | Awaiting S.O.'s response | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | PEN | Approved with Comments | 6 | "Piperack P&IDs" | AWC
000094 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0002 | 0 | 131242-WSW41-CD-IM-0002 | 2023-09-08 | Submission Of BIM Coordination VCM Model (Aug – 2023) | For Information | 2023-10-06 | 2023-09-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000094 | 2023-09-08 | 2023-09-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Aug – 2023)" | INF
000095 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0007 | 0 | 131242-WSW41-MI-IM-0007 | 2023-09-11 | BIM Bi-Weekly Meeting Minutes 0007_20230906 | For Information | 2023-10-09 | 2023-10-03 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000095 | 2023-09-11 | 2023-09-11 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0007_20230906" | INF
000096 | 00 | Darren | Piping/ BS | NA | 131242 | WST02 | CL | B | 0002 | 0 | 131242-WST02-CL-B-0002 | 2023-09-12 | Engineering Calculation Report For Fire Hydrant Pipe | Rev 0: Rejected as requested by contractor. | 2023-10-10 | 2023-11-10 | 43 | Rejected | NO |  | YES | Resubmitted | 0 |  | Kindly refer to Submittal 000193 | 000096&&000193 | 2023-09-12 | 2023-11-17 | 1 | REJ | Not Approved | 2 | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" | NAP
000097 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0003 | 0 | 131242-WST02-CL-B-0003 | 2023-09-12 | Engineering Calculation Report For Potable Water Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-10-10 | 2023-11-10 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097&&000194 | 2023-09-12 | 2023-11-17 | 1 | NAP | (VOID NOT IN USE) | 2 | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" | VOID
000097 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 1 | 131242-WST02-CL-BP-8000 | 2024-05-30 | Engineering Calculation Report For Potable Water Pipe | Rev 1: Not approved - Revise and Resubmit | 2024-06-20 | 2024-07-09 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-08-09 | To check with C2D for resubmission | 000097 | 2024-05-30 | 2025-02-18 | 3 | NAP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" | APP
000097 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 2 | 131242-WST02-CL-BP-8000 | 2024-10-17 | Engineering Calculation Report For Potable Water Pipe | Rev 2: Not approved - Revise and Resubmit | 2024-11-07 | 2024-11-25 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097 | 2024-05-30 | 2025-02-18 | 3 | NAP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" | APP
000097 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 3 | 131242-WST02-CL-BP-8000 | 2025-02-18 | Engineering Calculation Report For Potable Water Pipe | Rev3: Approved | 2025-03-10 | 2025-03-25 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097 | 2024-05-30 | 2025-02-18 | 3 | APP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" | APP
000098 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 0 | 131242-WSW41-RT-PM-0004 | 2023-09-13 | C4B Monthly Progress Report Number No.04 (08/23) | Rev. 0 - Not Approved need to re-submit (see attached comment sheet) | 2023-10-11 | 2023-09-20 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000098 | 2023-09-13 | 2023-10-04 | 1 | NAP | Approved | 2 | "C4B Monthly Progress Report Number No.04 (08/23)" | APP
000098 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 1 | 131242-WSW41-RT-PM-0004 | 2023-10-04 | C4B Monthly Progress Report Number No.04 (08/23) | Approved | 2023-10-24 | 2023-10-06 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000098 | 2023-09-13 | 2023-10-04 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.04 (08/23)" | APP
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | 0 | 131242-WSW41-DR-M-5002 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | 0 | 131242-WSW41-DR-M-5003 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | 0 | 131242-WSW41-DR-M-5004 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | 0 | 131242-WSW41-DR-M-5005 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | 0 | 131242-WSW41-DR-M-5006 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | 0 | 131242-WSW41-DR-M-5007 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | 0 | 131242-WSW41-DR-M-5008 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5001 | A1 | 131242-WSW41-DR-M-5001 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-01 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 | Submitted | Under M2 submission (Shall be Submitted After M3 WT) | 000099 | 2024-03-11 | 2024-03-11 | A1 | AWC | Approved with Comments | 1 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | A1 | 131242-WSW41-DR-M-5002 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | A1 | 131242-WSW41-DR-M-5003 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | A1 | 131242-WSW41-DR-M-5004 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | A1 | 131242-WSW41-DR-M-5005 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | A1 | 131242-WSW41-DR-M-5006 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | A1 | 131242-WSW41-DR-M-5007 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | A1 | 131242-WSW41-DR-M-5008 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" | AWC
000100 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0001 | 0 | 131242-WSD11-PO-M-0001 | 2023-09-14 | Unpriced PO for THP Package (Cambi) | For Information | 2023-10-12 | 2023-11-27 | 52 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000100 | 2023-09-14 | 2023-09-14 | 0 | INF | For Information | 1 | "Unpriced PO for THP Package (Cambi)" | INF
000101 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0005 | 0 | 131242-WSW41-PP-HS-0005 | 2023-09-14 | Heat Stress Prevention Program | Approved | 2023-10-12 | 2023-09-25 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000101 | 2023-09-14 | 2023-09-14 | 0 | APP | Approved | 1 | "Heat Stress Prevention Program" | APP
000102 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 0 | 131242-WSW41-VI-M-0011 | 2023-09-18 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000102 | 2023-09-18 | 2024-06-07 | 2 | AWC | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | APP
000102 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 1 | 131242-WSW41-VI-M-0011 | 2024-01-04 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-24 | 2024-02-15 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Drawings are ready to re-submit. Pending update data sheet from INGERSOLL-RAND. | 000102 | 2023-09-18 | 2024-06-07 | 2 | AWC | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | APP
000102 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 2 | 131242-WSW41-VI-M-0011 | 2024-06-07 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 2: Approved | 2024-06-28 | 2024-07-12 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000102 | 2023-09-18 | 2024-06-07 | 2 | APP | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | APP
000103 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 0 | 131242-WSW41-VI-M-0004 | 2023-09-18 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 |  | 000103 | 2023-09-18 | 2025-05-30 | 1 | AWC | Approved | 2 | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" | APP
000103 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 1 | 131242-WSW41-VI-M-0004 | 2025-05-30 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev1: Approved | 2025-06-19 | 2025-08-01 | 45 | Approved | NO |  | YES | Resubmitted | 0 | 2025-02-20 |  | 000103 | 2023-09-18 | 2025-05-30 | 1 | APP | Approved | 2 | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" | APP
000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0008 | 0 | 131242-WSW41-MI-P-0008 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000104 | 2023-09-19 | 2023-09-19 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | INF
000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0009 | 0 | 131242-WSW41-MI-P-0009 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000104 | 2023-09-19 | 2023-09-19 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | INF
000105 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0012 | 0 | 131242-WSW41-LT-PM-0012 | 2023-09-19 | CV of Team Member (WSHO) | Approved | 2023-10-17 | 2023-10-18 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000105 | 2023-09-19 | 2023-09-19 | 0 | APP | Approved | 1 | "CV of Team Member (WSHO)" | APP
000106 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0004 | 0 | 131242-WSW41-PS-PM-0004 | 2023-09-21 | Monthly Progress Presentation No. 04 (0823) | For Information | 2023-10-19 | 2023-09-25 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000106 | 2023-09-21 | 2023-09-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 04 (0823)" | INF
000107 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 0 | 131242-WSW41-VI-M-0006 | 2023-09-25 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Approved with Comments. To revise and resubmit. Refer to comments file. | 2023-10-23 | 2023-10-16 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | In Progress | 000107 | 2023-09-25 | 2024-07-31 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" | APP
000107 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 1 | 131242-WSW41-VI-M-0006 | 2024-07-31 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Rev 1: Approved | 2024-08-21 | 2024-09-02 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000107 | 2023-09-25 | 2024-07-31 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" | APP
000108 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | Superceded | 131242-WSW41-CT-W-0001 | 2023-09-27 | On-Demand Bond for THP System | Rev(0): Rejected as requested by Contractor. Note Contractor need to attach a transmittal signed by PUB to the said submittal. | 2023-10-25 | 2023-10-02 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000108 | 2023-09-27 | 2023-10-03 | 0 | REJ | Approved | 2 | "On-Demand Bond for THP System" | APP
000108 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | 0 | 131242-WSW41-CT-W-0001 | 2023-10-03 | On-Demand Bond for THP System | Approved. | 2023-10-23 | 2023-10-09 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000108 | 2023-09-27 | 2023-10-03 | 0 | APP | Approved | 2 | "On-Demand Bond for THP System" | APP
000109 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0010 | 0 | 131242-WSW41-MI-C-0010 | 2023-09-27 | CSA Meeting Minutes 0010_20230802 | For Information | 2023-10-25 | 2023-10-18 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000109 | 2023-09-27 | 2023-09-27 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0010_20230802" | INF
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | 0 | 131242-WST00-DR-S-0001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 | 2024-07-18 | MEICA layout released on 29/02/2024. Updating as per latest Layout changes of SSN-SH-002 area with Pump pit. Tenwit updating In-Progress. | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | 0 | 131242-WST00-DR-S-0002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | 0 | 131242-WST00-DR-S-0003_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | 0 | 131242-WST02-DR-S-1006_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | 0 | 131242-WST02-DR-S-1007_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | 0 | 131242-WST02-DR-S-1008_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST606 | 0 | 131242-WST02-DR-S-1013_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | 0 | 131242-WST02-DR-S-3000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST606 | 0 | 131242-WST02-DR-S-3001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5000_ST606 | 0 | 131242-WST02-DR-S-5000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606 | 0 | 131242-WST02-DR-S-5001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606 | 0 | 131242-WST02-DR-S-5002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST606 | 0 | 131242-WST02-DR-S-5005_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | 0 | 131242-WST02-DR-S-7000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | 0 | 131242-WST02-DR-S-7001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | 0 | 131242-WST02-DR-S-7002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST606 | 0 | 131242-WST02-DR-S-8001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " | NAP
000111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0003 | 0 | 131242-WSW41-PC-W-0003 | 2023-09-29 | PAYMENT CLAIM NO.3 | Approved | 2023-10-27 | 2023-10-23 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000111 | 2023-09-29 | 2023-09-29 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.3" | APP
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-1_URA | 0 | 131242-WST02-DR-A-3D-1_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "SSN URA Submission" | NAP
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-2_URA | 0 | 131242-WST02-DR-A-3D-2_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "SSN URA Submission" | NAP
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A | 131242-WST02-DR-A-1000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A | 131242-WST02-DR-A-1001_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A | 131242-WST02-DR-A-1002_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A | 131242-WST02-DR-A-1003_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A | 131242-WST02-DR-A-1004_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A | 131242-WST02-DR-A-1006_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A | 131242-WST02-DR-A-1009_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A | 131242-WST02-DR-A-2000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A | 131242-WST02-DR-A-2001_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A | 131242-WST02-DR-A-2002_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A | 131242-WST02-DR-A-2003_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | NAP | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" | NAP
000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" | NAP
000112 | 00 | Zora | CSA | NA | GFA DWG Supporting Docs | NA | NA | NA | NA | NA | GFA DWG Supporting Docs-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" | NAP
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-06 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | S000112.0_Reply_2023 10 17 | NA | NA | NA | NA | A1 | S000112.0_Reply_2023 10 17-NA-NA-NA-NA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-10-17 | A1 | AWC | Approved with Comments | 1 | "SSN URA Submission" | AWC
000112 | 01 | Zora | CSA | NA | Supporting Docs | NA | NA | NA | NA | NA | Supporting Docs-NA-NA-NA-NA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-10-17 | NA | AWC | Approved with Comments | 1 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 | 2024-08-16 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" | AWC
000112 | 02 | Zora/ HP | CSA | NA | S000112.1_Reply_2023 10 17 | NA | NA | NA | NA | NA | S000112.1_Reply_2023 10 17-NA-NA-NA-NA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-11-07 | 2023-11-07 | NA | AWC | Approved with Comments | 1 | "SSN URA Submission" | AWC
000113 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | E | 0001 | 0 | 131242-WSW41-MS-E-0001 | 2023-10-04 | MSRA, SWP for Soil Resistivity Test | Approved with Comments | 2023-11-01 | 2023-10-13 | 7 | Approved with Comments | YES | 2023-11-02 | NO | Resubmitted | 0 |  |  | 000113 | 2023-10-04 | 2023-10-04 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Soil Resistivity Test" | AWC
000114 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0008 | 0 | 131242-WSW41-MI-IM-0008 | 2023-10-05 | BIM Bi-Weekly Meeting Minutes 0008_20230920 | For Information | 2023-11-02 | 2023-10-16 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000114 | 2023-10-05 | 2023-10-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0008_20230920" | INF
000115 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 0 | 131242-WSW41-PP-PC-0002 | 2023-10-05 | Project Control Plan | Rev. 0 - Approved with comments, need to re-submit (refer comment sheet) | 2023-11-02 | 2023-10-27 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000115 | 2023-10-05 | 2023-11-10 | 1 | AWC | Approved | 2 | "Project Control Plan" | APP
000115 | 01 | Stanley | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 1 | 131242-WSW41-PP-PC-0002 | 2023-11-10 | Project Control Plan | Rev. 1 - Approved. | 2023-12-01 | 2023-11-15 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000115 | 2023-10-05 | 2023-11-10 | 1 | APP | Approved | 2 | "Project Control Plan" | APP
000116 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0002 | 0 | 131242-WSW41-CN-M-0002 | 2023-10-06 | Proposed change of Manufacturer for SSN Aeration blowers | Rejected as CES requested as No RFC is needed according to the discussion with S.O. | 2023-11-03 | 2023-10-25 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000116 | 2023-10-06 | 2023-10-06 | 0 | REJ | Rejected | 1 | "Proposed change of Manufacturer for SSN Aeration blowers" | REJ
000117 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 0 | 131242-WSW41-CN-M-0001 | 2023-10-06 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Rev 0: Not approved - Revise and Resubmit | 2023-11-03 | 2023-11-28 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000117 | 2023-10-06 | 2023-12-12 | 1 | NAP | Approved with Comments | 2 | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" | AWC
000117 | 01 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 1 | 131242-WSW41-CN-M-0001 | 2023-12-12 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-03 | 2024-01-29 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000117 | 2023-10-06 | 2023-12-12 | 1 | AWC | Approved with Comments | 2 | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" | AWC
000118 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 0 | 131242-WSW41-MS-C-0004 | 2023-10-06 | MSRA, SWP for Bored Piling Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000118 | 2023-10-06 | 2023-11-01 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Bored Piling Work" | AWC
000118 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 1 | 131242-WSW41-MS-C-0004 | 2023-11-01 | MSRA, SWP for Bored Piling Work | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-22 | 2023-12-01 | 22 | Approved with Comments | YES | 2023-12-21 | NO | Resubmitted | 0 |  |  | 000118 | 2023-10-06 | 2023-11-01 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Bored Piling Work" | AWC
000119 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0005 | 0 | 131242-WSW41-MS-C-0005 | 2023-10-06 | MSRA, SWP for Site Set-Up & Associated Works (Seong) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-19 | 9 | Approved with Comments | YES | 2023-11-08 | NO | Resubmitted | 0 |  |  | 000119 | 2023-10-06 | 2023-10-06 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | AWC
000120 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003 | 2023-10-06 | Milestone 1.1 (Sidewide piperack) | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-11-03 | 2024-03-28 | 124 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000121 | 2023-10-06 | 2023-10-10 | 0 | AWC | For Information | 2 | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | INF
000120 | 01 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 0 | 131242-WSW41-CD-IM-0028 | 2024-05-27 | Milestone 1.2 Sitewide Pipe Rack | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-05-27 | 2024-06-05 | 1 | NAP | Approved with Comments | 2 | "Milestone 1.2 Sitewide Pipe Rack" | AWC
000120 | 02 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 1 | 131242-WSW41-CD-IM-0028 | 2024-06-05 | Milestone 1.2 Sitewide Pipe Rack | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-05-27 | 2024-06-05 | 1 | AWC | Approved with Comments | 2 | "Milestone 1.2 Sitewide Pipe Rack" | AWC
000120 | 03 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2024-08-24 | Milestone 2 Sitewide Pipe Rack | Rev3: Not Approved, as requested by contractor. | 2024-09-12 | 2024-10-01 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | REJ | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | NAP | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.2 | 131242-WSW41-DR-M-1000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.2 | 131242-WSW41-DR-M-3000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.2 | 131242-WSW41-DR-M-3001 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.2 | 131242-WSW41-DR-M-3002 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.2 | 131242-WSW41-DR-M-3003 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.2 | 131242-WSW41-DR-M-3004 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.2 | 131242-WSW41-DR-M-3005 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.2 | 131242-WSW41-DR-M-4000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.2 | 131242-WSW41-DR-M-4001 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.2 | 131242-WSW41-DR-M-4002 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.2 | 131242-WSW41-DR-M-4003 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.2 | 131242-WSW41-DR-M-4004 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.2 | 131242-WSW41-DR-M-4005 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.2 | 131242-WSW41-DR-M-8000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | AWC | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | A.2 | 131242-WSW41-DR-EK-1000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | A.2 | 131242-WSW41-DR-EK-3000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.3 | 131242-WSW41-DR-M-1000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.3 | 131242-WSW41-DR-M-3000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.3 | 131242-WSW41-DR-M-3001 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.3 | 131242-WSW41-DR-M-3002 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.3 | 131242-WSW41-DR-M-3003 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.3 | 131242-WSW41-DR-M-3004 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.3 | 131242-WSW41-DR-M-3005 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.3 | 131242-WSW41-DR-M-4000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.3 | 131242-WSW41-DR-M-4001 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.3 | 131242-WSW41-DR-M-4002 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.3 | 131242-WSW41-DR-M-4003 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.3 | 131242-WSW41-DR-M-4004 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.3 | 131242-WSW41-DR-M-4005 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.3 | 131242-WSW41-DR-M-8000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" | AWC
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 1 | 131242-WSW41-CD-IM-0042 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | AWC | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | AWC
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 1130 | A | 131242-WSW41-DR-E-1130 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2025-10-08 | 2025-10-08 | A | AWC | Approved with Comments | 1 | "Milestone 3 Sitewide Pipe Rack" | AWC
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 3000 | A | 131242-WSW41-DR-E-3000 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2025-10-08 | 2025-10-08 | A | AWC | Approved with Comments | 1 | "Milestone 3 Sitewide Pipe Rack" | AWC
000121 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003 | 2023-10-10 | Submission Of BIM Coordination VCM Model (Sept – 2023) | For Information | 2023-11-07 | 2023-10-23 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000121 | 2023-10-06 | 2023-10-10 | 0 | INF | For Information | 2 | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | INF
000122 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0006 | 0 | 131242-WSW41-MS-C-0006 | 2023-10-10 | MSRA, SWP for Erection of Site Office (Cape) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-07 | 2023-10-18 | 6 | Approved with Comments | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000122 | 2023-10-10 | 2023-10-10 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Erection of Site Office (Cape)" | AWC
000123 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0006 | 0 | 131242-WSW41-PP-HS-0006 | 2023-10-10 | Traffic Management Plan | Approved | 2023-11-07 | 2023-10-18 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000123 | 2023-10-10 | 2023-10-10 | 0 | APP | Approved | 1 | "Traffic Management Plan " | APP
000124 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | PP | PM | 0003 | 0 | 131242-WSW41-PP-PM-0003 | 2023-10-10 | Project Execution Plan | Rev. 0 - Not Approved - need to re-submit (refer comment sheet) | 2023-11-07 | 2023-10-27 | 13 | Not Approved | YES | 2023-11-16 | NO | Resubmitted | 0 |  |  | 000124 | 2023-10-10 | 2023-10-10 | 0 | NAP | Not Approved | 1 | "Project Execution Plan" | NAP
000125 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0011 | 0 | 131242-WSW41-VI-C-0011 | 2023-10-11 | Vendor Approval of UXO Survey – EXPLOMO | Approved | 2023-11-08 | 2023-10-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000125 | 2023-10-11 | 2023-10-11 | 0 | APP | Approved | 1 | "Vendor Approval of UXO Survey – EXPLOMO" | APP
000126 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0010 | 0 | 131242-WSW41-MI-P-0010 | 2023-10-12 | Process & MEICA Meeting Minutes 0010_20230928 | For Information | 2023-11-09 | 2024-03-18 | 112 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000126 | 2023-10-12 | 2023-10-12 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0010_20230928" | INF
000127 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0005 | 0 | 131242-WSW41-RT-PM-0005 | 2023-10-14 | C4B Monthly Progress Report Number No.05 (09/23) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-10 | 2023-10-27 | 9 | Not Approved | YES | 2023-11-16 | NO | Resubmitted | 0 |  |  | 000127 | 2023-10-14 | 2023-10-14 | 0 | NAP | Not Approved | 1 | "C4B Monthly Progress Report Number No.05 (09/23)" | NAP
000128 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A | 131242-WST00-DR-C-8001_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | 1 | 131242-WST00-DR-C-8001_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-19 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A | 131242-WST02-DR-C-3001_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A.1 | 131242-WST00-DR-C-8001_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A.1 | 131242-WST02-DR-C-5004_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A.1 | 131242-WST02-DR-C-5005_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A.1 | 131242-WST02-DR-C-5006_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A.1 | 131242-WST02-DR-C-5007_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A.1 | 131242-WST02-DR-C-1023_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A.1 | 131242-WST02-DR-C-1024_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A.1 | 131242-WST02-DR-C-3000_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A.1 | 131242-WST02-DR-C-3001_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000128 | 03 | Zora | CSA | NA | 131242 | NA | NA | NA | S# 128 Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-NA-S# 128 Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  | To close after addressing the comments of S#475 . Zora to follow up with Grace for JMH calculation | 000128 | 2024-06-12 | 2024-06-12 | NA | NAP | Not Approved | 1 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | NAP
000128 | 04 | Aaron | CSA | NA | 131242 | WST02 | NA | C | S# 128 Cmt Sheet Reply 2024 10 08 | NA | 131242-WST02-NA-C-S# 128 Cmt Sheet Reply 2024 10 08 | 2024-10-08 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-28 | 2024-10-29 | 15 | Not Approved | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000128 | 2024-10-08 | 2024-10-08 | NA | NAP | Not Approved | 1 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | NAP
000129 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0007 | 0 | 131242-WSW41-MS-C-0007 | 2023-10-17 | MSRA, SWP for Erection of Site Office (UXO) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | YES | 2023-11-21 | NO | Resubmitted | 0 |  |  | 000129 | 2023-10-17 | 2023-10-17 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Erection of Site Office (UXO)" | AWC
000130 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0004 | 0 | 131242-WSW41-PC-W-0004 | 2023-10-18 | PAYMENT CLAIM NO.4 | Rev(0): Approved. Please refer to S.O. correspondence no. 73 dated 20 Oct 2023. | 2023-11-16 | 2023-10-23 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000130 | 2023-10-18 | 2023-10-18 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.4" | APP
000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0011 | 0 | 131242-WSW41-MI-C-0011 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000131 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" | INF
000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0012 | 0 | 131242-WSW41-MI-C-0012 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000131 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" | INF
000132 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 0 | 131242-WSW41-SP-C-0003 | 2023-10-19 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-17 | 2023-11-17 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000132 | 2023-10-19 | 2023-12-21 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | APP
000132 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 1 | 131242-WSW41-SP-C-0003 | 2023-12-21 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Approved | 2024-01-12 | 2024-01-15 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000132 | 2023-10-19 | 2023-12-21 | 1 | APP | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | APP
000133 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 0 | 131242-WSD11-BQ-P-0001 | 2023-10-20 | THP Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-20 | 2023-11-27 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000133 | 2023-10-20 | 2024-04-26 | 1 | AWC | Approved with Comments | 2 | "THP Equipment List" | AWC
000133 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 1 | 131242-WSD11-BQ-P-0001 | 2024-04-26 | THP Equipment List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-17 | 2024-05-27 | 21 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2024-07-31 |  | 000133 | 2023-10-20 | 2024-04-26 | 1 | AWC | Approved with Comments | 2 | "THP Equipment List" | AWC
000134 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0012 | 0 | 131242-WSW41-VI-C-0012 | 2023-10-23 | Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-11-17 | 19 | Approved with Comments | YES | 2023-12-07 | NO | Resubmitted | 0 |  |  | 000134 | 2023-10-23 | 2023-10-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD." | AWC
000135 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 0 | 131242-WSW41-VI-M-0002 | 2023-10-23 | Preliminary Design and Vendor Approval of Blower (Robuschi) | Rev 0: Not approved - Revise and Resubmit | 2023-11-21 | 2023-11-27 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000135 | 2023-10-23 | 2024-06-25 | 2 | NAP | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | AWC
000135 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 1 | 131242-WSW41-VI-M-0002 | 2023-12-26 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-16 | 2024-01-29 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To re-submit after vendor provide update data sheet and drawing. Kick-off meeting done on 26 March | 000135 | 2023-10-23 | 2024-06-25 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | AWC
000135 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 2 | 131242-WSW41-VI-M-0002 | 2024-06-25 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-07-15 | 2024-07-31 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000135 | 2023-10-23 | 2024-06-25 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | AWC
000136 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SK | Z | 0001 | 0 | 131242-WSW41-SK-Z-0001 | 2023-10-23 | Time Lapse Camera Location | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-12-18 | 40 | Approved with Comments | YES | 2024-01-05 | NO | Resubmitted | 0 |  |  | 000136 | 2023-10-23 | 2023-10-23 | 0 | AWC | Approved with Comments | 1 | "Time Lapse Camera Location" | AWC
000137 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0005 | 0 | 131242-WSW41-PS-PM-0005 | 2023-10-25 | Monthly Progress Presentation No. 05 (0923) | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000137 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 05 (0923)" | INF
000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0003 | 0 | 131242-WSW41-MI-PM-0003 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000138 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | INF
000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0004 | 0 | 131242-WSW41-MI-PM-0004 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000138 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | INF
000139 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 0 | 131242-WSW41-VI-M-0003 | 2023-10-25 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-11-23 | 2023-12-22 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 | Yibo to check with JK for process data. Vendor need to provide revised design data and layout drawings once Process confirmed. | 000139 | 2023-10-25 | 2024-11-06 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" | APP
000139 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 1 | 131242-WSW41-VI-M-0003 | 2024-11-06 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 1: Approved | 2024-11-26 | 2025-03-04 | 84 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000139 | 2023-10-25 | 2024-11-06 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" | APP
000140 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0001 | 0 | 131242-WSD11-PS-P-0001 | 2023-10-25 | Thermal Hydrolysis Process Presentation | For Information | 2023-11-23 | 2023-11-27 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000140 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Thermal Hydrolysis Process Presentation" | INF
000141 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 0 | 131242-WSD11-CH-P-0001 | 2023-10-25 | Process Functional Description | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-23 | 64 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000141 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 1 | 131242-WSD11-CH-P-0001 | 2024-04-02 | Process Functional Description | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-04-26 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-08-30 | R0: AWC | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000141 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 2 | 131242-WSD11-CH-P-0001 | 2024-07-28 | Process Functional Description | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000141 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 3 | 131242-WSD11-CH-P-0001 | 2024-09-30 | Process Functional Description | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-12-05 | 48 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000142 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 0 | 131242-WSD11-CH-P-0002 | 2023-10-25 | Process Design Basis | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-15 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" | AWC
000142 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 1 | 131242-WSD11-CH-P-0002 | 2024-03-20 | THP Process Design Basis | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-26 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-08-30 | R0: AWC | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" | AWC
000142 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 2 | 131242-WSD11-CH-P-0002 | 2024-07-28 | THP Process Design Basis | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" | AWC
000142 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 3 | 131242-WSD11-CH-P-0002 | 2024-11-04 | THP Process Design Basis | Rev 3: Approved with Comments. No active comments on the document. Resubmittal is required if there are any changes during detail engineering. No resubmittal at the moment. | 2024-11-22 | 2025-01-02 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" | AWC
000143 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2024-08-26 | B | NAP | Approved with Comments | 3 | "THP Process Flow Diagram" | AWC
000143 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | NAP
000143 | 00 | Joo Kwan | Process | NA | DGN FILES | WSD11 | DR | P | 7001 | A | DGN FILES-WSD11-DR-P-7001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2023-10-26 | A | NAP | Not Approved | 1 | "THP Process Flow Diagram" | NAP
000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001 | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-08 | 2024-03-28 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 |  | 000143 | 2023-10-26 | 2024-08-26 | B | AWC | Approved with Comments | 3 | "THP Process Flow Diagram" | AWC
000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | A | 131242-WSD11-DR-P-7002 | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-17 | 2024-03-28 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2024-03-18 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "THP Process Flow Diagram" | AWC
000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | B | 131242-WSD11-DR-P-7001 | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | 33 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2024-08-26 | B | AWC | Approved with Comments | 3 | "THP Process Flow Diagram" | AWC
000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | B | 131242-WSD11-DR-P-7002 | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | 33 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  |  | 000143 | 2024-03-18 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "THP Process Flow Diagram" | AWC
000144 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 0 | 131242-WSW41-QA-C-0001 | 2023-10-27 | Inspection Test Plan for Earthwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000144 | 2023-10-27 | 2023-12-21 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Earthwork" | APP
000144 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 1 | 131242-WSW41-QA-C-0001 | 2023-12-21 | Inspection Test Plan for Earthwork | Approved | 2024-01-12 | 2024-01-15 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000144 | 2023-10-27 | 2023-12-21 | 1 | APP | Approved | 2 | "Inspection Test Plan for Earthwork" | APP
000145 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 0 | 131242-WSW41-QA-C-0002 | 2023-10-27 | Inspection Test Plan for Bored piling work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Bored piling work" | APP
000145 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002 | 2023-12-21 | Inspection Test Plan for Bored piling work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | AWC | Approved | 3 | "Inspection Test Plan for Bored piling work" | APP
000145 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002 | 2024-01-29 | Inspection Test Plan for Bored piling work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Bored piling work" | APP
000146 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 0 | 131242-WSW41-QA-C-0003 | 2023-10-27 | Inspection Test Plan for Reinforcement work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Reinforcement work" | APP
000146 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003 | 2023-12-21 | Inspection Test Plan for Reinforcement work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | AWC | Approved | 3 | "Inspection Test Plan for Reinforcement work" | APP
000146 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003 | 2024-01-29 | Inspection Test Plan for Reinforcement work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Reinforcement work" | APP
000147 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 0 | 131242-WSW41-QA-C-0004 | 2023-10-27 | Inspection Test Plan for Concreting Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Concreting Work" | APP
000147 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004 | 2023-12-21 | Inspection Test Plan for Concreting Work | Not Approved. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-12 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Concreting Work" | APP
000147 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004 | 2024-01-29 | Inspection Test Plan for Concreting Work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Concreting Work" | APP
000148 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 0 | 131242-WSW41-QA-C-0005 | 2023-10-27 | Inspection Test Plan for Formwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000148 | 2023-10-27 | 2023-12-21 | 1 | NAP | Approved with Comments | 2 | "Inspection Test Plan for Formwork" | AWC
000148 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 1 | 131242-WSW41-QA-C-0005 | 2023-12-21 | Inspection Test Plan for Formwork | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | YES | 2024-02-02 | NO | Resubmitted | 0 | 2024-03-13 |  | 000148 | 2023-10-27 | 2023-12-21 | 1 | AWC | Approved with Comments | 2 | "Inspection Test Plan for Formwork" | AWC
000149 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0006 | 0 | 131242-WSW41-QA-C-0006 | 2023-10-27 | Inspection Test Plan for Waterproofing Concrete and Application Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | YES | 2023-12-07 | NO | Resubmitted | 0 | 2024-01-11 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000149 | 2023-10-27 | 2023-10-27 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Waterproofing Concrete and Application Work" | NAP
000150 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0007 | 0 | 131242-WSW41-QA-C-0007 | 2023-10-27 | Inspection Test Plan for Roadwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | YES | 2023-12-07 | NO | Resubmitted | 0 | 2024-01-12 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000150 | 2023-10-27 | 2023-10-27 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Roadwork" | NAP
000151 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | E | 0000 | 0 | 131242-WSD11-BQ-E-0000 | 2023-10-27 | THP-Electrical Load List | Approved with comments. To Revise and resubmit. Please refer to the comment sheet. | 2023-11-27 | 2024-02-02 | 70 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" | AWC
000151 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 1 | 131242-WSD11-BQ-E-0000 | 2024-03-28 | THP-Electrical Load List | Rev 0: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2024-04-19 | 2024-08-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" | AWC
000151 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 2 | 131242-WSD11-BQ-E-0000 | 2025-02-10 | THP-Electrical Load List | Rev 2: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 60 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" | AWC
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0009 | 0 | 131242-WSW41-MI-IM-0009 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | INF
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0009 | 0 | 131242-WSW41-PS-IM-0009 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | INF
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0010 | 0 | 131242-WSW41-MI-IM-0010 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | INF
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0010 | 0 | 131242-WSW41-PS-IM-0010 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | INF
000153 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0011 | 0 | 131242-WSW41-MI-P-0011 | 2023-10-30 | Process & MEICA Meeting Minutes 0011_20231012 | For Information | 2023-11-28 | 2024-03-18 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000153 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0011_20231012" | INF
000154 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0015 | 0 | 131242-WSW41-LT-PM-0015 | 2023-10-31 | CV of Team Member (WSHC) | Approved | 2023-11-29 | 2023-12-04 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000154 | 2023-10-31 | 2023-10-31 | 0 | APP | Approved | 1 | "CV of Team Member (WSHC)" | APP
000155 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0002 | 0 | 131242-WSW41-CT-W-0002 | 2023-10-31 | Professional Indemnity Insurance Letter | Acceptable for information. | 2023-11-29 | 2023-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000155 | 2023-10-31 | 2023-10-31 | 0 | INF | For Information | 1 | "Professional Indemnity Insurance Letter" | INF
000156 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LT | AGC | 0001 | 0 | 131242-WSW41-LT-AGC-0001 | 2023-11-02 | Approval Letter to Commence Works Requiring Earth Control Measure | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-01 | 2023-11-09 | 5 | Approved with Comments | YES | 2023-11-29 | NO | Resubmitted | 0 |  |  | 000156 | 2023-11-02 | 2023-11-02 | 0 | AWC | Approved with Comments | 1 | "Approval Letter to Commence Works Requiring Earth Control Measure" | AWC
000157 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0002 | 0 | 131242-WSW41-PS-HS-0002 | 2023-11-02 | Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023 | For Information | 2023-12-01 | 2023-12-01 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000157 | 2023-11-02 | 2023-11-02 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | INF
000158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 0 | 131242-WST02-BQ-E-0000 | 2023-11-03 | SSN Electrical Load List | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2023-12-04 | 2024-04-29 | 126 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000158 | 2023-11-03 | 2025-02-10 | 1 | AWC | Approved with Comments | 2 | "SSN Electrical Load List" | AWC
000158 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 1 | 131242-WST02-BQ-E-0000 | 2025-02-10 | SSN Electrical Load List | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 60 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000158 | 2023-11-03 | 2025-02-10 | 1 | AWC | Approved with Comments | 2 | "SSN Electrical Load List" | AWC
000159 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0007 | 0 | 131242-WSW41-PP-HS-0007 | 2023-11-03 | Haze Management Plan | Approved | 2023-12-04 | 2023-12-01 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000159 | 2023-11-03 | 2023-11-03 | 0 | APP | Approved | 1 | "Haze Management Plan " | APP
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | A | 131242-WST02-DR-EL-1000 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | A | 131242-WST02-DR-EL-1001 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | A | 131242-WST02-DR-EL-1002 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | A | 131242-WST02-DR-EL-1003 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | A | 131242-WST02-DR-EL-1004 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | AWC
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA | PENDING C2D | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | B | 131242-WST02-DR-EL-1002 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | B | 131242-WST02-DR-EL-1003 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | AWC
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | C | 131242-WST02-DR-EL-1000 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | C | 131242-WST02-DR-EL-1001 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | C | 131242-WST02-DR-EL-1002 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | C | 131242-WST02-DR-EL-1003 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | C | 131242-WST02-DR-EL-1004 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | AWC
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | D | 131242-WST02-DR-EL-1000 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | D | 131242-WST02-DR-EL-1001 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | D | 131242-WST02-DR-EL-1002 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | D | 131242-WST02-DR-EL-1003 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 4 | "SSN Lighting Layout Plan" | AWC
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | D | 131242-WST02-DR-EL-1004 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | AWC
000161 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0004 | D | 131242-WST02-CD-IM-0004 | 2023-11-06 | Submission of Milestone 1.1 Underground Services Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2023-11-06 | 2023-11-06 | D | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 Underground Services Model" | AWC
000161 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-IM-0022 | 2024-05-27 | Milestone 1.2 Underground Services | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | NAP | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | AWC
000161 | 02 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 1 | 131242-WST02-CD-IM-0022 | 2024-06-05 | Milestone 1.2 Underground Services | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | This M2 submission includes all discipline documents for the relevant area. | 000161 | 2024-10-05 | 2025-09-29 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1300 | A | 131242-WST02-DR-E-1300 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1301 | A | 131242-WST02-DR-E-1301 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1302 | A | 131242-WST02-DR-E-1302 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3300 | A | 131242-WST02-DR-E-3300 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3301 | A | 131242-WST02-DR-E-3301 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1022 | A.2 | 131242-WST02-DR-M-1022 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000161 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044 | 2025-09-29 | Milestone 3 Underground Services | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-17 | 2026-01-27 | 86 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  | This M2 submission includes all discipline documents for the relevant area. | 000161 | 2024-10-05 | 2025-09-29 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | AWC
000162 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005 | 2023-11-06 | Submission of Milestone 1.1 Pump Stataion and Blower Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000164 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 2 | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" | AWC
000162 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2024-05-27 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 | Requested to reject on 03 June |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | NAP | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | NAP
000162 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 1 | 131242-WST02-CD-IM-0025 | 2024-06-05 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | AWC | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | AWC | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | C | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | B | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | NAP | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | C | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | B | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | NAP
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 438 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | NAP | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | NAP
000163 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0007 | 0 | 131242-WST02-CD-IM-0007 | 2023-11-06 | Submission of Milestone 1.1 Water Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 Water Tank" | AWC
000163 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-IM-0023 | 2024-06-03 | Milestone 1.2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-24 | 2024-07-05 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000367 | 2024-03-18 | 2024-06-03 | 0 | AWC | Approved with Comments | 2 | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0055 | 0 | 131242-WST02-CD-IM-0055 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | 0 | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | NAP
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1315 | A | 131242-WST02-DR-E-1315 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3324 | A | 131242-WST02-DR-E-3324 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3325 | A | 131242-WST02-DR-E-3325 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3326 | A | 131242-WST02-DR-E-3326 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3327 | A | 131242-WST02-DR-E-3327 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3328 | A | 131242-WST02-DR-E-3328 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1112 | A | 131242-WST02-DR-I-1112 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1113 | A | 131242-WST02-DR-I-1113 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1114 | A | 131242-WST02-DR-I-1114 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3028 | A | 131242-WST02-DR-I-3028 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3029 | A | 131242-WST02-DR-I-3029 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3030 | A | 131242-WST02-DR-I-3030 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3031 | A | 131242-WST02-DR-I-3031 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3033 | A | 131242-WST02-DR-I-3033 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1003 | A | 131242-WST02-DR-M-1003 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1006 | A | 131242-WST02-DR-M-1006 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3001 | A | 131242-WST02-DR-M-3001 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3002 | A | 131242-WST02-DR-M-3002 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3005 | A | 131242-WST02-DR-M-3005 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4001 | A | 131242-WST02-DR-M-4001 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000461 | 2024-05-06 | 2025-04-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1008 | A | 131242-WST02-DR-M-1008 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1010 | A | 131242-WST02-DR-M-1010 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1012 | A | 131242-WST02-DR-M-1012 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1015 | A | 131242-WST02-DR-M-1015 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1016 | A | 131242-WST02-DR-M-1016 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" | AWC
000163 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052 | 2025-12-16 | Milestone 3 SSN Water Tank | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-01-27 | 30 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000163&&001034 | 2025-02-10 | 2025-12-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | AWC
000164 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005 | 2023-11-06 | Submission of Milestone 1.1 Astrea Separator Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000164 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 2 | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" | AWC
000164 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-IM-0024 | 2024-06-04 | Milestone 1.2 SSN Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 442 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | AWC
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | A | 131242-WST02-CL-EL-7000 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | A | 131242-WST02-CL-EL-7001 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | A | 131242-WST02-CL-EL-7002 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | A | 131242-WST02-CL-EL-7003 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | A | 131242-WST02-CL-EL-7004 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | B | 131242-WST02-CL-EL-7000 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | B | 131242-WST02-CL-EL-7001 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | B | 131242-WST02-CL-EL-7002 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | B | 131242-WST02-CL-EL-7003 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | B | 131242-WST02-CL-EL-7004 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" | INF
000166 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 0 | 131242-WSW41-QA-A-0001 | 2023-11-06 | Inspection Test Plan for Architectural work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-07 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000166 | 2023-11-06 | 2024-12-05 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Architectural work " | APP
000166 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 1 | 131242-WSW41-QA-A-0001 | 2024-12-05 | Inspection Test Plan for Architectural work | Rev.1: Approved | 2024-12-26 | 2024-12-23 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000166 | 2023-11-06 | 2024-12-05 | 1 | APP | Approved | 2 | "Inspection Test Plan for Architectural work " | APP
000167 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 0 | 131242-WSW41-QA-A-0002 | 2023-11-06 | Inspection Test Plan for Plastering and Painting Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000167 | 2023-11-06 | 2024-12-13 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Plastering and Painting Work" | APP
000167 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 1 | 131242-WSW41-QA-A-0002 | 2024-12-13 | Inspection Test Plan for Plastering and Painting Work | Rev 1 Approved | 2025-01-03 | 2024-12-23 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000167 | 2023-11-06 | 2024-12-13 | 1 | APP | Approved | 2 | "Inspection Test Plan for Plastering and Painting Work" | APP
000168 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0003 | 0 | 131242-WSW41-QA-A-0003 | 2023-11-06 | Inspection Test Plan for Installation of Raised Access Floor System Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 22 | Not Approved | YES | 2023-12-26 | NO | Resubmitted | 0 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000168 | 2023-11-06 | 2023-11-06 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Installation of Raised Access Floor System Work" | NAP
000169 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0004 | 0 | 131242-WSW41-QA-A-0004 | 2023-11-06 | Inspection Test Plan for Installation of Door and Window Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-12 | 26 | Not Approved | YES | 2024-01-01 | NO | Resubmitted | 0 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000169 | 2023-11-06 | 2023-11-06 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Installation of Door and Window Work" | NAP
000170 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 0 | 131242-WSW41-VI-M-1001 | 2023-11-06 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-02-14 | 72 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | AWC
000170 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 1 | 131242-WSW41-VI-M-1001 | 2024-11-23 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-14 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | AWC
000170 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 2 | 131242-WSW41-VI-M-1001 | 2025-01-21 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-10 | 2025-04-27 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | AWC
000171 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | A | 131242-WSD11-DR-I-7000 | 2023-11-06 | THP Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2023-12-05 | 2023-11-21 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000171 | 2023-11-06 | 2024-07-29 | C | NAP | Approved with Comments | 3 | "THP Control System Architecture Drawing" | AWC
000171 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | B | 131242-WSD11-DR-I-7000 | 2024-03-13 | THP Control System Architecture Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-03 | 2024-06-13 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000171 | 2023-11-06 | 2024-07-29 | C | NAP | Approved with Comments | 3 | "THP Control System Architecture Drawing" | AWC
000171 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7000 | C | 131242-WSD11-DR-I-7000 | 2024-07-29 | THP Control System Architecture Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-19 | 2024-08-30 | 24 | Approved with Comments | YES | 2024-09-19 | NO | Resubmitted | 0 |  |  | 000171 | 2023-11-06 | 2024-07-29 | C | AWC | Approved with Comments | 3 | "THP Control System Architecture Drawing" | AWC
000172 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 0 | 131242-WSD11-CL-P-0001 | 2023-11-08 | THP Compressed Air Calculation | Approved with Comments. To revise and resubmit. Refer to comments files | 2023-12-07 | 2024-01-17 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" | AWC
000172 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 1 | 131242-WSD11-CL-P-0001 | 2024-04-19 | THP Compressed Air Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-07-26 | 70 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" | AWC
000172 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 2 | 131242-WSD11-CL-P-0001 | 2024-08-15 | THP Compressed Air Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-11-07 | 60 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" | AWC
000173 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 0 | 131242-WST02-CL-P-0001 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | 2 | AWC | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000173 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | A | 131242-WST02-DR-P-7011 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | AWC | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000173 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 1 | 131242-WST02-CL-P-0001 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | 2 | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000173 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | B | 131242-WST02-DR-P-7011 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000173 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 2 | 131242-WST02-CL-P-0001 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  | Resubmitted as per SO comments | 000173 | 2023-11-08 | 2024-08-07 | 2 | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000173 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | C | 131242-WST02-DR-P-7011 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " | APP
000174 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0006 | 0 | 131242-WSW41-RT-PM-0006 | 2023-11-08 | C4B Monthly Progress Report Number No.06 (10/23) | Rev. 0 - Approved | 2023-12-07 | 2023-11-21 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000174 | 2023-11-08 | 2023-11-08 | 0 | APP | Approved | 1 | "C4B Monthly Progress Report Number No.06 (10/23)" | APP
000175 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0009 | 0 | 131242-WSW41-CD-IM-0009 | 2023-11-08 | Submission Of BIM Coordination VCM Model (Oct – 2023) | For Information | 2023-12-07 | 2023-11-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000175 | 2023-11-08 | 2023-11-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Oct – 2023)" | INF
000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0011 | 0 | 131242-WSW41-MI-IM-0011 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000176 | 2023-11-09 | 2023-11-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" | INF
000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0011 | 0 | 131242-WSW41-PS-IM-0011 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000176 | 2023-11-09 | 2023-11-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" | INF
000177 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 0 | 131242-WSD11-DS-M-0001 | 2023-11-09 | Data Sheet of Air Compressor | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-08 | 2024-01-22 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | APP
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 1 | 131242-WSD11-DS-M-0001 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 | Rev 0: AWC | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | APP
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0161 | A | 131242-WSD11-DR-M-0161 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0101 | A | 131242-WSD11-DR-M-0101 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0102 | A | 131242-WSD11-DR-M-0102 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0103 | A | 131242-WSD11-DR-M-0103 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0104 | A | 131242-WSD11-DR-M-0104 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0131 | A | 131242-WSD11-DR-M-0131 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0132 | A | 131242-WSD11-DR-M-0132 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0133 | A | 131242-WSD11-DR-M-0133 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " | AWC
000177 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 2 | 131242-WSD11-DS-M-0001 | 2024-08-12 | Data Sheet of Air Compressor System | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-25 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | APP
000177 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 3 | 131242-WSD11-DS-M-0001 | 2024-11-06 | Data Sheet of Air Compressor System | Rev 3: Approved | 2024-11-26 | 2024-12-05 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | APP | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | APP
000178 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 0 | 131242-WSD11-DS-M-0005 | 2023-11-10 | Data Sheet of Pressure Vessel | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-18 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" | APP
000178 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 1 | 131242-WSD11-DS-M-0005 | 2024-03-20 | Data Sheet of Pressure Vessel | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-29 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | Related to Detailed Design Report. | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" | APP
000178 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 2 | 131242-WSD11-DS-M-0005 | 2024-07-28 | Data Sheet of Pressure Vessel | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" | APP
000178 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 3 | 131242-WSD11-DS-M-0005 | 2024-11-22 | Data Sheet of Pressure Vessel | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. [Rev2 comments were not addressed by CES] | 2024-12-12 | 2024-12-05 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" | APP
000178 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 4 | 131242-WSD11-DS-M-0005 | 2025-03-04 | Data Sheet of Pressure Vessel | Rev 4: Approved. Please furnish PE Endorsement. | 2025-03-24 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | APP | Approved | 5 | "Data Sheet of Pressure Vessel" | APP
000179 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 0 | 131242-WSD11-DS-M-0006 | 2023-11-10 | Data Sheet of PreCoolers | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-22 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2023-11-10 | 2024-03-19 | 1 | AWC | Approved with Comments | 2 | "Data Sheet of PreCoolers" | AWC
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 1 | 131242-WSD11-DS-M-0006 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | No re-submission required | 000179 | 2023-11-10 | 2024-03-19 | 1 | AWC | Approved with Comments | 2 | "Data Sheet of PreCoolers" | AWC
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0007 | B | 131242-WSD11-DR-M-0007 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2024-03-19 | 2024-03-19 | B | AWC | Approved with Comments | 1 | "Data Sheet of PreCoolers" | AWC
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0008 | B | 131242-WSD11-DR-M-0008 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2024-03-19 | 2024-03-19 | B | AWC | Approved with Comments | 1 | "Data Sheet of PreCoolers" | AWC
000180 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 0 | 131242-WSD11-DS-M-0007 | 2023-11-10 | Data Sheet of PGS | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Related to Detailed Design Report. | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" | AWC
000180 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 1 | 131242-WSD11-DS-M-0007 | 2024-03-25 | Data Sheet of PGS | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-16 | 2024-05-30 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | Rev 0: AWC | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" | AWC
000180 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 2 | 131242-WSD11-DS-M-0007 | 2024-07-28 | Data Sheet of PGS | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-09-02 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" | AWC
000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 3 | 131242-WSD11-DS-M-0007 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" | AWC
000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0020 | 0 | 131242-WSD11-DS-E-0020 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000180 | 2024-09-30 | 2024-09-30 | 0 | AWC | Approved with Comments | 1 | "Data Sheet of PGS" | AWC
000181 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 0 | 131242-WSD11-DS-M-0008 | 2023-11-10 | Data Sheet of PGC | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000181 | 2023-11-10 | 2025-03-06 | 2 | AWC | Approved | 3 | "Data Sheet of PGC" | APP
000181 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 1 | 131242-WSD11-DS-M-0008 | 2024-03-19 | Data Sheet of PGC | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | Related to Detailed Design Report. | 000181 | 2023-11-10 | 2025-03-06 | 2 | AWC | Approved | 3 | "Data Sheet of PGC" | APP
000181 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 2 | 131242-WSD11-DS-M-0008 | 2025-03-06 | Data Sheet of PGC | Rev 2: Approved. | 2025-03-26 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000181 | 2023-11-10 | 2025-03-06 | 2 | APP | Approved | 3 | "Data Sheet of PGC" | APP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 00 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA-NA | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182 | 2023-11-10 | 2023-11-10 | NA | NAP | Not Approved | 2 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2024-01-04 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2024-01-24 | 2024-02-15 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000182 | 01 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA-NA | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182 | 2023-11-10 | 2023-11-10 | NA | INF | Not Approved | 2 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | NAP
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0010 | 0 | 131242-WST02-CD-IM-0010 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" | REJ
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0011 | 0 | 131242-WST02-CD-IM-0011 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" | REJ
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0012 | 0 | 131242-WST02-CD-IM-0012 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" | REJ
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | M3 | Z | 8900 | 0 | 131242-WST02-M3-Z-8900 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" | REJ
000183 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | RT | IM | 9005 | 0 | 131242-WSW41-RT-IM-9005 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" | REJ
000184 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0013 | 0 | 131242-WSW41-MI-C-0013 | 2023-11-14 | CSA Meeting Minutes 0013_20231019 | For Information | 2023-12-12 | 2023-11-23 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000184 | 2023-11-14 | 2023-11-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0013_20231019" | INF
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD | A | 131242-WST02-DR-A-1000_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  | To follow up to submit Prolog | 000185 | 2023-11-15 | 2023-11-15 | A | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD | A | 131242-WST02-DR-A-1001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_FSSD | A1 | 131242-WST02-DR-A-9000_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A1 | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_FSSD | A1 | 131242-WST02-DR-A-9001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A1 | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | P | 7001_FSSD | SSN PFD | 131242-WST02-DR-P-7001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | SSN PFD | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | AntiprexT AD 1020 XP_English | NA | NA | NA | NA | NA | AntiprexT AD 1020 XP_English-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | Caustic Soda 50% SDS | NA | NA | NA | NA | NA | Caustic Soda 50% SDS-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | Ferric Chloride SDS | NA | NA | NA | NA | NA | Ferric Chloride SDS-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG | NA | NA | NA | NA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022 | NA | NA | NA | NA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | TWRP C4B SSN_chemical inventory | NA | NA | NA | NA | NA | TWRP C4B SSN_chemical inventory-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000185 | 00 | Aaron | CSA | NA | WST02_SSN-FSSD-WA 01 & 02 | NA | NA | NA | NA | NA | WST02_SSN-FSSD-WA 01 & 02-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | NAP
000186 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0006 | 0 | 131242-WSW41-PS-PM-0006 | 2023-11-15 | Monthly Progress Presentation No. 06 (1023) | For Information | 2023-12-13 | 2023-11-16 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000186 | 2023-11-15 | 2023-11-15 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 06 (1023)" | INF
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | 0 | 131242-WST02-DR-P-6300 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | 0 | 131242-WST02-DR-P-6301 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | 0 | 131242-WST02-DR-P-6500 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | B | 131242-WST02-DR-P-6300 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-16 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | B | 131242-WST02-DR-P-6301 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | B | 131242-WST02-DR-P-6500 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000187 | 02 | Qili | Process | NA | 131242 | WST02 | NA | P | S#187 Cmt Reply Sheet | NA | 131242-WST02-NA-P-S#187 Cmt Reply Sheet | 2024-10-01 | Plant Drain and Safety Shower P&ID | Rev 2: The submittal is merged with SRC 731. All the open comments from this submittal are transferred to SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000187 | 2024-10-01 | 2024-10-01 | NA | APP | Approved | 1 | "Plant Drain and Safety Shower P&ID" | APP
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | A | 131242-WST02-DR-BF-1000 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | A | 131242-WST02-DR-BF-1001 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A | 131242-WST02-DR-BF-7000 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2024-09-28 | A.1 | NAP | Approved with Comments | 2 | "Fire Alarm-Gas Suppression" | AWC
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A | 131242-WST02-DR-BF-7003 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" | AWC
000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A.1 | 131242-WST02-DR-BF-7000 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2024-09-28 | A.1 | AWC | Approved with Comments | 2 | "Fire Alarm-Gas Suppression" | AWC
000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A.1 | 131242-WST02-DR-BF-7003 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | B | 131242-WST02-DR-BF-1000 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | B | 131242-WST02-DR-BF-1001 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1006 | B | 131242-WST02-DR-BF-1006 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2025-09-11 | 2025-09-11 | B | AWC | Approved with Comments | 1 | "Fire Alarm-Gas Suppression" | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5003 | B | 131242-WST02-DR-BF-5003 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2025-09-11 | 2025-09-11 | B | AWC | Approved with Comments | 1 | "Fire Alarm-Gas Suppression" | AWC
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | B | 131242-WST02-DR-BF-7003 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" | AWC
000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A | 131242-WST02-DR-BP-1000 | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-12 | 84 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A | 131242-WST02-DR-BP-7000 | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-13 | 85 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.1 | 131242-WST02-DR-BP-7000 | 2024-09-26 | Plumbing and Sanitary (SSN Area) | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | AWC | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.1 | 131242-WST02-DR-BP-1000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | AWC | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A | 131242-WST02-DR-BP-5000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2025-02-24 | 2025-07-15 | A.1 | AWC | Approved with Comments | 2 | "SSN Plumbing and Sanitary " | AWC
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | PEN | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.2 | 131242-WST02-DR-BP-1000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | PEN | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | AWC
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A.1 | 131242-WST02-DR-BP-5000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2025-02-24 | 2025-07-15 | A.1 | PEN | Approved with Comments | 2 | "SSN Plumbing and Sanitary " | AWC
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A | 131242-WST02-DR-BF-1002 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 | Schemiatic to submit 27 Jul 24. Layout drawing shall be confirm with Digie | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A | 131242-WST02-DR-BF-1003 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A | 131242-WST02-DR-BF-1004 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190 | 2023-11-15 | 2025-02-21 | A.1 | AWC | Approved with Comments | 2 | "Hose Reel (SSN Area)" | AWC
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | AWC
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A.1 | 131242-WST02-DR-BF-1002 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 | 2025-02-20 |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A.1 | 131242-WST02-DR-BF-1003 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A.1 | 131242-WST02-DR-BF-1004 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190 | 2023-11-15 | 2025-02-21 | A.1 | AWC | Approved with Comments | 2 | "Hose Reel (SSN Area)" | AWC
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A.1 | 131242-WST02-DR-BF-7001 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | AWC
000191 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0010 | 0 | 131242-WSW41-CD-IM-0010 | 2023-11-17 | Electrical Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 94 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2023-11-17 | 2023-11-17 | 0 | AWC | Approved with Comments | 1 | "Electrical Building" | AWC
000191 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027 | 2024-06-04 | Milestone 1.2 Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2024-06-04 | 2026-01-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0059 | 0 | 131242-WSW41-CD-IM-0059 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1003 | B_MS2 | 131242-WST02-DR-B-1003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1004 | B_MS2 | 131242-WST02-DR-B-1004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1005 | B_MS2 | 131242-WST02-DR-B-1005 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1006 | B_MS2 | 131242-WST02-DR-B-1006 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1000 | A.1 | 131242-WST02-DR-BF-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1001 | A.1 | 131242-WST02-DR-BF-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1011 | A9 | 131242-WST02-DR-BF-1011 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1012 | A9 | 131242-WST02-DR-BF-1012 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1000 | A.1 | 131242-WST02-DR-BH-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1001 | A.2 | 131242-WST02-DR-BH-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1002 | A.1_MS2 | 131242-WST02-DR-BF-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1003 | A.1_MS2 | 131242-WST02-DR-BF-1003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1310 | A | 131242-WST02-DR-E-1310 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1311 | A | 131242-WST02-DR-E-1311 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1312 | A | 131242-WST02-DR-E-1312 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1313 | A | 131242-WST02-DR-E-1313 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3310 | A | 131242-WST02-DR-E-3310 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3311 | A | 131242-WST02-DR-E-3311 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3312 | A | 131242-WST02-DR-E-3312 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3313 | A | 131242-WST02-DR-E-3313 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3314 | A | 131242-WST02-DR-E-3314 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3315 | A | 131242-WST02-DR-E-3315 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3316 | A | 131242-WST02-DR-E-3316 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3317 | A | 131242-WST02-DR-E-3317 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3318 | A | 131242-WST02-DR-E-3318 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3319 | A | 131242-WST02-DR-E-3319 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3320 | A | 131242-WST02-DR-E-3320 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3321 | A | 131242-WST02-DR-E-3321 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000554 | 2024-07-10 | 2025-05-15 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000555 | 2024-07-10 | 2025-05-15 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5002 | A | 131242-WST02-DR-I-5002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5003 | A | 131242-WST02-DR-I-5003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5004 | A | 131242-WST02-DR-I-5004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5005 | A | 131242-WST02-DR-I-5005 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000461 | 2024-05-06 | 2025-05-15 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1002 | A | 131242-WST02-DR-M-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3000 | A | 131242-WST02-DR-M-3000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" | AWC
000191 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027 | 2026-01-16 | Milestone 3 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000191 | 2024-06-04 | 2026-01-16 | 0 | PEN | Approved with Comments | 2 | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | AWC
000192 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0008 | 0 | 131242-WSW41-CD-IM-0008 | 2023-11-17 | Chemical Dosing Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 94 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2023-11-17 | 2023-11-17 | 0 | AWC | Approved with Comments | 1 | "Chemical Dosing Area" | AWC
000192 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0026 | 1 | 131242-WSW41-CD-IM-0026 | 2024-06-04 | Milestone 1.2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2024-06-04 | 2024-06-04 | 1 | AWC | Approved with Comments | 1 | "Milestone 1.2 SSN Chemical Dosing Area" | AWC
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2026-01-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | AWC
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | AWC
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1004 | A | 131242-WST02-DR-M-1004 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Chemical Dosing Area" | AWC
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3003 | A | 131242-WST02-DR-M-3003 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Chemical Dosing Area" | AWC
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2025-05-15 | 2026-01-16 | 0 | PEN | Approved with Comments | 2 | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | AWC
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1317 | C | 131242-WST02-DR-E-1317 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | C | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" | PEN
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3333 | A | 131242-WST02-DR-E-3333 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | A | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" | PEN
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3334 | A | 131242-WST02-DR-E-3334 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | A | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" | PEN
000193 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0002 | 1 | 131242-WST02-CL-B-0002 | 2023-11-17 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-12-15 | 2023-12-18 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000096&&000193 | 2023-09-12 | 2023-11-17 | 1 | NAP | Not Approved | 2 | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" | NAP
000193 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8001 | 0 | 131242-WST02-CL-BF-8001 | 2024-04-04 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 1: Approved | 2024-04-25 | 2024-04-26 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000193 | 2024-04-04 | 2024-04-04 | 0 | APP | Approved | 1 | "Engineering Calculation Report for Fire Hydrant Pipe" | APP
000194 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | CL | B | 0003 | 1 | 131242-WST02-CL-B-0003 | 2023-11-17 | Engineering Calculation Report for Potable Water Pipe | This submission is withdrown. As submitted wrongly as a new submission, which should be a Rev.1 for submittal no. 000097. | 2023-12-15 | 2023-12-06 | 13 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 | Resubmission of Submittal 000097 |  | 000097&&000194 | 2023-09-12 | 2023-11-17 | 1 | VOID | (VOID NOT IN USE) | 2 | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" | VOID
000195 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0005 | 0 | 131242-WSW41-MI-PM-0005 | 2023-11-20 | Monthly Progress Meeting Minutes 0005_20231017 | For Information | 2023-12-18 | 2023-11-23 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000195 | 2023-11-20 | 2023-11-20 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0005_20231017" | INF
000196 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0006 | 0 | 131242-WSW41-MI-PM-0006 | 2023-11-15 | Monthly Progress Meeting Minutes 0006_20231114 | For Information | 2023-12-13 | 2023-11-23 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000196 | 2023-11-15 | 2023-11-15 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0006_20231114" | INF
000197 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | A | 131242-WSD11-DR-E-7000 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 114 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 |  | 000197 | 2023-11-21 | 2025-01-21 | B | AWC | Approved with Comments | 2 | "THP Overall Single Line Diagram" | AWC
000197 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | B | 131242-WSD11-DR-E-7000 | 2025-01-21 | THP Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-02-10 | 2025-04-30 | 71 | Approved with Comments | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000197 | 2023-11-21 | 2025-01-21 | B | AWC | Approved with Comments | 2 | "THP Overall Single Line Diagram" | AWC
000198 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7001 | 0 | 131242-WSD11-DR-E-7001 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 114 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 | To drop an email for combination of S198, S197. To reply the comment sheet as noted and to resubmit in order to close. | 000198 | 2023-11-21 | 2023-11-21 | 0 | AWC | Approved with Comments | 1 | "THP Overall Single Line Diagram" | AWC
000199 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 0 | 131242-WST02-CL-E-0001 | 2023-11-22 | SSN Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | NAP | Approved with Comments | 3 | "SSN Cable Sizing Calculations" | AWC
000199 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 1 | 131242-WST02-CL-E-0001 | 2024-06-24 | SSN Cable Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Cable Sizing Calculations" | AWC
000199 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 2 | 131242-WST02-CL-E-0001 | 2025-05-30 | SSN Cable Sizing Calculations | Rev 2: Approved with comments. To revise and resubmit. | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Cable Sizing Calculations" | AWC
000200 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 0 | 131242-WST02-VI-E-0000 | 2023-11-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet. | 2023-12-20 | 2023-12-22 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | APP
000200 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 1 | 131242-WST02-VI-E-0000 | 2024-05-13 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-03 | 2024-07-04 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | APP
000200 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 2 | 131242-WST02-VI-E-0000 | 2024-07-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 2: Approved. | 2024-08-12 | 2024-10-29 | 71 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | APP
000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | A | 131242-WST02-DR-E-7000 | 2023-11-22 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 |  | 000201 | 2023-11-22 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" | AWC
000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | A | 131242-WST02-DR-E-7001 | 2023-11-23 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-21 | 2024-04-29 | 112 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000201 | 2023-11-23 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" | AWC
000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | B | 131242-WST02-DR-E-7000 | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | 57 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000201 | 2023-11-22 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" | AWC
000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | B | 131242-WST02-DR-E-7001 | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | 57 | Awaiting S.O.'s response | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000201 | 2023-11-23 | 2025-02-14 | B | PEN | Approved with Comments | 2 | "SSN Overall Single Line Diagram" | AWC
000202 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 0 | 131242-WSD11-BQ-E-0001 | 2023-11-22 | THP Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | NAP | Approved with Comments | 4 | "THP Cable List" | AWC
000202 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 1 | 131242-WSD11-BQ-E-0001 | 2024-06-12 | THP Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-03 | 2024-08-16 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" | AWC
000202 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 2 | 131242-WSD11-BQ-E-0001 | 2025-04-10 | THP Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-30 | 2025-05-08 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" | AWC
000202 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 3 | 131242-WSD11-BQ-E-0001 | 2025-07-21 | THP Cable List | Rev 3: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-02 | 31 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" | AWC
000203 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | A | 131242-WSD11-CL-E-0000 | 2023-11-22 | THP Cable sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000203 | 2023-11-22 | 2024-06-12 | B | NAP | Approved with Comments | 2 | "THP Cable sizing Calculations" | AWC
000203 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | B | 131242-WSD11-CL-E-0000 | 2024-06-12 | THP Cable sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. | 2024-07-03 | 2024-08-16 | 47 | Approved with Comments | YES | 2024-09-05 | NO | Resubmitted | 0 |  |  | 000203 | 2023-11-22 | 2024-06-12 | B | AWC | Approved with Comments | 2 | "THP Cable sizing Calculations" | AWC
000204 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 0 | 131242-WST02-BQ-E-0001 | 2023-11-22 | SSN Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | NAP | Approved with Comments | 4 | "SSN Cable List" | AWC
000204 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 1 | 131242-WST02-BQ-E-0001 | 2024-06-24 | SSN Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" | AWC
000204 | 02 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 2 | 131242-WST02-BQ-E-0001 | 2025-04-18 | SSN Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-08 | 2025-05-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" | AWC
000204 | 03 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 3 | 131242-WST02-BQ-E-0001 | 2025-07-11 | SSN Cable List | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-07-31 | 2025-07-23 | 8 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | B | 131242-WST02-DR-EK-1000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-18 |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | B | 131242-WST02-DR-EK-1001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | B | 131242-WST02-DR-EK-1002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | B | 131242-WST02-DR-EK-1003 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | B | 131242-WST02-DR-EK-1004 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | B | 131242-WST02-DR-EK-1005 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | B | 131242-WST02-DR-EK-2000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | B | 131242-WST02-DR-EK-2001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | B | 131242-WST02-DR-EK-2002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | B | 131242-WST02-DR-EK-2003 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | B | 131242-WST02-DR-EK-5000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | B | 131242-WST02-DR-EK-5001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | B | 131242-WST02-DR-EK-5002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | C | 131242-WST02-DR-EK-1003 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | C | 131242-WST02-DR-EK-1004 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | C | 131242-WST02-DR-EK-2000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | C | 131242-WST02-DR-EK-2001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | C | 131242-WST02-DR-EK-2002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | C | 131242-WST02-DR-EK-2003 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | C | 131242-WST02-DR-EK-5000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | C | 131242-WST02-DR-EK-5001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | C | 131242-WST02-DR-EK-5002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | AWC
000206 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 0 | 131242-WST02-CL-P-0002 | 2023-11-22 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-02-26 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | pending Puriteq confirmation | 000206 | 2023-11-22 | 2025-03-04 | 1 | AWC | For Information | 2 | "Preliminary Sizing Calculation for SSN Future OCF System" | INF
000206 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 1 | 131242-WST02-CL-P-0002 | 2025-03-04 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 1: For Information | 2025-03-24 | 2025-10-06 | 154 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000206 | 2023-11-22 | 2025-03-04 | 1 | INF | For Information | 2 | "Preliminary Sizing Calculation for SSN Future OCF System" | INF
000207 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002 | 2023-11-22 | THP Equipment Sizing Calculation Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-03-07 | 76 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000207&&000212 | 2023-11-22 | 2023-11-24 | 0 | AWC | (VOID NOT IN USE) | 2 | "THP Equipment Sizing Calculation Sheet" | VOID
000207 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | Comment_CES Reply 2024 03 11 | NA | 131242-WSD11-CL-P-Comment_CES Reply 2024 03 11 | 2024-03-11 | THP Equipment Sizing Calculation Sheet | Rev 1: Approved | 2024-04-01 | 2024-04-29 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  | Rev 0 : AWC | 000207 | 2024-03-11 | 2024-03-11 | NA | APP | Approved | 1 | "THP Equipment Sizing Calculation Sheet" | APP
000208 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 0 | 131242-WSD11-RT-E-0001 | 2023-11-22 | THP Atex Hazardous Area Assessment Report | Rev 0: For Information. Response to comment sheet required. | 2023-12-20 | 2024-05-15 | 125 | For Information | NO |  | YES | Resubmitted | 0 | 2024-07-31 |  | 000208 | 2023-11-22 | 2024-09-11 | 1 | INF | For Information | 2 | "THP Atex Hazardous Area Assessment Report" | INF
000208 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 1 | 131242-WSD11-RT-E-0001 | 2024-09-11 | THP Atex Hazardous Area Assessment Report | Rev 1: For Information. | 2024-10-01 | 2024-10-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000208 | 2023-11-22 | 2024-09-11 | 1 | INF | For Information | 2 | "THP Atex Hazardous Area Assessment Report" | INF
000209 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0012 | 0 | 131242-WSW41-MI-P-0012 | 2023-11-24 | C4B Minutes of Engineering Process & MEICA Meeting No.0012 | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000209 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of Engineering Process & MEICA Meeting No.0012" | INF
000210 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0003 | 0 | 131242-WST02-MI-P-0003 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000210 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of SSN Ad Hoc Meeting" | INF
000211 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0004 | 0 | 131242-WST02-MI-P-0004 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000211 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of SSN Ad Hoc Meeting" | INF
000212 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002 | 2023-11-24 | THP Equipment Sizing Calculation Sheet | This submittal is withdrawn. As already submitted these drawings under in the submittal 000207 on 22 Nov 2023. | 2023-12-22 | 2023-12-08 | 10 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000207&&000212 | 2023-11-22 | 2023-11-24 | 0 | VOID | (VOID NOT IN USE) | 2 | "THP Equipment Sizing Calculation Sheet" | VOID
000213 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0014 | 0 | 131242-WSW41-MI-C-0014 | 2023-11-27 | C4B Minutes of CSA Progress Meeting No.0014 | For Information | 2023-12-26 | 2023-12-13 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000213 | 2023-11-27 | 2023-11-27 | 0 | INF | For Information | 1 | "C4B Minutes of CSA Progress Meeting No.0014" | INF
000214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0005 | 0 | 131242-WSW41-PC-W-0005 | 2023-11-27 | PAYMENT CLAIM NO.5 | Approved. Please refer to S.O. Correspondence No. 0089 dated 1 Dec 2023. | 2023-12-26 | 2023-12-06 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000214 | 2023-11-27 | 2023-11-27 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.5" | APP
000215 | 00 | Franklin | PMT | NA | 131242 | WSW41 | LT | PM | 0016 | 0 | 131242-WSW41-LT-PM-0016 | 2023-11-29 | Clarification on Anammox Reactor Design Capacity | Rev 0: For Information. Please find our respond as attached. | 2023-12-28 | 2024-07-26 | 172 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000215 | 2023-11-29 | 2023-11-29 | 0 | INF | For Information | 1 | "Clarification on Anammox Reactor Design Capacity" | INF
000216 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 0 | 131242-WSW41-QA-C-0008 | 2023-11-30 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-29 | 2023-12-05 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000216 | 2023-11-30 | 2023-12-12 | 1 | AWC | Approved | 2 | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | APP
000216 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 1 | 131242-WSW41-QA-C-0008 | 2023-12-12 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Approved | 2024-01-03 | 2024-01-12 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000216 | 2023-11-30 | 2023-12-12 | 1 | APP | Approved | 2 | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | APP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | 0 | 131242-WSD11-DR-EL-1000 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | 0 | 131242-WSD11-DR-EL-1001 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | 0 | 131242-WSD11-DR-EL-1002 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | 0 | 131242-WSD11-DR-EL-1003 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | 0 | 131242-WSD11-DR-EL-1004 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | A | 131242-WSD11-DR-EP-1000 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-26 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | A | 131242-WSD11-DR-EP-1001 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | A | 131242-WSD11-DR-EP-1002 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | A | 131242-WSD11-DR-EP-1003 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | A | 131242-WSD11-DR-EP-1004 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | C | 131242-WSD11-DR-EP-1000 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | C | 131242-WSD11-DR-EP-1001 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | C | 131242-WSD11-DR-EP-1002 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | C | 131242-WSD11-DR-EP-1003 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | C | 131242-WSD11-DR-EP-1004 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | A | 131242-WSD11-DR-EL-1000 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | A | 131242-WSD11-DR-EL-1001 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | A | 131242-WSD11-DR-EL-1002 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | A | 131242-WSD11-DR-EL-1003 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | A | 131242-WSD11-DR-EL-1004 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A | 131242-WST02-DR-BH-1000 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A | 131242-WST02-DR-BH-1001 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A | 131242-WST02-DR-BH-7000 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A | 131242-WST02-DR-BH-7001 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.1 | 131242-WST02-DR-BH-7000 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.1 | 131242-WST02-DR-BH-7001 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.2 | 131242-WST02-DR-BH-5000 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | NAP | Approved with Comments | 4 | "Building Services ACMV" | AWC
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.2 | 131242-WST02-DR-BH-7000 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.2 | 131242-WST02-DR-BH-7001 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.3 | 131242-WST02-DR-BH-5000 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" | AWC
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.3 | 131242-WST02-DR-BH-7000 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.3 | 131242-WST02-DR-BH-7001 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | A | 131242-WST02-DR-BE-7000 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | A | 131242-WST02-DR-BE-7001 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | A | 131242-WST02-DR-BE-7002 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | A | 131242-WST02-DR-BE-7003 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | A | 131242-WST02-DR-BE-7004 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | A | 131242-WST02-DR-BE-7005 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | A | 131242-WST02-DR-BE-7006 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | A | 131242-WST02-DR-BE-7007 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | B | 131242-WST02-DR-BE-7000 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 | TBA | Pending from C2D | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | B | 131242-WST02-DR-BE-7001 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | B | 131242-WST02-DR-BE-7002 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | B | 131242-WST02-DR-BE-7003 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | B | 131242-WST02-DR-BE-7004 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | B | 131242-WST02-DR-BE-7005 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | B | 131242-WST02-DR-BE-7006 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | B | 131242-WST02-DR-BE-7007 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" | NAP
000221 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0002 | 0 | 131242-WSD11-PO-M-0002 | 2023-12-01 | Unpriced PO for Air Compressor System | For Information | 2024-01-02 | 2024-01-17 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000221 | 2023-12-01 | 2023-12-01 | 0 | INF | For Information | 1 | "Unpriced PO for Air Compressor System" | INF
000222 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0010 | 0 | 131242-WSD11-DS-M-0010 | 2023-12-01 | Progressive Cavity Pumps | Rev 0: Not approved - Revise and Resubmit | 2024-01-02 | 2024-03-07 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000222 | 2023-12-01 | 2023-12-01 | 0 | NAP | Not Approved | 1 | "Progressive Cavity Pumps" | NAP
000222 | 01 | Joo Kwan | Process | NA | 131242 | NA | DS | M | S222 Cmt Sheet Reply 2024 07 22 | NA | 131242-NA-DS-M-S222 Cmt Sheet Reply 2024 07 22 | 2024-07-22 | Progressive Cavity Pumps | Rev 1: Rejected based on contractor's request. Reply to contractor reply is attached herewith. | 2024-08-12 | 2024-08-29 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000222 | 2024-07-22 | 2024-07-22 | NA | REJ | Rejected | 1 | "Progressive Cavity Pumps" | REJ
000223 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 0 | 131242-WSD11-DS-M-0009 | 2023-12-01 | THP Plant Safety Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet | 2024-01-02 | 2024-03-07 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | JV to follow up with JK to close the submittal | 000223 | 2023-12-01 | 2024-07-28 | 1 | AWC | Approved with Comments | 2 | "THP Plant Safety Valve" | AWC
000223 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 1 | 131242-WSD11-DS-M-0009 | 2024-07-28 | THP Plant Safety Valve | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-16 | 2024-08-01 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000223 | 2023-12-01 | 2024-07-28 | 1 | AWC | Approved with Comments | 2 | "THP Plant Safety Valve" | AWC
000224 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 0 | 131242-WSD11-SP-P-0001 | 2023-12-01 | THP System Control Philosophy | The submittal is approved with comments, resubmittal is required. | 2024-01-02 | 2024-01-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000224 | 2023-12-01 | 2024-03-01 | 1 | AWC | Approved with Comments | 2 | "THP System Control Philosophy" | AWC
000224 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 1 | 131242-WSD11-SP-P-0001 | 2024-03-01 | THP System Control Philosophy | Rev1- The submittal is approved with comments, resubmittal is required. The comments are | 2024-03-21 | 2024-04-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | JV to follow up with JK to close the submittal | 000224 | 2023-12-01 | 2024-03-01 | 1 | AWC | Approved with Comments | 2 | "THP System Control Philosophy" | AWC
000224 | 02 | Joo Kwan | Process | NA | 131242 | NA | SP | P | Cmt Sheet Reply S224.0 2024 07 30 | NA | 131242-NA-SP-P-Cmt Sheet Reply S224.0 2024 07 30 | 2024-07-30 | THP System Control Philosophy | Rev2- Although there are no active comments on the document, the document is still approved as noted to accommodate for the changes if any during the detail engineering. | 2024-08-20 | 2024-09-24 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000224 | 2024-07-30 | 2024-07-30 | NA | AWC | Approved with Comments | 1 | "THP System Control Philosophy" | AWC
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1000 | 0 | 131242-WST02-DR-BH-1000 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1001 | 0 | 131242-WST02-DR-BH-1001 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7000 | 0 | 131242-WST02-DR-BH-7000 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7001 | 0 | 131242-WST02-DR-BH-7001 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | AWC
000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0012 | 0 | 131242-WSW41-MI-IM-0012 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000226 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" | INF
000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0013 | 0 | 131242-WSW41-MI-IM-0013 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000226 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" | INF
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | A | 131242-WST02-DR-EP-1000 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | A | 131242-WST02-DR-EP-1001 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | A | 131242-WST02-DR-EP-1002 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | AWC
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | A | 131242-WST02-DR-EP-1003 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" | NAP
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | A | 131242-WST02-DR-EP-1004 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | AWC
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | B | 131242-WST02-DR-EP-1000 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | B | 131242-WST02-DR-EP-1001 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | B | 131242-WST02-DR-EP-1002 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | AWC
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | B | 131242-WST02-DR-EP-1003 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" | NAP
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | AWC
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | AWC
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | C | 131242-WST02-DR-EP-1003 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" | NAP
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | C | 131242-WST02-DR-EP-1004 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | AWC
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | D | 131242-WST02-DR-EP-1000 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 | TBA |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | D | 131242-WST02-DR-EP-1001 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | AWC
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | D | 131242-WST02-DR-EP-1002 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | AWC
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | D | 131242-WST02-DR-EP-1003 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | PEN | Not Approved | 4 | "SSN Power Layout Plan" | NAP
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | D | 131242-WST02-DR-EP-1004 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | AWC
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1005 | D | 131242-WST02-DR-EP-1005 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000227 | 2026-01-19 | 2026-01-19 | D | PEN | Awaiting S.O.'s response | 1 | "SSN Power Layout Plan" | PEN
000228 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | RT | C | 0001 | 0 | 131242-WSW41-RT-C-0001 | 2023-12-05 | UXO Scanning Report | Approved | 2024-01-04 | 2023-12-14 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000228 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "UXO Scanning Report" | INF
000229 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 0 | 131242-WSW41-VI-M-0005 | 2023-12-05 | Preliminary Design and Vendor Approval of Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-04 | 2024-04-17 | 96 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 | To provide Vendor drawings after PO issued. | 000229 | 2023-12-05 | 2024-08-20 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Mixer " | APP
000229 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 1 | 131242-WSW41-VI-M-0005 | 2024-08-20 | Preliminary Design and Vendor Approval of Mixer | Rev 1: Approved | 2024-09-09 | 2024-09-02 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000229 | 2023-12-05 | 2024-08-20 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Mixer " | APP
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | 0 | 131242-WSD11-DR-P-6000 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 | To submit Detailed Design . Related to Detailed Design Report. | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | 0 | 131242-WSD11-DR-P-6001 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | 0 | 131242-WSD11-DR-P-6002 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | 0 | 131242-WSD11-DR-P-6003 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | 0 | 131242-WSD11-DR-P-6004 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | 0 | 131242-WSD11-DR-P-6005 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | 0 | 131242-WSD11-DR-P-6006 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | 0 | 131242-WSD11-DR-P-6007 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | 0 | 131242-WSD11-DR-P-6008 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | 0 | 131242-WSD11-DR-P-6009 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | 0 | 131242-WSD11-DR-P-6010 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | 0 | 131242-WSD11-DR-P-6011 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | 0 | 131242-WSD11-DR-P-6012 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | 0 | 131242-WSD11-DR-P-6013 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | 0 | 131242-WSD11-DR-P-6014 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | 0 | 131242-WSD11-DR-P-6015 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | 0 | 131242-WSD11-DR-P-6016 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | 0 | 131242-WSD11-DR-P-6017 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | 0 | 131242-WSD11-DR-P-6018 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | B | 131242-WSD11-DR-P-6000 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 | Heng Peng to provide DGN dwg | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | B | 131242-WSD11-DR-P-6001 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | B | 131242-WSD11-DR-P-6002 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | B | 131242-WSD11-DR-P-6003 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | B | 131242-WSD11-DR-P-6004 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | B | 131242-WSD11-DR-P-6005 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | B | 131242-WSD11-DR-P-6006 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | B | 131242-WSD11-DR-P-6007 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | B | 131242-WSD11-DR-P-6008 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | B | 131242-WSD11-DR-P-6009 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | B | 131242-WSD11-DR-P-6010 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | B | 131242-WSD11-DR-P-6011 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | B | 131242-WSD11-DR-P-6012 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | B | 131242-WSD11-DR-P-6013 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | B | 131242-WSD11-DR-P-6014 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | B | 131242-WSD11-DR-P-6015 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | B | 131242-WSD11-DR-P-6016 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | B | 131242-WSD11-DR-P-6017 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | B | 131242-WSD11-DR-P-6018 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | C | 131242-WSD11-DR-P-6000 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | C | 131242-WSD11-DR-P-6001 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | C | 131242-WSD11-DR-P-6002 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | C | 131242-WSD11-DR-P-6003 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | C | 131242-WSD11-DR-P-6004 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | C | 131242-WSD11-DR-P-6005 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | C | 131242-WSD11-DR-P-6006 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | C | 131242-WSD11-DR-P-6007 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | C | 131242-WSD11-DR-P-6008 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | C | 131242-WSD11-DR-P-6009 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | C | 131242-WSD11-DR-P-6010 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | C | 131242-WSD11-DR-P-6011 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | C | 131242-WSD11-DR-P-6012 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | C | 131242-WSD11-DR-P-6013 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | C | 131242-WSD11-DR-P-6014 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | C | 131242-WSD11-DR-P-6015 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | C | 131242-WSD11-DR-P-6016 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | C | 131242-WSD11-DR-P-6017 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | C | 131242-WSD11-DR-P-6018 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | C | 131242-WSD11-DR-P-6019 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | C | 131242-WSD11-DR-P-6020 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | C | 131242-WSD11-DR-P-6021 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | C | 131242-WSD11-DR-P-6022 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | C | 131242-WSD11-DR-P-6023 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | C | 131242-WSD11-DR-P-6024 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | C | 131242-WSD11-DR-P-6025 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | C | 131242-WSD11-DR-P-6026 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | C | 131242-WSD11-DR-P-6027 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | C | 131242-WSD11-DR-P-6028 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | C | 131242-WSD11-DR-P-6029 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | C | 131242-WSD11-DR-P-6030 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | C | 131242-WSD11-DR-P-6031 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | C | 131242-WSD11-DR-P-6032 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | C | 131242-WSD11-DR-P-6033 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | C | 131242-WSD11-DR-P-6034 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | C | 131242-WSD11-DR-P-6035 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | C | 131242-WSD11-DR-P-6036 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | C | 131242-WSD11-DR-P-6050 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | C | 131242-WSD11-DR-P-6063 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | C | 131242-WSD11-DR-P-6101 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | C | 131242-WSD11-DR-P-6121 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | C | 131242-WSD11-DR-P-6200 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | C | 131242-WSD11-DR-P-6300 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | C | 131242-WSD11-DR-P-6400 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | C | 131242-WSD11-DR-P-6600 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | C | 131242-WSD11-DR-P-6601 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | D | 131242-WSD11-DR-P-6000 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | D | 131242-WSD11-DR-P-6001 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | D | 131242-WSD11-DR-P-6002 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | D | 131242-WSD11-DR-P-6003 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | D | 131242-WSD11-DR-P-6004 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | D | 131242-WSD11-DR-P-6005 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | D | 131242-WSD11-DR-P-6006 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | D | 131242-WSD11-DR-P-6007 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | D | 131242-WSD11-DR-P-6008 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | D | 131242-WSD11-DR-P-6009 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | D | 131242-WSD11-DR-P-6010 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | D | 131242-WSD11-DR-P-6011 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | D | 131242-WSD11-DR-P-6012 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | D | 131242-WSD11-DR-P-6013 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | D | 131242-WSD11-DR-P-6014 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | D | 131242-WSD11-DR-P-6015 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | D | 131242-WSD11-DR-P-6016 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | D | 131242-WSD11-DR-P-6017 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | D | 131242-WSD11-DR-P-6018 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | D | 131242-WSD11-DR-P-6019 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | D | 131242-WSD11-DR-P-6020 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | D | 131242-WSD11-DR-P-6021 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | D | 131242-WSD11-DR-P-6022 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | D | 131242-WSD11-DR-P-6023 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | D | 131242-WSD11-DR-P-6024 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | D | 131242-WSD11-DR-P-6025 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | D | 131242-WSD11-DR-P-6026 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | D | 131242-WSD11-DR-P-6027 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | D | 131242-WSD11-DR-P-6028 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | D | 131242-WSD11-DR-P-6029 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | D | 131242-WSD11-DR-P-6030 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | D | 131242-WSD11-DR-P-6031 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | D | 131242-WSD11-DR-P-6032 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | D | 131242-WSD11-DR-P-6033 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | D | 131242-WSD11-DR-P-6034 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | D | 131242-WSD11-DR-P-6035 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | D | 131242-WSD11-DR-P-6036 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | D | 131242-WSD11-DR-P-6050 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6051 | D | 131242-WSD11-DR-P-6051 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2025-06-17 | 2025-06-17 | D | AWC | Approved with Comments | 1 | "P&ID of THP Train 1" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | D | 131242-WSD11-DR-P-6063 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | D | 131242-WSD11-DR-P-6070 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | D | 131242-WSD11-DR-P-6101 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | D | 131242-WSD11-DR-P-6121 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | D | 131242-WSD11-DR-P-6200 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | D | 131242-WSD11-DR-P-6300 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | D | 131242-WSD11-DR-P-6400 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | D | 131242-WSD11-DR-P-6600 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | D | 131242-WSD11-DR-P-6601 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST604_BCA | A1 | 131242-WST02-DR-S-1001_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2023-12-07 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | AWC
000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST604_BCA | A1 | 131242-WST02-DR-S-5001_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2023-12-07 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | AWC
000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-05 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604_BCA | A1 | 131242-WST02-DR-C-1001_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604_BCA | A1 | 131242-WST02-DR-C-1002_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604_BCA | A1 | 131242-WST02-DR-C-5001_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604_BCA | A1 | 131242-WST02-DR-C-7000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000231 | 01 | Zora/ HP | CSA | NA | A1798-00002-2018-ST604_NOA | NA | NA | NA | NA | NA | A1798-00002-2018-ST604_NOA-NA-NA-NA-NA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | NA | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | AWC
000232 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 0 | 131242-WSW41-VI-M-0007 | 2023-12-08 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-09 | 2024-02-26 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 | Yibo WIP | 000232 | 2023-12-08 | 2025-02-28 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | APP
000232 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 1 | 131242-WSW41-VI-M-0007 | 2024-07-29 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-19 | 2024-09-02 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | In progress. Only one ICA comment is open (s/n.19), will reconfirm with ICA team, Try resubmit in 1 week. | 000232 | 2023-12-08 | 2025-02-28 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | APP
000232 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 2 | 131242-WSW41-VI-M-0007 | 2025-02-28 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 2: Approved | 2025-03-20 | 2025-11-24 | 191 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000232 | 2023-12-08 | 2025-02-28 | 2 | APP | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | APP
000233 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0012 | 0 | 131242-WSW41-CD-IM-0012 | 2023-12-08 | Submission Of BIM Coordination VCM Model (Nov – 2023) | For Information | 2024-01-09 | 2023-12-26 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000233 | 2023-12-08 | 2023-12-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Nov – 2023)" | INF
000234 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0007 | 0 | 131242-WSW41-RT-PM-0007 | 2023-12-11 | C4B Monthly Progress Report Number No.07 (11/23) | Rev. 0 - Approved with comments (need to re-submit) | 2024-01-10 | 2023-12-18 | 5 | Approved with Comments | YES | 2024-01-05 | NO | Resubmitted | 0 |  |  | 000234 | 2023-12-11 | 2023-12-11 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.07 (11/23)" | AWC
000235 | 00 | Zora | CSA | NA | 131242 | WSW41 | RT | C | 0002 | 0 | 131242-WSW41-RT-C-0002 | 2023-12-12 | ULT Test Report of 600mm Dia. Bored Pile | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-11 | 2023-12-18 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000235 | 2023-12-12 | 2023-12-22 | 1 | AWC | Approved with Comments | 2 | "ULT Test Report of 600mm Dia. Bored Pile " | AWC
000235 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0002 | 1 | 131242-WSW41-RT-C-0002 | 2023-12-22 | ULT Test Report of 600mm Dia. Bored Pile | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-15 | 2024-01-16 | 17 | Approved with Comments | YES | 2024-02-05 | NO | Resubmitted | 0 |  |  | 000235 | 2023-12-12 | 2023-12-22 | 1 | AWC | Approved with Comments | 2 | "ULT Test Report of 600mm Dia. Bored Pile " | AWC
000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | A | 131242-WSD11-DR-E-1100 | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-19 |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | A | 131242-WSD11-DR-E-1101 | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | B | 131242-WSD11-DR-E-1105 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" | AWC
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | B | 131242-WSD11-DR-E-1106 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | C | 131242-WSD11-DR-E-1100 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | C | 131242-WSD11-DR-E-1101 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | C | 131242-WSD11-DR-E-1102 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | C | 131242-WSD11-DR-E-1103 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | C | 131242-WSD11-DR-E-1104 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | C | 131242-WSD11-DR-E-1105 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" | AWC
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | C | 131242-WSD11-DR-E-1106 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" | AWC
000237 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0001 | 0 | 131242-WST02-VI-E-0001 | 2023-12-12 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | Not Approved. To revise and resubmit. Please refer to comment sheet | 2024-01-11 | 2024-01-24 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000237 | 2023-12-12 | 2023-12-12 | 0 | NAP | Not Approved | 1 | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | NAP
000237 | 01 | Freedomer | EICA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S237.0 2024 07 22 | NA | 131242-NA-NA-NA-Cmt Sheet Reply S237.0 2024 07 22 | 2024-07-22 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | R1: Rejected as requested by C4B | 2024-08-12 | 2024-08-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000237 | 2024-07-22 | 2024-07-22 | NA | NAP | Not Approved | 1 | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | NAP
000238 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 0 | 131242-WSW41-VI-M-1000 | 2023-12-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Not Approved. To revise and resubmit. | 2024-01-15 | 2024-02-19 | 47 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | NAP | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | APP
000238 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 1 | 131242-WSW41-VI-M-1000 | 2024-03-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-04 | 2024-04-17 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-30 |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | AWC | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | APP
000238 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 2 | 131242-WSW41-VI-M-1000 | 2024-08-07 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | APP | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | APP
000239 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 0 | 131242-WSW41-VI-M-1002 | 2023-12-14 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-02-19 | 47 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000239 | 2023-12-14 | 2024-04-02 | 1 | NAP | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | AWC
000239 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 1 | 131242-WSW41-VI-M-1002 | 2024-04-02 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. Please note, that the approval, corresponds to the brand/manufacturer proposed by contractor in this submittal. Approval does not include assessment for Trader/Distributor. | 2024-04-23 | 2024-04-15 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000239 | 2023-12-14 | 2024-04-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | AWC
000240 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0015 | 0 | 131242-WSW41-MI-C-0015 | 2023-12-14 | CSA Meeting Minutes 0015_20231116 | For Information | 2024-01-15 | 2024-01-25 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000240 | 2023-12-14 | 2023-12-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0015_20231116" | INF
000241 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0001 | 0 | 131242-WST02-VI-I-0001 | 2023-12-14 | Preliminary design and Vendor Approval – SSN Package (ICA) | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-26 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000241 | 2023-12-14 | 2024-05-02 | 1 | NAP | Approved with Comments | 2 | "Preliminary design and Vendor Approval – SSN Package (ICA)" | AWC
000241 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0001 | 1 | 131242-WST02-VI-I-0001 | 2024-05-02 | Preliminary design and Vendor Approval – SSN Package (ICA) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-23 | 2024-06-18 | 33 | Approved with Comments | YES | 2024-07-08 | NO | Resubmitted | 0 |  | Pending from MP | 000241 | 2023-12-14 | 2024-05-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – SSN Package (ICA)" | AWC
000242 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 0 | 131242-WSD11-DS-I-0003 | 2023-12-14 | THP PLC RIO Component Datasheet | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000242 | 2023-12-14 | 2024-03-11 | 1 | NAP | Not Approved | 2 | "THP PLC RIO Component Datasheet" | NAP
000242 | 01 | Low | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 1 | 131242-WSD11-DS-I-0003 | 2024-03-11 | THP PLC RIO Component Datasheet | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-01 | 2024-05-15 | 47 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000242 | 2023-12-14 | 2024-03-11 | 1 | NAP | Not Approved | 2 | "THP PLC RIO Component Datasheet" | NAP
000243 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 0 | 131242-WSD11-CH-I-0001 | 2023-12-14 | THP IO List | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000243 | 2023-12-14 | 2024-07-16 | 1 | NAP | Not Approved | 2 | "THP IO List" | NAP
000243 | 01 | Low | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 1 | 131242-WSD11-CH-I-0001 | 2024-07-16 | THP IO List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. To revise and resubmit. | 2024-08-05 | 2024-09-17 | 45 | Not Approved | YES | 2024-10-07 | NO | Resubmitted | 0 |  |  | 000243 | 2023-12-14 | 2024-07-16 | 1 | NAP | Not Approved | 2 | "THP IO List" | NAP
000244 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0004 | 0 | 131242-WST02-CL-B-0004 | 2023-12-14 | Heat Load Calculation Report for ACMV | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-03-12 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000244 | 2023-12-14 | 2023-12-14 | 0 | NAP | Not Approved | 1 | "Heat Load Calculation Report for ACMV" | NAP
000244 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 0 | 131242-WST02-CL-BH-8001 | 2024-05-14 | Heat Load Calculation Report for ACMV | Not approved - Revise and Resubmit | 2024-06-04 | 2024-08-14 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000244 | 2024-05-14 | 2025-03-20 | 2 | NAP | Approved | 2 | "Heat Load Calculation Report for ACMV" | APP
000244 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 2 | 131242-WST02-CL-BH-8001 | 2025-03-20 | Heat Load Calculation Report for ACMV | Rev 2: Approved | 2025-04-09 | 2025-05-25 | 47 | Approved | NO |  | YES | Resubmitted | 0 | Pending EICA input | Doc name duplicate with S#193, Fire Hydrant Calculation/ Pending by EICA info and C2D . Freedomer follow up | 000244 | 2024-05-14 | 2025-03-20 | 2 | APP | Approved | 2 | "Heat Load Calculation Report for ACMV" | APP
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1103 | A | 131242-WST02-DR-E-1103 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000245 | 2023-12-18 | 2023-12-18 | A | NAP | Not Approved | 1 | "SSN Earthing Layout Plan" | NAP
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B | 131242-WST02-DR-E-1100 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B | 131242-WST02-DR-E-1101 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B | 131242-WST02-DR-E-1102 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B_endorsed | 131242-WST02-DR-E-1100 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B_endorsed | 131242-WST02-DR-E-1101 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B_endorsed | 131242-WST02-DR-E-1102 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B_endorsed | 131242-WST02-DR-E-7750 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B_endorsed | 131242-WST02-DR-E-7751 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B_endorsed | 131242-WST02-DR-E-7752 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | AWC
000246 | 00 | Lilian | PMT | NA | 131242 | WSW41 | LT | PM | 0017 | 0 | 131242-WSW41-LT-PM-0017 | 2023-12-18 | THP Layout and Code Compliance | As requested by contractor via email dated 5 Feb 24 to withdraw the submission. | 2024-01-17 | 2024-02-06 | 36 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000246 | 2023-12-18 | 2023-12-18 | 0 | VOID | (VOID NOT IN USE) | 1 | "THP Layout and Code Compliance" | VOID
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1011 | 0 | 131242-WSW41-SD-S-1011 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  | Zora checking comment sheet | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | NAP
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1012 | 0 | 131242-WSW41-SD-S-1012 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  |  | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | NAP
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1013 | 0 | 131242-WSW41-SD-S-1013 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  |  | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | NAP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0001_ST601 | A | 131242-WST00-CL-G-0001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST601 – ERSS Design < 4m Depth" | NAP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0003_ST601 | NA | 131242-WST00-CH-IM-0003_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 1 | "ST601 – ERSS Design < 4m Depth" | NAP
000248 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA-NA | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 2 | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | NAP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-06 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-19 | Heng Peng to clear BIM comments. Pending BIM updates | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST602 | A | 131242-WST00-DR-C-8001_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" | NAP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0002_ST602 | A | 131242-WST00-CL-G-0002_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" | NAP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0004_ST602 | NA | 131242-WST00-CH-IM-0004_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" | NAP
000249 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA-NA | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 2 | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | NAP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2024-02-24 | 2024-07-02 | A.1 | NAP | Approved | 3 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-11 | 2024-07-01 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending Tenwit update. (Roobin) | 000249 | 2024-02-24 | 2024-07-02 | A.1 | AWC | Approved | 3 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A.1 | 131242-WST00-DR-G-8001_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  | R2_APP | 000249 | 2024-02-24 | 2024-07-02 | A.1 | APP | Approved | 3 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A.1 | 131242-WST00-DR-G-0100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A.1 | 131242-WST00-DR-G-0101_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A.1 | 131242-WST00-DR-G-1100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A.1 | 131242-WST00-DR-G-1101_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A.1 | 131242-WST00-DR-G-1102_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A.1 | 131242-WST00-DR-G-3100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" | APP
000250 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0001 | 0 | 131242-WSW41-VI-M-0001 | 2023-12-22 | Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-23 | 2024-02-26 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000250 | 2023-12-22 | 2023-12-22 | 0 | AWC | Approved with Comments | 1 | "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" | AWC
000251 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 0 | 131242-WST02-BQ-I-0001 | 2023-12-26 | C4B SSN PLC/ RIO Panel Component Catalogue | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-24 | 2024-01-29 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000251 | 2023-12-26 | 2024-04-08 | 1 | NAP | Not Approved | 2 | "C4B SSN PLC/ RIO Panel Component Catalogue" | NAP
000251 | 01 | Low | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 1 | 131242-WST02-BQ-I-0001 | 2024-04-08 | C4B SSN PLC/ RIO Panel Component Catalogue | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-29 | 2024-05-15 | 27 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 |  | Pending from MP | 000251 | 2023-12-26 | 2024-04-08 | 1 | NAP | Not Approved | 2 | "C4B SSN PLC/ RIO Panel Component Catalogue" | NAP
000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | A | 131242-WSW41-DR-EK-1000 | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 | ?? |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | A | 131242-WSW41-DR-EK-3000 | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000 | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000 | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | C | 131242-WSW41-DR-EK-1000 | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | 50 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | C | 131242-WSW41-DR-EK-3000 | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | 50 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | AWC
000253 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0013 | 0 | 131242-WSW41-MI-P-0013 | 2023-12-27 | Process & MEICA Meeting Minutes 0013_20231123 | Rev 0: For Information | 2024-01-25 | 2024-05-21 | 104 | For Information | NO |  | YES | Resubmitted | 0 | 2024-03-06 | Waiting for C2D reply | 000253 | 2023-12-27 | 2023-12-27 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0013_20231123" | INF
000254 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0018 | 0 | 131242-WSW41-LT-PM-0018 | 2023-12-28 | CV of WSHS | Approved | 2024-01-26 | 2024-02-14 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000254 | 2023-12-28 | 2023-12-28 | 0 | APP | Approved | 1 | "CV of WSHS" | APP
000255 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0011 | 0 | 131242-WSD11-CD-IM-0011 | 2023-12-28 | Submission of Milestone 1.1 THP MCC Room | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-01-26 | 2024-03-28 | 65 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2023-12-28 | 2023-12-28 | 0 | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 THP MCC Room" | AWC
000255 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034 | 2024-06-04 | Milestone 1.2 THP MCC Room | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-12-05 | 132 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | AWC
000255 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034 | 2025-02-26 | Milestone 2 THP MCC Room | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | AWC
000255 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 1 | 131242-WSD11-CD-IM-0034 | 2025-10-31 | Milestone 3 THP MCC Room | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-23 | 81 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | AWC
000256 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0003 | 0 | 131242-WSW41-CT-W-0003 | 2023-12-28 | On-Demand Bond for SSN | Approved. Address as per Chin Swee Rd address as the bond was submitted (in Nov 2023) was prior to the notice (in Dec 2023) of change of address. | 2024-01-26 | 2024-01-16 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000256 | 2023-12-28 | 2023-12-28 | 0 | APP | Approved | 1 | "On-Demand Bond for SSN" | APP
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6200 | 0 | 131242-WSD11-DR-P-6200 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 | Related to Detailed Design Report. | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6300 | 0 | 131242-WSD11-DR-P-6300 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6400 | 0 | 131242-WSD11-DR-P-6400 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6600 | 0 | 131242-WSD11-DR-P-6600 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6601 | 0 | 131242-WSD11-DR-P-6601 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | B | 131242-WSD11-DR-P-6200 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | B | 131242-WSD11-DR-P-6300 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | B | 131242-WSD11-DR-P-6400 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | B | 131242-WSD11-DR-P-6600 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | B | 131242-WSD11-DR-P-6601 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | B | 131242-WSD11-DR-P-6101 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | B | 131242-WSD11-DR-P-6121 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" | AWC
000258 | 00 | Yi Hao | Contracts | NA | 131242 | WST02 | PO | P | 0001 | 0 | 131242-WST02-PO-P-0001 | 2024-01-03 | Unpriced PO for SSN Package (MattenPlant) | For Information | 2024-01-31 | 2024-04-26 | 82 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000258 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Unpriced PO for SSN Package (MattenPlant)" | INF
000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0014 | 0 | 131242-WSW41-MI-P-0014 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | 99 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000259 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | INF
000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0015 | 0 | 131242-WSW41-MI-P-0015 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | 99 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000259 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | INF
000260 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0013 | 0 | 131242-WST02-CD-IM-0013 | 2024-01-05 | Milestone 1.1 SSN Overall Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-02-02 | 2024-03-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2024-01-05 | 2024-01-05 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 SSN Overall Area" | AWC
000260 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0038 | 0 | 131242-WST02-CD-IM-0038 | 2024-06-11 | Milestone 1.2 SSN Overall Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2024-06-11 | 2024-06-11 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 SSN Overall Area" | AWC
000260 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058 | 2025-05-15 | Milestone 2 SSN Overall Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2025-05-15 | 2025-10-31 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | AWC
000260 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058 | 2025-10-31 | Milestone 3 SSN Overall Area | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000260 | 2025-05-15 | 2025-10-31 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | AWC
000261 | 00 | Lilian | PMT | NA | 131242 | WSW41 | PC | W | 0006 | 0 | 131242-WSW41-PC-W-0006 | 2024-01-08 | PAYMENT CLAIM NO.6 | Approved. Please refer to S.O. correspondence no. 103 dated 8 Jan 2024. | 2024-02-05 | 2024-01-30 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000261 | 2024-01-08 | 2024-01-08 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.6" | APP
000262 | 00 | Geno | Piping | NA | 131242 | WST02 | SH | M | 1002 | 0 | 131242-WST02-SH-M-1002 | 2024-01-08 | Tie in Schedule for SSN | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-05 | 2024-05-27 | 100 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 | Waiting for SO RFI reply . KM & Qili to check with Karthic for the response | 000262 | 2024-01-08 | 2024-01-08 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for SSN" | AWC
000263 | 00 | Geno | Piping | NA | 131242 | WSD11 | SH | M | 1001 | 0 | 131242-WSD11-SH-M-1001 | 2024-01-09 | Tie in Schedule for THP | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 99 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 |  | 000263 | 2024-01-09 | 2024-01-09 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for THP" | AWC
000264 | 00 | Geno | Piping | NA | 131242 | WSW41 | SH | M | 5000 | 0 | 131242-WSW41-SH-M-5000 | 2024-01-09 | Tie in Schedule for Side wide | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 99 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 |  | 000264 | 2024-01-09 | 2024-01-09 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for Side wide" | AWC
000265 | 00 | Lilian/ Yi Hao | PMT | NA | 131242 | WSW41 | LT | PM | 0019 | 0 | 131242-WSW41-LT-PM-0019 | 2024-01-09 | Notice of Office Relocation | For Information | 2024-02-06 | 2024-05-02 | 82 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000265 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "Notice of Office Relocation" | INF
000266 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0013 | 0 | 131242-WSW41-CD-IM-0013 | 2024-01-09 | Submission Of BIM Coordination VCM Model (Dec – 2023) | For Information | 2024-02-06 | 2024-01-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000266 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Dec – 2023)" | INF
000267 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0016 | 0 | 131242-WSW41-MI-C-0016 | 2024-01-09 | CSA Meeting Minutes 0016_20231130 | For Information | 2024-02-06 | 2024-01-25 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000267 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0016_20231130" | INF
000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0014 | 0 | 131242-WSW41-MI-IM-0014 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000268 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" | INF
000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0015 | 0 | 131242-WSW41-MI-IM-0015 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000268 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" | INF
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6050 | A | 131242-WSD11-DR-P-6050 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 | Related to Detailed Design Report. | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6063 | A | 131242-WSD11-DR-P-6063 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6070 | A | 131242-WSD11-DR-P-6070 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | B | 131242-WSD11-DR-P-6050 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | B | 131242-WSD11-DR-P-6063 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6019 | A | 131242-WSD11-DR-P-6019 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | Resubmitted | Related to Detailed Design Report. | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6020 | A | 131242-WSD11-DR-P-6020 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6021 | A | 131242-WSD11-DR-P-6021 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6022 | A | 131242-WSD11-DR-P-6022 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6023 | A | 131242-WSD11-DR-P-6023 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6024 | A | 131242-WSD11-DR-P-6024 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6025 | A | 131242-WSD11-DR-P-6025 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6026 | A | 131242-WSD11-DR-P-6026 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6027 | A | 131242-WSD11-DR-P-6027 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6028 | A | 131242-WSD11-DR-P-6028 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6029 | A | 131242-WSD11-DR-P-6029 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6030 | A | 131242-WSD11-DR-P-6030 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6031 | A | 131242-WSD11-DR-P-6031 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6032 | A | 131242-WSD11-DR-P-6032 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6033 | A | 131242-WSD11-DR-P-6033 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6034 | A | 131242-WSD11-DR-P-6034 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6035 | A | 131242-WSD11-DR-P-6035 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6036 | A | 131242-WSD11-DR-P-6036 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | B | 131242-WSD11-DR-P-6019 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | B | 131242-WSD11-DR-P-6020 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | B | 131242-WSD11-DR-P-6021 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | B | 131242-WSD11-DR-P-6022 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | B | 131242-WSD11-DR-P-6023 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | B | 131242-WSD11-DR-P-6024 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | B | 131242-WSD11-DR-P-6025 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | B | 131242-WSD11-DR-P-6026 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | B | 131242-WSD11-DR-P-6027 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | B | 131242-WSD11-DR-P-6028 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | B | 131242-WSD11-DR-P-6029 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | B | 131242-WSD11-DR-P-6030 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | B | 131242-WSD11-DR-P-6031 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | B | 131242-WSD11-DR-P-6032 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | B | 131242-WSD11-DR-P-6033 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | B | 131242-WSD11-DR-P-6034 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | B | 131242-WSD11-DR-P-6035 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | B | 131242-WSD11-DR-P-6036 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | AWC
000271 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0013 | 0 | 131242-WSW41-VI-C-0013 | 2024-01-11 | Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd) | Approved | 2024-02-08 | 2024-01-22 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000271 | 2024-01-11 | 2024-01-11 | 0 | APP | Approved | 1 | "Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd)" | APP
000272 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | E | 8001 | 0 | 131242-WSD11-DR-E-8001 | 2024-01-11 | THP ATEX Zone Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached files for comments. | 2024-02-08 | 2024-05-15 | 89 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 | 2024-07-26 |  | 000272 | 2024-01-11 | 2024-01-11 | 0 | NAP | Not Approved | 1 | "THP ATEX Zone Drawing" | NAP
000273 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | LT | IM | 0001 | 0 | 131242-WSW41-LT-IM-0001 | 2024-01-12 | Common Data Environment (CDE) Set-Up and Rollout | For Information. This document should be part of BEP under CDE workflow | 2024-02-09 | 2024-02-27 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000273 | 2024-01-12 | 2024-01-12 | 0 | INF | For Information | 1 | "Common Data Environment (CDE) Set-Up and Rollout" | INF
000274 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 0 | 131242-WST02-CL-S-0003_ST612 | 2024-01-13 | ST612_Typical Railing Design Calculation | Rev 0: Not Approved. Please refer to comment sheet for resubmission. Drawing attached should be for information not "shop drawing". | 2024-02-09 | 2024-02-01 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" | AWC
000274 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 1 | 131242-WST02-CL-S-0003_ST612 | 2024-02-16 | ST612_Typical Railing Design Calculation | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-03-05 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" | AWC
000274 | 02 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 2 | 131242-WST02-CL-S-0003_ST612 | 2024-03-20 | ST612_Typical Railing Design Calculation | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-11 | 2024-05-13 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" | AWC
000274 | 03 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 3 | 131242-WST02-CL-S-0003_ST612 | 2024-06-06 | ST612_Typical Railing Design Calculation | Rev.3:Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-07-05 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-18 |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | AWC | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" | AWC
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612 | A | 131242-WST02-DR-S-8600_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2024-07-31 | A | AWC | Approved with Comments | 1 | "ST612_Typical Railing Design Calculation" | AWC
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | E | 131242-WST02-DR-S-5600_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | E | 131242-WST02-DR-S-5601_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | J | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | C | 131242-WST02-DR-S-5602_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | I | 131242-WST02-DR-S-5600_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | J | 131242-WST02-DR-S-5601_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | J | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | I | 131242-WST02-DR-S-5602_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | AWC
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A | 131242-WST02-DR-S-1000_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A | 131242-WST02-DR-S-1006_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A | 131242-WST02-DR-S-1007_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A | 131242-WST02-DR-S-1008_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A | 131242-WST02-DR-S-1013_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A | 131242-WST02-DR-S-1014_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A | 131242-WST02-DR-S-1015_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A | 131242-WST02-DR-S-1016_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A | 131242-WST02-DR-S-1017_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A | 131242-WST02-DR-S-1018_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A | 131242-WST02-DR-S-1019_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A | 131242-WST02-DR-S-1020_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A | 131242-WST02-DR-S-1021_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A | 131242-WST02-DR-S-1022_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A | 131242-WST02-DR-S-3005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A | 131242-WST02-DR-S-3008_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A | 131242-WST02-DR-S-3009_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A | 131242-WST02-DR-S-5005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A | 131242-WST02-DR-S-5006_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A | 131242-WST02-DR-S-7002_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A | 131242-WST02-DR-S-7003_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A | 131242-WST02-DR-S-7004_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A | 131242-WST02-DR-S-7005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A | 131242-WST02-DR-S-8003_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A.1 | 131242-WST02-DR-S-1000_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-04-25 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-07-19 | Heng Peng: BIM to clear Aaron comments | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A.1 | 131242-WST02-DR-S-1006_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A.1 | 131242-WST02-DR-S-1007_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A.1 | 131242-WST02-DR-S-1008_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A.1 | 131242-WST02-DR-S-1013_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A.1 | 131242-WST02-DR-S-1014_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A.1 | 131242-WST02-DR-S-1015_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A.1 | 131242-WST02-DR-S-1016_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A.1 | 131242-WST02-DR-S-1017_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A.1 | 131242-WST02-DR-S-1018_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A.1 | 131242-WST02-DR-S-1019_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A.1 | 131242-WST02-DR-S-1020_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A.1 | 131242-WST02-DR-S-1021_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A.1 | 131242-WST02-DR-S-1022_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A.1 | 131242-WST02-DR-S-3005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A.1 | 131242-WST02-DR-S-3008_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A.1 | 131242-WST02-DR-S-3009_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A.1 | 131242-WST02-DR-S-5005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A.1 | 131242-WST02-DR-S-5006_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A.1 | 131242-WST02-DR-S-7002_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A.1 | 131242-WST02-DR-S-7003_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A.1 | 131242-WST02-DR-S-7004_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A.1 | 131242-WST02-DR-S-7005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A.1 | 131242-WST02-DR-S-8003_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000276 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0008 | 0 | 131242-WSW41-RT-PM-0008 | 2024-01-16 | C4B Monthly Progress Report Number No.08 (12/23) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-02-14 | 2024-01-31 | 11 | Approved with Comments | YES | 2024-02-20 | NO | Resubmitted | 0 |  |  | 000276 | 2024-01-16 | 2024-01-16 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.08 (12/23)" | AWC
000277 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 0 | 131242-WSW41-LC-Z-0001 | 2024-01-16 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. Please append COS. | 2024-02-14 | 2024-01-22 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000277 | 2024-01-16 | 2024-02-02 | 1 | INF | For Information | 2 | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | INF
000277 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 1 | 131242-WSW41-LC-Z-0001 | 2024-02-02 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. | 2024-02-23 | 2024-02-19 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000277 | 2024-01-16 | 2024-02-02 | 1 | INF | For Information | 2 | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | INF
000278 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0001 | 0 | 131242-WSD11-RT-P-0001 | 2024-01-17 | THP - Basis of Design Report | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-15 | 2024-03-01 | 32 | Approved with Comments | YES | 2024-03-21 | NO | Resubmitted | 0 | 2024-07-19 |  | 000278 | 2024-01-17 | 2024-01-17 | 0 | AWC | Approved with Comments | 1 | "THP - Basis of Design Report" | AWC
000279 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0016 | 0 | 131242-WSW41-MI-P-0016 | 2024-01-18 | Process & MEICA Meeting Minutes 0016_20240104 | Rev 0: For Information | 2024-02-16 | 2024-05-21 | 88 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000279 | 2024-01-18 | 2024-01-18 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0016_20240104" | INF
000280 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0020 | 0 | 131242-WSW41-LT-PM-0020 | 2024-01-20 | CV of Team Member (ECO cum ECMO) | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-19 | 2024-02-01 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000280 | 2024-01-20 | 2024-04-12 | 1 | NAP | Approved | 2 | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | APP
000280 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0020 | 1 | 131242-WSW41-LT-PM-0020 | 2024-04-12 | CV of Team Member (ECO) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000280 | 2024-01-20 | 2024-04-12 | 1 | APP | Approved | 2 | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | APP
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 1100 | A | 131242-WSW41-DR-E-1100 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 | To withdraw | Combined with Prolog 000252 - Sitewide Piperack Lightning Protection System | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" | AWC
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 2000 | A | 131242-WSW41-DR-E-2000 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" | AWC
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 5000 | A | 131242-WSW41-DR-E-5000 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" | AWC
000282 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0021 | 0 | 131242-WSW41-LT-PM-0021 | 2024-01-23 | Assign of Builder License (CES_SDC Pte. Ltd.) | For Information | 2024-02-21 | 2024-05-10 | 78 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000282 | 2024-01-23 | 2024-01-23 | 0 | INF | For Information | 1 | "Assign of Builder License (CES_SDC Pte. Ltd.)" | INF
000283 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0007 | 0 | 131242-WSW41-MI-PM-0007 | 2024-01-23 | Monthly Progress Meeting Minutes 0007_20231219 | For Information | 2024-02-21 | 2024-01-24 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000283 | 2024-01-23 | 2024-01-23 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0007_20231219" | INF
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | B | NAP | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-02-16 | 2024-02-16 | A1 | NAP | Not Approved | 2 | "IFC of ST604 : Piling design of Minor Structures " | NAP
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B | 131242-WST02-DR-C-1001_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A1 | 131242-WST02-DR-C-1002_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | A2 | NAP | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | NAP
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  | Zora to reply. (Refer to submission 340 Amendment of ST604) | 000284 | 2024-01-23 | 2024-02-16 | B | AWC | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  |  | 000284 | 2024-02-16 | 2024-02-16 | A1 | AWC | Not Approved | 2 | "IFC of ST604 : Piling design of Minor Structures " | NAP
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B1 | 131242-WST02-DR-C-1001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A2 | 131242-WST02-DR-C-1002_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | A2 | AWC | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | AWC
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | NAP
000285 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0007 | 0 | 131242-WSW41-PS-PM-0007 | 2024-01-24 | Monthly Progress Presentation No. 07 (1123) | For Information | 2024-02-22 | 2024-01-29 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000285 | 2024-01-24 | 2024-01-24 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 07 (1123)" | INF
000286 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0008 | 0 | 131242-WSW41-PS-PM-0008 | 2024-01-24 | Monthly Progress Presentation No. 08 (1223) | For Information | 2024-02-22 | 2024-01-25 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000286 | 2024-01-24 | 2024-01-24 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 08 (1223)" | INF
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5000_ST604 | A | 131242-WST02-SD-C-5000_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5001_ST604 | A | 131242-WST02-SD-C-5001_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5002_ST604 | A | 131242-WST02-SD-C-5002_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5003_ST604 | A | 131242-WST02-SD-C-5003_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5004_ST604 | A | 131242-WST02-SD-C-5004_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 8000_ST604 | A | 131242-WST02-SD-C-8000_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 00 | Zora | CSA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing | NA | NA | NA | NA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing -NA-NA-NA-NA | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | NA | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5000_ST604 | B | 131242-WST02-SD-S-5000_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-15 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-04-18 | D | NAP | Approved with Comments | 2 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | AWC
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5001_ST604 | B | 131242-WST02-SD-S-5001_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5002_ST604 | B | 131242-WST02-SD-S-5002_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5003_ST604 | B | 131242-WST02-SD-S-5003_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5004_ST604 | B | 131242-WST02-SD-S-5004_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8000_ST604 | B | 131242-WST02-SD-S-8000_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | NAP
000287 | 02 | Zora | CSA | NA | 131242 | NA | SD | S | Relpy to comment Sheet | NA | 131242-NA-SD-S-Relpy to comment Sheet | 2024-02-28 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1&2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-03-20 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-28 | 2024-02-28 | NA | AWC | Approved with Comments | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | AWC
000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5000_ST604 | D | 131242-WST02-SD-S-5000_ST604 | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-21 | 23 | Approved with Comments | YES | 2024-06-10 | NO | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-04-18 | D | AWC | Approved with Comments | 2 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | AWC
000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5012_ST604 | D | 131242-WST02-SD-S-5012_ST604 | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-21 | 23 | Approved with Comments | YES | 2024-06-10 | NO | Resubmitted | 0 |  |  | 000287 | 2024-04-18 | 2024-04-18 | D | AWC | Approved with Comments | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" | AWC
000288 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0007 | 0 | 131242-WSW41-PC-W-0007 | 2024-01-24 | PAYMENT CLAIM NO.7 | Approved. Please refer to S.O. correspondence no. 116 dated 25 Jan 2024. | 2024-02-22 | 2024-02-15 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000288 | 2024-01-24 | 2024-01-24 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.7" | APP
000289 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 0 | 131242-WSW41-CN-I-0001 | 2024-01-26 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-02-26 | 2024-04-17 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000289 | 2024-01-26 | 2024-04-19 | 1 | NAP | Rejected | 2 | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | REJ
000289 | 01 | Low | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 1 | 131242-WSW41-CN-I-0001 | 2024-04-19 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 1: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-05-21 | 22 | Rejected | YES | 2024-06-10 | NO | Resubmitted | 0 |  | (RFC) NO.: 1230207-RFC-0004 R1 | 000289 | 2024-01-26 | 2024-04-19 | 1 | REJ | Rejected | 2 | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | REJ
000290 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | I | 0002 | 0 | 131242-WSD11-DS-I-0002 | 2024-02-01 | Control Valves Data Sheet (THP) | Rev 0: Not approved - Revise and Resubmit | 2024-03-01 | 2024-04-29 | 62 | Not Approved | YES | 2024-05-17 | NO | Resubmitted | 0 | 2024-08-02 |  | 000290 | 2024-02-01 | 2024-02-01 | 0 | NAP | Not Approved | 1 | "Control Valves Data Sheet (THP)" | NAP
000291 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0015 | 0 | 131242-WSD11-CD-IM-0015 | 2024-02-01 | Milestone 1.1 THP EICA Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033 | 2024-06-04 | Milestone 1.2 THP EICA Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0_wd | 131242-WSD11-CD-IM-0033 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A_wd | 131242-WSD11-DR-E-1030 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | REJ | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A_wd | 131242-WSD11-DR-E-3010 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | REJ | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A_wd | 131242-WSD11-DR-E-3011 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | REJ | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A_wd | 131242-WSD11-DR-E-3012 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | REJ | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 1 | 131242-WSD11-CD-IM-0033 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | AWC
000292 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0017 | 0 | 131242-WSD11-CD-IM-0017 | 2024-02-01 | Milestone 1.1 THP Overall & Equipment Layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Overall & Equipment Layout" | AWC
000292 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2024-06-11 | Milestone 1.2 THP Overall & Equipment Layout | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | PEN | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 228 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 228 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 228 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | PEN | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | PEN | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | PEN | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | NAP
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A.1 | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | AWC
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000293 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0018 | 0 | 131242-WSD11-CD-IM-0018 | 2024-02-01 | Milestone 1.1 THP A100 Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP A100 Silo Area inside Biosolid Building" | AWC
000293 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030 | 2024-06-11 | Milestone 1.2 THP A100 Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | AWC
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 2: Not approved - Revise and Resubmit. No Electrical / ICA Cutsheets attached with submittal. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | NAP | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | AWC
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1130 | A | 131242-WSD11-DR-M-1130 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-11-09 | 2024-11-09 | A | NAP | Not Approved | 1 | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | NAP
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1131 | A | 131242-WSD11-DR-M-1131 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-11-09 | 2024-11-09 | A | NAP | Not Approved | 1 | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | NAP
000293 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030 | 2025-04-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | AWC
000293 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030 | 2025-10-31 | Milestone 3 THP A100 Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-20 | 80 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | AWC
000294 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0019 | 0 | 131242-WSD11-CD-IM-0019 | 2024-02-01 | Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032 | 2024-06-11 | Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_WD | A | 131242-WSD11-DR-B-1003_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_WD | A | 131242-WSD11-DR-BH-1000_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_WD | A | 131242-WSD11-DR-BH-1001_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_WD | A | 131242-WSD11-DR-BH-1002_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_WD | A | 131242-WSD11-DR-BH-3000_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175 | A_WD | 131242-WSD11-DR-M-1175 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176 | A_WD | 131242-WSD11-DR-M-1176 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177 | A_WD | 131242-WSD11-DR-M-1177 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178 | A_WD | 131242-WSD11-DR-M-1178 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179 | A_WD | 131242-WSD11-DR-M-1179 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180 | A_WD | 131242-WSD11-DR-M-1180 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | REJ
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | AWC
000295 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 0 | 131242-WSW41-VI-M-0017 | 2024-02-01 | Preliminary Design and Vendor Approval of Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-04-16 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 | Related to Tank accessories. In Progress. To check the lead time after PO issue to meet the ROS date (1st Wk of Oct 24) | 000295 | 2024-02-01 | 2024-07-31 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" | AWC
000295 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 1 | 131242-WSW41-VI-M-0017 | 2024-07-31 | Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-21 | 2024-08-29 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000295 | 2024-02-01 | 2024-07-31 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" | AWC
000296 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 0 | 131242-WSW41-SP-C-0004 | 2024-02-01 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-01 | 2024-02-16 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | NAP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | APP
000296 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 1 | 131242-WSW41-SP-C-0004 | 2024-06-13 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-28 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | NAP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | APP
000296 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 2 | 131242-WSW41-SP-C-0004 | 2024-07-15 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.2: Approved | 2024-08-02 | 2024-08-12 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | APP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | APP
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A | 131242-WSW41-DR-M-5100 | 2024-02-01 | Pipe Support Standard - General Notes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A | 131242-WSW41-DR-M-5101 | 2024-02-01 | Pipe Support Standard - S01 U-Bolt | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A | 131242-WSW41-DR-M-5102 | 2024-02-01 | Pipe Support Standard - S02 SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A | 131242-WSW41-DR-M-5103 | 2024-02-01 | Pipe Support Standard - S03 PAD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A | 131242-WSW41-DR-M-5104 | 2024-02-01 | Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A | 131242-WSW41-DR-M-5105 | 2024-02-01 | Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5106 | A | 131242-WSW41-DR-M-5106 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5107 | A | 131242-WSW41-DR-M-5107 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 2" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A | 131242-WSW41-DR-M-5108 | 2024-02-01 | Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A | 131242-WSW41-DR-M-5109 | 2024-02-01 | Pipe Support Standard - S08 SLIDE STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A | 131242-WSW41-DR-M-5110 | 2024-02-01 | Pipe Support Standard - S09 TIGHT STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A | 131242-WSW41-DR-M-5111 | 2024-02-01 | Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A | 131242-WSW41-DR-M-5112 | 2024-02-01 | Pipe Support Standard - S11 GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A | 131242-WSW41-DR-M-5113 | 2024-02-01 | Pipe Support Standard - S12 STOPPER FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5114 | A | 131242-WSW41-DR-M-5114 | 2024-02-01 | Pipe Support Standard - S13 BRACKET SUPPORT | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S13 BRACKET SUPPORT" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5115 | A | 131242-WSW41-DR-M-5115 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5116 | A | 131242-WSW41-DR-M-5116 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5117 | A | 131242-WSW41-DR-M-5117 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5118 | A | 131242-WSW41-DR-M-5118 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5119 | A | 131242-WSW41-DR-M-5119 | 2024-02-01 | Pipe Support Standard - S16 STANCHION | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S16 STANCHION" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5120 | A | 131242-WSW41-DR-M-5120 | 2024-02-01 | Pipe Support Standard - S17 STANCHION (REINFORCED) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S17 STANCHION (REINFORCED)" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A | 131242-WSW41-DR-M-5121 | 2024-02-01 | Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5122 | A | 131242-WSW41-DR-M-5122 | 2024-02-01 | Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A | 131242-WSW41-DR-M-5123 | 2024-02-01 | Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A | 131242-WSW41-DR-M-5124 | 2024-02-01 | Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5125 | A | 131242-WSW41-DR-M-5125 | 2024-02-01 | Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450)" | AWC
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5126 | A | 131242-WSW41-DR-M-5126 | 2024-02-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.1 | 131242-WSW41-DR-M-5101 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A.1 | 131242-WSW41-DR-M-5102 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A.1 | 131242-WSW41-DR-M-5103 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.1 | 131242-WSW41-DR-M-5104 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A.1 | 131242-WSW41-DR-M-5105 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A.1 | 131242-WSW41-DR-M-5108 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A.1 | 131242-WSW41-DR-M-5109 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A.1 | 131242-WSW41-DR-M-5110 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.1 | 131242-WSW41-DR-M-5111 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A.1 | 131242-WSW41-DR-M-5112 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A.1 | 131242-WSW41-DR-M-5113 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A.1 | 131242-WSW41-DR-M-5121 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A.1 | 131242-WSW41-DR-M-5123 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A.1 | 131242-WSW41-DR-M-5124 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | AWC
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A | 131242-WSW41-DR-M-5140 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-03-13 | 2025-06-25 | A.1 | AWC | Approved with Comments | 2 | "Standard Pipe Support - For All Area " | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.2 | 131242-WSW41-DR-M-5101 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.2 | 131242-WSW41-DR-M-5104 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.2 | 131242-WSW41-DR-M-5111 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5139 | A | 131242-WSW41-DR-M-5139 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-06-25 | 2025-06-25 | A | AWC | Approved with Comments | 1 | "Standard Pipe Support - For All Area " | AWC
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A.1 | 131242-WSW41-DR-M-5140 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-03-13 | 2025-06-25 | A.1 | AWC | Approved with Comments | 2 | "Standard Pipe Support - For All Area " | AWC
000298 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0017 | 0 | 131242-WSW41-MI-P-0017 | 2024-02-02 | Process & MEICA Meeting Minutes 0017_20240118 | Rev 0: For Information | 2024-03-04 | 2024-05-21 | 77 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000298 | 2024-02-02 | 2024-02-02 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0017_20240118" | INF
000299 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 0 | 131242-WST02-VI-E-0002 | 2024-02-03 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-03-04 | 2024-03-01 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | APP
000299 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 1 | 131242-WST02-VI-E-0002 | 2024-03-25 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-04-16 | 2024-05-23 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | APP
000299 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 2 | 131242-WST02-VI-E-0002 | 2024-06-07 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-06-28 | 2024-08-15 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | APP
000299 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 3 | 131242-WST02-VI-E-0002 | 2024-10-16 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 3: Approved. | 2024-11-06 | 2024-11-04 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | APP | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | APP
000300 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0003 | 0 | 131242-WSW41-PS-HS-0003 | 2024-02-03 | Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024 | Rev 0: Noted for information | 2024-03-04 | 2024-03-18 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000300 | 2024-02-03 | 2024-02-03 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | INF
000301 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0008 | 0 | 131242-WSW41-MI-PM-0008 | 2024-02-05 | Monthly Progress Meeting Minutes 0008_20240123 | For Information | 2024-03-05 | 2024-02-07 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000301 | 2024-02-05 | 2024-02-05 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0008_20240123" | INF
000302 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0014 | 0 | 131242-WSD11-CD-IM-0014 | 2024-02-06 | Milestone 1.1 THP Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-06 | 2024-03-28 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-02-06 | 2024-02-06 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Compressed Air System" | AWC
000302 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0029 | 0 | 131242-WSD11-CD-IM-0029 | 2024-06-11 | Milestone 1.2 THP Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-06-11 | 2024-06-11 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 THP Compressed Air System" | AWC
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 0 | 131242-WSD11-CD-IM-0047 | 2024-10-17 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | AWC
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1165 | A.1 | 131242-WSD11-DR-M-1165 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | NAP | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1166 | A.1 | 131242-WSD11-DR-M-1166 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | NAP | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1020 | A | 131242-WSD11-DR-E-1020 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1021 | A | 131242-WSD11-DR-E-1021 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3000 | A | 131242-WSD11-DR-E-3000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3001 | A | 131242-WSD11-DR-E-3001 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" | NAP
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 1000 | A.1_MS2 | 131242-WSB01-DR-BH-1000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 3000 | A.1_MS2 | 131242-WSB01-DR-BH-3000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 5000 | A.1_MS2 | 131242-WSB01-DR-BH-5000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000302 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 1 | 131242-WSD11-CD-IM-0047 | 2025-04-10 | Milestone 2 THP Compressed Air System | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-30 | 2025-07-02 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | AWC
000302 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 2 | 131242-WSD11-CD-IM-0047 | 2025-10-27 | Milestone 3 THP Compressed Air System | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1003_ST605_BCA | A1 | 131242-WST02-DR-C-1003_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide DGN drawing | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1004_ST605_BCA | A1 | 131242-WST02-DR-C-1004_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5002_ST605_BCA | A1 | 131242-WST02-DR-C-5002_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7001_ST605_BCA | A1 | 131242-WST02-DR-C-7001_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8001_ST605_BCA | A1 | 131242-WST00-DR-C-8001_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | ST605-NOA | A1 | 131242-WST02-DR-C-ST605-NOA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | AWC
000304 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0020 | 0 | 131242-WSW41-CD-IM-0020 | 2024-02-06 | Submission Of BIM Coordination VCM Model (Jan–2024) | For Information | 2024-03-06 | 2024-02-22 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000304 | 2024-02-06 | 2024-02-06 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Jan–2024)" | INF
000305 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0009 | 0 | 131242-WSW41-RT-PM-0009 | 2024-02-08 | C4B Monthly Progress Report Number No.09 (01 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-03-08 | 2024-03-08 | 21 | Approved with Comments | YES | 2024-03-28 | NO | Resubmitted | 0 |  |  | 000305 | 2024-02-08 | 2024-02-08 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.09 (01 24)" | AWC
000306 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0008 | 0 | 131242-WSW41-PC-W-0008 | 2024-02-08 | Payment Claim No. 8 | Rev(0): Approved. Refer to S.O. correspondence no. 121 dated 9 Feb 2024. | 2024-03-08 | 2024-05-10 | 66 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000306 | 2024-02-08 | 2024-02-08 | 0 | APP | Approved | 1 | "Payment Claim No. 8" | APP
000307 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | A | 131242-WST02-DR-EP-5000 | 2024-02-13 | Typical Installation Details for Power | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 64 | Rejected | NO |  | YES | Resubmitted | 0 | 2025-02-27 |  | 000307 | 2024-02-13 | 2025-03-25 | B | REJ | Not Approved | 2 | "Typical Installation Details for Power" | NAP
000307 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | B | 131242-WST02-DR-EP-5000 | 2025-03-25 | Typical Installation Details for Power | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Not Approved | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000307 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Power" | NAP
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7002 | A | 131242-WST02-DR-E-7002 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2024-02-13 | A | NAP | Not Approved | 1 | "SSN Single Line Diagram for MOV DB" | NAP
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | A | 131242-WST02-DR-E-7003 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | NAP | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | A | 131242-WST02-DR-E-7004 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | NAP | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | B | 131242-WST02-DR-E-7003 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | B | 131242-WST02-DR-E-7004 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | B | 131242-WST02-DR-E-7005 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | B | 131242-WST02-DR-E-7006 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | B | 131242-WST02-DR-E-7007 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | B | 131242-WST02-DR-E-7008 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | C | 131242-WST02-DR-E-7003 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | C | 131242-WST02-DR-E-7004 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | C | 131242-WST02-DR-E-7005 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | C | 131242-WST02-DR-E-7006 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | C | 131242-WST02-DR-E-7007 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | C | 131242-WST02-DR-E-7008 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" | AWC
000309 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | A | 131242-WST02-BQ-E-0003 | 2024-02-13 | SSN Listing of Interface Points | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000309 | 2024-02-13 | 2024-07-22 | B | AWC | Approved with Comments | 2 | "SSN Listing of Interface Points" | AWC
000309 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | B | 131242-WST02-BQ-E-0003 | 2024-07-22 | SSN Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-10-29 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO NEED TO RESUBMIT | No need to resubmit as there is no major updates made - "Please resubmit if there are major updates or changes to the information stated". | 000309 | 2024-02-13 | 2024-07-22 | B | AWC | Approved with Comments | 2 | "SSN Listing of Interface Points" | AWC
000310 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | A | 131242-WST02-DR-EL-5000 | 2024-02-13 | Typical Installation Details for Lighting | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 64 | Not Approved | NO |  | YES | Resubmitted | 0 | 2025-02-27 |  | 000310 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Lighting" | NAP
000310 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | B | 131242-WST02-DR-EL-5000 | 2025-03-25 | Typical Installation Details for Lighting | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Not Approved | YES | 2025-05-26 | NO | Resubmitted | 0 |  | To check with C2D | 000310 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Lighting" | NAP
000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | A | 131242-WSD11-DR-EK-1000 | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 | 2025-02-19 |  | 000311 | 2024-02-13 | 2025-02-25 | B | NAP | Approved with Comments | 2 | "THP Lightning Protection System" | AWC
000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | A | 131242-WSD11-DR-EK-3000 | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | NAP | Approved with Comments | 2 | "THP Lightning Protection System" | AWC
000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | B | 131242-WSD11-DR-EK-1000 | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | AWC | Approved with Comments | 2 | "THP Lightning Protection System" | AWC
000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | B | 131242-WSD11-DR-EK-3000 | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | AWC | Approved with Comments | 2 | "THP Lightning Protection System" | AWC
000312 | 00 | Soe Myat | PMT | NA | 131242 | WSW41 | LT | PM | 0022 | 0 | 131242-WSW41-LT-PM-0022 | 2024-02-14 | CV of Team Member (QA/QC Manager) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-03-13 | 2024-02-19 | 3 | Approved with Comments | YES | 2024-03-08 | NO | Resubmitted | 0 |  |  | 000312 | 2024-02-14 | 2024-02-14 | 0 | AWC | Approved with Comments | 1 | "CV of Team Member (QA/QC Manager)" | AWC
000313 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0018 | 0 | 131242-WSW41-MI-P-0018 | 2024-02-15 | Process & MEICA Meeting Minutes 0018_20240201 | Rev 0: For Information | 2024-03-14 | 2024-05-21 | 68 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000313 | 2024-02-15 | 2024-02-15 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0018_20240201" | INF
000314 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0001 | 0 | 131242-WSW41-RT-HS-0001 | 2024-02-15 | 1st CONSAAS Audit report_2023 | Rev 0: Noted for information | 2024-03-14 | 2024-03-18 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000314 | 2024-02-15 | 2024-02-15 | 0 | INF | For Information | 1 | "1st CONSAAS Audit report_2023" | INF
000315 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 0 | 131242-WSW41-VI-I-0001 | 2024-02-19 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-03-18 | 2024-04-08 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000315 | 2024-02-19 | 2024-04-15 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | AWC
000315 | 01 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 1 | 131242-WSW41-VI-I-0001 | 2024-04-15 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-05-15 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000315 | 2024-02-19 | 2024-04-15 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | AWC
000315 | 02 | Balaji/ Karthik | EICA | NA | Comment Reply Sheet 20240716 | NA | NA | NA | NA | A.C | Comment Reply Sheet 20240716-NA-NA-NA-NA | 2024-07-17 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 44 | Approved with Comments | YES | 2024-10-07 | NO | Resubmitted | 0 |  |  | 000315 | 2024-07-17 | 2024-07-17 | A.C | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | AWC
000316 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0001 | 0 | 131242-WSW41-QA-M-0001 | 2024-02-20 | Inspection Test Plan for Structural Steel Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-08-14 | 126 | Not Approved | YES | 2024-09-03 | NO | Resubmitted | 0 |  |  | 000316 | 2024-02-20 | 2024-02-20 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Structural Steel Work" | NAP
000317 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | VI | HS | 0002 | 0 | 131242-WSW41-VI-HS-0002 | 2024-02-20 | Vendor Approval of CONSAAS Audit (ACE EHS) | Rev 0: Noted for information | 2024-03-19 | 2024-03-18 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000317 | 2024-02-20 | 2024-02-20 | 0 | INF | For Information | 1 | "Vendor Approval of CONSAAS Audit (ACE EHS)" | INF
000318 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 0 | 131242-WST02-VI-E-0003 | 2024-02-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to the comment sheet | 2024-03-20 | 2024-03-20 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | APP
000318 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 1 | 131242-WST02-VI-E-0003 | 2024-05-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-11 | 2024-07-04 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | APP
000318 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 2 | 131242-WST02-VI-E-0003 | 2024-07-22 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 2: Approved. | 2024-08-12 | 2024-09-24 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | APP
000319 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0009 | 0 | 131242-WSW41-PS-PM-0009 | 2024-02-21 | Monthly Progress Presentation No. 09 (0124) | For Information | 2024-03-20 | 2024-02-22 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000319 | 2024-02-21 | 2024-02-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 09 (0124)" | INF
000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0017 | 0 | 131242-WSW41-MI-C-0017 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000320 | 2024-02-22 | 2024-02-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" | INF
000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0018 | 0 | 131242-WSW41-MI-C-0018 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000320 | 2024-02-22 | 2024-02-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" | INF
000321 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 0 | 131242-WSD11-BQ-E-0003 | 2024-02-23 | THP Listing of Interface Points | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-03-22 | 2024-05-15 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000321 | 2024-02-23 | 2025-07-21 | 1 | NAP | Approved with Comments | 2 | "THP Listing of Interface Points" | AWC
000321 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 1 | 131242-WSD11-BQ-E-0003 | 2025-07-21 | THP Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-10-01 | 52 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000321 | 2024-02-23 | 2025-07-21 | 1 | AWC | Approved with Comments | 2 | "THP Listing of Interface Points" | AWC
000322 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 0 | 131242-WST02-CH-P-0002 | 2024-02-23 | Process Functional Description | Rev 0 : There are no active comments on the submittal. However, if there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 2024-03-22 | 2024-03-13 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-19 | If there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000322 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 1 | 131242-WST02-CH-P-0002 | 2024-07-23 | Process Functional Description | Rev 1: Approved | 2024-08-13 | 2024-08-29 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000322 | 2024-02-23 | 2025-03-04 | 3 | APP | Approved with Comments | 4 | "Process Functional Description" | AWC
000322 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 2 | 131242-WST02-CH-P-0002 | 2024-10-15 | Process Functional Description | Rev 2: Approved with comments. Please address the comments and resubmit. | 2024-11-05 | 2024-12-18 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000322 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 3 | 131242-WST02-CH-P-0002 | 2025-03-04 | Process Functional Description | Rev 3: Approved with comments. Resubmittal is required if there are any changes during the detail engineering. | 2025-03-24 | 2025-04-28 | 39 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" | AWC
000323 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0019 | 0 | 131242-WSW41-MI-P-0019 | 2024-02-23 | Process & MEICA Meeting Minutes 0019_20240215 | Rev 0: For Information | 2024-03-22 | 2024-05-21 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000323 | 2024-02-23 | 2024-02-23 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0019_20240215" | INF
000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0001 | 0 | 131242-WSD11-LT-P-0001 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | 93 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000324 | 2024-02-24 | 2024-02-24 | 0 | REJ | Rejected | 1 | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | REJ
000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0002 | 0 | 131242-WSD11-LT-P-0002 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | 93 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000324 | 2024-02-24 | 2024-02-24 | 0 | REJ | Rejected | 1 | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | REJ
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | REJ | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | B | 131242-WST02-DR-S-1003_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-20 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A1 | 131242-WST02-DR-S-1003_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-17 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-06 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | NAP
000326 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 0 | 131242-WSD11-PO-E-0001 | 2024-02-26 | Unpriced PO for Transformer (Hitachi) | Rev 0: Rejected. Please refer to attached file to comments. | 2024-03-25 | 2024-03-20 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000326 | 2024-02-26 | 2024-03-20 | 1 | REJ | For Information | 2 | "Unpriced PO for Transformer (Hitachi)" | INF
000326 | 01 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 1 | 131242-WSD11-PO-E-0001 | 2024-03-20 | Unpriced PO for Transformer (Hitachi) | For Information | 2024-04-11 | 2024-04-29 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000326 | 2024-02-26 | 2024-03-20 | 1 | INF | For Information | 2 | "Unpriced PO for Transformer (Hitachi)" | INF
000327 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0004 | 0 | 131242-WSD11-PO-M-0004 | 2024-02-26 | Unpriced PO for Blower (Aerzen) | For Information | 2024-03-25 | 2024-05-21 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000327 | 2024-02-26 | 2024-02-26 | 0 | INF | For Information | 1 | "Unpriced PO for Blower (Aerzen)" | INF
000328 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0003 | 0 | 131242-WSD11-PO-M-0003 | 2024-02-26 | Unpriced PO for Diffuser (Xylem) | For Information | 2024-03-25 | 2024-05-21 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000328 | 2024-02-26 | 2024-02-26 | 0 | INF | For Information | 1 | "Unpriced PO for Diffuser (Xylem)" | INF
000329 | 00 | Low | EICA | NA | 131242 | WST02 | VI | I | 0002 | 0 | 131242-WST02-VI-I-0002 | 2024-02-28 | Vendor Approval of SSN Package (ORP Analyser) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-04-08 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  | To check with Qili whether ORP required or not. | 000329 | 2024-02-28 | 2024-02-28 | 0 | VOID | (VOID NOT IN USE) | 1 | "Vendor Approval of SSN Package (ORP Analyser)" | VOID
000330 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | MI | I | 0001 | 0 | 131242-WSD11-MI-I-0001 | 2024-02-28 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 0: Accepted for information. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-05-09 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000330 | 2024-02-28 | 2024-02-28 | 0 | AWC | Approved with Comments | 1 | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | AWC
000330 | 01 | Freedomer | EICA | NA | 131242 | NA | MI | E | Comment Reply Sheet 20240716 S330.0 | NA | 131242-NA-MI-E-Comment Reply Sheet 20240716 S330.0 | 2024-07-17 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 1: Accepted for information. No resubmission required. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 44 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000330 | 2024-07-17 | 2024-07-17 | NA | INF | For Information | 1 | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | INF
000331 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0003 | 0 | 131242-WSD11-LT-P-0003 | 2024-02-28 | THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-27 | 2024-03-20 | 15 | Not Approved | YES | 2024-04-09 | NO | Resubmitted | 0 | 2024-07-19 |  | 000331 | 2024-02-28 | 2024-02-28 | 0 | NAP | Not Approved | 1 | "THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor" | NAP
000332 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | A.1 | 131242-WSW41-VI-M-0018 | 2024-02-29 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rejected as requested by Contractor as there still need to attach the document | 2024-03-28 | 2024-03-01 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | REJ | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | APP
000332 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018 | 2024-03-04 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-22 | 2024-04-15 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | AWC | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | APP
000333 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0019 | 0 | 131242-WSW41-VI-M-0019 | 2024-02-29 | Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-28 | 2024-04-16 | 33 | Approved with Comments | YES | 2024-05-06 | NO | Resubmitted | 0 |  |  | 000333 | 2024-02-29 | 2024-02-29 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." | AWC
000334 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 0 | 131242-WST02-VI-E-0004 | 2024-02-29 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | AWC
000334 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 1 | 131242-WST02-VI-E-0004 | 2024-03-26 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-17 | 2024-04-29 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | AWC
000334 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 2 | 131242-WST02-VI-E-0004 | 2024-05-16 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-06 | 2024-07-04 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | AWC
000334 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 3 | 131242-WST02-VI-E-0004 | 2024-07-28 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-16 | 2024-08-16 | 14 | Approved with Comments | YES | 2024-09-05 | NO | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | AWC
000335 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0009 | 0 | 131242-WSW41-MI-PM-0009 | 2024-03-01 | Monthly Progress Meeting Minutes 0009_20240220 | For Information | 2024-04-01 | 2024-03-04 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000335 | 2024-03-01 | 2024-03-01 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0009_20240220" | INF
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | A | 131242-WST02-SD-S-8001_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | C | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | A | 131242-WST02-SD-S-5005_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | A | 131242-WST02-SD-S-5006_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | A | 131242-WST02-SD-S-5007_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | A | 131242-WST02-SD-S-5008_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | A | 131242-WST02-SD-S-5009_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | A | 131242-WST02-SD-S-5010_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A | 131242-WST02-SD-S-5011_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | A.1 | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | C | 131242-WST02-SD-S-8001_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to clear BIM comments. | 000336 | 2024-03-01 | 2024-05-17 | C | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | D | 131242-WST02-SD-S-5005_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | B | 131242-WST02-SD-S-5006_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | D | 131242-WST02-SD-S-5007_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | D | 131242-WST02-SD-S-5008_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | B | 131242-WST02-SD-S-5009_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | B | 131242-WST02-SD-S-5010_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A.1 | 131242-WST02-SD-S-5011_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | A.1 | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5013_ST605 | B | 131242-WST02-SD-S-5013_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-05-17 | 2024-05-17 | B | NAP | Not Approved | 1 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | NAP
000337 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1003 | 0 | 131242-WSW41-VI-M-1003 | 2024-03-01 | Vendor Approval of cPVC Pipes & Fittings (GF) | Approved | 2024-04-01 | 2024-04-17 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000337 | 2024-03-01 | 2024-03-01 | 0 | APP | Approved | 1 | "Vendor Approval of cPVC Pipes & Fittings (GF)" | APP
000338 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-03-01 | PUB DC Drainage Submission | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-03-28 | PUB DC Drainage Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-13 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A | 131242-WST02-DR-A-1000_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A | 131242-WST02-DR-A-1002_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A | 131242-WST02-DR-A-1003_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A | 131242-WST02-DR-A-1004_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A | 131242-WST02-DR-A-1009_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A | 131242-WST02-DR-A-2000_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A | 131242-WST02-DR-A-2001_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A | 131242-WST02-DR-A-2002_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A | 131242-WST02-DR-A-2003_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A | 131242-WST02-DR-A-2007_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_PUB | B | 131242-WST02-DR-A-0001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_PUB | B | 131242-WST02-DR-A-0002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | B | 131242-WST02-DR-A-1000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | B | 131242-WST02-DR-A-1001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | B | 131242-WST02-DR-A-1002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | B | 131242-WST02-DR-A-1003_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | B | 131242-WST02-DR-A-1004_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | B | 131242-WST02-DR-A-1006_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A | NAP | Not Approved | 2 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | B | 131242-WST02-DR-A-1009_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | B | 131242-WST02-DR-A-2000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | B | 131242-WST02-DR-A-2001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | B | 131242-WST02-DR-A-2002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | B | 131242-WST02-DR-A-2003_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | B | 131242-WST02-DR-A-2007_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | B | 131242-WST02-DR-A-3000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A.2 | NAP | Not Approved | 2 | "PUB DC Drainage Submission " | NAP
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_PUB | B | 131242-WST02-DR-A-5004_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " | NAP
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | REJ | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | REJ | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.2 | 131242-WST02-DR-A-1000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.4 | 131242-WST02-DR-A-1001_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | PEN | Rejected | 9 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.4 | 131242-WST02-DR-A-1002_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.4 | 131242-WST02-DR-A-1003_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.4 | 131242-WST02-DR-A-1004_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_PUB | A | 131242-WST02-DR-A-1005_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2026-01-12 | 2026-01-12 | A | PEN | Awaiting S.O.'s response | 1 | "PUB DC Drainage Submission " | PEN
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | A | 131242-WST02-DR-A-1006_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A | PEN | Not Approved | 2 | "PUB DC Drainage Submission " | NAP
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.4 | 131242-WST02-DR-A-1009_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.4 | 131242-WST02-DR-A-2000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " | REJ
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A.4 | 131242-WST02-DR-A-2001_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A.4 | 131242-WST02-DR-A-2002_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A.4 | 131242-WST02-DR-A-2003_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A.4 | 131242-WST02-DR-A-2007_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " | NAP
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | A.2 | 131242-WST02-DR-A-3000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A.2 | PEN | Not Approved | 2 | "PUB DC Drainage Submission " | NAP
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0016 | 0 | 131242-WSW41-MI-IM-0016 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | INF
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0017 | 0 | 131242-WSW41-MI-IM-0017 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | INF
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0018 | 0 | 131242-WSW41-MI-IM-0018 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | INF
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 00 | Zora | CSA | NA | 131242 | NA | DR | S | Submission Acknowledgement | A.1 | 131242-NA-DR-S-Submission Acknowledgement | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340 | 2024-03-05 | 2024-03-05 | A.1 | INF | For Information | 1 | "ST615 – Amendment of ST604 (BCA Submission for Information) " | INF
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to clear BIM comments and to provide Native files | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000341 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 0 | 131242-WSD11-CD-I-0004 | 2024-03-05 | THP UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" | AWC
000341 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 1 | 131242-WSD11-CD-I-0004 | 2024-04-19 | THP UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" | AWC
000341 | 02 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 2 | 131242-WSD11-CD-I-0004 | 2024-10-22 | THP UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2024-12-18 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" | AWC
000341 | 03 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 3 | 131242-WSD11-CD-I-0004 | 2025-01-21 | THP UPS Loading List | Not Approved - Revise and resubmit | 2025-02-10 | 2025-05-15 | 82 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" | AWC
000341 | 04 | Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 4 | 131242-WSD11-CD-I-0004 | 2025-05-27 | THP UPS Loading List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-16 | 2025-09-11 | 77 | Approved with Comments | YES | 2025-10-01 | NO | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | AWC | Approved with Comments | 5 | "THP UPS Loading List" | AWC
000342 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | CD | I | 0007 | 0 | 131242-WST02-CD-I-0007 | 2024-03-05 | SSN UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000342 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0007 | 1 | 131242-WST02-CD-I-0007 | 2024-04-19 | SSN UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000342 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 2 | 131242-WST02-CD-I-0007 | 2024-11-20 | SSN UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-10 | 2024-12-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000342 | 03 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 3 | 131242-WST02-CD-I-0007 | 2025-01-21 | SSN UPS Loading List | Rev 3: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-10 | 2025-03-04 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000342 | 04 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 4 | 131242-WST02-CD-I-0007 | 2025-03-06 | SSN UPS Loading List | Not Approved - Revise and resubmit | 2025-03-26 | 2025-05-15 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000342 | 05 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 5 | 131242-WST02-CD-I-0007 | 2025-06-16 | SSN UPS Loading List | Rev 5: Approved with comments. No need resubmission. Refer attached file for comments. | 2025-07-04 | 2025-09-11 | 63 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | AWC | Approved with Comments | 6 | "SSN UPS Loading List" | AWC
000343 | 00 | Yuen Fatt | PMT | NA | 131242 | WSW41 | LT | PM | 0023 | 0 | 131242-WSW41-LT-PM-0023 | 2024-03-06 | CV of Team Member (LEW) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-04 | 2024-05-20 | 53 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000343 | 2024-03-06 | 2024-03-06 | 0 | AWC | Approved with Comments | 1 | "CV of Team Member (LEW)" | AWC
000344 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 0 | 131242-WST02-VI-I-0004 | 2024-03-06 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-09 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000344 | 2024-03-06 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductivity Analyser)" | AWC
000344 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 1 | 131242-WST02-VI-I-0004 | 2024-12-05 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000344 | 2024-03-06 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductivity Analyser)" | AWC
000345 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003 | 2024-03-06 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-15 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | AWC
000345 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003 | 2024-10-04 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rejected as requested | 2024-10-24 | 2024-10-18 | 10 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | REJ | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | AWC
000345 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 1 | 131242-WST02-VI-I-0003 | 2024-10-18 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | AWC
000345 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 2 | 131242-WST02-VI-I-0003 | 2025-02-27 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 3: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | AWC
000346 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 0 | 131242-WST02-VI-I-0005 | 2024-03-07 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-05 | 2024-05-16 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000346 | 2024-03-07 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" | AWC
000346 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 1 | 131242-WST02-VI-I-0005 | 2024-12-05 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000346 | 2024-03-07 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" | AWC
000347 | 00 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0008 | 0 | 131242-WSW41-MS-C-0008 | 2024-03-08 | MSRA, SWP for Time Lapse Camera Steel Pole Erection | Approved | 2024-04-08 | 2024-03-20 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000347 | 2024-03-08 | 2024-03-08 | 0 | APP | Approved | 1 | "MSRA, SWP for Time Lapse Camera Steel Pole Erection" | APP
000348 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0014 | 0 | 131242-WSW41-CD-IM-0014 | 2024-03-08 | Submission Of BIM Coordination VCM Model (Feb-2024) | For Information | 2024-04-08 | 2024-03-20 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000348 | 2024-03-08 | 2024-03-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Feb-2024)" | INF
000349 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | 0 | 131242-WSD11-CL-EL-7000 | 2024-03-08 | THP Lux Calculation and Luminaire Schedule | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-08 | 2024-05-07 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000349 | 2024-03-08 | 2024-07-16 | B | NAP | For Information | 2 | "THP Lux Calculation and Luminaire Schedule" | INF
000349 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | B | 131242-WSD11-CL-EL-7000 | 2024-07-16 | THP Lux Calculation and Luminaire Schedule | Rev 1: For Information. | 2024-08-05 | 2024-10-29 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000349 | 2024-03-08 | 2024-07-16 | B | INF | For Information | 2 | "THP Lux Calculation and Luminaire Schedule" | INF
000350 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 0 | 131242-WST02-VI-I-0006 | 2024-03-11 | Vendor Approval of SSN Package (pH Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-09 | 2024-05-14 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000350 | 2024-03-11 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (pH Analyzer)" | AWC
000350 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 1 | 131242-WST02-VI-I-0006 | 2024-12-05 | Vendor Approval of SSN Package (pH Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000350 | 2024-03-11 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (pH Analyzer)" | AWC
000351 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 0 | 131242-WSW41-SP-C-0005 | 2024-03-11 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-04-09 | 2024-03-26 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000351 | 2024-03-11 | 2024-06-20 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | APP
000351 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 1 | 131242-WSW41-SP-C-0005 | 2024-06-20 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Rev.1: Approved | 2024-07-10 | 2024-06-28 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000351 | 2024-03-11 | 2024-06-20 | 1 | APP | Approved | 2 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | APP
000352 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 0 | 131242-WSW41-VI-M-1009 | 2024-03-12 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rejected. The proposed vendor is dealer/sales representative and not the manufacturer/brand of pipes and fittings. | 2024-04-11 | 2024-04-17 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000352 | 2024-03-12 | 2024-05-10 | 1 | REJ | Approved | 2 | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | APP
000352 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 1 | 131242-WSW41-VI-M-1009 | 2024-05-10 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rev 0: Approved Please note, that the approval, corresponds to the brand (FROCH and JNDIA) proposed by CES_SDC in this submittal. Approval does not include assessment for TRADER. | 2024-05-31 | 2024-08-06 | 62 | Approved | NO |  | YES | Resubmitted | 0 |  | R0_Rej | 000352 | 2024-03-12 | 2024-05-10 | 1 | APP | Approved | 2 | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | APP
000353 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0020 | 0 | 131242-WSW41-MI-P-0020 | 2024-03-12 | Process & MEICA Meeting Minutes 0020_20240229 | Rev 0: For Information | 2024-04-11 | 2024-05-21 | 50 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000353 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0020_20240229" | INF
000354 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0004 | 0 | 131242-WSW41-PS-HS-0004 | 2024-03-12 | Incentive / Disincentive Audit Scheme for November 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000354 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for November 2023" | INF
000355 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0005 | 0 | 131242-WSW41-PS-HS-0005 | 2024-03-12 | Incentive / Disincentive Audit Scheme for December 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000355 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for December 2023" | INF
000356 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 0 | 131242-WST02-CL-E-0000 | 2024-03-12 | SSN Transformer Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-11 | 2024-05-20 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000356 | 2024-03-12 | 2025-05-30 | 2 | NAP | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" | AWC
000356 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 1 | 131242-WST02-CL-E-0000 | 2024-12-14 | SSN Transformer Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-03 | 2025-02-13 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-04 |  | 000356 | 2024-03-12 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" | AWC
000356 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 2 | 131242-WST02-CL-E-0000 | 2025-05-30 | SSN Transformer Sizing Calculations | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  | Pending Reply from Sunlight. Pending UPS details from Jacobs | 000356 | 2024-03-12 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" | AWC
000357 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0024 | 0 | 131242-WSW41-LT-PM-0024 | 2024-03-12 | Notice of Unforeseeable Underground Obstruction Near Chemical Dosing | Refer to S.O. Correspondence No.150. | 2024-04-11 | 2024-05-10 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  | Refer to S.O. Correspondence No.150. | 000357 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Notice of Unforeseeable Underground Obstruction Near Chemical Dosing" | INF
000358 | 00 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 0 | 131242-WST02-BQ-P-0001 | 2024-03-12 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-05-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | AWC | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" | INF
000358 | 01 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 1 | 131242-WST02-BQ-P-0001 | 2024-07-24 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-14 | 2024-08-29 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | AWC | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" | INF
000358 | 02 | Qili | Process | NA | 131242 | WST02 | BQ | P | 0001 | 2 | 131242-WST02-BQ-P-0001 | 2024-11-15 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 2: For Information | 2024-12-05 | 2025-03-04 | 77 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | INF | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" | INF
000359 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 0 | 131242-WSD11-VI-I-0001 | 2024-03-13 | Vendor Approval of THP Train Instrument | Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-12 | 2024-05-16 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | AWC
000359 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 1 | 131242-WSD11-VI-I-0001 | 2024-06-07 | Vendor Approval of THP Train Instrument (Siemens) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-05 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | AWC
000359 | 02 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 2 | 131242-WSD11-VI-I-0001 | 2024-08-20 | Vendor Approval of THP Train Instrument (Siemens) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-09-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | AWC
000359 | 03 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 3 | 131242-WSD11-VI-I-0001 | 2025-03-21 | Vendor Approval of THP Train Instrument (Siemens) | Rev 3: Approved with comments (except Electromagnetic flowmeter). To revise and resubmit. Refer attached file for comments. | 2025-04-10 | 2025-05-06 | 32 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | AWC
000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | A | 131242-WST02-DR-P-7001 | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | A | 131242-WST02-DR-P-7002 | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7001 | B | 131242-WST02-DR-P-7001 | 2024-06-19 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7002 | B | 131242-WST02-DR-P-7002 | 2024-03-14 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | 105 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | comments received on 14 Feb | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | D | 131242-WST02-DR-P-7001 | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | D | 131242-WST02-DR-P-7002 | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" | AWC
000361 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0006 | 0 | 131242-WSW41-PS-HS-0006 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Jan 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000361 | 2024-03-14 | 2024-03-14 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for Jan 2024" | INF
000362 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0007 | 0 | 131242-WSW41-PS-HS-0007 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Feb 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000362 | 2024-03-14 | 2024-03-14 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for Feb 2024" | INF
000363 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-IM-0022 | 2024-03-15 | Milestone 1.2 - Underground Services | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | REJ | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | AWC
000364 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-IM-0024 | 2024-03-15 | Milestone 1.2 - SSN Pump Station and Lamella Clarifier | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | AWC
000365 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0028 | 0 | 131242-WST02-CD-IM-0028 | 2024-03-15 | Milestone 1.2 - Sitewide Pipe Rack | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000365 | 2024-03-15 | 2024-03-15 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - Sitewide Pipe Rack" | REJ
000366 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0035 | 0 | 131242-WST02-CD-IM-0035 | 2024-03-15 | Milestone 1.2 - SSN Minor Drain | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000366 | 2024-03-15 | 2024-03-15 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Minor Drain" | REJ
000367 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-IM-0023 | 2024-03-18 | Milestone 1.2 - SSN Water Tank | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000367 | 2024-03-18 | 2024-06-03 | 0 | REJ | Approved with Comments | 2 | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" | AWC
000368 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2024-03-18 | Milestone 1.2 - SSN Pump Station and Blower | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | REJ | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | NAP
000369 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0026 | 0 | 131242-WST02-CD-IM-0026 | 2024-03-18 | Milestone 1.2 - SSN Chemical Dosing Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000369 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Chemical Dosing Area " | REJ
000370 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0027 | 0 | 131242-WST02-CD-IM-0027 | 2024-03-18 | Milestone 1.2 - SSN Electrical Building | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000370 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Electrical Building " | REJ
000371 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0029 | 0 | 131242-WST02-CD-IM-0029 | 2024-03-18 | Milestone 1.2 - THP Air Compress System | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000371 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Air Compress System " | REJ
000372 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0030 | 0 | 131242-WST02-CD-IM-0030 | 2024-03-18 | Milestone 1.2 - THP Silo Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000372 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Silo Area " | REJ
000373 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0031 | 0 | 131242-WST02-CD-IM-0031 | 2024-03-18 | Milestone 1.2 - THP Trains | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000373 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Trains " | REJ
000374 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0032 | 0 | 131242-WST02-CD-IM-0032 | 2024-03-18 | Milestone 1.2 - THP Drainage | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000374 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Drainage " | REJ
000375 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0033 | 0 | 131242-WST02-CD-IM-0033 | 2024-03-18 | Milestone 1.2 - THP Building Service | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000375 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Building Service" | REJ
000376 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0034 | 0 | 131242-WST02-CD-IM-0034 | 2024-03-18 | Milestone 1.2 - THP MCC Room | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000376 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP MCC Room " | REJ
000377 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0010 | 0 | 131242-WSW41-RT-PM-0010 | 2024-03-18 | C4B Monthly Progress Report Number No.10 (02 24) | Rev. 0 - Approved with comments - need to re-submit (see attached comment sheet) | 2024-04-17 | 2024-04-01 | 10 | Approved with Comments | YES | 2024-04-19 | NO | Resubmitted | 0 |  |  | 000377 | 2024-03-18 | 2024-03-18 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.10 (02 24)" | AWC
000378 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 0 | 131242-WSD11-SP-I-0002 | 2024-03-19 | Plant Control Narrative | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-30 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP info | 000378 | 2024-03-19 | 2024-10-21 | 1 | AWC | Approved with Comments | 3 | "Plant Control Narrative" | AWC
000378 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 1 | 131242-WSD11-SP-I-0002 | 2024-10-21 | Plant Control Narrative | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000378 | 2024-03-19 | 2024-10-21 | 1 | AWC | Approved with Comments | 3 | "Plant Control Narrative" | AWC
000378 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 2 | 131242-WSD11-SP-I-0002 | 2024-10-21 | Plant Control Narrative | Rev 2: Approved. Please note: if there are any changes in controls, C4B will have to re-issue the document.” | 2024-11-11 | 2025-10-10 | 254 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000378 | 2024-03-19 | 2024-10-21 | 1 | APP | Approved with Comments | 3 | "Plant Control Narrative" | AWC
000379 | 00 | Boopathi | PMT | NA | 131242 | WSW41 | VI | C | 0014 | 0 | 131242-WSW41-VI-C-0014 | 2024-03-19 | Vendor Approval for Waterproof Additive Specialist (CementAID) | Approved. | 2024-04-18 | 2024-03-26 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000379 | 2024-03-19 | 2024-03-19 | 0 | APP | Approved | 1 | "Vendor Approval for Waterproof Additive Specialist (CementAID)" | APP
000380 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | AWC | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | AWC
000380 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 1 | 131242-WSW41-SP-C-0007 | 2024-06-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-06-28 | 6 | Approved with Comments | YES | 2024-07-18 | NO | Resubmitted | 29 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | AWC | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | AWC
000381 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0006 | 0 | 131242-WSW41-SP-C-0006 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | 4 | Approved with Comments | YES | 2024-04-15 | NO | Resubmitted | 0 |  |  | 000381 | 2024-03-20 | 2024-03-20 | 0 | AWC | Approved with Comments | 1 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance)" | AWC
000382 | 00 | Zora | CSA | NA | 131242 | WSW41 | CN | C | 0001 | 0 | 131242-WSW41-CN-C-0001 | 2024-03-20 | RFC For SSN Surface Drainage Layout | Approved | 2024-04-19 | 2024-08-29 | 116 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000382 | 2024-03-20 | 2024-03-20 | 0 | APP | Approved | 1 | "RFC For SSN Surface Drainage Layout" | APP
000383 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0025 | 0 | 131242-WSW41-LT-PM-0025 | 2024-03-20 | Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rejected | 2024-04-19 | 2024-06-21 | 67 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000383 | 2024-03-20 | 2024-03-20 | 0 | REJ | Rejected | 1 | "Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | REJ
000383 | 01 | Theint Theint | Contracts | NA | 131242 | WSW41 | LT | PM | 0033 | 0 | 131242-WSW41-LT-PM-0033 | 2024-06-22 | Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rev 1: Approved | 2024-07-11 | 2024-08-28 | 47 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000383 | 2024-06-22 | 2024-06-22 | 0 | APP | Approved | 1 | "Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | APP
000384 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 0 | 131242-WST02-CL-P-0003 | 2024-03-20 | SSN Process Design Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-19 | 2024-04-25 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP info | 000384 | 2024-03-20 | 2024-08-01 | 1 | AWC | Approved with Comments | 2 | "SSN Process Design Calculation" | AWC
000384 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 1 | 131242-WST02-CL-P-0003 | 2024-08-01 | SSN Process Design Calculation | Rev 1: Approved with Comments. Although there are no active comments the submittal is approved with comments to accommodate changes and resubmittal during the detail engineering. | 2024-08-22 | 2024-09-04 | 24 | Approved with Comments | YES | 2024-09-24 | NO | Resubmitted | 0 |  |  | 000384 | 2024-03-20 | 2024-08-01 | 1 | AWC | Approved with Comments | 2 | "SSN Process Design Calculation" | AWC
000385 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 0 | 131242-WST02-CH-P-0001 | 2024-03-20 | SSN Process Design Basis | R0: Not Approved. Please resubmit | 2024-04-19 | 2024-04-30 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | NAP | Approved with Comments | 4 | "SSN Process Design Basis" | AWC
000385 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 1 | 131242-WST02-CH-P-0001 | 2024-08-02 | SSN Process Design Basis | R1: Approved with comments. Address the comments and resubmit. | 2024-08-23 | 2024-09-04 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" | AWC
000385 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 2 | 131242-WST02-CH-P-0001 | 2024-11-04 | SSN Process Design Basis | R2: Approved with comments. Address the comments and resubmit. | 2024-11-22 | 2025-01-09 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 | comments received on 14 Feb | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" | AWC
000385 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 3 | 131242-WST02-CH-P-0001 | 2025-02-24 | SSN Process Design Basis | R3: Approved with comments. | 2025-03-14 | 2025-03-13 | 13 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 | 2025-02-19 |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" | AWC
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0001_ST617 | 0 | 131242-WSD11-CL-S-0001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST617 | A | 131242-WSW41-DR-S-1000_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1001_ST617 | A | 131242-WSW41-DR-S-1001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1002_ST617 | A | 131242-WSW41-DR-S-1002_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1003_ST617 | A | 131242-WSW41-DR-S-1003_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST617 | A | 131242-WSW41-DR-S-2001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST617 | A | 131242-WSW41-DR-S-2002_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2003_ST617 | A | 131242-WSW41-DR-S-2003_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF01 reaction table | 0 | 131242-WSD11-CL-NA-THP_PF01 reaction table | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF02_PR01 reaction table | 0 | 131242-WSD11-CL-NA-THP_PF02_PR01 reaction table | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | NAP
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | A | 131242-WSD11-DR-S-1004_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-07-04 | 2024-10-11 | B | NAP | Approved with Comments | 2 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | B | 131242-WSD11-DR-S-0300_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | B | 131242-WSD11-DR-S-0301_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | B | 131242-WSD11-DR-S-1000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | B | 131242-WSD11-DR-S-1001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | B | 131242-WSD11-DR-S-1002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | B | 131242-WSD11-DR-S-1003_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | B | 131242-WSD11-DR-S-1004_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386 | 2024-07-04 | 2024-10-11 | B | AWC | Approved with Comments | 2 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | B | 131242-WSD11-DR-S-2000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | B | 131242-WSD11-DR-S-2001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | B | 131242-WSD11-DR-S-3000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | B | 131242-WSD11-DR-S-3001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | B | 131242-WSD11-DR-S-3002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | B | 131242-WSD11-DR-S-5000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | B | 131242-WSD11-DR-S-5001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | B | 131242-WSD11-DR-S-5002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | B | 131242-WSD11-DR-S-5003_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | B | 131242-WSD11-DR-S-5004_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | B | 131242-WSD11-DR-S-5005_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | B | 131242-WSD11-DR-S-5006_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | B | 131242-WSD11-DR-S-8000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000387 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0010 | 0 | 131242-WSW41-PS-PM-0010 | 2024-03-22 | Monthly Progress Presentation No. 10 (0224) | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000387 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 10 (0224)" | INF
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0019 | 0 | 131242-WSW41-MI-C-0019 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | INF
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0020 | 0 | 131242-WSW41-MI-C-0020 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | INF
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0021 | 0 | 131242-WSW41-MI-C-0021 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | INF
000389 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0009 | 0 | 131242-WSW41-PC-W-0009 | 2024-03-23 | Payment Claim No.9 | Rev(0): Approved. Refer to S.O. correspondence no. 137 dated 27 Mar 2024. | 2024-04-23 | 2024-05-10 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000389 | 2024-03-23 | 2024-03-23 | 0 | APP | Approved | 1 | "Payment Claim No.9" | APP
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A | 131242-WSD11-DR-I-1000 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 | 2024-07-16 |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A | 131242-WSD11-DR-I-1001 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A | 131242-WSD11-DR-I-1002 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A | 131242-WSD11-DR-I-1003 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A | 131242-WSD11-DR-I-3000 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A | 131242-WSD11-DR-I-3001 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A | 131242-WSD11-DR-I-3002 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A.1 | 131242-WSD11-DR-I-1000 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-16 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A.1 | 131242-WSD11-DR-I-1001 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A.1 | 131242-WSD11-DR-I-1002 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A.1 | 131242-WSD11-DR-I-1003 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A.1 | 131242-WSD11-DR-I-3000 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A.1 | 131242-WSD11-DR-I-3001 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A.1 | 131242-WSD11-DR-I-3002 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | INF
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | 0 | 131242-WSD11-DR-M-1170 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  | Submitted as S000681.1 | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | 0 | 131242-WSD11-DR-M-1171 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | 0 | 131242-WSD11-DR-M-1172 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | 0 | 131242-WSD11-DR-M-3170 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | 0 | 131242-WSD11-DR-M-3171 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7308 | A | 131242-WSD11-DR-I-7308 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7309 | A | 131242-WSD11-DR-I-7309 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7310 | A | 131242-WSD11-DR-I-7310 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7311 | A | 131242-WSD11-DR-I-7311 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7312 | A | 131242-WSD11-DR-I-7312 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7313 | A | 131242-WSD11-DR-I-7313 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7314 | A | 131242-WSD11-DR-I-7314 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7315 | A | 131242-WSD11-DR-I-7315 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7316 | A | 131242-WSD11-DR-I-7316 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7317 | A | 131242-WSD11-DR-I-7317 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7318 | A | 131242-WSD11-DR-I-7318 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7319 | A | 131242-WSD11-DR-I-7319 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7320 | A | 131242-WSD11-DR-I-7320 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7321 | A | 131242-WSD11-DR-I-7321 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | B | 131242-WSD11-DR-I-7307 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | NAP | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | B | 131242-WSD11-DR-I-7308 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | B | 131242-WSD11-DR-I-7309 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | B | 131242-WSD11-DR-I-7310 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | B | 131242-WSD11-DR-I-7311 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | B | 131242-WSD11-DR-I-7312 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | B | 131242-WSD11-DR-I-7313 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | B | 131242-WSD11-DR-I-7314 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | B | 131242-WSD11-DR-I-7315 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | B | 131242-WSD11-DR-I-7316 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | B | 131242-WSD11-DR-I-7317 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | B | 131242-WSD11-DR-I-7318 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | B | 131242-WSD11-DR-I-7319 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | B | 131242-WSD11-DR-I-7320 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | B | 131242-WSD11-DR-I-7321 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | C | 131242-WSD11-DR-I-7306 | 2024-11-19 | Compressor Sequencer Panel | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-09 | 2024-12-18 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | NAP | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | D | 131242-WSD11-DR-I-7306 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7307 | D | 131242-WSD11-DR-I-7307 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7308 | D | 131242-WSD11-DR-I-7308 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7309 | D | 131242-WSD11-DR-I-7309 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7310 | D | 131242-WSD11-DR-I-7310 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7311 | D | 131242-WSD11-DR-I-7311 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7312 | D | 131242-WSD11-DR-I-7312 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7313 | D | 131242-WSD11-DR-I-7313 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7314 | D | 131242-WSD11-DR-I-7314 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7315 | D | 131242-WSD11-DR-I-7315 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7316 | D | 131242-WSD11-DR-I-7316 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7317 | D | 131242-WSD11-DR-I-7317 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7318 | D | 131242-WSD11-DR-I-7318 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7319 | D | 131242-WSD11-DR-I-7319 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7320 | D | 131242-WSD11-DR-I-7320 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7321 | D | 131242-WSD11-DR-I-7321 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7322 | D | 131242-WSD11-DR-I-7322 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7323 | D | 131242-WSD11-DR-I-7323 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7324 | D | 131242-WSD11-DR-I-7324 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7325 | D | 131242-WSD11-DR-I-7325 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7326 | D | 131242-WSD11-DR-I-7326 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7327 | D | 131242-WSD11-DR-I-7327 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7328 | D | 131242-WSD11-DR-I-7328 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7306 | E | 131242-WSD11-DR-I-7306 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | E | 131242-WSD11-DR-I-7307 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | E | 131242-WSD11-DR-I-7308 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | E | 131242-WSD11-DR-I-7309 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | E | 131242-WSD11-DR-I-7310 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | E | 131242-WSD11-DR-I-7311 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | E | 131242-WSD11-DR-I-7312 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | E | 131242-WSD11-DR-I-7313 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | E | 131242-WSD11-DR-I-7314 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | E | 131242-WSD11-DR-I-7315 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | E | 131242-WSD11-DR-I-7316 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | E | 131242-WSD11-DR-I-7317 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | E | 131242-WSD11-DR-I-7318 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | E | 131242-WSD11-DR-I-7319 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | E | 131242-WSD11-DR-I-7320 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | E | 131242-WSD11-DR-I-7321 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7322 | E | 131242-WSD11-DR-I-7322 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7323 | E | 131242-WSD11-DR-I-7323 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7324 | E | 131242-WSD11-DR-I-7324 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7325 | E | 131242-WSD11-DR-I-7325 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7326 | E | 131242-WSD11-DR-I-7326 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7327 | E | 131242-WSD11-DR-I-7327 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7328 | E | 131242-WSD11-DR-I-7328 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" | AWC
000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700 | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" | AWC
000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701 | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" | AWC
000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700 | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 | TBA | To check with Yibo and will advise later the submission date. | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" | AWC
000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701 | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 | TBA | To check with Yibo and will advise later the submission date. | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" | AWC
000395 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | A | 131242-WSD11-DR-E-3160 | 2024-03-25 | Air Compressor Motor Outline Drawing | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached files for comments. | 2024-04-24 | 2024-05-16 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 |  | 000395 | 2024-03-25 | 2024-08-16 | B | AWC | Approved | 2 | "Air Compressor Motor Outline Drawing " | APP
000395 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | B | 131242-WSD11-DR-E-3160 | 2024-08-16 | Air Compressor Motor Outline Drawing | Rev 1: Approved. | 2024-09-05 | 2024-11-04 | 56 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000395 | 2024-03-25 | 2024-08-16 | B | APP | Approved | 2 | "Air Compressor Motor Outline Drawing " | APP
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2024-10-30 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A | 131242-WST02-DR-A-2000_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.1 | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.1 | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.1 | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A.1 | 131242-WST02-DR-A-1006_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.1 | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.1 | 131242-WST02-DR-A-2000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.1 | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.1 | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.1 | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A | 131242-WST02-DR-A-3000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A.2 | NAP | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_LTA_NPKS | A | 131242-WST02-DR-A-5004_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2024-10-30 | A | NAP | Not Approved | 1 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2024-10-30 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0002_LTA_NPKS | B | 131242-WST02-DR-A-0002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "LTA & Nparks submission Set" | NAP
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  | Rejected as CES requested as drawings need to be included PE endorsement | 000396 | 2024-03-25 | 2026-01-09 | A.2 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | REJ | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | REJ | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.2 | 131242-WST02-DR-A-1000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.4 | 131242-WST02-DR-A-1001_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.4 | 131242-WST02-DR-A-1002_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.4 | 131242-WST02-DR-A-1003_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.4 | 131242-WST02-DR-A-1004_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_LTA_NPKS | A | 131242-WST02-DR-A-1005_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2026-01-09 | 2026-01-09 | A | PEN | Awaiting S.O.'s response | 1 | "LTA & Nparks submission Set" | PEN
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A | 131242-WST02-DR-A-1006_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A | PEN | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.4 | 131242-WST02-DR-A-1009_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.4 | 131242-WST02-DR-A-2000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | PEN | Rejected | 7 | "LTA & Nparks submission Set" | REJ
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.4 | 131242-WST02-DR-A-2001_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.4 | 131242-WST02-DR-A-2002_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.4 | 131242-WST02-DR-A-2003_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A.4 | 131242-WST02-DR-A-2007_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" | NAP
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A.2 | 131242-WST02-DR-A-3000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A.2 | PEN | Not Approved | 2 | "LTA & Nparks submission Set" | NAP
000397 | 00 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0000_NEA | A | 131242-WST02-DR-A-0000_NEA | 2024-03-25 | NEA DC submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-03-25 | 2024-03-25 | A | NAP | Not Approved | 1 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.1 | 131242-WST02-DR-A-1001_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.1 | 131242-WST02-DR-A-1002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.1 | 131242-WST02-DR-A-1003_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.1 | 131242-WST02-DR-A-1004_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A.1 | 131242-WST02-DR-A-1006_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.1 | 131242-WST02-DR-A-1009_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.1 | 131242-WST02-DR-A-2000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 3 | "NEA DC submission Set " | REJ
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.1 | 131242-WST02-DR-A-2001_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.1 | 131242-WST02-DR-A-2002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.1 | 131242-WST02-DR-A-2003_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A | 131242-WST02-DR-A-2007_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A | 131242-WST02-DR-A-3000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_NEA | A | 131242-WST02-DR-A-5004_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2024-10-30 | A | NAP | Not Approved | 1 | "NEA DC submission Set " | NAP
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_NEA | B | 131242-WST02-DR-A-0002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "NEA DC submission Set " | NAP
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  | Rejected as CES requested as drawings need to be included PE endorsement | 000397 | 2024-10-30 | 2026-01-06 | A.2 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.3 | 131242-WST02-DR-A-1002_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.3 | 131242-WST02-DR-A-1003_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.3 | 131242-WST02-DR-A-1004_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.3 | 131242-WST02-DR-A-1009_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.2 | 131242-WST02-DR-A-2000_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 3 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.2 | 131242-WST02-DR-A-1000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.4 | 131242-WST02-DR-A-1001_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.4 | 131242-WST02-DR-A-1002_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.4 | 131242-WST02-DR-A-1003_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.4 | 131242-WST02-DR-A-1004_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_NEA | A | 131242-WST02-DR-A-1005_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2026-01-06 | 2026-01-06 | A | PEN | Awaiting S.O.'s response | 1 | "NEA DC submission Set " | PEN
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A | 131242-WST02-DR-A-1006_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.4 | 131242-WST02-DR-A-1009_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.4 | 131242-WST02-DR-A-2000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 3 | "NEA DC submission Set " | REJ
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.4 | 131242-WST02-DR-A-2001_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.4 | 131242-WST02-DR-A-2002_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.4 | 131242-WST02-DR-A-2003_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A.4 | 131242-WST02-DR-A-2007_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A.2 | 131242-WST02-DR-A-3000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | PEN | Not Approved | 2 | "NEA DC submission Set " | NAP
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6000 | A | 131242-WST02-DR-P-6000 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | A | 131242-WST02-DR-P-6001 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | A | 131242-WST02-DR-P-6002 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | A | 131242-WST02-DR-P-6003 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | A | 131242-WST02-DR-P-6004 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | A | 131242-WST02-DR-P-6005 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | A | 131242-WST02-DR-P-6006 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | A | 131242-WST02-DR-P-6007 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | A | 131242-WST02-DR-P-6008 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | A | 131242-WST02-DR-P-6009 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | A | 131242-WST02-DR-P-6010 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | A | 131242-WST02-DR-P-6011 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | A | 131242-WST02-DR-P-6012 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | A | 131242-WST02-DR-P-6013 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | A | 131242-WST02-DR-P-6014 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000398 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#398 CES Reply | NA | 131242-WST02-NA-P-S#398 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev 1: the submittal is closed as per the request of C4B contractor and merged to SRC 731 | 2024-10-21 | 2024-10-24 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398 | 2024-10-01 | 2024-10-01 | NA | AWC | Approved with Comments | 1 | "P&ID for SSN Process" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | A | 131242-WST02-DR-P-6015 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | A | 131242-WST02-DR-P-6016 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | A | 131242-WST02-DR-P-6017 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | A | 131242-WST02-DR-P-6018 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | A | 131242-WST02-DR-P-6019 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | A | 131242-WST02-DR-P-6020 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000399 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | NA | NA | S#399 CES Reply | NA | 131242-WSD11-NA-NA-S#399 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev1: The submittal is merged with SRC 731. | 2024-10-21 | 2024-11-07 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399 | 2024-10-01 | 2024-10-01 | NA | AWC | Approved with Comments | 1 | "P&ID for SSN Process" | AWC
000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | A | 131242-WST02-DR-P-6200 | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | A | 131242-WST02-DR-P-6600 | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000400 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#400 CES Reply | NA | 131242-WST02-NA-P-S#400 CES Reply | 2024-10-01 | P&ID for SSN Plant Water and Instrument Air | Rev 1: The submittal is closed and merged with SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000400 | 2024-10-01 | 2024-10-01 | NA | APP | Approved | 1 | "P&ID for SSN Plant Water and Instrument Air" | APP
000401 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7000 | A | 131242-WST02-DR-I-7000 | 2024-03-26 | SSN Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-25 | 2024-04-30 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000401 | 2024-03-26 | 2024-08-26 | B | NAP | Approved with Comments | 2 | "SSN Control System Architecture Drawing" | AWC
000401 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7000 | B | 131242-WST02-DR-I-7000 | 2024-08-26 | SSN Control System Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-13 | 2024-10-16 | 37 | Approved with Comments | YES | 2024-11-05 | NO | Resubmitted | 0 |  |  | 000401 | 2024-03-26 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "SSN Control System Architecture Drawing" | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-10 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A | 131242-WST02-DR-A-2000_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.1 | 131242-WST02-DR-A-1001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.1 | 131242-WST02-DR-A-1003_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.1 | 131242-WST02-DR-A-1009_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.1 | 131242-WST02-DR-A-2000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.1 | 131242-WST02-DR-A-2002_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.1 | 131242-WST02-DR-A-2003_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_FSSD_BP | A | 131242-WST02-DR-A-5004_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2024-10-16 | A | NAP | Not Approved | 1 | "SSN_FSSD (BP) Submission " | NAP
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | CL | A | 0001_FSSD_BP | A | 131242-WST02-CL-A-0001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2024-10-16 | A | NAP | Not Approved | 1 | "SSN_FSSD (BP) Submission " | NAP
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.2 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.2 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.3 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.3 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.3 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.3 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.3 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.3 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | B | 131242-WST02-DR-A-3000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.2 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.3 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | NAP | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.4 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | AWC | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | AWC | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | AWC | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | AWC | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | AWC | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | PEN | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | PEN | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | PEN | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | PEN | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " | AWC
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | PEN | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " | AWC
000403 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SP | P | 0001 | 0 | 131242-WST02-SP-P-0001 | 2024-03-27 | SSN Control Philosophy | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-26 | 2024-05-23 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP resubmission | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" | AWC
000403 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 1 | 131242-WST02-SP-P-0001 | 2024-08-12 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-03 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" | AWC
000403 | 02 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 2 | 131242-WST02-SP-P-0001 | 2024-10-03 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-11-07 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" | AWC
000403 | 03 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 3 | 131242-WST02-SP-P-0001 | 2025-03-14 | SSN Control Philosophy | Approved with Comments | 2025-04-03 | 2025-05-15 | 44 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" | AWC
000404 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0004 | 0 | 131242-WST02-CL-P-0004 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | AWC | Approved | 3 | "SSN Chemical Consumption Calculation" | APP
000404 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 1 | 131242-WST02-CL-P-0004 | 2024-07-28 | SSN Chemical Consumption Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | AWC | Approved | 3 | "SSN Chemical Consumption Calculation" | APP
000404 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 2 | 131242-WST02-CL-P-0004 | 2024-10-16 | SSN Chemical Consumption Calculation | Rev 2: Approved | 2024-11-06 | 2024-11-15 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | APP | Approved | 3 | "SSN Chemical Consumption Calculation" | APP
000405 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0002 | 0 | 131242-WSD11-RT-P-0002 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-30 | 45 | Approved with Comments | YES | 2024-06-19 | NO | Resubmitted | 0 |  | After addressing BODR | 000405 | 2024-03-28 | 2024-03-28 | 0 | AWC | Approved with Comments | 1 | "SSN Chemical Consumption Calculation" | AWC
000406 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 0 | 131242-WST02-CL-E-0005 | 2024-03-28 | SSN 22kV MV Power Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | NAP | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" | APP
000406 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 1 | 131242-WST02-CL-E-0005 | 2024-07-06 | SSN 22kV MV Power Cable Sizing Calculations | Rev 1: Approved with comments. To revise and resubmit. | 2024-07-25 | 2024-07-22 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | AWC | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" | APP
000406 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 2 | 131242-WST02-CL-E-0005 | 2025-02-19 | SSN 22kV MV Power Cable Sizing Calculations | Rev 2: Approved. | 2025-03-11 | 2025-05-06 | 54 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | APP | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" | APP
000407 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | P | 0001 | 0 | 131242-WST02-RT-P-0001 | 2024-03-28 | Basic Design Report of SSN Package | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-05-03 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000407 | 2024-03-28 | 2024-11-18 | 2 | NAP | Approved with Comments | 3 | "Basic Design Report of SSN Package" | AWC
000407 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 1 | 131242-WST02-RT-P-0001 | 2024-05-23 | Basic Design Report of SSN Package | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-12 | 2024-07-04 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To follow up with MP for resubmission | 000407 | 2024-03-28 | 2024-11-18 | 2 | AWC | Approved with Comments | 3 | "Basic Design Report of SSN Package" | AWC
000407 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 2 | 131242-WST02-RT-P-0001 | 2024-11-18 | Basic Design Report of SSN Package | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-06 | 2025-01-08 | 37 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 | 2025-03-31 | comments received on 14 Feb | 000407 | 2024-03-28 | 2024-11-18 | 2 | AWC | Approved with Comments | 3 | "Basic Design Report of SSN Package" | AWC
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0015 | 1 | 131242-WST02-DS-M-0015 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | 0 | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0016 | A | 131242-WST02-DR-M-0016 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0015 | A | 131242-WST02-DR-M-0015 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0015 | 0 | 131242-WST02-DS-M-0015 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000408 | 2024-03-28 | 2024-07-05 | 0 | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0016 | B | 131242-WST02-DR-M-0016 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0015 | B | 131242-WST02-DR-M-0015 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000408 | 01 | Qili | Process | NA | 131242 | WST02 | CL | M | 0001 | 0 | 131242-WST02-CL-M-0001 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-07-05 | 2024-07-05 | 0 | AWC | Approved with Comments | 1 | "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | AWC
000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0016 | 0 | 131242-WST02-DS-M-0016 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | 2 | NAP | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0017 | 0 | 131242-WST02-DR-M-0017 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | NAP | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 1 | 131242-WST02-DS-M-0016 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000409 | 2024-03-28 | 2025-03-14 | 2 | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-07-05 | 2025-03-14 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 2 | 131242-WST02-DS-M-0016 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | 2 | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-07-05 | 2025-03-14 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Biomass Separator " | AWC
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A | 131242-WST02-DR-S-1003_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide Native DGN sets | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A | 131242-WST02-DR-S-7001_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A | 131242-WST02-DR-S-8001_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST609 | A | 131242-WST02-DR-S-1001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 | 2024-07-26 | Tenwit in Progress | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2001_ST609 | A | 131242-WST02-DR-S-2001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 | Tenwit in Progress |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3001_ST609 | A | 131242-WST02-DR-S-3001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST609 | A | 131242-WST02-DR-S-1002_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST609 | A | 131242-WST02-DR-S-1000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2000_ST609 | A | 131242-WST02-DR-S-2000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST609 | A | 131242-WST02-DR-S-3000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide Native DGN sets and Aaron to address the comments | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_NOA | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_NOA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000412 | 2024-04-02 | 2024-04-02 | C | NAP | Not Approved | 1 | "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_Fdn Advice Letter | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_Fdn Advice Letter | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000412 | 2024-04-02 | 2024-04-02 | C | NAP | Not Approved | 1 | "ST615 BCA Approved Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-04 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng: BIM Pending to clear BIM comments | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " | NAP
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1000 | C01 | 131242-WSD11-DR-M-1000 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  | Pending DGN dwg drawing and CAMBI updates and to update Tagging | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" | AWC
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1001 | C01 | 131242-WSD11-DR-M-1001 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" | AWC
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1002 | C01 | 131242-WSD11-DR-M-1002 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" | AWC
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1003 | C01 | 131242-WSD11-DR-M-1003 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" | AWC
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1004 | C01 | 131242-WSD11-DR-M-1004 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" | AWC
000415 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0006 | 0 | 131242-WST02-CL-P-0006 | 2024-04-03 | SSN Equipment Sizing Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-05-23 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-04-03 | 2024-08-12 | 1 | AWC | Approved with Comments | 2 | "SSN Equipment Sizing Calculation" | AWC
000415 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0006 | 1 | 131242-WST02-CL-P-0006 | 2024-08-12 | SSN Equipment Sizing Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-11 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-04-03 | 2024-08-12 | 1 | AWC | Approved with Comments | 2 | "SSN Equipment Sizing Calculation" | AWC
000415 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | Comment Reply Sheet 20241118 S415.1 | NA | 131242-WST02-CL-P-Comment Reply Sheet 20241118 S415.1 | 2024-11-18 | SSN Equipment Sizing Calculation | Rev 2: Approved with Comments. The submittal is requested to be discontinued by CES. | 2024-12-06 | 2025-01-08 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-11-18 | 2024-11-18 | NA | AWC | Approved with Comments | 1 | "SSN Equipment Sizing Calculation" | AWC
000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0005 | 0 | 131242-WST02-CL-P-0005 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | 2 | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7010 | 0 | 131242-WST02-DR-P-7010 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000416 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 1 | 131242-WST02-CL-P-0005 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | Pending MP updates, Need PE endosement | 000416 | 2024-04-03 | 2025-03-24 | 2 | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000416 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | B | 131242-WST02-DR-P-7010 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000416 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 2 | 131242-WST02-CL-P-0005 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | 140 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | 2 | APP | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000416 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | C | 131242-WST02-DR-P-7010 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | 140 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | APP | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" | APP
000417 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 0 | 131242-WSD11-VI-I-0002 | 2024-04-04 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-04-18 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000417 | 2024-04-04 | 2024-08-15 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | AWC
000417 | 01 | Karthik/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 1 | 131242-WSD11-VI-I-0002 | 2024-08-15 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-04 | 2024-11-08 | 61 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000417 | 2024-04-04 | 2024-08-15 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1003 | A | 131242-WST02-DR-B-1003 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1004 | A | 131242-WST02-DR-B-1004 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1005 | A | 131242-WST02-DR-B-1005 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1006 | A | 131242-WST02-DR-B-1006 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1007 | A | 131242-WST02-DR-B-1007 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7001 | A | 131242-WST02-DR-B-7001 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7002 | A | 131242-WST02-DR-B-7002 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7003 | A | 131242-WST02-DR-B-7003 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1003 | B | 131242-WST02-DR-B-1003 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1004 | B | 131242-WST02-DR-B-1004 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1005 | B | 131242-WST02-DR-B-1005 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1006 | B | 131242-WST02-DR-B-1006 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1007 | B | 131242-WST02-DR-B-1007 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7001 | B | 131242-WST02-DR-B-7001 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7002 | B | 131242-WST02-DR-B-7002 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7003 | B | 131242-WST02-DR-B-7003 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | AWC
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1011 | A | 131242-WST02-DR-BF-1011 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1012 | A | 131242-WST02-DR-BF-1012 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1013 | A | 131242-WST02-DR-BF-1013 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | NAP | Approved with Comments | 2 | "SSN Public Address System" | AWC
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 7103 | A | 131242-WST02-DR-BF-7103 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | NAP | Approved with Comments | 2 | "SSN Public Address System" | AWC
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1011 | B | 131242-WST02-DR-BF-1011 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1012 | B | 131242-WST02-DR-BF-1012 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | AWC
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1013 | B | 131242-WST02-DR-BF-1013 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | AWC | Approved with Comments | 2 | "SSN Public Address System" | AWC
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 7103 | B | 131242-WST02-DR-BF-7103 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | AWC | Approved with Comments | 2 | "SSN Public Address System" | AWC
000420 | 00 | Suresh | PCM | NA | 131242 | WSW41 | MI | PM | 0010 | 0 | 131242-WSW41-MI-PM-0010 | 2024-04-04 | Monthly Progress Meeting Minutes 0010_20240319 | For Information | 2024-05-06 | 2024-04-05 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000420 | 2024-04-04 | 2024-04-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0010_20240319" | INF
000421 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 0 | 131242-WSD11-DS-M-0013 | 2024-04-05 | Data Sheet and Drawing of THP Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | APP
000421 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 1 | 131242-WSD11-DS-M-0013 | 2024-08-12 | Data Sheet of THP Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | APP
000421 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 2 | 131242-WSD11-DS-M-0013 | 2025-01-26 | Data Sheet of THP Feed Pump | Rev 2: Approved | 2025-02-13 | 2025-04-27 | 65 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | APP | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | APP
000422 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 0 | 131242-WSD11-DS-M-0014 | 2024-04-06 | Data Sheet and Drawing of Reactor Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" | APP
000422 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 1 | 131242-WSD11-DS-M-0014 | 2024-08-12 | Data Sheet and Drawing of Reactor Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" | APP
000422 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 2 | 131242-WSD11-DS-M-0014 | 2025-04-10 | Data Sheet and Drawing of Reactor Feed Pump | Rev 2: Approved | 2025-04-30 | 2025-10-06 | 127 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | APP | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" | APP
000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0001 | A | 131242-WSD11-DR-S-0001 | 2024-04-06 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423 | 2024-04-06 | 2024-04-06 | A | NAP | Not Approved | 1 | "Compressed Air System - Anchor Bolts Details & Plinth Details" | NAP
000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 0 | 131242-WSD11-CL-S-0004 | 2024-04-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423 | 2024-04-05 | 2024-06-05 | 1 | NAP | Not Approved | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" | NAP
000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301 | A | 131242-WSD11-DR-S-5301 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-06-26 | 2024-06-19 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423&&000536 | 2024-06-05 | 2024-06-26 | B | APP | Approved with Comments | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | AWC
000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 1 | 131242-WSD11-CL-S-0004 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-07-04 | 2024-06-19 | 10 | Awaiting S.O.'s response | YES | 2024-07-09 | NO | Resubmitted | 0 |  |  | 000423 | 2024-04-05 | 2024-06-05 | 1 | PEN | Not Approved | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" | NAP
000424 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0037 | 0 | 131242-WSW41-CD-IM-0037 | 2024-04-08 | Submission Of BIM Coordination VCM Model (Mar-2024) | For Information | 2024-05-08 | 2024-04-19 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000424 | 2024-04-08 | 2024-04-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Mar-2024)" | INF
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 | 131242-WST02-DR-S-A1798-00002-2018_NOA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A.1 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide Native DGN sets and Aaron to address the comments | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 | 131242-WST02-DR-S-A1798-00002-2018_NOA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A.1 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " | NAP
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A2 | 131242-WST02-DR-S-1003_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A2 | 131242-WST02-DR-S-7001_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A2 | 131242-WST02-DR-S-8001_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A.2 | 131242-WST02-DR-S-1003_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-17 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A.2 | 131242-WST02-DR-S-7001_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A.2 | 131242-WST02-DR-S-8001_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | INF
000427 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 0 | 131242-WSW41-CL-S-0004 | 2024-04-08 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-22 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000427 | 2024-04-08 | 2024-04-23 | 1 | NAP | Approved | 2 | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | APP
000427 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 1 | 131242-WSW41-CL-S-0004 | 2024-04-23 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.1: Approved | 2024-05-14 | 2024-05-02 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000427 | 2024-04-08 | 2024-04-23 | 1 | APP | Approved | 2 | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | APP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608 | 0 | 131242-WST02-CL-S-0002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | 0 | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1005_ST608 | A | 131242-WST02-DR-S-1005_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST608 | A | 131242-WST02-DR-S-1001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST608 | A | 131242-WST02-DR-S-1002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2000_ST608 | A | 131242-WST02-DR-S-2000_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST608 | A | 131242-WST02-DR-S-3000_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST608 | A | 131242-WST02-DR-S-1003_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2001_ST608 | A | 131242-WST02-DR-S-2001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST608 | A | 131242-WST02-DR-S-3001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST608 | A | 131242-WST02-DR-S-1004_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2002_ST608 | A | 131242-WST02-DR-S-2002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608 | B | 131242-WST00-DR-S-8005_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-10 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608 | B | 131242-WST02-DR-S-0302_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608 | B | 131242-WST02-DR-S-1200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608 | B | 131242-WST02-DR-S-1201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608 | B | 131242-WST02-DR-S-1202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608 | B | 131242-WST02-DR-S-1203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608 | B | 131242-WST02-DR-S-1204_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608 | B | 131242-WST02-DR-S-1205_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608 | B | 131242-WST02-DR-S-2200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608 | B | 131242-WST02-DR-S-2201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608 | B | 131242-WST02-DR-S-2202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608 | B | 131242-WST02-DR-S-2203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608 | B | 131242-WST02-DR-S-3200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608 | B | 131242-WST02-DR-S-3201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608 | B | 131242-WST02-DR-S-3202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608 | B | 131242-WST02-DR-S-5200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608 | B | 131242-WST02-DR-S-5201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608 | B | 131242-WST02-DR-S-5202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608 | B | 131242-WST02-DR-S-5203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608 | B | 131242-WST02-DR-S-5204_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608 | B | 131242-WST02-DR-S-5205_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608 | B | 131242-WST02-DR-S-5206_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608 | B | 131242-WST02-DR-S-5207_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608 | B | 131242-WST02-DR-S-5208_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608 | B | 131242-WST02-DR-S-5209_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000428 | 02 | Aaron | CSA | NA | 131242 | WST02 | NA | C | NA | CES REPLY SHEET S428 | 131242-WST02-NA-C-NA | 2024-10-22 | ST608 – SSN Shelters Details | Rev.2: Not Approved. No updated drawings were submitted. | 2024-11-12 | 2024-12-18 | 41 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000428 | 2024-10-22 | 2024-10-22 | CES REPLY SHEET S428 | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" | NAP
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A | 131242-WST02-DR-M-1022 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1023 | A | 131242-WST02-DR-M-1023 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | AWC
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | AWC
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1026 | A | 131242-WST02-DR-M-1026 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1027 | A | 131242-WST02-DR-M-1027 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A.1 | 131242-WST02-DR-M-1022 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-02-26 | Shall update and submit under as built drawing | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | AWC
000430 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 0 | 131242-WSW41-SH-M-1002 | 2024-04-11 | Piping Special Item List | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-06-13 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000430 | 2024-04-11 | 2024-08-01 | 1 | INF | For Information | 2 | "Piping Special Item List" | INF
000430 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 1 | 131242-WSW41-SH-M-1002 | 2024-08-01 | Piping Special Item List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-08-22 | 2024-09-02 | 22 | For Information | NO |  | YES | Resubmitted | 0 | 2025-03-31 | Piping Special Item List is "For Information", will update after design is freezed. | 000430 | 2024-04-11 | 2024-08-01 | 1 | INF | For Information | 2 | "Piping Special Item List" | INF
000431 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0028 | 0 | 131242-WSW41-LT-PM-0028 | 2024-04-12 | CV OF TEAM MEMBER (WSHO) | Not Approved. The proposed candidate doesn’t fully meet the requirement of 5 years’ experience as WSHO. Therefore, proposed candidate is disapproved. | 2024-05-13 | 2024-06-06 | 39 | Not Approved | YES | 2024-06-26 | NO | Resubmitted | 0 |  |  | 000431 | 2024-04-12 | 2024-04-12 | 0 | NAP | Not Approved | 1 | "CV OF TEAM MEMBER (WSHO)" | NAP
000432 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0002 | 0 | 131242-WSD11-BQ-P-0002 | 2024-04-12 | THP Valve List | Rev 0: For Information | 2024-05-13 | 2024-07-26 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000432 | 2024-04-12 | 2024-04-12 | 0 | INF | For Information | 1 | "THP Valve List" | INF
000433 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | 14 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | NAP | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | AWC
000434 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0008 | 0 | 131242-WSW41-SP-C-0008 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | 14 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000434 | 2024-04-12 | 2024-04-12 | 0 | NAP | Not Approved | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024" | NAP
000435 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0026 | 0 | 131242-WSW41-LT-PM-0026 | 2024-04-13 | Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project) | For Information | 2024-05-13 | 2024-05-10 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000435 | 2024-04-13 | 2024-04-13 | 0 | INF | For Information | 1 | "Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project)" | INF
000436 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 0 | 131242-WST02-VI-I-0008 | 2024-04-15 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-14 | 2024-05-23 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000436 | 2024-04-15 | 2024-11-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (TSS Analyser - Optical)" | AWC
000436 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 1 | 131242-WST02-VI-I-0008 | 2024-11-28 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 1: Approved with comments. No need resubmission. Refer attached file for comments. | 2024-12-18 | 2025-03-25 | 83 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000436 | 2024-04-15 | 2024-11-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (TSS Analyser - Optical)" | AWC
000437 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | A.1 | 131242-WSW41-RT-PM-0011 | 2024-04-16 | C4B Monthly Progress Report Number No.11 (03 24) | Rejected as per CES request | 2024-05-15 | 2024-04-17 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | REJ | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" | APP
000437 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 0 | 131242-WSW41-RT-PM-0011 | 2024-04-18 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-05-09 | 2024-05-13 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | AWC | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" | APP
000437 | 02 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 1 | 131242-WSW41-RT-PM-0011 | 2024-06-11 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 2 - Approved | 2024-07-02 | 2024-06-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | APP | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" | APP
000438 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 0 | 131242-WST02-VI-I-0007 | 2024-04-16 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-05-23 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | AWC
000438 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 1 | 131242-WST02-VI-I-0007 | 2024-07-28 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-16 | 2024-09-18 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | AWC
000438 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 2 | 131242-WST02-VI-I-0007 | 2024-10-18 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | AWC
000438 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 3 | 131242-WST02-VI-I-0007 | 2025-02-27 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 48 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | AWC
000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | A | 131242-WST02-DR-E-3150 | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | NAP | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | A | 131242-WST02-DR-E-3151 | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | NAP | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | C | 131242-WST02-DR-E-3150 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | B | 131242-WST02-DR-E-3151 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | C | 131242-WST02-DR-E-3153 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | C | 131242-WST02-DR-E-3154 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | C | 131242-WST02-DR-E-3155 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | B | 131242-WST02-DR-E-3156 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | C | 131242-WST02-DR-E-3158 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | C | 131242-WST02-DR-E-3159 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | C | 131242-WST02-DR-E-7010 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | AWC
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | C | 131242-WST02-DR-E-7011 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | D | 131242-WST02-DR-E-3150 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | D | 131242-WST02-DR-E-3154 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | D | 131242-WST02-DR-E-3155 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | D | 131242-WST02-DR-E-3159 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | E | 131242-WST02-DR-E-7010 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | AWC
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | E | 131242-WST02-DR-E-7011 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | E | 131242-WST02-DR-E-3150 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | E | 131242-WST02-DR-E-3154 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | E | 131242-WST02-DR-E-3155 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | E | 131242-WST02-DR-E-3159 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | F | 131242-WST02-DR-E-7010 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | AWC
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | F | 131242-WST02-DR-E-7011 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" | AWC
000440 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | 0 | 131242-WST02-DR-E-7010 | 2024-04-16 | SSN Transformer Marshalling Box Schematic Wiring Diagram | Rev 0: Rejected. Not required to resubmit. Please refer to attached comments sheet. | 2024-05-15 | 2024-05-20 | 24 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | REJ | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | AWC
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7005 | A | 131242-WST02-DR-I-7005 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-04-16 | A | NAP | Not Approved | 1 | "SSN sample AC/DC/IO circuit diagram" | NAP
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7006 | A | 131242-WST02-DR-I-7006 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-04-16 | A | NAP | Not Approved | 1 | "SSN sample AC/DC/IO circuit diagram" | NAP
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7007 | A | 131242-WST02-DR-I-7007 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-08-20 | B | NAP | Not Approved | 2 | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7007 | B | 131242-WST02-DR-I-7007 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  | Pending from MP | 000441 | 2024-04-16 | 2024-08-20 | B | NAP | Not Approved | 2 | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7008 | B | 131242-WST02-DR-I-7008 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7009 | B | 131242-WST02-DR-I-7009 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7010 | B | 131242-WST02-DR-I-7010 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7011 | B | 131242-WST02-DR-I-7011 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7012 | B | 131242-WST02-DR-I-7012 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" | NAP
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7013 | B | 131242-WST02-DR-I-7013 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" | NAP
000442 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0038 | 0 | 131242-WSW41-CD-IM-0038 | 2024-04-17 | Milestone 1.2 - SSN Overall Changes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-16 | 2024-07-05 | 57 | Approved with Comments | YES | 2024-07-25 | NO | Resubmitted | 0 |  |  | 000442 | 2024-04-17 | 2024-04-17 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 - SSN Overall Changes" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000444 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0009 | 0 | 131242-WSW41-SP-C-0009 | 2024-04-17 | Reinforcement Bar delivery & Testing Summary -February 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-02 | 11 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000444 | 2024-04-17 | 2024-04-17 | 0 | AWC | Approved with Comments | 1 | "Reinforcement Bar delivery & Testing Summary -February 2024" | AWC
000445 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-M-0001 | 2024-04-17 | Sidewide Piperack Line List | Rev 0: Not approved - Revise and Resubmit | 2024-05-16 | 2024-07-26 | 72 | Not Approved | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000445&&001749 | 2024-04-17 | 2025-10-16 | 0 | NAP | Approved with Comments | 2 | "Sidewide Piperack Line List" && "Line List for Hydrotest (Sitewide PipeRack)" | AWC
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000 | 0 | 131242-WSD11-DR-S-1000 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-04-19 | 2024-04-19 | 0 | NAP | Not Approved | 1 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | NAP
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001 | A | 131242-WSD11-DR-S-1001 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-04-19 | 2024-04-19 | A | NAP | Not Approved | 1 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | NAP
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | A | 131242-WSD11-CL-S-0005 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | APP
000446 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 1 | 131242-WSD11-CL-S-0005 | 2024-05-31 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-10 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | APP
000446 | 02 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 5 | 131242-WSD11-CL-S-0005 | 2024-07-16 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-05 | 2024-08-16 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 7 | 131242-WSD11-CL-S-0005 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | AWC | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1400 | A | 131242-WSD11-DR-S-1400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1401 | A | 131242-WSD11-DR-S-1401 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1402 | A | 131242-WSD11-DR-S-1402 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1403 | A | 131242-WSD11-DR-S-1403 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2400 | A | 131242-WSD11-DR-S-2400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5400 | A | 131242-WSD11-DR-S-5400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8003 | A | 131242-WSD11-DR-S-8003 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-08-28 | A | AWC | Approved with Comments | 1 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | AWC
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1400 | B | 131242-WSD11-DR-S-1400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1401 | B | 131242-WSD11-DR-S-1401 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1402 | B | 131242-WSD11-DR-S-1402 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1403 | B | 131242-WSD11-DR-S-1403 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2400 | B | 131242-WSD11-DR-S-2400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5400 | B | 131242-WSD11-DR-S-5400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000446 | 04 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8003 | B | 131242-WST00-DR-S-8003 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-10-07 | 2024-10-07 | B | APP | Approved | 1 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | APP
000447 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0011 | 0 | 131242-WSW41-SP-C-0011 | 2024-04-22 | Reinforcement Bar Test Reports -Rebar Size (H10 &H16) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-05-21 | 2024-05-02 | 8 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000447 | 2024-04-22 | 2024-04-22 | 0 | AWC | Approved with Comments | 1 | "Reinforcement Bar Test Reports -Rebar Size (H10 &H16)" | AWC
000448 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 0 | 131242-WSW41-MS-C-0009 | 2024-04-24 | MSRA,SWP for Bored Piling WLT | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-24 | 2024-05-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000448 | 2024-04-24 | 2024-05-10 | 1 | NAP | Approved | 2 | "MSRA,SWP for Bored Piling WLT" | APP
000448 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 1 | 131242-WSW41-MS-C-0009 | 2024-05-10 | MSRA,SWP for Bored Piling WLT | Rev.1: Approved | 2024-05-31 | 2024-05-20 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000448 | 2024-04-24 | 2024-05-10 | 1 | APP | Approved | 2 | "MSRA,SWP for Bored Piling WLT" | APP
000449 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | VI | S | 0003 | 0 | 131242-WSW41-VI-S-0003 | 2024-04-25 | Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd) | Approved | 2024-05-27 | 2024-05-02 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000449 | 2024-04-25 | 2024-04-25 | 0 | APP | Approved | 1 | "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | APP
000450 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0004 | 0 | 131242-WSW41-VI-S-0004 | 2024-04-25 | Vendor Approval of ERSS Works (Singlee) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-02 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000450 | 2024-04-25 | 2024-04-25 | 0 | NAP | Not Approved | 1 | "Vendor Approval of ERSS Works (Singlee)" | NAP
000450 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | G | 0002 | 0 | 131242-WSW41-VI-G-0002 | 2024-07-09 | Vendor Approval of ERSS Works (Singlee) | Rev.1: Not Approved. Submission incomplete, proposed vendor is different in R0 and R1. Please resubmit with comment respond sheet. | 2024-07-29 | 2024-07-17 | 6 | Not Approved | YES | 2024-08-06 | NO | Resubmitted | 0 |  |  | 000450 | 2024-07-09 | 2024-07-09 | 0 | NAP | Not Approved | 1 | "Vendor Approval of ERSS Works (Singlee)" | NAP
000451 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0010 | 0 | 131242-WSW41-PC-W-0010 | 2024-04-25 | Payment Claim No.10 | Rev(0): Approved. Please refer to S.O. correspondence no. 15 dated 7 May 2024. | 2024-05-27 | 2024-05-13 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000451 | 2024-04-25 | 2024-04-25 | 0 | APP | Approved | 1 | "Payment Claim No.10" | APP
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | AWC
000453 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0011 | 0 | 131242-WSW41-PS-PM-0011 | 2024-04-26 | Monthly Progress Presentation No. 11 (0324) | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000453 | 2024-04-26 | 2024-04-26 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 11 (0324)" | INF
000454 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0011 | 0 | 131242-WSW41-MI-PM-0011 | 2024-04-26 | Monthly Progress Meeting Minutes 0011_20240423 | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000454 | 2024-04-26 | 2024-04-26 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0011_20240423" | INF
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | B | 131242-WST02-DR-C-8001_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  | To close after addressing the comments of S#475 & S#128.3. | 000455&&000466 | 2024-04-30 | 2024-05-07 | 0 | NAP | Not Approved | 2 | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610_BCA | B | 131242-WST02-DR-C-1023_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610_BCA | B | 131242-WST02-DR-C-1024_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610_BCA | B | 131242-WST02-DR-C-3000_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610_BCA | B | 131242-WST02-DR-C-3001_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610_BCA | B | 131242-WST02-DR-C-5004_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610_BCA | B | 131242-WST02-DR-C-5005_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610_BCA | B | 131242-WST02-DR-C-5006_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610_BCA | B | 131242-WST02-DR-C-5007_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " | NAP
000456 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 0 | 131242-WSW41-QA-M-0002 | 2024-04-30 | Inspection and test plan for Compressed Air System | Rev 0: Not approved - Revise and Resubmit | 2024-05-30 | 2024-07-15 | 54 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000456 | 2024-04-30 | 2024-07-22 | 1 | NAP | Approved | 2 | "Inspection and test plan for Compressed Air System" | APP
000456 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 1 | 131242-WSW41-QA-M-0002 | 2024-07-22 | Inspection and test plan for Compressed Air System | Rev 1: Approved | 2024-08-12 | 2024-08-20 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000456 | 2024-04-30 | 2024-07-22 | 1 | APP | Approved | 2 | "Inspection and test plan for Compressed Air System" | APP
000457 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0008 | 0 | 131242-WSW41-PS-HS-0008 | 2024-04-30 | Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024 | For Information | 2024-05-30 | 2024-06-06 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000457 | 2024-04-30 | 2024-04-30 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | INF
000458 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 0 | 131242-WST02-DS-E-0007 | 2024-04-30 | SSN Transformer Data Sheet | Rev 0: Approved with comments. To revise and resubmit.Please refer to attached file for comments. | 2024-05-30 | 2024-05-20 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" | AWC
000458 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 1 | 131242-WST02-DS-E-0007 | 2024-07-09 | SSN Transformer Data Sheet | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-29 | 2024-09-10 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" | AWC
000458 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 2 | 131242-WST02-DS-E-0007 | 2024-10-15 | SSN Transformer Data Sheet | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-05 | 2024-11-04 | 14 | Approved with Comments | YES | 2024-11-22 | NO | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" | AWC
000459 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0009 | 0 | 131242-WST02-VI-I-0009 | 2024-05-02 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-31 | 2024-07-02 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" | AWC
000459 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 1 | 131242-WST02-VI-I-0009 | 2024-07-30 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-18 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" | AWC
000459 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 2 | 131242-WST02-VI-I-0009 | 2025-02-27 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" | AWC
000460 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0021 | 0 | 131242-WSW41-MI-P-0021 | 2024-05-02 | Process & MEICA Meeting Minutes 0021_20240328 | For information | 2024-05-31 | 2024-07-26 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000460 | 2024-05-02 | 2024-05-02 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0021_20240328" | INF
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1000 | 0 | 131242-WST02-DR-M-1000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 | 2025-02-28 | 2nd priority | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" | AWC
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4001 | 0 | 131242-WST02-DR-M-4001 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000163&&000461 | 2024-05-06 | 2025-04-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4002 | 0 | 131242-WST02-DR-M-4002 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | NAP
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4003 | 0 | 131242-WST02-DR-M-4003 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" | AWC
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000191&&000461 | 2024-05-06 | 2025-05-15 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | AWC
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7000 | 0 | 131242-WST02-DR-M-7000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" | AWC
000462 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 0 | 131242-WST02-VI-I-0010 | 2024-05-07 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | AWC
000462 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 1 | 131242-WST02-VI-I-0010 | 2024-08-01 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | AWC
000462 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 2 | 131242-WST02-VI-I-0010 | 2025-02-27 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | AWC
000463 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 0 | 131242-WST02-VI-I-0011 | 2024-05-07 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | AWC
000463 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 1 | 131242-WST02-VI-I-0011 | 2024-07-24 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-18 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | AWC
000463 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 2 | 131242-WST02-VI-I-0011 | 2024-11-09 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | AWC
000464 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 0 | 131242-WST02-VI-I-0012 | 2024-05-07 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" | AWC
000464 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 1 | 131242-WST02-VI-I-0012 | 2024-08-01 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" | AWC
000464 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 2 | 131242-WST02-VI-I-0012 | 2024-11-08 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" | AWC
000465 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 0 | 131242-WSW41-MS-C-0010 | 2024-05-07 | MSRA,SWP for Bored Piling PDA Test | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-06-12 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000465 | 2024-05-07 | 2024-06-19 | 1 | AWC | Approved | 2 | "MSRA,SWP for Bored Piling PDA Test" | APP
000465 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 1 | 131242-WSW41-MS-C-0010 | 2024-06-19 | MSRA,SWP for Bored Piling PDA Test | Approved | 2024-07-09 | 2024-07-01 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000465 | 2024-05-07 | 2024-06-19 | 1 | APP | Approved | 2 | "MSRA,SWP for Bored Piling PDA Test" | APP
000466 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | 0 | 131242-WST02-DR-C-8001_ST610_BCA | 2024-05-07 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-05-20 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000455&&000466 | 2024-04-30 | 2024-05-07 | 0 | NAP | Not Approved | 2 | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | NAP
000466 | 01 | Aaron | CSA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-NA-Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | 13 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  | To close after addressing the comments of S#475, S#128.3 | 000466 | 2024-06-12 | 2024-06-12 | NA | NAP | Not Approved | 1 | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | NAP
000467 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0039 | 0 | 131242-WSW41-CD-IM-0039 | 2024-05-08 | Submission Of BIM Coordination VCM Model (Apr-2024) | For Information | 2024-06-06 | 2024-05-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000467 | 2024-05-08 | 2024-05-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Apr-2024)" | INF
000468 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 0 | 131242-WST02-RT-C-0001 | 2024-05-09 | Design for Safety Report 2 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-06 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | NAP | Approved with Comments | 4 | "Design for Safety Report 2" | AWC
000468 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 1 | 131242-WST02-RT-C-0001 | 2024-06-07 | Design for Safety Report 2 | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-05 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | NAP | Approved with Comments | 4 | "Design for Safety Report 2" | AWC
000468 | 02 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001 | 2024-08-21 | Design for Safety Report 2 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-17 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | AWC | Approved with Comments | 4 | "Design for Safety Report 2" | AWC
000468 | 03 | Leslie | Project | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001 | 2024-11-03 | Design for Safety Report 2 | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-12-07 | 25 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | AWC | Approved with Comments | 4 | "Design for Safety Report 2" | AWC
000469 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | C | 0005 | 0 | 131242-WSW41-CL-C-0005 | 2024-05-10 | Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47) | Rev.0: Approved | 2024-06-10 | 2024-05-20 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000469 | 2024-05-10 | 2024-05-10 | 0 | APP | Approved | 1 | "Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47)" | APP
000470 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0022 | 0 | 131242-WSW41-MI-P-0022 | 2024-05-13 | Process & MEICA Meeting Minutes 0022_20240425 | Rev 0: For Information | 2024-06-11 | 2024-08-14 | 67 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000470 | 2024-05-13 | 2024-05-13 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0022_20240425" | INF
000471 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-A-1000 | 2024-05-13 | NEA Waiver Submission of SSN Plant | For Information | 2024-06-11 | 2024-05-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | INF | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0022 | 0 | 131242-WSW41-MI-C-0022 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000472 | 2024-05-17 | 2024-05-17 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" | INF
000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0023 | 0 | 131242-WSW41-MI-C-0023 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000472 | 2024-05-17 | 2024-05-17 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" | INF
000473 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 0 | 131242-WSW41-RT-PM-0012 | 2024-04-18 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-05-17 | 2024-06-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000473 | 2024-04-18 | 2024-06-11 | 1 | AWC | Approved | 2 | "C4B Monthly Progress Report Number No.12 (04 24)" | APP
000473 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 1 | 131242-WSW41-RT-PM-0012 | 2024-06-11 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 1 - Approved | 2024-07-02 | 2024-06-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000473 | 2024-04-18 | 2024-06-11 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.12 (04 24)" | APP
000474 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 0 | 131242-WSW41-VI-M-1010 | 2024-05-18 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 0: Not approved - Revise and Resubmit | 2024-06-18 | 2024-07-04 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | NAP | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | AWC
000474 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 1 | 131242-WSW41-VI-M-1010 | 2024-09-06 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 1: Not approved - Revise and Resubmit | 2024-09-26 | 2024-09-12 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | NAP | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | AWC
000474 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 2 | 131242-WSW41-VI-M-1010 | 2024-10-17 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-07 | 2024-11-15 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610 | 2024-05-18 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | D | 131242-WST00-DR-C-8001_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | D | 131242-WST02-DR-C-1023_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | D | 131242-WST02-DR-C-1024_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | D | 131242-WST02-DR-C-5004_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | D | 131242-WST02-DR-C-5005_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | D | 131242-WST02-DR-C-5006_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | D | 131242-WST02-DR-C-3000_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | D | 131242-WST02-DR-C-3001_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | AWC | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | D | 131242-WST02-DR-C-5007_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | AWC
000475 | 03 | Zora | CSA | NA | 131242 | WST02 | NA | C | Cmt Sheet Reply 2024 10 07 | NA | 131242-WST02-NA-C-Cmt Sheet Reply 2024 10 07 | 2024-10-09 | IFC of ST610 (Underground Services) | Rev.3: Approved with comments. | 2024-10-29 | 2024-10-24 | 11 | Approved with Comments | YES | 2024-11-13 | NO | Resubmitted | 0 |  |  | 000475 | 2024-10-09 | 2024-10-09 | NA | AWC | Approved with Comments | 1 | "IFC of ST610 (Underground Services) " | AWC
000476 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 0 | 131242-WST02-VI-I-0016 | 2024-05-21 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-20 | 2024-07-02 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 |  | 000476 | 2024-05-21 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | AWC
000476 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 1 | 131242-WST02-VI-I-0016 | 2025-03-17 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000476 | 2024-05-21 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | AWC
000477 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0023 | 0 | 131242-WSW41-MI-P-0023 | 2024-05-23 | Process & MEICA Meeting Minutes 0023_20240509 | Rev 0: For Information | 2024-06-21 | 2024-08-14 | 59 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000477 | 2024-05-23 | 2024-05-23 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0023_20240509" | INF
000478 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CN | S | 0001 | 0 | 131242-WSD11-CN-S-0001 | 2024-05-23 | Handrail design loading & Testing of THP Train by CAMBI | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-03 | 7 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  | Resubmission on hold and to resubmit after BCA approval of CAMBI Steel Structure | 000478 | 2024-05-23 | 2024-05-23 | 0 | NAP | Not Approved | 1 | "Handrail design loading & Testing of THP Train by CAMBI" | NAP
000479 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0001 | 0 | 131242-WSD11-CN-E-0001 | 2024-05-23 | Proposed change of SS316 Cable Tray within THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-18 | 18 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000479 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Proposed change of SS316 Cable Tray within THP Module" | REJ
000480 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0002 | 0 | 131242-WSD11-CN-E-0002 | 2024-05-23 | Proposed change of Carbon loaded GRP Junction Box within THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000480 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Proposed change of Carbon loaded GRP Junction Box within THP Module" | REJ
000481 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0003 | 0 | 131242-WSD11-CN-E-0003 | 2024-05-23 | Separate Terminal Box for Motor Space Heater | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | 14 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000481 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Separate Terminal Box for Motor Space Heater" | REJ
000482 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0004 | 0 | 131242-WSD11-CN-E-0004 | 2024-05-23 | Local Control Station with THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | 14 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000482 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Local Control Station with THP Module" | REJ
000483 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | I | 0002 | 0 | 131242-WSD11-CN-I-0002 | 2024-05-23 | Pressure Instrument Mounting in THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000483 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Pressure Instrument Mounting in THP Module" | REJ
000484 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | M | 0001 | 0 | 131242-WSD11-CN-M-0001 | 2024-05-23 | Pump Color within THP Module | Rev 0: Rejected Refer to attached file for comments. | 2024-06-21 | 2024-08-08 | 55 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000484 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Pump Color within THP Module" | REJ
000485 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0020 | 0 | 131242-WSW41-VI-E-0020 | 2024-05-23 | Vendor Approval of Electrical Installer (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-21 | 2024-07-04 | 30 | Approved with Comments | YES | 2024-07-24 | NO | Resubmitted | 0 |  |  | 000485 | 2024-05-23 | 2024-05-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Electrical Installer (Cyclect)" | AWC
000486 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | I | 0020 | 0 | 131242-WSW41-VI-I-0020 | 2024-05-23 | Vendor Approval of ICA Installer Submission (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-21 | 2024-07-02 | 28 | Approved with Comments | YES | 2024-07-22 | NO | Resubmitted | 0 |  |  | 000486 | 2024-05-23 | 2024-05-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of ICA Installer Submission (Cyclect)" | AWC
000487 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | K | 0001 | 0 | 131242-WSW41-MS-K-0001 | 2024-05-27 | MSRA & SWP for Mobilization and Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | 10 | Approved with Comments | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000487 | 2024-05-27 | 2024-05-27 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP for Mobilization and Demobilization of Machinery" | AWC
000488 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0001 | 0 | 131242-WSW41-MS-G-0001 | 2024-05-27 | MSRA & SWP for Sheet Piling Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | 10 | Not Approved | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000488 | 2024-05-27 | 2024-05-27 | 0 | NAP | Not Approved | 1 | "MSRA & SWP for Sheet Piling Work" | NAP
000489 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0002 | 0 | 131242-WST02-RT-C-0002 | 2024-05-28 | Project Safety Review for ERSS | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-18 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000489 | 2024-05-28 | 2024-07-09 | 1 | AWC | Approved with Comments | 2 | "Project Safety Review for ERSS" | AWC
000489 | 01 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0002 | 1 | 131242-WST02-RT-C-0002 | 2024-07-09 | Project Safety Review for ERSS | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-29 | 2024-08-12 | 24 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000489 | 2024-05-28 | 2024-07-09 | 1 | AWC | Approved with Comments | 2 | "Project Safety Review for ERSS" | AWC
000490 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 0 | 131242-WST02-RT-C-0003 | 2024-05-28 | Report of DFS (Guide 3) for ERSS | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-13 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000490 | 2024-05-28 | 2024-06-19 | 1 | NAP | Approved | 2 | "Report of DFS (Guide 3) for ERSS" | APP
000490 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 1 | 131242-WST02-RT-C-0003 | 2024-06-19 | Report of DFS (Guide 3) for ERSS | Rev.1: Approved | 2024-07-09 | 2024-07-12 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000490 | 2024-05-28 | 2024-06-19 | 1 | APP | Approved | 2 | "Report of DFS (Guide 3) for ERSS" | APP
000491 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0030 | 0 | 131242-WSW41-LT-PM-0030 | 2024-05-28 | CV of Team member (Planner) | Rev. 0 - Approved with comments. Please refer to attached comment sheet | 2024-06-26 | 2024-06-10 | 9 | Approved with Comments | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000491 | 2024-05-28 | 2024-05-28 | 0 | AWC | Approved with Comments | 1 | "CV of Team member (Planner)" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | A | 131242-WST02-DR-M-5000 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | A | 131242-WST02-DR-M-5001 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | A | 131242-WST02-DR-M-5002 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | A | 131242-WST02-DR-M-5003 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | A | 131242-WST02-DR-M-5004 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | A | 131242-WST02-DR-M-5005 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | A | 131242-WST02-DR-M-5006 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | A | 131242-WST02-DR-M-5007 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | A | 131242-WST02-DR-M-5008 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7001 | A | 131242-WST02-SH-M-7001 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7002 | A | 131242-WST02-SH-M-7002 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7003 | A | 131242-WST02-SH-M-7003 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7004 | A | 131242-WST02-SH-M-7004 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7005 | A | 131242-WST02-SH-M-7005 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7006 | A | 131242-WST02-SH-M-7006 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7007 | A | 131242-WST02-SH-M-7007 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | B | 131242-WST02-DR-M-5000 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | B | 131242-WST02-DR-M-5001 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | B | 131242-WST02-DR-M-5002 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | B | 131242-WST02-DR-M-5003 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | B | 131242-WST02-DR-M-5004 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | B | 131242-WST02-DR-M-5005 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | B | 131242-WST02-DR-M-5006 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | B | 131242-WST02-DR-M-5007 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | B | 131242-WST02-DR-M-5008 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | B | 131242-WST02-DR-M-7001 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | B | 131242-WST02-DR-M-7002 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | B | 131242-WST02-DR-M-7003 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | B | 131242-WST02-DR-M-7004 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | B | 131242-WST02-DR-M-7005 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | B | 131242-WST02-DR-M-7006 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | B | 131242-WST02-DR-M-7007 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | C.1 | 131242-WST02-DR-M-5000 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 | 2025-02-24 |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | C.1 | 131242-WST02-DR-M-5001 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | C.1 | 131242-WST02-DR-M-5002 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | C.1 | 131242-WST02-DR-M-5003 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | C.1 | 131242-WST02-DR-M-5004 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | C.1 | 131242-WST02-DR-M-5005 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | C.1 | 131242-WST02-DR-M-5006 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | C.1 | 131242-WST02-DR-M-5007 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | C.1 | 131242-WST02-DR-M-5008 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | C.2 | 131242-WST02-DR-M-7001 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | C.1 | 131242-WST02-DR-M-7002 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | C.1 | 131242-WST02-DR-M-7003 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | C.1 | 131242-WST02-DR-M-7004 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | C.1 | 131242-WST02-DR-M-7005 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | C.2 | 131242-WST02-DR-M-7006 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | C.2 | 131242-WST02-DR-M-7007 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" | AWC
000493 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0015 | 0 | 131242-WSW41-VI-C-0015 | 2024-05-29 | Vendor Approval of Testing Laboratory (TUV) | Approved | 2024-06-27 | 2024-06-03 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000493 | 2024-05-29 | 2024-05-29 | 0 | APP | Approved | 1 | "Vendor Approval of Testing Laboratory (TUV)" | APP
000494 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 0 | 131242-WSW41-MS-C-0011 | 2024-05-29 | Method Statement for Concrete Temperature Control and Monitoring | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-10 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | NAP | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" | AWC
000494 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 1 | 131242-WSW41-MS-C-0011 | 2024-06-18 | Method Statement for Concrete Temperature Control and Monitoring | Rev.1:Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-08 | 2024-07-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | AWC | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" | AWC
000494 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 2 | 131242-WSW41-MS-C-0011 | 2024-07-28 | Method Statement for Concrete Temperature Control and Monitoring | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2024-08-16 | 2024-08-13 | 11 | Approved with Comments | YES | 2024-09-02 | NO | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | AWC | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" | AWC
000495 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SU | K | 0001 | 0 | 131242-WSW41-SU-K-0001 | 2024-05-29 | Time Lapse Surveys_Apr 24 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-03 | 3 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000495 | 2024-05-29 | 2024-05-29 | 0 | NAP | Not Approved | 1 | "Time Lapse Surveys_Apr 24" | NAP
000496 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0029 | 0 | 131242-WSW41-LT-PM-0029 | 2024-05-30 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24 | Rev(0): Received for S.O.'s assessment. Please refer to S.O. correspondence no. 211 dated 22 Aug 2024. | 2024-06-28 | 2024-08-26 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000496 | 2024-05-30 | 2024-05-30 | 0 | INF | For Information | 1 | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24" | INF
000497 | 00 | Low | EICA | NA | 131242 | WSD11 | CN | I | 0001 | 0 | 131242-WSD11-CN-I-0001 | 2024-05-30 | General Deviation from ICA G & P Spec | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-27 | 63 | Rejected | YES | 2024-09-16 | NO | Resubmitted | 0 |  | (RFC) NO.: 1230207-RFC-0013 | 000497 | 2024-05-30 | 2024-05-30 | 0 | REJ | Rejected | 1 | "General Deviation from ICA G & P Spec" | REJ
000498 | 00 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0012 | 0 | 131242-WSW41-SP-C-0012 | 2024-05-30 | Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-06-12 | 9 | Approved with Comments | YES | 2024-07-02 | NO | Resubmitted | 0 |  |  | 000498 | 2024-05-30 | 2024-05-30 | 0 | AWC | Approved with Comments | 1 | "Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115)" | AWC
000499 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 0 | 131242-WSD11-VI-M-0002 | 2024-05-30 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-28 | 2024-07-18 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000499 | 2024-05-30 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" | AWC
000499 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 1 | 131242-WSD11-VI-M-0002 | 2025-03-14 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 82 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 000499 | 2024-05-30 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" | AWC
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601_BCA | B | 131242-WST00-DR-G-8000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | B | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601_BCA | C | 131242-WST00-DR-G-0001_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601_BCA | C | 131242-WST00-DR-G-0002_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601_BCA | C | 131242-WST00-DR-G-1000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601_BCA | C | 131242-WST00-DR-G-1001_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601_BCA | C | 131242-WST00-DR-G-1002_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601_BCA | C | 131242-WST00-DR-G-1003_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601_BCA | C | 131242-WST00-DR-G-1004_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601_BCA | C | 131242-WST00-DR-G-3000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " | INF
000501 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 0 | 131242-WST02-VI-I-0014 | 2024-05-31 | Vendor Approval of SSN Package (Thermal Flow Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000501 | 2024-05-31 | 2025-01-08 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow Switches)" | AWC
000501 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 1 | 131242-WST02-VI-I-0014 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow Switches) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-05-06 | 84 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000501 | 2024-05-31 | 2025-01-08 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow Switches)" | AWC
000502 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 0 | 131242-WST02-VI-I-0015 | 2024-05-31 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000502 | 2024-05-31 | 2024-08-27 | 1 | AWC | Approved | 2 | "Vendor Approval of SSN Package (Pressure Gauges)" | APP
000502 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 1 | 131242-WST02-VI-I-0015 | 2024-08-27 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 1: Approved. | 2024-09-16 | 2024-11-08 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000502 | 2024-05-31 | 2024-08-27 | 1 | APP | Approved | 2 | "Vendor Approval of SSN Package (Pressure Gauges)" | APP
000503 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 0 | 131242-WST02-VI-I-0013 | 2024-06-01 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000503 | 2024-06-01 | 2025-01-08 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | AWC
000503 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 1 | 131242-WST02-VI-I-0013 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-03-17 | 48 | Approved with Comments | YES | 2025-04-04 | NO | Resubmitted | 0 |  |  | 000503 | 2024-06-01 | 2025-01-08 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | AWC
000504 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 0 | 131242-WSW41-VI-M-1011 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-01 | 2024-07-18 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000504 | 2024-06-01 | 2024-11-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | AWC
000504 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 1 | 131242-WSW41-VI-M-1011 | 2024-11-02 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-21 | 2024-12-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000504 | 2024-06-01 | 2024-11-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | AWC
000505 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1012 | 0 | 131242-WSW41-VI-M-1012 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves) | Rev 0: Not approved - Revise and Resubmit | 2024-07-01 | 2024-08-01 | 43 | Not Approved | YES | 2024-08-21 | NO | Resubmitted | 0 |  | This document is no longer valid and should be marked as "Voided." | 000505 | 2024-06-01 | 2024-06-01 | 0 | NAP | Not Approved | 1 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves)" | NAP
000506 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0011 | 0 | 131242-WSW41-PC-W-0011 | 2024-06-03 | Payment Claim No.11 | For Information | 2024-07-02 | 2024-06-27 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000506 | 2024-06-03 | 2024-06-03 | 0 | INF | For Information | 1 | "Payment Claim No.11" | INF
000507 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0010 | 0 | 131242-WST02-CL-P-0010 | 2024-06-03 | Blower Pressure Loss Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-07-02 | 2024-07-31 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | NAP | Approved with Comments | 3 | "Blower Pressure Loss Calculation" | AWC
000507 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 1 | 131242-WST02-CL-P-0010 | 2024-10-22 | Blower Pressure Loss Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2024-11-19 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | AWC | Approved with Comments | 3 | "Blower Pressure Loss Calculation" | AWC
000507 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 2 | 131242-WST02-CL-P-0010 | 2025-09-10 | Blower Pressure Loss Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. Provide PE endorsement | 2025-09-30 | 2026-02-23 | 118 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | AWC | Approved with Comments | 3 | "Blower Pressure Loss Calculation" | AWC
000508 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0031 | 0 | 131242-WSW41-LT-PM-0031 | 2024-06-04 | Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump] | Refer to S.O. Correspondence No.0194. | 2024-07-03 | 2024-08-16 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000508 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump]" | INF
000509 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0012 | 0 | 131242-WSW41-MI-PM-0012 | 2024-06-04 | Monthly Progress Meeting Minutes 0012_20240521 | For Information | 2024-07-03 | 2024-06-04 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000509 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0012_20240521" | INF
000510 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0012 | 0 | 131242-WSW41-PS-PM-0012 | 2024-06-04 | Monthly Progress Presentation No. 12 (0424) | For Information | 2024-07-03 | 2024-06-04 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000510 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 12 (0424)" | INF
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3180 | A | 131242-WST02-DR-M-3180 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3181 | A | 131242-WST02-DR-M-3181 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3182 | A | 131242-WST02-DR-M-3182 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5131 | A | 131242-WST02-DR-M-5131 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5132 | A | 131242-WST02-DR-M-5132 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5133 | A | 131242-WST02-DR-M-5133 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5101 | A | 131242-WST02-DR-M-5101 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5102 | A | 131242-WST02-DR-M-5102 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 0 | 131242-WST02-DS-M-0002 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-10-25 | 1 | NAP | Approved with Comments | 2 | "SSN Blower GA drawings and Data Sheets" | AWC
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0011 | 0 | 131242-WST02-DS-E-0011 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0017 | 0 | 131242-WST02-DS-E-0017 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | I | 0003 | 0 | 131242-WST02-DS-I-0003 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0001 | 0 | 131242-WST02-OM-I-0001 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0002 | 0 | 131242-WST02-OM-I-0002 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" | NAP
000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 1 | 131242-WST02-DS-M-0002 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | 21 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-10-25 | 1 | AWC | Approved with Comments | 2 | "SSN Blower GA drawings and Data Sheets" | AWC
000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0101 | B | 131242-WST02-DR-M-0101 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | 21 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000511 | 2024-10-25 | 2024-10-25 | B | AWC | Approved with Comments | 1 | "SSN Blower GA drawings and Data Sheets" | AWC
000512 | 00 | Radha | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 0 | 131242-WSW41-MS-C-0012 | 2024-06-05 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-27 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000512 | 2024-06-05 | 2024-07-02 | 1 | AWC | Approved | 2 | "MSRA, SWP for Bored Pile Hacking and Rectification works" | APP
000512 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 1 | 131242-WSW41-MS-C-0012 | 2024-07-02 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.1: Approved | 2024-07-22 | 2024-07-26 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000512 | 2024-06-05 | 2024-07-02 | 1 | APP | Approved | 2 | "MSRA, SWP for Bored Pile Hacking and Rectification works" | APP
000513 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 0 | 131242-WST02-VI-I-0017 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | AWC
000513 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 1 | 131242-WST02-VI-I-0017 | 2024-09-16 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | AWC
000513 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 2 | 131242-WST02-VI-I-0017 | 2025-01-10 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-30 | 2025-02-12 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | AWC
000513 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 3 | 131242-WST02-VI-I-0017 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | AWC
000514 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 0 | 131242-WST02-VI-I-0018 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Switch) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" | AWC
000514 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 1 | 131242-WST02-VI-I-0018 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Switch) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" | AWC
000514 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 2 | 131242-WST02-VI-I-0018 | 2025-05-20 | Vendor Approval of SSN Package (Pressure Switch) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-09 | 2025-10-01 | 96 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" | AWC
000515 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 0 | 131242-WST02-VI-I-0019 | 2024-06-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" | AWC
000515 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 1 | 131242-WST02-VI-I-0019 | 2024-08-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-27 | 2024-09-18 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" | AWC
000515 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 2 | 131242-WST02-VI-I-0019 | 2025-03-17 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" | AWC
000516 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0040 | 0 | 131242-WSW41-CD-IM-0040 | 2024-06-07 | Submission Of BIM Coordination VCM Model (May-2024) | For Information | 2024-07-08 | 2024-06-22 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000516 | 2024-06-07 | 2024-06-07 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (May-2024)" | INF
000517 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0024 | 0 | 131242-WSW41-MI-P-0024 | 2024-06-10 | Process & MEICA Meeting Minutes 0024_20240523 | Minutes of meeting are accepted for information. | 2024-07-09 | 2024-07-02 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000517 | 2024-06-10 | 2024-06-10 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0024_20240523" | INF
000518 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 0 | 131242-WSW41-MS-C-0013 | 2024-06-10 | MSRA, SWP for Plate Load Test | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-06-27 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000518 | 2024-06-10 | 2024-07-04 | 1 | NAP | Approved with Comments | 2 | "MSRA, SWP for Plate Load Test" | AWC
000518 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 1 | 131242-WSW41-MS-C-0013 | 2024-07-04 | MSRA, SWP for Plate Load Test | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-05 | 22 | Approved with Comments | YES | 2024-08-23 | NO | Resubmitted | 0 |  |  | 000518 | 2024-06-10 | 2024-07-04 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Plate Load Test" | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 8003_ST613_BCA | A | 131242-WST00-DR-S-8003_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 | 2024-08-16 | Heng Peng to provide latest DGN & PDF drawing | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613_BCA | A | 131242-WST02-DR-S-1000_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613_BCA | A | 131242-WST02-DR-S-1006_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613_BCA | A | 131242-WST02-DR-S-1007_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613_BCA | A | 131242-WST02-DR-S-1008_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613_BCA | A | 131242-WST02-DR-S-1013_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613_BCA | A | 131242-WST02-DR-S-5005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613_BCA | A | 131242-WST02-DR-S-1014_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613_BCA | A | 131242-WST02-DR-S-1015_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613_BCA | A | 131242-WST02-DR-S-1016_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613_BCA | A | 131242-WST02-DR-S-1017_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613_BCA | A | 131242-WST02-DR-S-1018_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613_BCA | A | 131242-WST02-DR-S-1019_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613_BCA | A | 131242-WST02-DR-S-1020_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613_BCA | A | 131242-WST02-DR-S-1021_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613_BCA | A | 131242-WST02-DR-S-1022_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613_BCA | A | 131242-WST02-DR-S-3005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613_BCA | A | 131242-WST02-DR-S-3008_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613_BCA | A | 131242-WST02-DR-S-3009_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613_BCA | A | 131242-WST02-DR-S-7002_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613_BCA | A | 131242-WST02-DR-S-7003_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613_BCA | A | 131242-WST02-DR-S-7004_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613_BCA | A | 131242-WST02-DR-S-7005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613_BCA | A | 131242-WST02-DR-S-5006_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | AWC
000520 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0013 | 0 | 131242-WSW41-RT-PM-0013 | 2024-06-12 | C4B Monthly Progress Report Number No.13 (05 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-07-11 | 2024-06-28 | 12 | Approved with Comments | YES | 2024-07-18 | NO | Resubmitted | 0 |  |  | 000520 | 2024-06-12 | 2024-06-12 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.13 (05 24)" | AWC
000521 | 00 | David | Mech | NA | 131242 | WSW41 | SP | M | 8002 | 0 | 131242-WSW41-SP-M-8002 | 2024-06-12 | Datasheet for Thermal Insulation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-11 | 2024-08-29 | 56 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-03-28 | In Progress | 000521 | 2024-06-12 | 2024-06-12 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Thermal Insulation" | AWC
000522 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 0 | 131242-WSW41-VI-C-0016 | 2024-06-13 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-12 | 2024-06-28 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | NAP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | APP
000522 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 1 | 131242-WSW41-VI-C-0016 | 2024-07-04 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-17 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | NAP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | APP
000522 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 2 | 131242-WSW41-VI-C-0016 | 2024-07-22 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | R2: Approved | 2024-08-12 | 2024-08-12 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | APP
000523 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0006 | 0 | 131242-WSW41-CL-S-0006 | 2024-06-14 | Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94 | Rev.0: Approved | 2024-07-15 | 2024-06-28 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000523 | 2024-06-14 | 2024-06-14 | 0 | APP | Approved | 1 | "Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94" | APP
000524 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0032 | 0 | 131242-WSW41-LT-PM-0032 | 2024-06-14 | NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source | Refer to S.O. Correspondence No.000213 dated 23-Aug-2024. | 2024-07-15 | 2024-08-26 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000524 | 2024-06-14 | 2024-06-14 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source " | INF
000525 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0014 | 0 | 131242-WSW41-MS-C-0014 | 2024-06-18 | MSRA & SWP of Civil & Structure Work (Substructure) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | 9 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000525 | 2024-06-18 | 2024-06-18 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP of Civil & Structure Work (Substructure)" | AWC
000526 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0015 | 0 | 131242-WSW41-MS-C-0015 | 2024-06-18 | MSRA & SWP of Mobilization & Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | 9 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000526 | 2024-06-18 | 2024-06-18 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP of Mobilization & Demobilization of Machinery" | AWC
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A | 131242-WSB01-DR-BH-1000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A | 131242-WSB01-DR-BH-3000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A | 131242-WSB01-DR-BH-5000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A.1 | 131242-WSB01-DR-BH-1000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A.1 | 131242-WSB01-DR-BH-3000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A.1 | 131242-WSB01-DR-BH-5000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | AWC
000528 | 00 | Balaji | EICA | NA | 131242 | WSW41 | VI | I | 0002 | 0 | 131242-WSW41-VI-I-0002 | 2024-06-19 | Vendor Approval of Communication Cable (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-17 | 2024-08-05 | 33 | Approved with Comments | YES | 2024-08-23 | NO | Resubmitted | 0 |  |  | 000528 | 2024-06-19 | 2024-06-19 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Communication Cable (Keystone)" | AWC
000529 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0025 | 0 | 131242-WSW41-MI-P-0025 | 2024-06-20 | Process & MEICA Meeting Minutes 0025_20240606 | For Information | 2024-07-18 | 2024-08-08 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000529 | 2024-06-20 | 2024-06-20 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0025_20240606" | INF
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | C | 131242-WST00-DR-S-0001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | C | 131242-WST00-DR-S-0002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | C | 131242-WST00-DR-S-0003_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | C | 131242-WST02-DR-S-1006_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | C | 131242-WST02-DR-S-1007_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | C | 131242-WST02-DR-S-1008_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | C | 131242-WST02-DR-S-3000_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5001_ST606 | C | 131242-WST00-DR-S-5001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | C | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5002_ST606 | C | 131242-WST00-DR-S-5002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | C | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | C | 131242-WST02-DR-S-7000_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | C | 131242-WST02-DR-S-7001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | C | 131242-WST02-DR-S-7002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8002_ST606 | A | 131242-WST00-DR-S-8002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | A | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | D | 131242-WST00-DR-G-0001_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | D | 131242-WST00-DR-G-0002_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | D | 131242-WST00-DR-G-1000_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | D | 131242-WST00-DR-G-1001_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | D | 131242-WST00-DR-G-1002_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | D | 131242-WST00-DR-G-1003_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | D | 131242-WST00-DR-G-1004_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 5100_ST601 | D | 131242-WST00-DR-G-5100_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-06-21 | 2024-06-21 | D | AWC | Approved with Comments | 1 | "IFC of ST601 – ERSS < 4m " | AWC
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | D.1 | 131242-WST00-DR-G-8000_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | E | 131242-WST00-DR-G-0001_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-12 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | E | 131242-WST00-DR-G-0002_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | E | 131242-WST00-DR-G-1000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | E | 131242-WST00-DR-G-1004_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | E | 131242-WST00-DR-G-3000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3001_ST601 | E | 131242-WST00-DR-G-3001_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3002_ST601 | E | 131242-WST00-DR-G-3002_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3003_ST601 | E | 131242-WST00-DR-G-3003_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " | APP
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | E | 131242-WST00-DR-G-8000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | APP
000532 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0009 | 0 | 131242-WSW41-QA-C-0009 | 2024-06-25 | Monthly Concrete Cube Records for Structural works (02 24) | For Information | 2024-07-23 | 2024-07-05 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000532 | 2024-06-25 | 2024-06-25 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works (02 24)" | INF
000533 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 0 | 131242-WSW41-PC-W-0012 | 2024-06-25 | Payment Claim No.12 | Rev (0): Rejected due to some PDA test were done in June 2024. | 2024-07-23 | 2024-06-28 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000533 | 2024-06-25 | 2024-06-28 | 1 | REJ | Approved | 2 | "Payment Claim No.12" | APP
000533 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 1 | 131242-WSW41-PC-W-0012 | 2024-06-28 | Payment Claim No.12 | Rev (1): Approved, refer to SO Correspondence No. 0181 dated 2 July 2024. | 2024-07-18 | 2024-11-07 | 94 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000533 | 2024-06-25 | 2024-06-28 | 1 | APP | Approved | 2 | "Payment Claim No.12" | APP
000534 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6601 | 0 | 131242-WST02-DR-P-6601 | 2024-06-26 | SSN Blower P&ID | Rev 0: Not approved - Revise and Resubmit | 2024-07-24 | 2024-07-31 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000534 | 2024-06-26 | 2024-06-26 | 0 | NAP | Not Approved | 1 | "SSN Blower P&ID" | NAP
000534 | 01 | Qili | Process | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S000534 | NA | 131242-NA-NA-NA-Cmt Sheet Reply S000534 | 2024-08-15 | SSN Blower P&ID | Rev 1: Rejected | 2024-09-04 | 2024-09-06 | 16 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000534 | 2024-08-15 | 2024-08-15 | NA | REJ | Rejected | 1 | "SSN Blower P&ID" | REJ
000535 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0003 | 0 | 131242-WSD11-BQ-P-0003 | 2024-06-26 | THP Line List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-24 | 2024-08-29 | 46 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000535 | 2024-06-26 | 2024-06-26 | 0 | AWC | Approved with Comments | 1 | "THP Line List" | AWC
000536 | 00 | Zora/ HP | CSA | NA | 131242 | WSD11 | DR | S | 5301 | B | 131242-WSD11-DR-S-5301 | 2024-06-26 | IFC of Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-05 | 7 | Approved with Comments | YES | 2024-07-25 | NO | Resubmitted | 0 | 2024-07-16 | Zora obtain QP endorsement on the drawing and Heng Peng to provide latest DGN and Tenwit (Kalaban) updating the minor comments | 000423&&000536 | 2024-06-05 | 2024-06-26 | B | AWC | Approved with Comments | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | AWC
000537 | 00 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 0 | 131242-WSD11-CL-M-0010 | 2024-06-27 | Design Calculation for Instrument Air Receiver | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-06 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000537 | 2024-06-27 | 2024-09-03 | 1 | AWC | Approved | 2 | "Design Calculation for Instrument Air Receiver" | APP
000537 | 01 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 1 | 131242-WSD11-CL-M-0010 | 2024-09-03 | Design Calculation for Instrument Air Receiver | Rev 1: Approved | 2024-09-23 | 2024-09-05 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000537 | 2024-06-27 | 2024-09-03 | 1 | APP | Approved | 2 | "Design Calculation for Instrument Air Receiver" | APP
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009_ST607_BCA | A | 131242-WST02-DR-S-1009_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538 | 2024-07-01 | 2024-07-01 | A | NAP | Not Approved | 1 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | NAP
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000539 | 00 | Mohan | QAQC | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004 | 2024-07-02 | Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-30 | 2024-07-15 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000539&&000567 | 2024-07-02 | 2024-07-15 | 0 | AWC | Approved | 2 | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " | APP
000540 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005 | 2024-07-02 | Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616) | For Information | 2024-07-30 | 2024-07-15 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000540&&000568 | 2024-07-02 | 2024-07-15 | 0 | INF | Approved with Comments | 2 | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " | AWC
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | A | 131242-WST02-DR-M-5103 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | A | 131242-WST02-DR-M-5104 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | A | 131242-WST02-DR-M-5105 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | B | 131242-WST02-DR-M-5103 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | B | 131242-WST02-DR-M-5104 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | B | 131242-WST02-DR-M-5105 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | A | 131242-WST02-DR-M-5106 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | A | 131242-WST02-DR-M-5107 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | A | 131242-WST02-DR-M-5108 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0031 | 0 | 131242-WST02-DS-M-0031 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-01-16 | 0 | AWC | Approved with Comments | 1 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | D | 131242-WST02-DR-M-5103 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | D | 131242-WST02-DR-M-5104 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | D | 131242-WST02-DR-M-5105 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | B | 131242-WST02-DR-M-5106 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | B | 131242-WST02-DR-M-5107 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | B | 131242-WST02-DR-M-5108 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" | AWC
000542 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0026 | A | 131242-WSW41-MI-P-0026 | 2024-07-03 | Process & MEICA Meeting Minutes 0026_20240624 | Rev 0: For Information | 2024-07-31 | 2024-08-29 | 41 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000542 | 2024-07-03 | 2024-07-03 | A | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0026_20240624" | INF
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7700 | C | 131242-WST02-DR-E-7700 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7701 | C | 131242-WST02-DR-E-7701 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7702 | C | 131242-WST02-DR-E-7702 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7703 | C | 131242-WST02-DR-E-7703 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7704 | C | 131242-WST02-DR-E-7704 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7705 | C | 131242-WST02-DR-E-7705 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7706 | C | 131242-WST02-DR-E-7706 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7707 | C | 131242-WST02-DR-E-7707 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7708 | C | 131242-WST02-DR-E-7708 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7709 | C | 131242-WST02-DR-E-7709 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7710 | C | 131242-WST02-DR-E-7710 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7711 | C | 131242-WST02-DR-E-7711 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7712 | C | 131242-WST02-DR-E-7712 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7713 | C | 131242-WST02-DR-E-7713 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7714 | C | 131242-WST02-DR-E-7714 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7715 | C | 131242-WST02-DR-E-7715 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7716 | C | 131242-WST02-DR-E-7716 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" | AWC
000544 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0034 | 0 | 131242-WSW41-LT-PM-0034 | 2024-07-04 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Please refer to comment sheet for resubmission. | 2024-08-01 | 2024-07-16 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000544 | 2024-07-04 | 2024-07-04 | 0 | INF | For Information | 1 | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | INF
000544 | 01 | Yuen Fatt | Project | NA | 131242 | NA | LT | PM | NA | NA | 131242-NA-LT-PM-NA | 2024-08-03 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Rev.1: Please refer to comment sheet for resubmission. | 2024-08-23 | 2024-08-19 | 10 | Not Approved | YES | 2024-09-06 | NO | Resubmitted | 0 |  | To change the title : Request Owner’s Approval for Use of Linabond Concrete Corrosion Protection Material | 000544 | 2024-08-03 | 2024-08-03 | NA | NAP | Not Approved | 1 | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | NAP
000545 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0006 | 0 | 131242-WST02-RT-C-0006 | 2024-07-04 | Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615) | Approved | 2024-08-01 | 2024-07-17 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000545 | 2024-07-04 | 2024-07-04 | 0 | APP | Approved | 1 | "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | APP
000546 | 00 | Theint Theint | Project | NA | 131242 | WSW41 | VI | S | 0005 | 0 | 131242-WSW41-VI-S-0005 | 2024-07-05 | Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-02 | 2024-07-18 | 9 | Not Approved | YES | 2024-08-07 | NO | Resubmitted | 0 |  |  | 000546 | 2024-07-05 | 2024-07-05 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | NAP
000547 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0002 | 0 | 131242-WSW41-PO-E-0002 | 2024-07-08 | Unpriced PO for Cables (Keystone) | For Information | 2024-08-05 | 2024-08-05 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000547 | 2024-07-08 | 2024-07-08 | 0 | INF | For Information | 1 | "Unpriced PO for Cables (Keystone)" | INF
000548 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-M-0005 | 2024-07-08 | Unpriced PO for Sludge Pump (Netzsch) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000548&&001516 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for Sludge Pump (Netzsch) " && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" | INF
000549 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-M-0006 | 2024-07-08 | Unpriced PO for cPVC Pipes (George Fischer) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000549&&001517 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for cPVC Pipes (George Fischer)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" | INF
000550 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jun-2024) | For Information | 2024-08-05 | 2024-07-23 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | INF
000551 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0002 | 0 | 131242-WSW41-MS-G-0002 | 2024-07-08 | MSRA & SWP for Pre-Augering Work | Rev.0: Approved | 2024-08-05 | 2024-08-08 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000551 | 2024-07-08 | 2024-07-08 | 0 | APP | Approved | 1 | "MSRA & SWP for Pre-Augering Work" | APP
000552 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 0 | 131242-WSW41-RT-PM-0014 | 2024-07-09 | C4B Monthly Progress Report Number No.14 (06 24) | Rejected as requested by Contractor | 2024-08-06 | 2024-07-09 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000552 | 2024-07-09 | 2024-07-13 | 1 | REJ | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.14 (06 24)" | AWC
000552 | 01 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 1 | 131242-WSW41-RT-PM-0014 | 2024-07-13 | C4B Monthly Progress Report Number No.14 (06 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-08-01 | 2024-07-30 | 11 | Approved with Comments | YES | 2024-08-19 | NO | Resubmitted | 0 |  |  | 000552 | 2024-07-09 | 2024-07-13 | 1 | AWC | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.14 (06 24)" | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 0 | 131242-WST02-CL-P-0007 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | I | 0004 | 0 | 131242-WST02-DS-I-0004 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-07-09 | 0 | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-11-02 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-03-06 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 1 | 131242-WST02-CL-P-0007 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-21 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0025 | A | 131242-WST02-DR-M-0025 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0026 | A | 131242-WST02-DR-M-0026 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-11-02 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5021 | A | 131242-WST02-DR-I-5021 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-03-06 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5022 | A | 131242-WST02-DR-M-5022 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1200 | A | 131242-WST02-DR-M-1200 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1201 | B | 131242-WST02-DR-M-1201 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | B | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1202 | B | 131242-WST02-DR-M-1202 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | B | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1203 | A | 131242-WST02-DR-M-1203 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1204 | A | 131242-WST02-DR-M-1204 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1205 | A | 131242-WST02-DR-M-1205 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1206 | A | 131242-WST02-DR-M-1206 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1207 | A | 131242-WST02-DR-M-1207 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1208 | A | 131242-WST02-DR-M-1208 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1209 | A | 131242-WST02-DR-M-1209 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1210 | A | 131242-WST02-DR-M-1210 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3203 | A | 131242-WST02-DR-M-3203 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3204 | A | 131242-WST02-DR-M-3204 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3205 | A | 131242-WST02-DR-M-3205 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3206 | A | 131242-WST02-DR-M-3206 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3207 | A | 131242-WST02-DR-M-3207 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3208 | A | 131242-WST02-DR-M-3208 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3209 | A | 131242-WST02-DR-M-3209 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3210 | A | 131242-WST02-DR-M-3210 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0020 | 0 | 131242-WST02-DS-M-0020 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-08-22 | 2025-08-22 | 0 | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" | AWC
000554 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000 | 2024-07-10 | SSN UPS and Battery Room Layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 38 | Not Approved | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000191&&000554 | 2024-07-10 | 2025-05-15 | A | NAP | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" | AWC
000555 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001 | 2024-07-10 | SSN Process Non-Process room layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 38 | Not Approved | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000191&&000555 | 2024-07-10 | 2025-05-15 | A | NAP | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" | AWC
000556 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 0 | 131242-WSD11-RT-EK-0000 | 2024-07-10 | THP LPS Risk Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" | AWC
000556 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 1 | 131242-WSD11-RT-EK-0000 | 2024-10-28 | THP LPS Risk Assessment Report | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-12-08 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" | AWC
000556 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 2 | 131242-WSD11-RT-EK-0000 | 2025-07-07 | THP LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 41 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" | AWC
000557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 0 | 131242-WST02-RT-EK-0000 | 2024-07-10 | SSN LPS Risk Assessment Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 54 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | NAP | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" | AWC
000557 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 1 | 131242-WST02-RT-EK-0000 | 2024-10-24 | SSN LPS Risk Assessment Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-11-14 | 2024-12-08 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | NAP | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" | AWC
000557 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 2 | 131242-WST02-RT-EK-0000 | 2025-07-07 | SSN LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 41 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" | AWC
000558 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0028 | 0 | 131242-WSW41-MI-IM-0028 | 2024-07-10 | BIM Bi-Weekly Meeting Minutes 0028_20240626 | For Information | 2024-08-07 | 2024-08-30 | 37 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000558 | 2024-07-10 | 2024-07-10 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0028_20240626" | INF
000559 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018 | 2024-07-12 | Preliminary Design and Vendor Approval for Parabolic Screen | Rev 0: Approved | 2024-08-12 | 2024-09-02 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | APP | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | APP
000560 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 0 | 131242-WSW41-VI-M-0020 | 2024-07-12 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000560 | 2024-07-12 | 2024-09-16 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" | APP
000560 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 1 | 131242-WSW41-VI-M-0020 | 2024-09-16 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 1: Approved | 2024-10-04 | 2024-09-24 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000560 | 2024-07-12 | 2024-09-16 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" | APP
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0024 | 0 | 131242-WSW41-MI-C-0024 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" | INF
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0025 | 0 | 131242-WSW41-MI-C-0025 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" | INF
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0026 | 0 | 131242-WSW41-MI-C-0026 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" | INF
000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0027 | 0 | 131242-WSW41-MI-C-0027 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000562 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0027,0028_June" | INF
000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0028 | 0 | 131242-WSW41-MI-C-0028 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000562 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0027,0028_June" | INF
000563 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0010 | 0 | 131242-WSW41-QA-C-0010 | 2024-07-12 | Monthly Concrete Cube Records for Structural works (03 24) | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-08-12 | 2024-08-12 | 21 | Not Approved | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000563 | 2024-07-12 | 2024-07-12 | 0 | NAP | Not Approved | 1 | "Monthly Concrete Cube Records for Structural works (03 24)" | NAP
000564 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0002 | 0 | 131242-WSW41-MS-E-0002 | 2024-07-12 | MSRA, SWP for Electrical Work | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-12 | 2024-09-24 | 52 | Not Approved | YES | 2024-10-14 | NO | Resubmitted | 0 |  |  | 000564 | 2024-07-12 | 2024-07-12 | 0 | NAP | Not Approved | 1 | "MSRA, SWP for Electrical Work" | NAP
000565 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 0 | 131242-WSW41-MS-M-0001 | 2024-07-13 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000565 | 2024-07-13 | 2024-09-05 | 1 | AWC | Approved | 2 | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " | APP
000565 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 1 | 131242-WSW41-MS-M-0001 | 2024-09-05 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 1: Approved | 2024-09-25 | 2024-10-03 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000565 | 2024-07-13 | 2024-09-05 | 1 | APP | Approved | 2 | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " | APP
000566 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0020 | 0 | 131242-WST02-VI-I-0020 | 2024-07-13 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-12 | 2024-08-06 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000566 | 2024-07-13 | 2024-08-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | AWC
000566 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0020 | 1 | 131242-WST02-VI-I-0020 | 2024-08-16 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-05 | 2024-10-10 | 39 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  | Vendor Changed to Fox | 000566 | 2024-07-13 | 2024-08-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | AWC
000567 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004 | 2024-07-15 | Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area | Approved | 2024-08-13 | 2024-08-12 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000539&&000567 | 2024-07-02 | 2024-07-15 | 0 | APP | Approved | 2 | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " | APP
000568 | 00 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005 | 2024-07-15 | Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-13 | 2024-08-22 | 28 | Approved with Comments | YES | 2024-09-11 | NO | Resubmitted | 0 |  |  | 000540&&000568 | 2024-07-02 | 2024-07-15 | 0 | AWC | Approved with Comments | 2 | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " | AWC
000569 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 0 | 131242-WSD11-CD-I-0002 | 2024-07-16 | THP Instrument Lists | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-17 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000569 | 2024-07-16 | 2024-12-13 | 1 | NAP | Not Approved | 2 | "THP Instrument Lists" | NAP
000569 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 1 | 131242-WSD11-CD-I-0002 | 2024-12-13 | THP Instrument Lists | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-03 | 2025-02-13 | 44 | Not Approved | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000569 | 2024-07-16 | 2024-12-13 | 1 | NAP | Not Approved | 2 | "THP Instrument Lists" | NAP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | A | 131242-WSD11-DR-EP-7100 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | A | 131242-WSD11-DR-EP-7101 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | A | 131242-WSD11-DR-EP-7102 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | A | 131242-WSD11-DR-EP-7103 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | A | 131242-WSD11-DR-EP-7104 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | A | 131242-WSD11-DR-EP-7105 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | A | 131242-WSD11-DR-EP-7106 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | A | 131242-WSD11-DR-EP-7107 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | C | 131242-WSD11-DR-EI-7000 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | C | 131242-WSD11-DR-EI-7001 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | C | 131242-WSD11-DR-EI-7002 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | C | 131242-WSD11-DR-EI-7003 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | C | 131242-WSD11-DR-EI-7004 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | C | 131242-WSD11-DR-EI-7005 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | C | 131242-WSD11-DR-EI-7006 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | C | 131242-WSD11-DR-EI-7007 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | C | 131242-WSD11-DR-EI-7008 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | C | 131242-WSD11-DR-EI-7009 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | C | 131242-WSD11-DR-EI-7010 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | C | 131242-WSD11-DR-EI-7020 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | C | 131242-WSD11-DR-EI-7021 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | C | 131242-WSD11-DR-EI-7022 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | C | 131242-WSD11-DR-EI-7023 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | C | 131242-WSD11-DR-EI-7024 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | C | 131242-WSD11-DR-EI-7025 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | C | 131242-WSD11-DR-EI-7026 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | C | 131242-WSD11-DR-EI-7027 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | C | 131242-WSD11-DR-EI-7028 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | C | 131242-WSD11-DR-EI-7029 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | C | 131242-WSD11-DR-EI-7030 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | C | 131242-WSD11-DR-EI-7031 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | AWC | Approved | 3 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | C | 131242-WSD11-DR-EP-3000 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | C | 131242-WSD11-DR-EP-3001 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | C | 131242-WSD11-DR-EP-3002 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | C | 131242-WSD11-DR-EP-3003 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | C | 131242-WSD11-DR-EP-3004 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | C | 131242-WSD11-DR-EP-3005 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | C | 131242-WSD11-DR-EP-3006 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | C | 131242-WSD11-DR-EP-3007 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | C | 131242-WSD11-DR-EP-3008 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | C | 131242-WSD11-DR-EP-3009 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | C | 131242-WSD11-DR-EP-3010 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | C | 131242-WSD11-DR-EP-3011 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | C | 131242-WSD11-DR-EP-3012 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | C | 131242-WSD11-DR-EP-3013 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | C | 131242-WSD11-DR-EP-7100 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | C | 131242-WSD11-DR-EP-7101 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | C | 131242-WSD11-DR-EP-7102 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | C | 131242-WSD11-DR-EP-7103 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | C | 131242-WSD11-DR-EP-7104 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | C | 131242-WSD11-DR-EP-7105 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | C | 131242-WSD11-DR-EP-7106 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | C | 131242-WSD11-DR-EP-7107 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | C | 131242-WSD11-DR-EP-7108 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | C | 131242-WSD11-DR-EP-7109 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | D | 131242-WSD11-DR-EI-7000 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | D | 131242-WSD11-DR-EI-7001 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | D | 131242-WSD11-DR-EI-7002 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | D | 131242-WSD11-DR-EI-7003 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | D | 131242-WSD11-DR-EI-7004 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | D | 131242-WSD11-DR-EI-7005 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | D | 131242-WSD11-DR-EI-7006 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | D | 131242-WSD11-DR-EI-7007 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | D | 131242-WSD11-DR-EI-7008 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | D | 131242-WSD11-DR-EI-7009 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | D | 131242-WSD11-DR-EI-7010 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | D | 131242-WSD11-DR-EI-7011 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2025-03-07 | 2025-10-23 | E | AWC | Approved | 2 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | D | 131242-WSD11-DR-EI-7020 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | D | 131242-WSD11-DR-EI-7021 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | D | 131242-WSD11-DR-EI-7022 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | D | 131242-WSD11-DR-EI-7023 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | D | 131242-WSD11-DR-EI-7024 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | D | 131242-WSD11-DR-EI-7025 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | D | 131242-WSD11-DR-EI-7026 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | D | 131242-WSD11-DR-EI-7027 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | D | 131242-WSD11-DR-EI-7028 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | D | 131242-WSD11-DR-EI-7029 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | D | 131242-WSD11-DR-EI-7030 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | D | 131242-WSD11-DR-EI-7031 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | AWC | Approved | 3 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | D | 131242-WSD11-DR-EP-3000 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | D | 131242-WSD11-DR-EP-3001 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | D | 131242-WSD11-DR-EP-3002 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | D | 131242-WSD11-DR-EP-3003 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | D | 131242-WSD11-DR-EP-3004 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | D | 131242-WSD11-DR-EP-3005 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | D | 131242-WSD11-DR-EP-3006 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | D | 131242-WSD11-DR-EP-3007 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | D | 131242-WSD11-DR-EP-3008 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | D | 131242-WSD11-DR-EP-3009 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | D | 131242-WSD11-DR-EP-3010 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | D | 131242-WSD11-DR-EP-3011 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | D | 131242-WSD11-DR-EP-3012 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | D | 131242-WSD11-DR-EP-3013 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | D | 131242-WSD11-DR-EP-7100 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | D | 131242-WSD11-DR-EP-7101 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | D | 131242-WSD11-DR-EP-7102 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | D | 131242-WSD11-DR-EP-7103 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | D | 131242-WSD11-DR-EP-7104 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | D | 131242-WSD11-DR-EP-7105 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | D | 131242-WSD11-DR-EP-7106 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | D | 131242-WSD11-DR-EP-7107 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | D | 131242-WSD11-DR-EP-7108 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | D | 131242-WSD11-DR-EP-7109 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | E | 131242-WSD11-DR-EI-7000 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | E | 131242-WSD11-DR-EI-7001 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | E | 131242-WSD11-DR-EI-7002 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | E | 131242-WSD11-DR-EI-7003 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | E | 131242-WSD11-DR-EI-7004 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | E | 131242-WSD11-DR-EI-7005 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | E | 131242-WSD11-DR-EI-7006 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | E | 131242-WSD11-DR-EI-7007 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | E | 131242-WSD11-DR-EI-7008 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | E | 131242-WSD11-DR-EI-7009 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | E | 131242-WSD11-DR-EI-7010 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | E | 131242-WSD11-DR-EI-7011 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2025-03-07 | 2025-10-23 | E | APP | Approved | 2 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | E | 131242-WSD11-DR-EI-7020 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | E | 131242-WSD11-DR-EI-7021 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | E | 131242-WSD11-DR-EI-7022 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | E | 131242-WSD11-DR-EI-7023 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | E | 131242-WSD11-DR-EI-7024 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | E | 131242-WSD11-DR-EI-7025 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | E | 131242-WSD11-DR-EI-7026 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | E | 131242-WSD11-DR-EI-7027 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | E | 131242-WSD11-DR-EI-7028 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | E | 131242-WSD11-DR-EI-7029 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | E | 131242-WSD11-DR-EI-7030 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | E | 131242-WSD11-DR-EI-7031 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | APP | Approved | 3 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | E | 131242-WSD11-DR-EP-3000 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | E | 131242-WSD11-DR-EP-3001 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | E | 131242-WSD11-DR-EP-3002 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | E | 131242-WSD11-DR-EP-3003 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | E | 131242-WSD11-DR-EP-3004 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | E | 131242-WSD11-DR-EP-3005 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | E | 131242-WSD11-DR-EP-3006 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | E | 131242-WSD11-DR-EP-3007 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | E | 131242-WSD11-DR-EP-3008 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | E | 131242-WSD11-DR-EP-3009 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | E | 131242-WSD11-DR-EP-3010 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | E | 131242-WSD11-DR-EP-3011 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | E | 131242-WSD11-DR-EP-3012 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | E | 131242-WSD11-DR-EP-3013 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | E | 131242-WSD11-DR-EP-7100 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | E | 131242-WSD11-DR-EP-7101 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | E | 131242-WSD11-DR-EP-7102 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | E | 131242-WSD11-DR-EP-7103 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | E | 131242-WSD11-DR-EP-7104 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | E | 131242-WSD11-DR-EP-7105 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | E | 131242-WSD11-DR-EP-7106 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | E | 131242-WSD11-DR-EP-7107 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | E | 131242-WSD11-DR-EP-7108 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | E | 131242-WSD11-DR-EP-7109 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | A | 131242-WSD11-DR-EI-7000 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | A | 131242-WSD11-DR-EI-7001 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | A | 131242-WSD11-DR-EI-7002 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | A | 131242-WSD11-DR-EI-7003 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | A | 131242-WSD11-DR-EI-7004 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | A | 131242-WSD11-DR-EI-7005 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | A | 131242-WSD11-DR-EI-7006 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | A | 131242-WSD11-DR-EI-7007 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | A | 131242-WSD11-DR-EI-7008 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | A | 131242-WSD11-DR-EI-7020 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | A | 131242-WSD11-DR-EI-7021 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | A | 131242-WSD11-DR-EI-7022 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | A | 131242-WSD11-DR-EI-7023 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | A | 131242-WSD11-DR-EI-7024 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | A | 131242-WSD11-DR-EI-7025 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | A | 131242-WSD11-DR-EI-7026 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | A | 131242-WSD11-DR-EI-7027 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" | APP
000571 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#571 Cmt Reply Sht | NA | 131242-WSD11-NA-NA-S#571 Cmt Reply Sht | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000571 | 2024-10-01 | 2024-10-01 | NA | NAP | Not Approved | 1 | "THP SLD" | NAP
000572 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302 | A | 131242-WSD11-DR-S-5302 | 2024-07-17 | IFC of BSB Silo Area Pump Plinth Details | For Information | 2024-08-15 | 2024-08-28 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000572 | 2024-07-17 | 2024-07-17 | A | INF | For Information | 1 | "IFC of BSB Silo Area Pump Plinth Details " | INF
000573 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5501 | A | 131242-WST02-DR-S-5501 | 2024-07-17 | IFC of SSN Electrical Building Transformer Plinth Details | Rev.0: Approved with comments. Revise and resubmit. | 2024-08-15 | 2024-09-14 | 43 | Approved with Comments | YES | 2024-10-03 | NO | Resubmitted | 0 |  |  | 000573 | 2024-07-17 | 2024-07-17 | A | AWC | Approved with Comments | 1 | "IFC of SSN Electrical Building Transformer Plinth Details " | AWC
000574 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0006 | 0 | 131242-WSW41-VI-S-0006 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000574 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | A | 131242-WSD11-DR-EP-3000 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | A | 131242-WSD11-DR-EP-3001 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | A | 131242-WSD11-DR-EP-3002 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | A | 131242-WSD11-DR-EP-3003 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | A | 131242-WSD11-DR-EP-3004 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | A | 131242-WSD11-DR-EP-3005 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | A | 131242-WSD11-DR-EP-3006 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | A | 131242-WSD11-DR-EP-3007 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | A | 131242-WSD11-DR-EP-3008 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | A | 131242-WSD11-DR-EP-3009 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" | APP
000575 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#575 Cmt Reply Sht | NA | 131242-WSD11-NA-NA-S#575 Cmt Reply Sht | 2024-10-01 | THP MCC Outline Drawing | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000575 | 2024-10-01 | 2024-10-01 | NA | NAP | Not Approved | 1 | "THP MCC Outline Drawing" | NAP
000576 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0007 | 0 | 131242-WSW41-VI-S-0007 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000576 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | APP
000577 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0017 | 0 | 131242-WSW41-VI-C-0017 | 2024-07-17 | Vendor Approval for PVC Lining System - (Linabond) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000577 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval for PVC Lining System - (Linabond)" | APP
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | C | 131242-WST02-DR-S-1000_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | C | 131242-WST02-DR-S-1006_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | C | 131242-WST02-DR-S-1007_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | C | 131242-WST02-DR-S-1008_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | C | 131242-WST02-DR-S-1013_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | B | 131242-WST02-DR-S-1014_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | C | 131242-WST02-DR-S-1015_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | C | 131242-WST02-DR-S-1016_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | C | 131242-WST02-DR-S-1017_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | C | 131242-WST02-DR-S-1018_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | C | 131242-WST02-DR-S-1019_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | C | 131242-WST02-DR-S-1020_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | C | 131242-WST02-DR-S-1021_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | C | 131242-WST02-DR-S-1022_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | C | 131242-WST02-DR-S-3005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | C | 131242-WST02-DR-S-3008_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | C | 131242-WST02-DR-S-3009_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | C | 131242-WST02-DR-S-5005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | C | 131242-WST02-DR-S-5006_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | C | 131242-WST02-DR-S-7002_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | C | 131242-WST02-DR-S-7003_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | C | 131242-WST02-DR-S-7004_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | C | 131242-WST02-DR-S-7005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | C | 131242-WST02-DR-S-8003_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | INF
000579 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0001 | 0 | 131242-WST02-CD-I-0001 | 2024-07-22 | SSN PLC I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-17 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | AWC
000579 | 01 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 1 | 131242-WST02-CD-I-0001 | 2024-11-06 | SSN RIO 0201 I/O List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-26 | 2024-12-18 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | AWC
000579 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 2 | 131242-WST02-CD-I-0001 | 2025-03-06 | SSN RIO 0201 I/O List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-26 | 2025-05-07 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | AWC
000579 | 03 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 3 | 131242-WST02-CD-I-0001 | 2025-06-16 | SSN RIO 0201 I/O List | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | AWC | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | AWC
000579 | 04 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 4 | 131242-WST02-CD-I-0001 | 2025-08-19 | SSN RIO 0201 I/O List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-15 | 19 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | AWC | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | AWC
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1191 | A | 131242-WSD11-DR-M-1191 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 | 2025-02-26 | To check with relevent area discipline (Target 28 Feb 2025) | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" | AWC
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3190 | A | 131242-WSD11-DR-M-3190 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" | AWC
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4000 | A | 131242-WSD11-DR-M-4000 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" | AWC
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9000 | A | 131242-WSD11-DR-M-9000 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" | AWC
000581 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 3100 | A.1 | 131242-WSW41-SD-S-3100 | 2024-07-23 | Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details | For Information | 2024-08-21 | 2024-08-14 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000581&&001085&&001906 | 2024-07-23 | 2025-12-17 | X | INF | Not Approved | 3 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
000582 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 1150 | A.1 | 131242-WSW41-SD-S-1150 | 2024-07-23 | Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details | For Information | 2024-08-21 | 2024-08-13 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000582 | 2024-07-23 | 2024-07-23 | A.1 | INF | For Information | 1 | "Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details" | INF
000583 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 0 | 131242-WSW41-VI-I-0003 | 2024-07-24 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2024-08-22 | 2024-09-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | NAP | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | AWC
000583 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 1 | 131242-WSW41-VI-I-0003 | 2024-11-29 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-19 | 2025-02-25 | 62 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | NAP | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | AWC
000583 | 02 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 2 | 131242-WSW41-VI-I-0003 | 2025-03-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-08 | 2025-03-25 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | AWC
000583 | 03 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 3 | 131242-WSW41-VI-I-0003 | 2025-06-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-09 | 2025-07-10 | 15 | Approved with Comments | YES | 2025-07-30 | NO | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | AWC
000584 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0027 | 0 | 131242-WSW41-MI-P-0027 | 2024-07-24 | Process & MEICA Meeting Minutes 0027_20240704 | Rev 0: For Information | 2024-08-22 | 2024-08-29 | 26 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000584 | 2024-07-24 | 2024-07-24 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0027_20240704" | INF
000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0013 | 0 | 131242-WSW41-SP-C-0013 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000585 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | INF
000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0014 | 0 | 131242-WSW41-SP-C-0014 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000585 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | INF
000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0016 | 0 | 131242-WSW41-SP-C-0016 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000586 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | INF
000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0017 | 0 | 131242-WSW41-SP-C-0017 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000586 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | INF
000587 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0008 | 0 | 131242-WSW41-VI-S-0008 | 2024-07-25 | Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd. | Approved | 2024-08-23 | 2024-08-12 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000587 | 2024-07-25 | 2024-07-25 | 0 | APP | Approved | 1 | "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | APP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" | AWC
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" | AWC
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-12 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" | AWC
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" | AWC
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-10-29 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | AWC | Approved with Comments | 3 | "THP URA Submission" | AWC
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | AWC | Approved with Comments | 3 | "THP URA Submission" | AWC
000589 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 0 | 131242-WST02-VI-E-0007 | 2024-07-26 | Vendor Approval of Earthing System & LPS Material | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached sheet for comments | 2024-08-26 | 2024-08-05 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000589 | 2024-07-26 | 2024-09-02 | 1 | AWC | Approved | 2 | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" | APP
000589 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 1 | 131242-WST02-VI-E-0007 | 2024-09-02 | Vendor Approval of Earthing System & LPS Material (Heng) | Rev 1: Approved. | 2024-09-20 | 2024-10-29 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000589 | 2024-07-26 | 2024-09-02 | 1 | APP | Approved | 2 | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" | APP
000590 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 0 | 131242-WST02-DS-E-0004 | 2024-07-27 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000590 | 2024-07-27 | 2025-04-09 | 2 | REJ | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | AWC
000590 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 1 | 131242-WST02-DS-E-0004 | 2024-12-02 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-20 | 2025-01-16 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000590 | 2024-07-27 | 2025-04-09 | 2 | AWC | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | AWC
000590 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 2 | 131242-WST02-DS-E-0004 | 2025-04-09 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-29 | 2025-05-08 | 21 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  | Pending reply from Sunlight. Will follow-up with Sunlight. | 000590 | 2024-07-27 | 2025-04-09 | 2 | AWC | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | AWC
000591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 0 | 131242-WSD11-CL-P-0003 | 2024-07-28 | PLant Drain Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-08-26 | 2024-09-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000591 | 2024-07-28 | 2024-10-21 | 1 | NAP | Approved | 2 | "PLant Drain Hydraulic Calculation" | APP
000591 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 1 | 131242-WSD11-CL-P-0003 | 2024-10-21 | PLant Drain Hydraulic Calculation | Rev 1: Approved | 2024-11-11 | 2024-11-15 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000591 | 2024-07-28 | 2024-10-21 | 1 | APP | Approved | 2 | "PLant Drain Hydraulic Calculation" | APP
000592 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0006 | 0 | 131242-WST02-VI-E-0006 | 2024-07-28 | Vendor Approval of SS Cable Ladder, Trays and Accessories | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | 13 | Approved with Comments | YES | 2024-09-04 | NO | Resubmitted | 0 |  | To follow-up with UNITED ULI. | 000592 | 2024-07-28 | 2024-07-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SS Cable Ladder, Trays and Accessories" | AWC
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5351 | 0 | 131242-WST02-DS-M-5351 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5361 | 0 | 131242-WST02-DS-M-5361 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5371 | 0 | 131242-WST02-DS-M-5371 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5381 | 0 | 131242-WST02-DS-M-5381 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5351 | 1 | 131242-WST02-DS-M-5351 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5361 | 1 | 131242-WST02-DS-M-5361 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5371 | 1 | 131242-WST02-DS-M-5371 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5381 | 1 | 131242-WST02-DS-M-5381 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" | AWC
000594 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0003 | 0 | 131242-WSW41-PO-E-0003 | 2024-07-29 | Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight) | Rev 0: For Information. | 2024-08-27 | 2024-08-05 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000594 | 2024-07-29 | 2024-07-29 | 0 | INF | For Information | 1 | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" | INF
000595 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0007 | 0 | 131242-WSW41-PO-M-0007 | 2024-07-30 | Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen) | For Information | 2024-08-28 | 2024-08-29 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000595 | 2024-07-30 | 2024-07-30 | 0 | INF | For Information | 1 | "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | INF
000596 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0035 | 0 | 131242-WSW41-LT-PM-0035 | 2024-07-30 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024 | Please refer to S.O. Correspondence No.229. | 2024-08-28 | 2024-10-07 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000596 | 2024-07-30 | 2024-07-30 | 0 | APP | Approved | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024" | APP
000597 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 0 | 131242-WSD11-CL-P-0006 | 2024-07-30 | Air Compressor Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-04 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000597 | 2024-07-30 | 2024-09-30 | 1 | AWC | Approved with Comments | 2 | "Air Compressor Pressure Loss Calculation" | AWC
000597 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 1 | 131242-WSD11-CL-P-0006 | 2024-09-30 | Air Compressor Pressure Loss Calculation | Rev 1: Approved with Comments. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 26 | Approved with Comments | YES | 2024-11-25 | NO | Resubmitted | 0 |  |  | 000597 | 2024-07-30 | 2024-09-30 | 1 | AWC | Approved with Comments | 2 | "Air Compressor Pressure Loss Calculation" | AWC
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5009 | A | 131242-WST02-DR-M-5009 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 | 2025-03-07 | Shall update and submit under as built drawing | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" | AWC
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5010 | A | 131242-WST02-DR-M-5010 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" | AWC
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7008 | A | 131242-WST02-SH-M-7008 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" | AWC
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7009 | A | 131242-WST02-SH-M-7009 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" | AWC
000599 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 0 | 131242-WSW41-VI-I-0004 | 2024-07-30 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-28 | 2024-10-10 | 52 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000599 | 2024-07-30 | 2024-11-02 | 1 | NAP | Not Approved | 2 | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" | NAP
000599 | 01 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 1 | 131242-WSW41-VI-I-0004 | 2024-11-02 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-21 | 2024-12-18 | 32 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000599 | 2024-07-30 | 2024-11-02 | 1 | NAP | Not Approved | 2 | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" | NAP
000600 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0004 | 0 | 131242-WSW41-QA-M-0004 | 2024-07-31 | Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings | Rev 0: Approved | 2024-08-29 | 2024-09-02 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000600 | 2024-07-31 | 2024-07-31 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | APP
000601 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 0 | 131242-WSD11-SP-I-0001 | 2024-07-31 | THP Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-29 | 2024-10-09 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" | AWC
000601 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 1 | 131242-WSD11-SP-I-0001 | 2025-05-19 | THP Functional Design Specification | Rev.1: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-06-06 | 2025-07-04 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" | AWC
000601 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 2 | 131242-WSD11-SP-I-0001 | 2025-08-12 | THP Functional Design Specification | Rev.2: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-09-01 | 2025-10-08 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" | AWC
000602 | 00 | Low | EICA | NA | 131242 | WSD11 | SP | I | 0003 | 0 | 131242-WSD11-SP-I-0003 | 2024-07-31 | THP Alarm List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-29 | 2024-11-08 | 72 | Not Approved | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000602 | 2024-07-31 | 2024-07-31 | 0 | NAP | Not Approved | 1 | "THP Alarm List" | NAP
000603 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1000 | 0 | 131242-WST02-CL-M-1000 | 2024-07-31 | SSN Underground Piping Stress Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-08-29 | 2024-09-02 | 23 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  | The Only comment is to get PE endorsement (Mech Piping PE) | 000603 | 2024-07-31 | 2024-07-31 | 0 | AWC | Approved with Comments | 1 | "SSN Underground Piping Stress Calculation Report" | AWC
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | A | 131242-WST02-DR-EI-7000 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | A | 131242-WST02-DR-EI-7001 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | A | 131242-WST02-DR-EI-7002 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | A | 131242-WST02-DR-EI-7003 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | A | 131242-WST02-DR-EI-7004 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | A | 131242-WST02-DR-EI-7005 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | A | 131242-WST02-DR-EI-7006 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | A | 131242-WST02-DR-EI-7007 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | A | 131242-WST02-DR-EI-7008 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | A | 131242-WST02-DR-EI-7009 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | A | 131242-WST02-DR-EI-7010 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | A | 131242-WST02-DR-EI-7011 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | REJ | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | NAP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | A | 131242-WST02-DR-EI-7020 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | A | 131242-WST02-DR-EI-7021 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | A | 131242-WST02-DR-EI-7022 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | A | 131242-WST02-DR-EI-7023 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | A | 131242-WST02-DR-EI-7024 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | A | 131242-WST02-DR-EI-7025 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | A | 131242-WST02-DR-EI-7026 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | A | 131242-WST02-DR-EI-7027 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | A | 131242-WST02-DR-EI-7028 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | A | 131242-WST02-DR-EI-7029 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | A | 131242-WST02-DR-EI-7030 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | REJ | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | NAP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | A | 131242-WST02-DR-EP-7100 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | A | 131242-WST02-DR-EP-7101 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | A | 131242-WST02-DR-EP-7102 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | A | 131242-WST02-DR-EP-7103 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | A | 131242-WST02-DR-EP-7104 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | A | 131242-WST02-DR-EP-7105 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | A | 131242-WST02-DR-EP-7106 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | A | 131242-WST02-DR-EP-7107 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | A | 131242-WST02-DR-EP-7108 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | A | 131242-WST02-DR-EP-7109 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | B | 131242-WST02-DR-EI-7000 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | B | 131242-WST02-DR-EI-7001 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | B | 131242-WST02-DR-EI-7002 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | B | 131242-WST02-DR-EI-7003 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | B | 131242-WST02-DR-EI-7004 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | B | 131242-WST02-DR-EI-7005 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | B | 131242-WST02-DR-EI-7006 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | B | 131242-WST02-DR-EI-7007 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | B | 131242-WST02-DR-EI-7008 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | B | 131242-WST02-DR-EI-7009 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | B | 131242-WST02-DR-EI-7010 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | B | 131242-WST02-DR-EI-7011 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | NAP | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | NAP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | B | 131242-WST02-DR-EI-7020 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | B | 131242-WST02-DR-EI-7021 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | B | 131242-WST02-DR-EI-7022 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | B | 131242-WST02-DR-EI-7023 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | B | 131242-WST02-DR-EI-7024 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | B | 131242-WST02-DR-EI-7025 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | B | 131242-WST02-DR-EI-7026 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | B | 131242-WST02-DR-EI-7027 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | B | 131242-WST02-DR-EI-7028 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | B | 131242-WST02-DR-EI-7029 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | B | 131242-WST02-DR-EI-7030 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | NAP | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | NAP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | B | 131242-WST02-DR-EP-3000 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | B | 131242-WST02-DR-EP-3001 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | B | 131242-WST02-DR-EP-3002 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | B | 131242-WST02-DR-EP-3003 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | B | 131242-WST02-DR-EP-3004 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | B | 131242-WST02-DR-EP-3005 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | B | 131242-WST02-DR-EP-3006 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | B | 131242-WST02-DR-EP-3007 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | B | 131242-WST02-DR-EP-7100 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | B | 131242-WST02-DR-EP-7101 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | B | 131242-WST02-DR-EP-7102 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | B | 131242-WST02-DR-EP-7103 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | B | 131242-WST02-DR-EP-7104 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | B | 131242-WST02-DR-EP-7105 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | B | 131242-WST02-DR-EP-7106 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | B | 131242-WST02-DR-EP-7107 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | B | 131242-WST02-DR-EP-7108 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | B | 131242-WST02-DR-EP-7109 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | C | 131242-WST02-DR-EI-7000 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | C | 131242-WST02-DR-EI-7001 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | C | 131242-WST02-DR-EI-7002 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | C | 131242-WST02-DR-EI-7003 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | C | 131242-WST02-DR-EI-7004 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | C | 131242-WST02-DR-EI-7005 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | C | 131242-WST02-DR-EI-7006 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | C | 131242-WST02-DR-EI-7007 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | C | 131242-WST02-DR-EI-7008 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | C | 131242-WST02-DR-EI-7009 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | C | 131242-WST02-DR-EI-7010 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | C | 131242-WST02-DR-EI-7020 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | C | 131242-WST02-DR-EI-7021 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | C | 131242-WST02-DR-EI-7022 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | C | 131242-WST02-DR-EI-7023 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | C | 131242-WST02-DR-EI-7024 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | C | 131242-WST02-DR-EI-7025 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | C | 131242-WST02-DR-EI-7026 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | C | 131242-WST02-DR-EI-7027 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | C | 131242-WST02-DR-EI-7028 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | C | 131242-WST02-DR-EI-7029 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | C | 131242-WST02-DR-EP-3000 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | C | 131242-WST02-DR-EP-3001 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | C | 131242-WST02-DR-EP-3002 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | C | 131242-WST02-DR-EP-3003 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | C | 131242-WST02-DR-EP-3004 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | C | 131242-WST02-DR-EP-3005 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | C | 131242-WST02-DR-EP-3006 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | C | 131242-WST02-DR-EP-3007 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | C | 131242-WST02-DR-EP-7100 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | C | 131242-WST02-DR-EP-7101 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | C | 131242-WST02-DR-EP-7102 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | C | 131242-WST02-DR-EP-7103 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | C | 131242-WST02-DR-EP-7104 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | C | 131242-WST02-DR-EP-7105 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | C | 131242-WST02-DR-EP-7106 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | C | 131242-WST02-DR-EP-7107 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | C | 131242-WST02-DR-EP-7108 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | C | 131242-WST02-DR-EP-7109 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | D | 131242-WST02-DR-EI-7000 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | D | 131242-WST02-DR-EI-7001 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | D | 131242-WST02-DR-EI-7002 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | D | 131242-WST02-DR-EI-7003 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | D | 131242-WST02-DR-EI-7004 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | D | 131242-WST02-DR-EI-7005 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | D | 131242-WST02-DR-EI-7006 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | D | 131242-WST02-DR-EI-7007 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | D | 131242-WST02-DR-EI-7008 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | D | 131242-WST02-DR-EI-7009 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | D | 131242-WST02-DR-EI-7010 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | D | 131242-WST02-DR-EI-7020 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | D | 131242-WST02-DR-EI-7021 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | D | 131242-WST02-DR-EI-7022 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | D | 131242-WST02-DR-EI-7023 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | D | 131242-WST02-DR-EI-7024 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | D | 131242-WST02-DR-EI-7025 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | D | 131242-WST02-DR-EI-7026 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | D | 131242-WST02-DR-EI-7027 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | D | 131242-WST02-DR-EI-7028 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | D | 131242-WST02-DR-EI-7029 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | D | 131242-WST02-DR-EP-3000 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | D | 131242-WST02-DR-EP-3001 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | D | 131242-WST02-DR-EP-3002 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | D | 131242-WST02-DR-EP-3003 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | D | 131242-WST02-DR-EP-3004 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | D | 131242-WST02-DR-EP-3005 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | D | 131242-WST02-DR-EP-3006 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | D | 131242-WST02-DR-EP-3007 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | D | 131242-WST02-DR-EP-7100 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | D | 131242-WST02-DR-EP-7101 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | D | 131242-WST02-DR-EP-7102 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | D | 131242-WST02-DR-EP-7103 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | D | 131242-WST02-DR-EP-7104 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | D | 131242-WST02-DR-EP-7105 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | D | 131242-WST02-DR-EP-7106 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | D | 131242-WST02-DR-EP-7107 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | D | 131242-WST02-DR-EP-7108 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | D | 131242-WST02-DR-EP-7109 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" | APP
000606 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 0 | 131242-WST02-VI-E-0008 | 2024-08-01 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-24 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000606 | 2024-08-01 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" | AWC
000606 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 1 | 131242-WST02-VI-E-0008 | 2024-10-28 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 1: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2024-11-18 | 2024-11-24 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000606 | 2024-08-01 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" | AWC
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | A | 131242-WST02-DR-EP-3000 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | A | 131242-WST02-DR-EP-3001 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | A | 131242-WST02-DR-EP-3002 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | A | 131242-WST02-DR-EP-3003 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | A | 131242-WST02-DR-EP-3004 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | A | 131242-WST02-DR-EP-3005 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | A | 131242-WST02-DR-EP-3006 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | A | 131242-WST02-DR-EP-3007 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | APP
000608 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0008 | 0 | 131242-WSW41-PO-M-0008 | 2024-08-01 | Unpriced PO for Centrifugal Pump (KSB) | For Information | 2024-08-30 | 2024-08-29 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000608 | 2024-08-01 | 2024-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Centrifugal Pump (KSB)" | INF
000609 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0009 | 0 | 131242-WSW41-PO-M-0009 | 2024-08-01 | Unpriced PO for FRP Tank (Jizhou Zhongyi) | For Information | 2024-08-30 | 2024-08-29 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000609 | 2024-08-01 | 2024-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for FRP Tank (Jizhou Zhongyi)" | INF
000610 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | K | 2001 | 0 | 131242-WST02-VI-K-2001 | 2024-08-01 | LPS Sample Materials – U-Clamp Connector | Rev 0: Approved. Please refer to attached sheet for comments | 2024-08-30 | 2024-08-05 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000610 | 2024-08-01 | 2024-08-01 | 0 | APP | Approved | 1 | "LPS Sample Materials – U-Clamp Connector" | APP
000611 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 0 | 131242-WSW41-SP-C-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-02 | 2024-08-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000611 | 2024-08-02 | 2024-08-02 | 0 | AWC | Approved with Comments | 2 | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | AWC
000611 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 1 | 131242-WSW41-SP-C-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Approved | 2024-08-23 | 2024-09-17 | 32 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000611 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved with Comments | 2 | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | AWC
000612 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0005 | 0 | 131242-WSW41-QA-M-0005 | 2024-08-02 | Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings | Rev 0: Approved | 2024-09-02 | 2024-09-02 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000612 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | APP
000613 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0013 | 0 | 131242-WSW41-PC-W-0013 | 2024-08-02 | Payment Claim No.13 | Rev(0): Approved. Please refer to S.O. correspondence no. 0196 dated 5 August 2024. | 2024-09-02 | 2024-08-16 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000613 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "Payment Claim No.13" | APP
000614 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0036 | 0 | 131242-WSW41-LT-PM-0036 | 2024-08-02 | NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions | Please refer to S.O. Correspondence No.229. | 2024-09-02 | 2024-10-07 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000614 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions" | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.2 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | AWC | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | AWC | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-16 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.2 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | APP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | APP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | APP
000616 | 00 | Qili | Process | NA | 131242 | WST02 | CL | M | 0002 | 0 | 131242-WST02-CL-M-0002 | 2024-08-05 | Strength Calculation for Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-02 | 20 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 | 2025-02-28 | Pending MP updates | 000616 | 2024-08-05 | 2024-08-05 | 0 | AWC | Approved with Comments | 1 | "Strength Calculation for Biomass Separator" | AWC
000617 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0009 | 0 | 131242-WSW41-PS-HS-0009 | 2024-08-05 | Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024 | For Information | 2024-09-03 | 2024-08-21 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000617 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" | INF
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | A | 131242-WSD11-DR-M-5051 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | A | 131242-WSD11-DR-M-5052 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | A | 131242-WSD11-DR-M-5053 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | A | 131242-WSD11-DR-M-5054 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | A | 131242-WSD11-DR-M-5071 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | A | 131242-WSD11-DR-M-5072 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | A | 131242-WSD11-DR-M-5073 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | A | 131242-WSD11-DR-M-5081 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | B | 131242-WSD11-DR-M-5051 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 | All comments on 2D Drawing (Mech/Elec.) was closed, minor cmt on 3D, need QA/QC checklist, Drafting team will follow up..-> in 1 to 2 weeks | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | B | 131242-WSD11-DR-M-5052 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | B | 131242-WSD11-DR-M-5053 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | B | 131242-WSD11-DR-M-5054 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | B | 131242-WSD11-DR-M-5071 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | B | 131242-WSD11-DR-M-5072 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | B | 131242-WSD11-DR-M-5073 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | B | 131242-WSD11-DR-M-5081 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | C | 131242-WSD11-DR-M-5051 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-02 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | C | 131242-WSD11-DR-M-5052 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | C | 131242-WSD11-DR-M-5053 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | C | 131242-WSD11-DR-M-5054 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | C | 131242-WSD11-DR-M-5071 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | C | 131242-WSD11-DR-M-5072 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | C | 131242-WSD11-DR-M-5073 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | C | 131242-WSD11-DR-M-5081 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | AWC
000619 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0006 | 0 | 131242-WSW41-RT-C-0006 | 2024-08-05 | Bored Piling Pile Eccentricity Reports (ECC 01 to 07) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Not Approved | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000619 | 2024-08-05 | 2024-08-05 | 0 | NAP | Not Approved | 1 | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" | NAP
000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0015 | 0 | 131242-WSW41-SP-C-0015 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000620 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | INF
000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0018 | 0 | 131242-WSW41-SP-C-0018 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000620 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | INF
000621 | 00 | Qili | Process | NA | 131242 | WST02 | MM | P | 0001 | 0 | 131242-WST02-MM-P-0001 | 2024-08-05 | SSN Reactor Floor flat Design Memo | For Information | 2024-09-03 | 2024-08-21 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000621 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "SSN Reactor Floor flat Design Memo" | INF
000622 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0028 | 0 | 131242-WSW41-MI-P-0028 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000622 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | INF
000622 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0029 | 0 | 131242-WSW41-MI-P-0029 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000622 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | INF
000623 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 0 | 131242-WSW41-QA-E-0001 | 2024-08-06 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-10-29 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000623 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 1 | 131242-WSW41-QA-E-0001 | 2024-11-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-14 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000623 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 2 | 131242-WSW41-QA-E-0001 | 2025-01-16 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000623 | 03 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 3 | 131242-WSW41-QA-E-0001 | 2025-02-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 3: Approved. | 2025-03-13 | 2025-04-27 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000623 | 04 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 4 | 131242-WSW41-QA-E-0001 | 2025-07-03 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 4: Approved with comments. To revise and resubmit. | 2025-07-23 | 2025-09-15 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000623 | 05 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 5 | 131242-WSW41-QA-E-0001 | 2025-10-08 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 5: Approved | 2025-10-28 | 2026-02-20 | 97 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | APP
000624 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 0 | 131242-WSW41-QA-M-0003 | 2024-08-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 0: Not approved - Revise and Resubmit | 2024-09-04 | 2024-09-06 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | APP
000624 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 1 | 131242-WSW41-QA-M-0003 | 2024-10-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 1: Not approved - Revise and Resubmit | 2024-10-29 | 2024-10-25 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | APP
000624 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 2 | 131242-WSW41-QA-M-0003 | 2024-11-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 2: Approved | 2024-12-11 | 2024-12-05 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | APP
000625 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0007 | 0 | 131242-WSW41-QA-M-0007 | 2024-08-06 | FAT Procedure for Air Receiver and Air Dryer (Compressor air system) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-09-04 | 21 | Approved with Comments | YES | 2024-09-24 | NO | Resubmitted | 0 |  |  | 000625 | 2024-08-06 | 2024-08-06 | 0 | AWC | Approved with Comments | 1 | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" | AWC
000626 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 0 | 131242-WST02-DS-E-0000 | 2024-08-07 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-05 | 2024-10-29 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000626 | 2024-08-07 | 2024-12-19 | 1 | AWC | Approved with Comments | 2 | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | AWC
000626 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 1 | 131242-WST02-DS-E-0000 | 2024-12-19 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-01-16 | 20 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000626 | 2024-08-07 | 2024-12-19 | 1 | AWC | Approved with Comments | 2 | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | AWC
000627 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0011 | 0 | 131242-WSW41-QA-C-0011 | 2024-08-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | 8 | Approved with Comments | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000627 | 2024-08-07 | 2024-08-07 | 0 | AWC | Approved with Comments | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" | AWC
000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0013 | 0 | 131242-WSW41-MI-PM-0013 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000628 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0013_20240618" | INF
000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0013 | 0 | 131242-WSW41-PS-PM-0013 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000628 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0013_20240618" | INF
000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0014 | 0 | 131242-WSW41-MI-PM-0014 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000629 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0014_20240723" | INF
000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0014 | 0 | 131242-WSW41-PS-PM-0014 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000629 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0014_20240723" | INF
000630 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 0 | 131242-WSW41-SP-C-0020 | 2024-08-07 | Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000630 | 2024-08-07 | 2024-10-02 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | APP
000630 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 1 | 131242-WSW41-SP-C-0020 | 2024-10-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.1: Approved | 2024-10-22 | 2024-10-14 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000630 | 2024-08-07 | 2024-10-02 | 1 | APP | Approved | 2 | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | APP
000631 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jul-2024) | Resubmit: Considering the VCM submitted only contains link, Contractor to provide full list of contents (from the link) per folder/zip file with file size and timestamp (Transmittal Cover). Also, Contractor to ensure that the link provided should be Contractor's OneDrive link or link to Contractor's CDE. | 2024-08-05 | 2024-08-08 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | INF
000631 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-08-12 | Submission Of BIM Coordination VCM Model (Jul-2024) | For Information | 2024-08-30 | 2024-08-26 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | INF
000632 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0016 | 0 | 131242-WSW41-MS-C-0016 | 2024-08-12 | MSRA, SWP for Erection, Dismantling and Use of Scaffold | Approved | 2024-09-09 | 2024-08-30 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000632 | 2024-08-12 | 2024-08-12 | 0 | APP | Approved | 1 | "MSRA, SWP for Erection, Dismantling and Use of Scaffold " | APP
000633 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0017 | 0 | 131242-WSW41-MS-C-0017 | 2024-08-12 | MSRA, SWP for Jet Grouting | Approved | 2024-09-09 | 2024-09-02 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000633 | 2024-08-12 | 2024-08-12 | 0 | APP | Approved | 1 | "MSRA, SWP for Jet Grouting" | APP
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0010 | 0 | 131242-WSD11-DS-E-0010 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" | AWC
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0012 | 0 | 131242-WSD11-DS-E-0012 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" | AWC
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0013 | 0 | 131242-WSD11-DS-E-0013 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" | AWC
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0014 | 0 | 131242-WSD11-DS-E-0014 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" | AWC
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0015 | 0 | 131242-WSD11-DS-E-0015 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" | AWC
000635 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 0 | 131242-WSD11-DS-M-0015 | 2024-08-12 | Data Sheet of Flash Tank Discharge Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000635 | 2024-08-12 | 2024-11-13 | 1 | AWC | Approved | 2 | "Data Sheet of Flash Tank Discharge Pump " | APP
000635 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 1 | 131242-WSD11-DS-M-0015 | 2024-11-13 | Data Sheet of Flash Tank Discharge Pump | Rev 1: Approved | 2024-12-03 | 2024-12-06 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000635 | 2024-08-12 | 2024-11-13 | 1 | APP | Approved | 2 | "Data Sheet of Flash Tank Discharge Pump " | APP
000636 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 0 | 131242-WSD11-DS-M-0016 | 2024-08-12 | Data Sheet of Precooler S2 CIRC Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000636 | 2024-08-12 | 2024-11-13 | 1 | AWC | Approved | 2 | "Data Sheet of Precooler S2 CIRC Pump" | APP
000636 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 1 | 131242-WSD11-DS-M-0016 | 2024-11-13 | Data Sheet of Precooler S2 CIRC Pump | Rev 1: Approved | 2024-12-03 | 2024-06-12 | 0 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000636 | 2024-08-12 | 2024-11-13 | 1 | APP | Approved | 2 | "Data Sheet of Precooler S2 CIRC Pump" | APP
000637 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 0 | 131242-WSD11-DS-M-0017 | 2024-08-12 | Data Sheet of Digester Feed Pump | Rev 0: Not approved - Revise and Resubmit | 2024-09-09 | 2024-10-09 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000637 | 2024-08-12 | 2025-03-04 | 1 | NAP | Approved | 2 | "Data Sheet of Digester Feed Pump" | APP
000637 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 1 | 131242-WSD11-DS-M-0017 | 2025-03-04 | Data Sheet of Digester Feed Pump | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000637 | 2024-08-12 | 2025-03-04 | 1 | APP | Approved | 2 | "Data Sheet of Digester Feed Pump" | APP
000638 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0018 | 0 | 131242-WSW41-VI-C-0018 | 2024-08-13 | Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-08-19 | 4 | Approved with Comments | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000638 | 2024-08-13 | 2024-08-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | AWC
000639 | 00 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 0 | 131242-WST02-SP-I-0002 | 2024-08-13 | SSN Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000639 | 2024-08-13 | 2025-02-21 | 1 | AWC | Approved with Comments | 2 | "SSN Functional Design Specification" | AWC
000639 | 01 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 1 | 131242-WST02-SP-I-0002 | 2025-02-21 | SSN Functional Design Specification | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-13 | 2025-03-13 | 14 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000639 | 2024-08-13 | 2025-02-21 | 1 | AWC | Approved with Comments | 2 | "SSN Functional Design Specification" | AWC
000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1165 | A | 131242-WSD11-DR-M-1165 | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 | 2025-02-28 | 2nd priority (Shall update and submit under as built drawing) | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | AWC | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | NAP
000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1166 | A | 131242-WSD11-DR-M-1166 | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | AWC | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | NAP
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612_BCA | F | 131242-WST02-DR-S-5600_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " | INF
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612_BCA | F | 131242-WST02-DR-S-5601_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " | INF
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612_BCA | F | 131242-WST02-DR-S-5602_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " | INF
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612_BCA | F | 131242-WST02-DR-S-8600_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " | INF
000642 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 0 | 131242-WSW41-QA-M-0008 | 2024-08-13 | Inspection Test Plan for HDPE Pipe Installation | As requested to reject this submittal. | 2024-09-10 | 2024-09-24 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000642 | 2024-08-13 | 2024-10-01 | 1 | REJ | Approved | 2 | "Inspection Test Plan for HDPE Pipe Installation" | APP
000642 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 1 | 131242-WSW41-QA-M-0008 | 2024-10-01 | Inspection Test Plan for HDPE Pipe Installation | Rev 1: Approved | 2024-10-21 | 2024-10-25 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000642 | 2024-08-13 | 2024-10-01 | 1 | APP | Approved | 2 | "Inspection Test Plan for HDPE Pipe Installation" | APP
000643 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 0 | 131242-WSW41-QA-M-0006 | 2024-08-13 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-10 | 2024-10-16 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | APP
000643 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006 | 2024-12-12 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 1: Approved | 2025-01-02 | 2025-01-20 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | APP
000643 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006 | 2025-09-25 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 2: Approved | 2025-10-15 | 2025-10-06 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | APP
000644 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 0 | 131242-WSD11-RT-EL-0000 | 2024-08-13 | THP Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" | NAP
000644 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 1 | 131242-WSD11-RT-EL-0000 | 2025-04-22 | THP Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-05-06 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" | NAP
000644 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000 | 2025-06-20 | THP Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-08-04 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" | NAP
000644 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000 | 2025-12-15 | THP Lux Simulation Report | Rev 3: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" | NAP
000645 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 0 | 131242-WST02-RT-EL-0000 | 2024-08-13 | SSN Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" | AWC
000645 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 1 | 131242-WST02-RT-EL-0000 | 2025-03-12 | SSN Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-05-06 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" | AWC
000645 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 2 | 131242-WST02-RT-EL-0000 | 2025-06-20 | SSN Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. | 2025-07-10 | 2025-08-04 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" | AWC
000645 | 03 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 3 | 131242-WST02-RT-EL-0000 | 2025-11-20 | SSN Lux Simulation Report | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-10 | 2025-12-17 | 19 | Approved with Comments | YES | 2026-01-06 | NO | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | AWC | Approved with Comments | 4 | "SSN Lux Simulation Report" | AWC
000646 | 00 | Low/ Fox | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-I-7002 | 2024-08-13 | Aeration Blower System Architecture Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-10 | 2024-08-27 | 10 | Approved with Comments | YES | 2024-09-16 | NO | Resubmitted | 0 |  |  | 000646&&001547 | 2024-08-13 | 2025-10-28 | B | AWC | Approved with Comments | 3 | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | AWC
000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 1900 | A | 131242-WST02-DR-S-1900 | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | 21 | Approved with Comments | YES | 2024-10-01 | NO | Resubmitted | 0 |  |  | 000647 | 2024-08-13 | 2024-08-13 | A | AWC | Approved with Comments | 1 | "Waterproofing Concrete Demarcation of SSN Main Water Tank " | AWC
000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 3900 | A | 131242-WST02-DR-S-3900 | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | 21 | Approved with Comments | YES | 2024-10-01 | NO | Resubmitted | 0 |  |  | 000647 | 2024-08-13 | 2024-08-13 | A | AWC | Approved with Comments | 1 | "Waterproofing Concrete Demarcation of SSN Main Water Tank " | AWC
000648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0012 | 0 | 131242-WSD11-DS-M-0012 | 2024-08-12 | Data Sheet of Desuperheater | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-09-03 | 16 | Approved with Comments | YES | 2024-09-23 | NO | Resubmitted | 0 |  |  | 000648 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "Data Sheet of Desuperheater " | AWC
000649 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0004 | 0 | 131242-WSD11-CL-P-0004 | 2024-08-15 | THP Feed Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-08 | 38 | Approved with Comments | YES | 2024-10-28 | NO | Resubmitted | 0 |  |  | 000649 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "THP Feed Pump Pressure Loss Calculation" | AWC
000650 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0008 | 0 | 131242-WSD11-CL-P-0008 | 2024-08-15 | Desuperheater Calculation | Rev 0: Approved with Comments. To revise and resubmit. Please include PE Endorsement. | 2024-09-12 | 2024-08-23 | 6 | Approved with Comments | YES | 2024-09-12 | NO | Resubmitted | 0 |  |  | 000650 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "Desuperheater Calculation" | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | A | 131242-WSD11-DR-M-5100 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | A | 131242-WSD11-DR-M-5110 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | A | 131242-WSD11-DR-M-5120 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | A | 131242-WSD11-DR-M-5130 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | A | 131242-WSD11-DR-M-5140 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | B | 131242-WSD11-DR-M-5100 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | B | 131242-WSD11-DR-M-5110 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | B | 131242-WSD11-DR-M-5120 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5121 | B | 131242-WSD11-DR-M-5121 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" | PEN
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | B | 131242-WSD11-DR-M-5130 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5131 | B | 131242-WSD11-DR-M-5131 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" | PEN
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5132 | B | 131242-WSD11-DR-M-5132 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" | PEN
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | B | 131242-WSD11-DR-M-5140 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5141 | B | 131242-WSD11-DR-M-5141 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" | PEN
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5142 | B | 131242-WSD11-DR-M-5142 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" | PEN
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | B | 131242-WSD11-DR-M-5150 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 177 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | AWC
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | B | 131242-WSD11-DR-M-5160 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 177 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | AWC
000652 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0030 | 0 | 131242-WSW41-MI-P-0030 | 2024-08-06 | Process & MEICA Meeting Minutes 0030_20240801 | Rev 0: For Information | 2024-09-04 | 2024-09-03 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000652 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0030_20240801" | INF
000653 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0010 | 0 | 131242-WSW41-PO-M-0010 | 2024-07-08 | Unpriced PO for Hyperbolix Mixer (Entec International) | For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000653 | 2024-07-08 | 2024-07-08 | 0 | INF | For Information | 1 | "Unpriced PO for Hyperbolix Mixer (Entec International)" | INF
000654 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0011 | 0 | 131242-WSW41-PO-M-0011 | 2024-08-15 | Unpriced PO for Dosing Pump (ProMinent) | Rev 0: For Information | 2024-09-12 | 2024-08-29 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000654 | 2024-08-15 | 2024-08-15 | 0 | APP | Approved | 1 | "Unpriced PO for Dosing Pump (ProMinent)" | APP
000655 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0010 | 0 | 131242-WSW41-QA-M-0010 | 2024-08-15 | Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-09-03 | 13 | Approved with Comments | YES | 2024-09-23 | NO | Resubmitted | 0 |  |  | 000655 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | AWC
000656 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 0 | 131242-WSD11-DS-M-0011 | 2024-08-16 | Data Sheet for Steam Sparger Package | Rev 0: Not approved - Revise and Resubmit | 2024-09-13 | 2024-09-10 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000656 | 2024-08-16 | 2025-02-18 | 1 | NAP | Approved | 2 | "Data Sheet for Steam Sparger Package" | APP
000656 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 1 | 131242-WSD11-DS-M-0011 | 2025-02-18 | Data Sheet for Steam Sparger Package | Rev 1: Approved | 2025-03-10 | 2025-03-10 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000656 | 2024-08-16 | 2025-02-18 | 1 | APP | Approved | 2 | "Data Sheet for Steam Sparger Package" | APP
000657 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0011 | 0 | 131242-WSW41-QA-M-0011 | 2024-08-19 | Procedure for Welding of Underground HDPE Pipe | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-16 | 2024-09-10 | 16 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000657 | 2024-08-19 | 2024-08-19 | 0 | AWC | Approved with Comments | 1 | "Procedure for Welding of Underground HDPE Pipe" | AWC
000658 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0015 | 0 | 131242-WSW41-RT-PM-0015 | 2024-08-19 | C4B Monthly Progress Report Number No.15 (07 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-09-16 | 2024-09-06 | 14 | Approved with Comments | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000658 | 2024-08-19 | 2024-08-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.15 (07 24)" | AWC
000659 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1382 | 0 | 131242-WST02-DS-E-1382 | 2024-08-19 | Sample Board Submission for uPVC Pipe 6” & 4” | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-09-16 | 2024-09-26 | 28 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000659 | 2024-08-19 | 2024-08-19 | 0 | APP | Approved | 1 | "Sample Board Submission for uPVC Pipe 6” & 4” " | APP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7020 | A | 131242-WST02-DR-I-7020 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7021 | A | 131242-WST02-DR-I-7021 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7022 | A | 131242-WST02-DR-I-7022 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7023 | A | 131242-WST02-DR-I-7023 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7024 | A | 131242-WST02-DR-I-7024 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7025 | A | 131242-WST02-DR-I-7025 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" | NAP
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | AWC
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A | 131242-WST02-DR-BF-1005 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " | AWC
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A | 131242-WST02-DR-BF-5001 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " | AWC
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A.1 | 131242-WST02-DR-BF-7002 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | AWC
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A.1 | 131242-WST02-DR-BF-1005 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " | AWC
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A.1 | 131242-WST02-DR-BF-5001 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " | AWC
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5002 | A.1 | 131242-WST02-DR-BF-5002 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2025-06-19 | 2025-06-19 | A.1 | AWC | Approved with Comments | 1 | "SSN External Fire Hydrant Layout & Details " | AWC
000662 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0009 | 0 | 131242-WSD11-CL-P-0009 | 2024-08-20 | Flash Tank Discharge Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-09 | 36 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  |  | 000662 | 2024-08-20 | 2024-08-20 | 0 | AWC | Approved with Comments | 1 | "Flash Tank Discharge Pump Pressure Loss Calculation" | AWC
000663 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0010 | 0 | 131242-WSD11-CL-P-0010 | 2024-08-20 | Precooler S2 Circ Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-08 | 35 | Approved with Comments | YES | 2024-10-28 | NO | Resubmitted | 0 |  |  | 000663 | 2024-08-20 | 2024-08-20 | 0 | AWC | Approved with Comments | 1 | "Precooler S2 Circ Pump Pressure Loss Calculation" | AWC
000664 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 0 | 131242-WSD11-CL-P-0007 | 2024-08-20 | Steam Sparger Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-09-10 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000664 | 2024-08-20 | 2025-04-10 | 1 | AWC | Approved | 2 | "Steam Sparger Calculation" | APP
000664 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 1 | 131242-WSD11-CL-P-0007 | 2025-04-10 | Steam Sparger Calculation | Rev 1: Approved. Please furnish PE Endorsement. | 2025-04-30 | 2025-10-06 | 127 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000664 | 2024-08-20 | 2025-04-10 | 1 | APP | Approved | 2 | "Steam Sparger Calculation" | APP
000665 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 0 | 131242-WST02-QA-E-0002 | 2024-08-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-09-24 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000665 | 2024-08-21 | 2024-10-25 | 1 | NAP | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | AWC
000665 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 1 | 131242-WST02-QA-E-0002 | 2024-10-25 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-04 | 6 | Approved with Comments | YES | 2024-11-22 | NO | Resubmitted | 0 |  |  | 000665 | 2024-08-21 | 2024-10-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | AWC
000666 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0010 | 0 | 131242-WSW41-PS-HS-0010 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Mar 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000666 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Mar 2024" | INF
000667 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0011 | 0 | 131242-WSW41-PS-HS-0011 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Apr 2024 | Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000667 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Apr 2024" | INF
000668 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0012 | 0 | 131242-WSW41-PS-HS-0012 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for May 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000668 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for May 2024" | INF
000669 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0013 | 0 | 131242-WSW41-PS-HS-0013 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Jun 2024 | Rev 0: Scoring confirmed to be at 93/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000669 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jun 2024" | INF
000670 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | - | 131242-WSW41-QA-C-0013 | 2024-08-22 | Monthly Concrete Cube Records for Structural works for Apr 2024 | Rejected as requested by Contractor | 2024-09-19 | 2024-08-30 | 6 | Rejected | NO |  | YES | Resubmitted | 0 |  | Request for Reject | 000670 | 2024-08-22 | 2024-08-27 | 0 | REJ | Rejected | 2 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " | REJ
000670 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | 0 | 131242-WSW41-QA-C-0013 | 2024-08-27 | Monthly Concrete Cube Records for Structural works for May 2024 | Rejected as requested by Contractor | 2024-09-16 |  | 414 | Awaiting S.O.'s response | YES | 2024-10-14 | NO | Overdue | 0 |  |  | 000670 | 2024-08-22 | 2024-08-27 | 0 | PEN | Rejected | 2 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " | REJ
000671 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 0 | 131242-WSW41-VI-E-0010 | 2024-08-23 | Vendor Approval of Surge Diverter | Rev 0: Approved with comments. Refer to attached file for comments. | 2024-09-20 | 2024-09-26 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000671 | 2024-08-23 | 2024-10-04 | 1 | AWC | Approved | 2 | "Vendor Approval of Surge Diverter " | APP
000671 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 1 | 131242-WSW41-VI-E-0010 | 2024-10-04 | Vendor Approval of Surge Diverter | Rev 1: Approved. | 2024-10-24 | 2024-10-29 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000671 | 2024-08-23 | 2024-10-04 | 1 | APP | Approved | 2 | "Vendor Approval of Surge Diverter " | APP
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1200 | A | 131242-WSD11-DR-M-1200 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 | 2025-03-05 | Submission unsuccessful on 11 Jul 2024. | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1201 | A | 131242-WSD11-DR-M-1201 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1202 | A | 131242-WSD11-DR-M-1202 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1203 | A | 131242-WSD11-DR-M-1203 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1204 | A | 131242-WSD11-DR-M-1204 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 8000 | A | 131242-WSD11-DR-M-8000 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | AWC
000673 | 00 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001 | 2024-08-23 | SSN 30 Percent ALMOP Report | Rev 0: Not approved - Revise and Resubmit | 2024-09-20 | 2024-09-06 | 10 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-08-23 | 2024-09-06 | 0 | REJ | Approved with Comments | 2 | "SSN 30 Percent ALMOP Report" | AWC
000673 | 01 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001 | 2024-09-06 | SSN 30 Percent ALMOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-14 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-08-23 | 2024-09-06 | 0 | AWC | Approved with Comments | 2 | "SSN 30 Percent ALMOP Report" | AWC
000673 | 02 | Qili | Process | NA | 131242 | WST02 | RT | Z | Comment Reply Sheet 20240716 S673.2 | 0 | 131242-WST02-RT-Z-Comment Reply Sheet 20240716 S673.2 | 2024-10-29 | SSN 30 Percent ALMOP Report | Rev 2: Approved | 2024-11-19 | 2024-11-27 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-10-29 | 2024-10-29 | 0 | APP | Approved | 1 | "SSN 30 Percent ALMOP Report" | APP
000674 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0037 | 0 | 131242-WSW41-LT-PM-0037 | 2024-08-23 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements | Received for information. Please refer to S.O. Correspondence no. 241 dated 23 Oct 2024. | 2024-09-20 | 2025-11-20 | 324 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000674 | 2024-08-23 | 2024-08-23 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements " | INF
000675 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 0 | 131242-WSW41-VI-M-0021 | 2024-08-23 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-09-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-14 | In Progress | 000675 | 2024-08-23 | 2025-07-02 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" | APP
000675 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 1 | 131242-WSW41-VI-M-0021 | 2025-07-02 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 1: Approved | 2025-07-22 | 2025-11-24 | 103 | Approved | NO |  | YES | Resubmitted | 0 | 2025-03-14 | In Progress | 000675 | 2024-08-23 | 2025-07-02 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" | APP
000676 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 0 | 131242-WST02-QA-E-0003 | 2024-08-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-29 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | NAP | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | AWC
000676 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 1 | 131242-WST02-QA-E-0003 | 2024-12-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-02-03 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | AWC
000676 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 2 | 131242-WST02-QA-E-0003 | 2025-02-07 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-27 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | AWC
000677 | 00 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 0 | 131242-WST02-SP-I-0001 | 2024-08-26 | SSN Control Narrative | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-23 | 2024-10-09 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000677 | 2024-08-26 | 2025-03-24 | 1 | AWC | Approved with Comments | 2 | "SSN Control Narrative" | AWC
000677 | 01 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 1 | 131242-WST02-SP-I-0001 | 2025-03-24 | SSN Control Narrative | Approved with Comments | 2025-04-11 | 2025-05-15 | 38 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 000677 | 2024-08-26 | 2025-03-24 | 1 | AWC | Approved with Comments | 2 | "SSN Control Narrative" | AWC
000678 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 0 | 131242-WSD11-RT-P-0003 | 2024-08-26 | THP HAZOP Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-09 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000678 | 2024-08-26 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "THP HAZOP Report" | AWC
000678 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 1 | 131242-WSD11-RT-P-0003 | 2024-10-28 | THP HAZOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2025-04-08 | 116 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000678 | 2024-08-26 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "THP HAZOP Report" | AWC
000679 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0021 | 0 | 131242-WSW41-VI-E-0021 | 2024-08-26 | Vendor Approval of Electrical Consultant – YHW LLP | Approved | 2024-09-23 | 2024-09-26 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000679 | 2024-08-26 | 2024-08-26 | 0 | APP | Approved | 1 | "Vendor Approval of Electrical Consultant – YHW LLP" | APP
000680 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | QA | C | 0014 | 0 | 131242-WST02-QA-C-0014 | 2024-08-27 | Laboratory Test Report on Soil Samples | For Information | 2024-09-24 | 2024-09-17 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000680 | 2024-08-27 | 2024-08-27 | 0 | INF | For Information | 1 | "Laboratory Test Report on Soil Samples" | INF
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.1 | 131242-WSD11-DR-M-1170 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.1 | 131242-WSD11-DR-M-1171 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.1 | 131242-WSD11-DR-M-1172 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.1 | 131242-WSD11-DR-M-1173 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | AWC | Approved | 2 | "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.1 | 131242-WSD11-DR-M-3170 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.1 | 131242-WSD11-DR-M-3171 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.1 | 131242-WSD11-DR-M-4100 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | AWC | Approved | 2 | "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.2 | 131242-WSD11-DR-M-1170 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-10 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.2 | 131242-WSD11-DR-M-1171 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.2 | 131242-WSD11-DR-M-1172 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.2 | 131242-WSD11-DR-M-1173 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | APP | Approved | 2 | "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.2 | 131242-WSD11-DR-M-3170 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.2 | 131242-WSD11-DR-M-3171 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | APP
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.2 | 131242-WSD11-DR-M-4100 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | APP | Approved | 2 | "Biosolid Building Piping Opening " | APP
000682 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 0 | 131242-WSW41-QA-C-0015 | 2024-08-29 | Plate Load test report | Rev.0:Not Approved. Please refer to attached comment sheet for resubmission. | 2024-09-26 | 2024-09-18 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000682 | 2024-08-29 | 2024-10-30 | 1 | NAP | Approved | 2 | "Plate Load test report " | APP
000682 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 1 | 131242-WSW41-QA-C-0015 | 2024-10-30 | Plate Load test report | Approved | 2024-11-20 | 2024-11-08 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000682 | 2024-08-29 | 2024-10-30 | 1 | APP | Approved | 2 | "Plate Load test report " | APP
000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0029 | 0 | 131242-WSW41-MI-C-0029 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000683 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" | INF
000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0030 | 0 | 131242-WSW41-MI-C-0030 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000683 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0019 | 0 | 131242-WSW41-MI-IM-0019 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0020 | 0 | 131242-WSW41-MI-IM-0020 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0021 | 0 | 131242-WSW41-MI-IM-0021 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0022 | 0 | 131242-WSW41-MI-IM-0022 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0023 | 0 | 131242-WSW41-MI-IM-0023 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0024 | 0 | 131242-WSW41-MI-IM-0024 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0025 | 0 | 131242-WSW41-MI-IM-0025 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0026 | 0 | 131242-WSW41-MI-IM-0026 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0027 | 0 | 131242-WSW41-MI-IM-0027 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0029 | 0 | 131242-WSW41-MI-IM-0029 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0030 | 0 | 131242-WSW41-MI-IM-0030 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0031 | 0 | 131242-WSW41-MI-IM-0031 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | INF
000685 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0031 | 0 | 131242-WSW41-MI-P-0031 | 2024-08-29 | Process & MEICA Meeting Minutes 0031_20240815 | Rev. 0 - For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000685 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0031_20240815" | INF
000686 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 0 | 131242-WSD11-DS-M-0021 | 2024-08-29 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 0: Not approved - Revise and Resubmit | 2024-09-26 | 2024-10-17 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | NAP | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" | APP
000686 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 1 | 131242-WSD11-DS-M-0021 | 2024-11-07 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-27 | 2024-12-05 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" | APP
000686 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 2 | 131242-WSD11-DS-M-0021 | 2025-01-20 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" | APP
000687 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0001 | 0 | 131242-WSD11-RT-Z-0001 | 2024-08-29 | THP 30 Percent ALMOP Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-17 | 35 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000687 | 2024-08-29 | 2024-08-29 | 0 | AWC | Approved with Comments | 1 | "THP 30 Percent ALMOP Study Report" | AWC
000688 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 0 | 131242-WSD11-QA-M-0012 | 2024-08-30 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-11-05 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000688 | 2024-08-30 | 2025-04-21 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | AWC
000688 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 1 | 131242-WSD11-QA-M-0012 | 2025-04-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-09 | 2025-09-08 | 100 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000688 | 2024-08-30 | 2025-04-21 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | AWC
000689 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 0 | 131242-WSW41-QA-E-0004 | 2024-08-30 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 0: Rejected. Refer to the attached file for comments. | 2024-09-27 | 2024-11-25 | 61 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | REJ | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | APP
000689 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 1 | 131242-WSW41-QA-E-0004 | 2025-02-07 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Refer to the attached file for comments. | 2025-02-27 | 2025-03-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | AWC | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | APP
000689 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 2 | 131242-WSW41-QA-E-0004 | 2025-03-14 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 2: Approved. | 2025-04-03 | 2025-05-07 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | APP | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | APP
000690 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0011 | 0 | 131242-WSD11-CL-P-0011 | 2024-08-30 | THP Plant Process Water Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-09-27 | 2024-10-29 | 42 | Not Approved | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000690 | 2024-08-30 | 2024-08-30 | 0 | NAP | Not Approved | 1 | "THP Plant Process Water Hydraulic Calculation" | NAP
000691 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 0 | 131242-WSW41-QA-M-0013 | 2024-08-31 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-10-14 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000691 | 2024-08-31 | 2025-04-17 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " | APP
000691 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 1 | 131242-WSW41-QA-M-0013 | 2025-04-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Approved | 2025-05-07 | 2025-05-19 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000691 | 2024-08-31 | 2025-04-17 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " | APP
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3000_ST607_BCA | A | 131242-WST02-DR-S-3000_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000692 | 2024-08-31 | 2024-08-31 | A | INF | For Information | 1 | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | INF
000693 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016 | 2024-08-31 | Monthly Concrete Cube Records for Structural works for July 2024 | For Information | 2024-09-27 | 2024-09-18 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000693&&000724 | 2024-08-31 | 2024-09-16 | 0 | INF | For Information | 2 | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" | INF
000694 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 0 | 131242-WSW41-QA-M-0015 | 2024-09-02 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-30 | 2024-10-13 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000694 | 2024-09-02 | 2025-03-27 | 1 | NAP | Approved | 2 | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" | APP
000694 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 1 | 131242-WSW41-QA-M-0015 | 2025-03-27 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Approved | 2025-04-16 | 2025-05-19 | 37 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000694 | 2024-09-02 | 2025-03-27 | 1 | APP | Approved | 2 | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" | APP
000695 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0038 | 0 | 131242-WSW41-LT-PM-0038 | 2024-09-03 | Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions | Rev(0): Rejected. Please refer to S.O. Correspondence No. 246 dated 7 Nov 2024. | 2024-10-01 | 2025-11-20 | 317 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000695 | 2024-09-03 | 2024-09-03 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions" | REJ
000696 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0014 | 0 | 131242-WSW41-PC-W-0014 | 2024-09-03 | Payment Claim No.14 | Rev(0): Approved. See S.O. correspondence no. 219 dated 6 Sep 2024. | 2024-10-01 | 2024-10-09 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000696 | 2024-09-03 | 2024-09-03 | 0 | APP | Approved | 1 | "Payment Claim No.14" | APP
000697 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 0 | 131242-WSD11-DS-M-0018 | 2024-09-03 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-14 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000697 | 2024-09-03 | 2025-05-05 | 1 | AWC | Approved with Comments | 2 | "Data Sheet for Pre Cooler Cooling Water Control Valve" | AWC
000697 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 1 | 131242-WSD11-DS-M-0018 | 2025-05-05 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | 235 | Awaiting S.O.'s response | YES | 2025-06-20 | NO | Overdue | 0 |  |  | 000697 | 2024-09-03 | 2025-05-05 | 1 | PEN | Approved with Comments | 2 | "Data Sheet for Pre Cooler Cooling Water Control Valve" | AWC
000698 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 0 | 131242-WSD11-DS-M-0019 | 2024-09-03 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-13 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | APP
000698 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 1 | 131242-WSD11-DS-M-0019 | 2024-11-13 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | APP
000698 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 2 | 131242-WSD11-DS-M-0019 | 2025-01-20 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | APP
000699 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0039 | 0 | 131242-WSW41-LT-PM-0039 | 2024-09-04 | Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024) | Rejected. Please refer to S.O. Correspondence no. 257 dated 2 Dec 2024. | 2024-10-02 | 2025-02-24 | 123 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000258. Sent to Vincent on 03 Dec 2025 | 000699 | 2024-09-04 | 2024-09-04 | 0 | REJ | Rejected | 1 | "Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024)" | REJ
000700 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0015 | 0 | 131242-WSW41-MI-PM-0015 | 2024-09-04 | Monthly Progress Meeting Minutes 0015_20240827 | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000700 | 2024-09-04 | 2024-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0015_20240827" | INF
000701 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0015 | 0 | 131242-WSW41-PS-PM-0015 | 2024-09-04 | Monthly Progress Presentation No. 15 (0824) | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000701 | 2024-09-04 | 2024-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 15 (0824)" | INF
000702 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0012 | 0 | 131242-WSW41-PO-M-0012 | 2024-09-05 | Unpriced LOA for Structural Steel Works (Sanhe) | Rev 0: For Information | 2024-10-03 | 2024-10-13 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000702 | 2024-09-05 | 2024-09-05 | 0 | INF | For Information | 1 | "Unpriced LOA for Structural Steel Works (Sanhe) " | INF
000703 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0018 | 0 | 131242-WSW41-MS-C-0018 | 2024-09-05 | MSRA for RC Super-Structural Work | Rev.0: Approved. Please refer to comment sheet. | 2024-10-03 | 2024-09-26 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000703 | 2024-09-05 | 2024-09-05 | 0 | APP | Approved | 1 | "MSRA for RC Super-Structural Work" | APP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_FSSD | A | 131242-WSD11-DR-A-2000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000704 | 2024-09-06 | 2024-09-06 | A | NAP | Not Approved | 1 | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_FSSD | A | 131242-WSD11-DR-A-3000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000704 | 2024-09-06 | 2024-09-06 | A | NAP | Not Approved | 1 | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | NAP
000705 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0019 | 0 | 131242-WSW41-VI-C-0019 | 2024-09-06 | Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-04 | 2024-09-26 | 14 | Approved with Comments | YES | 2024-10-16 | NO | Resubmitted | 0 |  |  | 000705 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | AWC
000706 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 0 | 131242-WST02-QA-E-0005 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | AWC | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | APP
000706 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 1 | 131242-WST02-QA-E-0005 | 2024-11-20 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-10 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | AWC | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | APP
000706 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 2 | 131242-WST02-QA-E-0005 | 2025-01-16 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | APP
000706 | 03 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 3 | 131242-WST02-QA-E-0005 | 2025-02-26 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-03-18 | 2025-05-06 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | APP
000706 | 04 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 4 | 131242-WST02-QA-E-0005 | 2025-07-03 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-07-23 | 2025-10-01 | 64 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | APP
000707 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 0 | 131242-WST02-QA-E-0006 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | APP
000707 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 1 | 131242-WST02-QA-E-0006 | 2024-12-20 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-02-20 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | APP
000707 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 2 | 131242-WST02-QA-E-0006 | 2025-10-08 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 2: Approved | 2025-10-28 | 2026-02-20 | 97 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | APP
000708 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0001 | 0 | 131242-WSW41-QA-I-0001 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000708 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | AWC
000709 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 0 | 131242-WSW41-QA-I-0002 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | AWC
000709 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 1 | 131242-WSW41-QA-I-0002 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | AWC
000709 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 2 | 131242-WSW41-QA-I-0002 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-29 |  | 122 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | PEN | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | AWC
000710 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 0 | 131242-WSW41-QA-I-0003 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | APP
000710 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 1 | 131242-WSW41-QA-I-0003 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | APP
000710 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 2 | 131242-WSW41-QA-I-0003 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 2: Approved | 2025-10-29 | 2026-02-20 | 96 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | APP
000711 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0011 | 0 | 131242-WST02-VI-E-0011 | 2024-09-06 | Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-09 | 23 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  | To follow-up with VICPLAS. | 000711 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" | AWC
000712 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007 | 2024-09-06 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev.0: Rejected as per Contractor's request. | 2024-10-04 | 2024-09-09 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000712 | 2024-09-06 | 2024-09-09 | 0 | REJ | Approved | 2 | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" | APP
000712 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007 | 2024-09-09 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev 1: Approved. Please refer to attached file and note our comments. | 2024-09-27 | 2024-10-29 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000712 | 2024-09-06 | 2024-09-09 | 0 | APP | Approved | 2 | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" | APP
000713 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0007 | 0 | 131242-WSW41-RT-C-0007 | 2024-09-06 | Bored Piling Pile Eccentricity Reports (ECC 08 to 12) | Not Approved | 2024-10-04 | 2024-09-13 | 5 | Not Approved | YES | 2024-10-03 | NO | Resubmitted | 0 |  |  | 000713 | 2024-09-06 | 2024-09-06 | 0 | NAP | Not Approved | 1 | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" | NAP
000714 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | DS | C | 1384 | 0 | 131242-WST02-DS-C-1384 | 2024-09-09 | Sample Board Submission for PVC lining System (Linabond) | For Information | 2024-10-07 | 2024-09-13 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000714 | 2024-09-09 | 2024-09-09 | 0 | INF | For Information | 1 | "Sample Board Submission for PVC lining System (Linabond)" | INF
000715 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SP | C | 0021 | 0 | 131242-WSW41-SP-C-0021 | 2024-09-09 | Datat Sheet for Steel Structure and Painting | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-07 | 2024-10-09 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000715 | 2024-09-09 | 2024-11-16 | 1 | NAP | Approved with Comments | 2 | "Datat Sheet for Steel Structure and Painting" | AWC
000715 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0021 | 1 | 131242-WSW41-SP-C-0021 | 2024-11-16 | Datat Sheet for Steel Structure and Painting | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-05 | 2024-12-08 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000715 | 2024-09-09 | 2024-11-16 | 1 | AWC | Approved with Comments | 2 | "Datat Sheet for Steel Structure and Painting" | AWC
000716 | 00 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 0 | 131242-WSD11-DS-M-0023 | 2024-09-09 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-07 | 2024-10-14 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | APP
000716 | 01 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 1 | 131242-WSD11-DS-M-0023 | 2024-11-13 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | APP
000716 | 02 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 2 | 131242-WSD11-DS-M-0023 | 2025-01-20 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | APP
000717 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0045 | 0 | 131242-WST02-CD-IM-0045 | 2024-09-09 | Submission Of BIM Coordination VCM Model (Aug-2024) | For Information. | 2024-10-07 | 2024-09-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000717 | 2024-09-09 | 2024-09-09 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Aug-2024)" | INF
000718 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 0 | 131242-WST02-DS-E-0010 | 2024-09-10 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-10-29 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | AWC
000718 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 1 | 131242-WST02-DS-E-0010 | 2024-12-19 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | AWC
000718 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 2 | 131242-WST02-DS-E-0010 | 2025-03-07 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-04-27 | 36 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | AWC
000719 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1383 | 0 | 131242-WST02-DS-E-1383 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0003) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000719 | 2024-09-10 | 2024-09-10 | 0 | APP | Approved | 1 | "Sample Board Submission for Lightning and Earthing System (MTF 0003)" | APP
000720 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1385 | 0 | 131242-WST02-DS-E-1385 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0005) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000720 | 2024-09-10 | 2024-09-10 | 0 | APP | Approved | 1 | "Sample Board Submission for Lightning and Earthing System (MTF 0005)" | APP
000721 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5451 | 0 | 131242-WST02-DS-M-5451 | 2024-09-10 | Data Sheet for Side Manway | Rev 0: Rejected | 2024-10-08 | 2024-10-11 | 23 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000721 | 2024-09-10 | 2024-09-10 | 0 | REJ | Rejected | 1 | "Data Sheet for Side Manway" | REJ
000722 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | Z | 0001 | 0 | 131242-WSW41-MS-Z-0001 | 2024-09-11 | MSRA SWP for Operating Forklift | Approved | 2024-10-09 | 2024-10-10 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000722 | 2024-09-11 | 2024-09-11 | 0 | APP | Approved | 1 | "MSRA SWP for Operating Forklift" | APP
000723 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0002 | 0 | 131242-WST02-RT-P-0002 | 2024-09-12 | Detailed Design Report – SSN PACKAGE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-11-07 | 40 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 | 2025-04-30 | comments received on 14 Feb | 000723 | 2024-09-12 | 2024-09-12 | 0 | AWC | Approved with Comments | 1 | "Detailed Design Report – SSN PACKAGE" | AWC
000724 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016 | 2024-09-16 | Mock-up Temperature Monitoring Test Reports (Alliance) | For Information | 2024-10-14 | 2024-09-26 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000693&&000724 | 2024-08-31 | 2024-09-16 | 0 | INF | For Information | 2 | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" | INF
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5351 | 0 | 131242-WST02-CL-P-5351 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5361 | 0 | 131242-WST02-CL-P-5361 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5371 | 0 | 131242-WST02-CL-P-5371 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5381 | 0 | 131242-WST02-CL-P-5381 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5351 | 1 | 131242-WST02-CL-P-5351 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-17 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5361 | 1 | 131242-WST02-CL-P-5361 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5371 | 1 | 131242-WST02-CL-P-5371 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5381 | 1 | 131242-WST02-CL-P-5381 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " | AWC
000726 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0016 | 0 | 131242-WSW41-RT-PM-0016 | 2024-09-16 | C4B Monthly Progress Report Number No.16 (08 24) | Rev. 0 - Approved with comments (need to re-submit; see attached comment sheet) | 2024-10-14 | 2024-10-01 | 11 | Approved with Comments | YES | 2024-10-21 | NO | Resubmitted | 0 |  |  | 000726 | 2024-09-16 | 2024-09-16 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.16 (08 24) " | AWC
000727 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0040 | 0 | 131242-WSW41-LT-PM-0040 | 2024-09-16 | NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA | Rejected. Please refer to S.O. Correspondence no. 258 dated 2 Dec 2024. | 2024-10-14 | 2025-02-24 | 115 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000257. Sent to Vincent on 03 Dec 2025 | 000727 | 2024-09-16 | 2024-09-16 | 0 | REJ | Rejected | 1 | "NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA" | REJ
000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 0 | 131242-WST02-DS-M-5301 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 0 | 131242-WST02-DS-M-5311 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 1 | 131242-WST02-DS-M-5301 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2024-12-31 | 2024-12-14 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 1 | 131242-WST02-DS-M-5311 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2025-01-08 | 2024-12-14 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 2 | 131242-WST02-DS-M-5301 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-10 | 2025-01-09 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | APP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 2 | 131242-WST02-DS-M-5311 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-20 | 2025-01-09 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | APP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | APP
000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5301 | 0 | 131242-WST02-CL-P-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | AWC
000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5311 | 0 | 131242-WST02-CL-P-5311 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | 18 | Approved with Comments | YES | 2024-11-01 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | AWC
000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5301 | 1 | 131242-WST02-CL-P-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-12-05 | 56 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | AWC
000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5311 | 1 | 131242-WST02-CL-P-5311 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-12-05 | 56 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | AWC
000730 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 0 | 131242-WST02-VI-E-0009 | 2024-09-18 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 0: Rejected. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-10 | 16 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000730 | 2024-09-18 | 2024-10-14 | 1 | REJ | Approved with Comments | 2 | "Vendor Approval of LPS Materials (Skypro_DEHN)" | AWC
000730 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 1 | 131242-WST02-VI-E-0009 | 2024-10-14 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 1: Approved with comments. Refer to attached file for comments. | 2024-11-04 | 2024-11-07 | 18 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 |  | To follow-up with SKYPRO. | 000730 | 2024-09-18 | 2024-10-14 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of LPS Materials (Skypro_DEHN)" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | B | 131242-WST02-DR-P-6000 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | B | 131242-WST02-DR-P-6001 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | B | 131242-WST02-DR-P-6002 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | B | 131242-WST02-DR-P-6003 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | B | 131242-WST02-DR-P-6004 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | B | 131242-WST02-DR-P-6005 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | B | 131242-WST02-DR-P-6006 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | B | 131242-WST02-DR-P-6007 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | B | 131242-WST02-DR-P-6008 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | B | 131242-WST02-DR-P-6009 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | B | 131242-WST02-DR-P-6010 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | B | 131242-WST02-DR-P-6011 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | B | 131242-WST02-DR-P-6012 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | B | 131242-WST02-DR-P-6013 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | B | 131242-WST02-DR-P-6014 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | B | 131242-WST02-DR-P-6015 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | B | 131242-WST02-DR-P-6016 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | B | 131242-WST02-DR-P-6017 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | B | 131242-WST02-DR-P-6018 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | B | 131242-WST02-DR-P-6019 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | B | 131242-WST02-DR-P-6020 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | B | 131242-WST02-DR-P-6200 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | C | 131242-WST02-DR-P-6300 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | C | 131242-WST02-DR-P-6301 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | C | 131242-WST02-DR-P-6500 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | B | 131242-WST02-DR-P-6600 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | C | 131242-WST02-DR-P-6000 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | C | 131242-WST02-DR-P-6001 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | C | 131242-WST02-DR-P-6002 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | C | 131242-WST02-DR-P-6003 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | C | 131242-WST02-DR-P-6004 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | C | 131242-WST02-DR-P-6005 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | C | 131242-WST02-DR-P-6006 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | C | 131242-WST02-DR-P-6007 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | C | 131242-WST02-DR-P-6008 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | C | 131242-WST02-DR-P-6009 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | C | 131242-WST02-DR-P-6010 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | C | 131242-WST02-DR-P-6011 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | C | 131242-WST02-DR-P-6012 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | C | 131242-WST02-DR-P-6013 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | C | 131242-WST02-DR-P-6014 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | C | 131242-WST02-DR-P-6015 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | C | 131242-WST02-DR-P-6016 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | C | 131242-WST02-DR-P-6017 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | C | 131242-WST02-DR-P-6018 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | C | 131242-WST02-DR-P-6019 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | C | 131242-WST02-DR-P-6020 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | C | 131242-WST02-DR-P-6200 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | C | 131242-WST02-DR-P-6600 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | AWC
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | AWC
000732 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0041 | 0 | 131242-WSW41-LT-PM-0041 | 2024-09-20 | CV of Team member (Construction Manager) | Rev 0: Approved | 2024-10-18 | 2024-10-14 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000732 | 2024-09-20 | 2024-09-20 | 0 | APP | Approved | 1 | "CV of Team member (Construction Manager)" | APP
000733 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 0 | 131242-WSW41-QA-M-0017 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000733 | 2024-09-20 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | AWC
000733 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 1 | 131242-WSW41-QA-M-0017 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-26 | 2025-03-21 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000733 | 2024-09-20 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | AWC
000734 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0016 | 0 | 131242-WSW41-QA-M-0016 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 32 | Approved with Comments | YES | 2024-11-25 | NO | Resubmitted | 0 |  |  | 000734 | 2024-09-20 | 2024-09-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " | AWC
000735 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0042 | 0 | 131242-WSW41-LT-PM-0042 | 2024-09-20 | Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area | Rev (0): Rejected. Please refer to S.O. correspondence no. 268 16 Dec 2024. | 2024-10-18 | 2025-11-20 | 304 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000735 | 2024-09-20 | 2024-09-20 | 0 | REJ | Rejected | 1 | "Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area" | REJ
000736 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0032 | 0 | 131242-WSW41-MI-P-0032 | 2024-09-27 | Process & MEICA Meeting Minutes 0032_20240829 | For Information | 2024-10-25 | 2024-10-10 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000736 | 2024-09-27 | 2024-09-27 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0032_20240829" | INF
000737 | 00 | Krishanthy | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008 | 2024-09-27 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-25 | 2024-10-24 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | AWC | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | APP
000737 | 01 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 1 | 131242-WSW41-RT-C-0008 | 2024-11-07 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.1: Approved | 2024-11-27 | 2024-11-28 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | APP | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | APP
000738 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0019 | 0 | 131242-WSW41-QA-M-0019 | 2024-09-28 | Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd) | Rev 0: Approved with comments. Refer to attached comment sheet for resubmission. | 2024-10-25 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000738 | 2024-09-28 | 2024-09-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | AWC
000739 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0016 | 0 | 131242-WSW41-MI-PM-0016 | 2024-10-01 | Monthly Progress Meeting Minutes 0016_20240924 | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000739 | 2024-10-01 | 2024-10-01 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0016_20240924" | INF
000740 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016 | 2024-10-01 | Monthly Progress Presentation No. 16 (0924) | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000740&&000793 | 2024-10-01 | 2024-10-31 | 0 | INF | For Information | 2 | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" | INF
000741 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 0 | 131242-WSW41-QA-M-0014 | 2024-10-02 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-30 | 2024-11-05 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000741 | 2024-10-02 | 2025-03-18 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | APP
000741 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 1 | 131242-WSW41-QA-M-0014 | 2025-03-18 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 1: Approved | 2025-04-07 | 2025-04-27 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000741 | 2024-10-02 | 2025-03-18 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | APP
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | C | 131242-WST00-DR-S-8005_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | C | 131242-WST02-DR-S-0302_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | C | 131242-WST02-DR-S-1200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | C | 131242-WST02-DR-S-1201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | C | 131242-WST02-DR-S-1202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | C | 131242-WST02-DR-S-1203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | C | 131242-WST02-DR-S-1204_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | C | 131242-WST02-DR-S-1205_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | C | 131242-WST02-DR-S-2200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | C | 131242-WST02-DR-S-2201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | C | 131242-WST02-DR-S-2202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | C | 131242-WST02-DR-S-2203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | C | 131242-WST02-DR-S-3200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | C | 131242-WST02-DR-S-3201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | C | 131242-WST02-DR-S-3202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | C | 131242-WST02-DR-S-5200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | C | 131242-WST02-DR-S-5201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | C | 131242-WST02-DR-S-5202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | C | 131242-WST02-DR-S-5203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | C | 131242-WST02-DR-S-5204_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | C | 131242-WST02-DR-S-5205_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | C | 131242-WST02-DR-S-5206_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | C | 131242-WST02-DR-S-5207_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | C | 131242-WST02-DR-S-5208_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | C | 131242-WST02-DR-S-5209_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608_BCA | 0 | 131242-WST02-CL-S-0002_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742 | 2024-10-04 | 2024-10-04 | 0 | INF | For Information | 1 | "BCA submission of ST608 – SSN Shelters (for Information) " | INF
000743 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0015 | 0 | 131242-WSW41-PC-W-0015 | 2024-10-04 | Payment Claim No.15 | Rev(0): Approved. Please refer to S.O. correspondence no. 230 dated 4 Oct 2024 | 2024-11-04 | 2024-10-09 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000743 | 2024-10-04 | 2024-10-04 | 0 | APP | Approved | 1 | "Payment Claim No.15" | APP
000744 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 0 | 131242-WSW41-QA-M-0018 | 2024-10-04 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-04 | 2024-10-11 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000744 | 2024-10-04 | 2024-10-30 | 1 | AWC | Approved | 2 | " Vendor Manufacturing Inspection test plan for Side Manway " | APP
000744 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 1 | 131242-WSW41-QA-M-0018 | 2024-10-30 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 1: Approved | 2024-11-20 | 2024-12-05 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000744 | 2024-10-04 | 2024-10-30 | 1 | APP | Approved | 2 | " Vendor Manufacturing Inspection test plan for Side Manway " | APP
000745 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0043 | 0 | 131242-WSW41-LT-PM-0043 | 2024-10-07 | Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 269 dated 17 Dec 2024. | 2024-11-05 | 2025-02-24 | 100 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000269. Sent to Vincent on 17 Dec 2025 | 000745 | 2024-10-07 | 2024-10-07 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024)" | REJ
000746 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0044 | 0 | 131242-WSW41-LT-PM-0044 | 2024-10-07 | CV of Team member (WSHO) | Approved | 2024-11-05 | 2024-11-15 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000746 | 2024-10-07 | 2024-10-07 | 0 | APP | Approved | 1 | "CV of Team member (WSHO)" | APP
000747 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0017 | 0 | 131242-WSW41-QA-C-0017 | 2024-10-08 | Mock-up Temperature Monitoring Test Reports - G40 (Pan U) | For Information | 2024-11-06 | 2024-10-14 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000747 | 2024-10-08 | 2024-10-08 | 0 | INF | For Information | 1 | "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" | INF
000748 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0046 | 0 | 131242-WSW41-CD-IM-0046 | 2024-10-08 | Submission Of BIM Coordination VCM Model (Sept-2024) | For Information. | 2024-11-06 | 2024-10-29 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000748 | 2024-10-08 | 2024-10-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Sept-2024)" | INF
000749 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | C | 0007 | 0 | 131242-WST02-CL-C-0007 | 2024-10-09 | Bar chair Design for SSN Water Tanks Raft Slabs | For Information | 2024-11-07 | 2024-10-14 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000749 | 2024-10-09 | 2024-10-09 | 0 | APP | Approved | 1 | "Bar chair Design for SSN Water Tanks Raft Slabs " | APP
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602_BCA | E | 131242-WST00-DR-G-0100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602_BCA | E | 131242-WST00-DR-G-0101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602_BCA | E | 131242-WST00-DR-G-1100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602_BCA | E | 131242-WST00-DR-G-1101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602_BCA | E | 131242-WST00-DR-G-3100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3101_ST602_BCA | E | 131242-WST00-DR-G-3101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 5101_ST602_BCA | E | 131242-WST00-DR-G-5101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602_BCA | E | 131242-WST00-DR-G-8001_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " | INF
000751 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | AWC | Approved | 3 | "Side Manway Calculation and GA Drawing" | APP
000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A | 131242-WST02-DR-M-5451 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A | 131242-WST02-DR-M-5452 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000751 | 01 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | AWC | Approved | 3 | "Side Manway Calculation and GA Drawing" | APP
000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000751 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-12-17 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | APP | Approved | 3 | "Side Manway Calculation and GA Drawing" | APP
000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | APP | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | APP | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" | AWC
000752 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 0 | 131242-WST02-RT-P-0003 | 2024-10-09 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-07 | 2024-11-15 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" | AWC
000752 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 1 | 131242-WST02-RT-P-0003 | 2024-12-10 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-31 | 2024-12-14 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" | AWC
000752 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 2 | 131242-WST02-RT-P-0003 | 2025-01-20 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-13 | 38 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" | AWC
000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1400 | 0 | 131242-WST02-DR-S-1400 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | INF | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5400 | 0 | 131242-WST02-DR-S-5400 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | INF | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
000754 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0045 | 0 | 131242-WSW41-LT-PM-0045 | 2024-10-10 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025 | 2024-11-08 | 2025-11-20 | 290 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000754 | 2024-10-10 | 2024-10-10 | 0 | REJ | Rejected | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | REJ
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 0 | 131242-WST02-DS-M-5501 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 | In progress. Process (Qili) will provide updated Datasheet (some change as Pump Calculation, we just received SO cmt sheet on Pump Calc last week) -> in 2 weeks | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 0 | 131242-WST02-DS-M-5511 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 0 | 131242-WST02-DS-M-5521 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 0 | 131242-WST02-DS-M-5531 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 0 | 131242-WST02-DS-M-5541 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 0 | 131242-WST02-DS-M-5551 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 1 | 131242-WST02-DS-M-5501 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 1 | 131242-WST02-DS-M-5511 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 1 | 131242-WST02-DS-M-5521 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 1 | 131242-WST02-DS-M-5531 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 1 | 131242-WST02-DS-M-5541 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 1 | 131242-WST02-DS-M-5551 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" | AWC
000756 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0020 | 0 | 131242-WSW41-QA-M-0020 | 2024-10-11 | Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-11 | 2024-11-19 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000756 | 2024-10-11 | 2024-10-11 | 0 | AWC | Approved with Comments | 1 | "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" | AWC
000757 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0018 | 0 | 131242-WSW41-QA-C-0018 | 2024-10-11 | Mock-up Temperature Monitoring Test Reports – G45 (Pan U) | For information. | 2024-11-11 | 2024-10-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000757 | 2024-10-11 | 2024-10-11 | 0 | INF | For Information | 1 | "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" | INF
000758 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 0 | 131242-WSW41-VI-M-1006 | 2024-10-12 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-24 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000758 | 2024-10-12 | 2025-01-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | AWC
000758 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 1 | 131242-WSW41-VI-M-1006 | 2025-01-16 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-05 | 2025-01-20 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | As per SO response, Resubmission is not required. | 000758 | 2024-10-12 | 2025-01-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | AWC
000759 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0_NIL | 131242-WSW41-MS-M-0002 | 2024-10-14 | Delivery and Storage of Compressor Package at Biosolids Building | Rev.0: As requested by Contractor to reject the submittal. | 2024-11-12 | 2024-10-14 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | REJ | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " | APP
000759 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0 | 131242-WSW41-MS-M-0002 | 2024-10-15 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 0: Approved with comments - Revise and Resubmit | 2024-11-05 | 2024-10-24 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | AWC | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " | APP
000759 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 1 | 131242-WSW41-MS-M-0002 | 2024-10-30 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 2: Approved | 2024-11-20 | 2024-12-03 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | APP | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " | APP
000760 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0014 | 0 | 131242-WSW41-PS-HS-0014 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Jul 2024 | Rev 0: Scoring confirmed to be at 98/100 | 2024-11-12 | 2024-11-15 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000760 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jul 2024" | INF
000761 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0015 | 0 | 131242-WSW41-PS-HS-0015 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Aug 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-11-12 | 2024-11-15 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000761 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Aug 2024" | INF
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0031 | 0 | 131242-WSW41-MI-C-0031 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | INF
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0032 | 0 | 131242-WSW41-MI-C-0032 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | INF
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0033 | 0 | 131242-WSW41-MI-C-0033 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | INF
000763 | 00 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 0 | 131242-WST02-CD-I-0005 | 2024-10-15 | SSN Instrument List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-13 | 2025-02-13 | 87 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000763 | 2024-10-15 | 2025-10-27 | 1 | NAP | Approved with Comments | 2 | "SSN Instrument List " | AWC
000763 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 1 | 131242-WST02-CD-I-0005 | 2025-10-27 | SSN Instrument List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-11-14 | 2026-01-26 | 65 | Approved with Comments | YES | 2026-02-13 | NO | Resubmitted | 0 |  |  | 000763 | 2024-10-15 | 2025-10-27 | 1 | AWC | Approved with Comments | 2 | "SSN Instrument List " | AWC
000764 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 0 | 131242-WSD11-QA-I-0004 | 2024-10-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-15 | 2025-03-25 | 113 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000764 | 2024-10-17 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | AWC
000764 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 1 | 131242-WSD11-QA-I-0004 | 2025-05-30 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-19 | 2025-06-04 | 3 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 000764 | 2024-10-17 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | AWC
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614 | A | 131242-WSW41-DR-S-0310_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614 | A | 131242-WSW41-DR-S-0311_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614 | A | 131242-WSW41-DR-S-0312_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614 | A | 131242-WSW41-DR-S-0313_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614 | A | 131242-WSW41-DR-S-0314_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614 | A | 131242-WSW41-DR-S-0315_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614 | A | 131242-WSW41-DR-S-0316_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614 | A | 131242-WSW41-DR-S-0317_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614 | A | 131242-WSW41-DR-S-1100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614 | A | 131242-WSW41-DR-S-1101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614 | A | 131242-WSW41-DR-S-1102_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614 | A | 131242-WSW41-DR-S-1103_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614 | A | 131242-WSW41-DR-S-1104_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614 | A | 131242-WSW41-DR-S-2100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614 | A | 131242-WSW41-DR-S-2101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614 | A | 131242-WSW41-DR-S-3100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614 | A | 131242-WSW41-DR-S-5100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614 | A | 131242-WSW41-DR-S-5101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614 | A | 131242-WSW41-DR-S-5102_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614 | A | 131242-WSW41-DR-S-5103_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614 | A | 131242-WSW41-DR-S-8002_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" | INF
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | CL | M | 5461 | 0 | 131242-WST02-CL-M-5461 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | 2 | AWC | Approved | 2 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5461 | A | 131242-WST02-DR-M-5461 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5463 | A | 131242-WST02-DR-M-5463 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | A.1 | 131242-WST02-DR-M-5461 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-12 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | The Only comment is to get PE endorsement (Mech PE) | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | A.1 | 131242-WST02-DR-M-5463 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-06 | 2024-12-12 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5461 | 2 | 131242-WST02-CL-M-5461 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | 2 | APP | Approved | 2 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | C | 131242-WST02-DR-M-5461 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | APP | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | C | 131242-WST02-DR-M-5463 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | APP | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | APP
000767 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0017 | 0 | 131242-WSW41-RT-PM-0017 | 2024-10-19 | C4B Monthly Progress Report Number No.17 (09 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-11-18 | 2024-10-25 | 4 | Approved with Comments | YES | 2024-11-14 | NO | Resubmitted | 0 |  |  | 000767 | 2024-10-19 | 2024-10-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.17 (09 24) " | AWC
000768 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0046 | 0 | 131242-WSW41-LT-PM-0046 | 2024-10-21 | Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings | Rev (0): Received for information. lease refer to S.O. correspondence no. 289 dated 21 Jan 2025. | 2024-11-19 | 2025-11-20 | 283 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000768 | 2024-10-21 | 2024-10-21 | 0 | INF | For Information | 1 | "Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings" | INF
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5501 | 0 | 131242-WST02-CL-P-5501 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 | 2025-04-30 | Pending model update, need PE endorsement | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5511 | 0 | 131242-WST02-CL-P-5511 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5521 | 0 | 131242-WST02-CL-P-5521 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5531 | 0 | 131242-WST02-CL-P-5531 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5541 | 0 | 131242-WST02-CL-P-5541 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5551 | 0 | 131242-WST02-CL-P-5551 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" | AWC
000770 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | K | 0001 | 0 | 131242-WST02-CL-K-0001 | 2024-10-22 | SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs | Rev 0: Approved with comments. Please refer to comment sheet. | 2024-11-20 | 2024-11-21 | 22 | Approved with Comments | YES | 2024-12-11 | NO | Resubmitted | 0 |  |  | 000770 | 2024-10-22 | 2024-10-22 | 0 | AWC | Approved with Comments | 1 | "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" | AWC
000771 | 00 | Radha | QAQC | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008 | 2024-10-22 | Bored Piling Pile Eccentricity Reports (ECC 13 to 18) | For Information. Please find attached comment sheet. | 2024-11-20 | 2024-11-04 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | INF | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | APP
000772 | 00 | Qili | Process | NA | 131242 | WST02 | RT | E | 0006 | 0 | 131242-WST02-RT-E-0006 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | 109 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000772 | 2024-10-23 | 2024-10-23 | 0 | AWC | Approved with Comments | 1 | "SSN Hazardous Area Assessment Report" | AWC
000772 | 00 | Qili | Process | NA | 131242 | WST02 | DR | E | 8001 | A | 131242-WST02-DR-E-8001 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | 109 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000772 | 2024-10-23 | 2024-10-23 | A | AWC | Approved with Comments | 1 | "SSN Hazardous Area Assessment Report" | AWC
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | A | 131242-WSW41-DR-S-0310_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | A | 131242-WSW41-DR-S-0311_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | A | 131242-WSW41-DR-S-0312_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | A | 131242-WSW41-DR-S-0313_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | A | 131242-WSW41-DR-S-0314_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | A | 131242-WSW41-DR-S-0315_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614_BCA | A | 131242-WSW41-DR-S-0316_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773 | 2024-10-23 | 2024-10-23 | A | INF | For Information | 1 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614_BCA | A | 131242-WSW41-DR-S-0317_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773 | 2024-10-23 | 2024-10-23 | A | INF | For Information | 1 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | A | 131242-WSW41-DR-S-1100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | A | 131242-WSW41-DR-S-1101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | A | 131242-WSW41-DR-S-1102_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | A | 131242-WSW41-DR-S-1103_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | A | 131242-WSW41-DR-S-1104_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | A | 131242-WSW41-DR-S-2100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | A | 131242-WSW41-DR-S-2101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | A | 131242-WSW41-DR-S-3100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | A | 131242-WSW41-DR-S-5100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | A | 131242-WSW41-DR-S-5101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | A | 131242-WSW41-DR-S-5102_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | A | 131242-WSW41-DR-S-5103_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | A | 131242-WSW41-DR-S-8002_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000774 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 0 | 131242-WSW41-DS-E-1386 | 2024-10-23 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-21 | 2024-11-21 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000774 | 2024-10-23 | 2024-12-20 | 1 | AWC | Rejected | 2 | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | REJ
000774 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 1 | 131242-WSW41-DS-E-1386 | 2024-12-20 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 1: Rejected. Wrong comment reply sheet has been attached. | 2025-01-10 | 2025-02-18 | 42 | Rejected | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000774 | 2024-10-23 | 2024-12-20 | 1 | REJ | Rejected | 2 | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | REJ
000775 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 0 | 131242-WSW41-MS-C-0019 | 2024-10-23 | MSRA for RC Wall | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-11-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" | AWC
000775 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019 | 2024-11-26 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2024-12-16 | 2024-12-18 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" | AWC
000775 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019 | 2024-12-19 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2025-01-09 | 2025-01-08 | 14 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" | AWC
000776 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0047 | 0 | 131242-WSW41-LT-PM-0047 | 2024-10-25 | Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works | Rejected. Please refer to S.O. correspondence no. 276 dated 7 January 2025. | 2024-11-25 | 2025-08-25 | 216 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000776 | 2024-10-25 | 2024-10-25 | 0 | REJ | Rejected | 1 | "Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works " | REJ
000777 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 0 | 131242-WSW41-VI-M-0010 | 2024-10-25 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-11-25 | 2024-11-27 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000777 | 2024-10-25 | 2025-01-11 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Spray Nozzles " | AWC
000777 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 1 | 131242-WSW41-VI-M-0010 | 2025-01-11 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000777 | 2024-10-25 | 2025-01-11 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Spray Nozzles " | AWC
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | AWC
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | AWC
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 2000 | A | 131242-WST02-DR-M-2000 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000778 | 2024-10-26 | 2024-10-26 | A | AWC | Approved with Comments | 1 | "SSN Piping Support Plan Layout (Cast-In Supports)" | AWC
000779 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 0001 | A | 131242-WST02-DR-M-0001 | 2024-10-26 | SSN Piping Drawing Index | Rev 0: For Information | 2024-11-25 | 2024-11-27 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000779 | 2024-10-26 | 2024-10-26 | A | INF | For Information | 1 | "SSN Piping Drawing Index" | INF
000780 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0009 | 0 | 131242-WSW41-VI-S-0009 | 2024-10-26 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-20 | 17 | Approved with Comments | YES | 2024-12-10 | NO | Resubmitted | 0 |  |  | 000780 | 2024-10-26 | 2024-10-26 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " | AWC
000781 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002 | 2024-10-26 | Vendor Approval of Raised Floor – Hemsco Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-15 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000781&&001325 | 2024-10-26 | 2025-05-28 | 0 | AWC | Approved | 2 | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " | APP
000782 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 0 | 131242-WSW41-QA-M-0021 | 2024-10-28 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 0: Not approved - Revise and Resubmit | 2024-11-26 | 2024-11-27 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000782 | 2024-10-28 | 2024-12-14 | 1 | NAP | Approved | 2 | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" | APP
000782 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 1 | 131242-WSW41-QA-M-0021 | 2024-12-14 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 1: Approved | 2025-01-03 | 2025-01-20 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000782 | 2024-10-28 | 2024-12-14 | 1 | APP | Approved | 2 | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" | APP
000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0001 | A | 131242-WSD11-DR-M-0001 | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000783 | 2024-10-28 | 2024-10-28 | A | INF | For Information | 1 | "THP Drawing Index" | INF
000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0002 | A | 131242-WSD11-DR-M-0002 | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000783 | 2024-10-28 | 2024-10-28 | A | INF | For Information | 1 | "THP Drawing Index" | INF
000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | A | 131242-WSD11-DR-M-5150 | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | 22 | Approved with Comments | YES | 2024-12-17 | NO | Resubmitted | 0 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | AWC
000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | A | 131242-WSD11-DR-M-5160 | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | 22 | Approved with Comments | YES | 2024-12-17 | NO | Resubmitted | 0 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | AWC
000785 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0016 | 0 | 131242-WSW41-PS-HS-0016 | 2024-10-28 | Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024 | For Information | 2024-11-26 | 2024-11-15 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000785 | 2024-10-28 | 2024-10-28 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | INF
000786 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0010 | 0 | 131242-WSW41-RT-C-0010 | 2024-10-28 | Report of DFS (GUIDE 3) for PIPE RACKS | Rev.0: Approved with comments. Revise and resubmit. | 2024-11-26 | 2024-12-08 | 30 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000786 | 2024-10-28 | 2024-10-28 | 0 | AWC | Approved with Comments | 1 | "Report of DFS (GUIDE 3) for PIPE RACKS" | AWC
000787 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0011 | 0 | 131242-WSW41-RT-C-0011 | 2024-10-28 | Report of PROJECT SAFETY REVIEW for PIPE RACKS | For Information | 2024-11-26 | 2024-12-18 | 37 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000787 | 2024-10-28 | 2024-10-28 | 0 | INF | For Information | 1 | "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | INF
000788 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0016 | 0 | 131242-WSW41-PC-W-0016 | 2024-10-29 | Payment Claim No.16 | Rev(0): Approved. Please refer to S.O. Correspondence no. 244 dated 1 Nov 2024. | 2024-11-27 | 2024-11-07 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000788 | 2024-10-29 | 2024-10-29 | 0 | APP | Approved | 1 | "Payment Claim No.16" | APP
000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9100 | A | 131242-WSD11-DR-M-9100 | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 26 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 | 2025-03-05 | 2nd priority (Shall update and submit under as built drawing) | 000789 | 2024-10-30 | 2024-10-30 | A | AWC | Approved with Comments | 1 | "THP Underground Piping and Cast in Details" | AWC
000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1190 | A | 131242-WSD11-DR-M-1190 | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 26 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000789 | 2024-10-30 | 2024-10-30 | A | AWC | Approved with Comments | 1 | "THP Underground Piping and Cast in Details" | AWC
000790 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0012 | 0 | 131242-WSW41-RT-C-0012 | 2024-10-30 | Quarterly Safety Review Follow Up on ERSS | For Information | 2024-11-28 | 2024-11-15 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000790&&001420 | 2024-10-30 | 2025-07-01 | 1 | INF | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0034 | 0 | 131242-WSW41-MI-C-0034 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000791 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | INF
000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0035 | 0 | 131242-WSW41-MI-C-0035 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000791 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | INF
000792 | 00 | PCM | PCM | NA | 131242 | WSW41 | MI | PM | 0017 | 0 | 131242-WSW41-MI-PM-0017 | 2024-10-31 | Monthly Progress Meeting Minutes 0017_20241023 | Rev. 0 - For Information | 2024-11-28 | 2024-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000792 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0017_20241023" | INF
000793 | 00 | PCM | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016 | 2024-10-31 | Monthly Progress Presentation No. 17 (1024) | For Information | 2024-11-28 | 2024-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000740&&000793 | 2024-10-01 | 2024-10-31 | 0 | INF | For Information | 2 | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" | INF
000794 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0001 | 0 | 131242-WST02-VI-A-0001 | 2024-10-31 | Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-28 | 2024-11-25 | 17 | Approved with Comments | YES | 2024-12-13 | NO | Resubmitted | 0 |  |  | 000794 | 2024-10-31 | 2024-10-31 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" | AWC
000795 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0022 | 0 | 131242-WSW41-QA-M-0022 | 2024-11-01 | FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver) | Rev 0: Approved | 2024-11-29 | 2024-12-05 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000795 | 2024-11-01 | 2024-11-01 | 0 | APP | Approved | 1 | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" | APP
000796 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0023 | 0 | 131242-WSW41-VI-E-0023 | 2024-11-02 | Vendor Approval of EICA Material and Accessories (Cable Gland) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-11-29 | 2024-11-24 | 15 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000796 | 2024-11-02 | 2024-11-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of EICA Material and Accessories (Cable Gland)" | AWC
000797 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0022 | 0 | 131242-WSW41-VI-E-0022 | 2024-11-02 | Preliminary Design and Vendor Approval of Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-29 | 2024-11-24 | 15 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000797 | 2024-11-02 | 2024-11-02 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval of Unistrut Support" | AWC
000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | A | 131242-WST02-DR-M-5311 | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-28 | In Progress | 000798 | 2024-11-04 | 2025-04-17 | B | AWC | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" | AWC
000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | A | 131242-WST02-DR-M-5301 | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | 23 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | AWC | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" | AWC
000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | B | 131242-WST02-DR-M-5311 | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | 247 | Awaiting S.O.'s response | YES | 2025-06-04 | NO | Overdue | 0 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | PEN | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" | AWC
000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | B | 131242-WST02-DR-M-5301 | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | 247 | Awaiting S.O.'s response | YES | 2025-06-04 | NO | Overdue | 113 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | PEN | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" | AWC
000799 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2001 | 0 | 131242-WSW41-VI-M-2001 | 2024-11-05 | Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package | Rev 0: Approved | 2024-12-03 | 2024-12-05 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000799 | 2024-11-05 | 2024-11-05 | 0 | APP | Approved | 1 | "Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package" | APP
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618 | A | 131242-WSD11-DR-S-2300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618 | A | 131242-WSD11-DR-S-3300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618 | A | 131242-WSD11-DR-S-3301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618 | A | 131242-WSD11-DR-S-5300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618 | A | 131242-WSD11-DR-S-5301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618 | A | 131242-WSD11-DR-S-5302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618 | A | 131242-WSD11-DR-S-5303_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618 | A | 131242-WSD11-DR-S-5304_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618 | A | 131242-WSD11-DR-S-5305_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618 | A | 131242-WSD11-DR-S-5306_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618 | A | 131242-WSD11-DR-S-5307_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618 | A | 131242-WSD11-DR-S-5308_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618 | A | 131242-WSD11-DR-S-5309_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618 | A | 131242-WSD11-DR-S-5310_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8001_ST618 | A | 131242-WSD11-DR-S-8001_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618 | A | 131242-WSD11-DR-S-0302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618 | A | 131242-WSD11-DR-S-1300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618 | A | 131242-WSD11-DR-S-1301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618 | A | 131242-WSD11-DR-S-1302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618 | A | 131242-WSD11-DR-S-1303_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618 | A | 131242-WSD11-DR-S-1304_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618 | A | 131242-WSD11-DR-S-1305_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" | AWC
000801 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0048 | 0 | 131242-WSW41-LT-PM-0048 | 2024-11-06 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 333 dated 17 April 2025. | 2024-12-04 | 2025-11-20 | 271 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000801 | 2024-11-06 | 2024-11-06 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024)" | INF
000802 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 0 | 131242-WSW41-VI-M-0008 | 2024-11-06 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-04 | 2024-12-05 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | AWC
000802 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 1 | 131242-WSW41-VI-M-0008 | 2025-01-26 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-04-27 | 65 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | AWC
000802 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 2 | 131242-WSW41-VI-M-0008 | 2025-06-16 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-11-24 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | AWC
000803 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0049 | 0 | 131242-WSW41-CD-IM-0049 | 2024-11-08 | Submission of BIM Coordination VCM Model (Oct 2024) | For Information | 2024-12-06 | 2024-11-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000803 | 2024-11-08 | 2024-11-08 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Oct 2024)" | INF
000804 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0018 | 0 | 131242-WSW41-RT-PM-0018 | 2024-11-09 | C4B Monthly Progress Report Number No.18 (10 24) | Rev. 0 - Approved with comments (need to re-submit / see attached comments sheet) | 2024-12-06 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000804 | 2024-11-09 | 2024-11-09 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.18 (10 24) " | AWC
000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0004 | 0 | 131242-WST02-CL-S-0004 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000805 | 2024-11-11 | 2024-11-11 | 0 | AWC | Approved with Comments | 1 | "Anchor bolt Details for pipe supports for post drill and Cast-in type" | AWC
000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0005 | 0 | 131242-WST02-CL-S-0005 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000805 | 2024-11-11 | 2024-11-11 | 0 | AWC | Approved with Comments | 1 | "Anchor bolt Details for pipe supports for post drill and Cast-in type" | AWC
000806 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 0 | 131242-WSW41-VI-M-0030 | 2024-11-11 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-09 | 2024-12-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-21 | In progress. as SO comment s/n.4, provide Vendor product presentation slides to SO on 14 Feb, will resubmit | 000806 | 2024-11-11 | 2025-03-20 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | AWC
000806 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 1 | 131242-WSW41-VI-M-0030 | 2025-03-20 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-11-24 | 177 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000806 | 2024-11-11 | 2025-03-20 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | AWC
000807 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 0 | 131242-WSW41-DS-E-1388 | 2024-11-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-21 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000807 | 2024-11-12 | 2025-03-12 | 1 | AWC | Approved | 2 | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | APP
000807 | 01 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 1 | 131242-WSW41-DS-E-1388 | 2025-03-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 1: Approved. | 2025-04-01 | 2025-05-05 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000807 | 2024-11-12 | 2025-03-12 | 1 | APP | Approved | 2 | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | APP
000808 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1387 | 0 | 131242-WSW41-DS-E-1387 | 2024-11-12 | Sample board submission for SS Cable ladder, trays & accessories (United U-Li) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-25 | 9 | Approved with Comments | YES | 2024-12-13 | NO | Resubmitted | 0 |  |  | 000808 | 2024-11-12 | 2024-11-12 | 0 | AWC | Approved with Comments | 1 | "Sample board submission for SS Cable ladder, trays & accessories (United U-Li)" | AWC
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1000 | A | 131242-WST02-DR-A-1000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | INF | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2000 | A | 131242-WST02-DR-A-2000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&001604&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 4 | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 3000 | B | 131242-WST02-DR-A-3000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | NAP
000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1003 | A | 131242-WST02-DR-A-1003 | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2002 | A | 131242-WST02-DR-A-2002 | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1004 | A | 131242-WST02-DR-A-1004 | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2003 | A | 131242-WST02-DR-A-2003 | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1009 | A | 131242-WST02-DR-A-1009 | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2007 | A | 131242-WST02-DR-A-2007 | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
000813 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 0 | 131242-WSW41-QA-M-0023 | 2024-11-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-05 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000813 | 2024-11-14 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | AWC
000813 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 1 | 131242-WSW41-QA-M-0023 | 2025-10-23 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-12 | 2025-12-23 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000813 | 2024-11-14 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | AWC
000814 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0019 | 0 | 131242-WSW41-QA-C-0019 | 2024-11-14 | Monthly Concrete Cube Records for Structural works for August 2024 | For Information | 2024-12-12 | 2024-12-07 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000814 | 2024-11-14 | 2024-11-14 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works for August 2024" | INF
000815 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0004 | 0 | 131242-WSW41-MS-M-0004 | 2024-11-15 | MSRA and SWP for Installation of Manway | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-05 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000815 | 2024-11-15 | 2024-11-15 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Installation of Manway" | AWC
000816 | 00 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0005 | 0 | 131242-WSW41-VI-I-0005 | 2024-11-16 | Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech) | Rev 0: Rejected. Based on CES request. | 2024-12-13 | 2024-12-05 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  | Email sent on 25 Nov 24 | 000816 | 2024-11-16 | 2024-11-16 | 0 | REJ | Rejected | 1 | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" | REJ
000817 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0024 | 0 | 131242-WSW41-VI-E-0024 | 2024-11-16 | Preliminary Design and Vendor Approval – HDMANN Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-13 | 2024-12-06 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000817 | 2024-11-16 | 2024-11-16 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval – HDMANN Unistrut Support" | AWC
000818 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0003 | 0 | 131242-WSW41-MS-M-0003 | 2024-11-16 | MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-06 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000818 | 2024-11-16 | 2024-11-16 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " | AWC
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-A-1001 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 2 | "THP Layout, Elevations and Section Details" && "THP BCA BP Submission" | INF
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A | 131242-WSD11-DR-A-1002 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A | 131242-WSD11-DR-A-1003 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A | 131242-WSD11-DR-A-2000 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A | 131242-WSD11-DR-A-3000 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
000820 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5000 | A | 131242-WSD11-DR-A-5000 | 2024-11-18 | THP Door and Finishes Schedules | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-18 | 22 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000820 | 2024-11-18 | 2024-11-18 | A | NAP | Not Approved | 1 | "THP Door and Finishes Schedules" | NAP
000821 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5006 | A | 131242-WSD11-DR-A-5006 | 2024-11-18 | THP Corridor & Stair Compartment Waterproofing Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-21 | 25 | Not Approved | YES | 2025-01-09 | NO | Resubmitted | 0 |  |  | 000821 | 2024-11-18 | 2024-11-18 | A | NAP | Not Approved | 1 | "THP Corridor & Stair Compartment Waterproofing Details" | NAP
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5001 | A | 131242-WSD11-DR-A-5001 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" | AWC
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5002 | A | 131242-WSD11-DR-A-5002 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" | AWC
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5003 | A | 131242-WSD11-DR-A-5003 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" | AWC
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5004 | A | 131242-WSD11-DR-A-5004 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" | AWC
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609 | D | 131242-WST00-DR-S-8004_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0300_ST609 | D | 131242-WST02-DR-S-0300_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609 | D | 131242-WST02-DR-S-0301_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609 | D | 131242-WST02-DR-S-0303_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609 | D | 131242-WST02-DR-S-0304_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609 | D | 131242-WST02-DR-S-0305_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609 | D | 131242-WST02-DR-S-0306_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609 | D | 131242-WST02-DR-S-0307_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609 | D | 131242-WST02-DR-S-0308_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609 | D | 131242-WST02-DR-S-0309_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1100_ST609 | D | 131242-WST02-DR-S-1100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609 | D | 131242-WST02-DR-S-1101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609 | D | 131242-WST02-DR-S-1102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609 | D | 131242-WST02-DR-S-1103_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609 | D | 131242-WST02-DR-S-2100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609 | D | 131242-WST02-DR-S-2101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609 | D | 131242-WST02-DR-S-2102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609 | D | 131242-WST02-DR-S-3100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609 | D | 131242-WST02-DR-S-3101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609 | D | 131242-WST02-DR-S-3102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609 | D | 131242-WST02-DR-S-5100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609 | D | 131242-WST02-DR-S-5101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609 | D | 131242-WST02-DR-S-5102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609 | D | 131242-WST02-DR-S-5103_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609 | D | 131242-WST02-DR-S-5104_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | INF
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | AWC
000825 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021 | 2024-11-20 | Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm | For Information | 2024-12-18 | 2024-11-27 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000825&&000952 | 2024-11-20 | 2025-01-04 | 0 | INF | For Information | 2 | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" | INF
000826 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 0 | 131242-WSD11-RT-E-0002 | 2024-11-20 | THP Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 |  | 000826 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Load Flow Study Report" | AWC
000826 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 1 | 131242-WSD11-RT-E-0002 | 2025-03-25 | THP Load Flow Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000826 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Load Flow Study Report" | AWC
000827 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 0 | 131242-WSD11-RT-E-0003 | 2024-11-20 | THP Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 |  | 000827 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Short Circuit Study Report" | AWC
000827 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 1 | 131242-WSD11-RT-E-0003 | 2025-03-25 | THP Short Circuit Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000827 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Short Circuit Study Report" | AWC
000828 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 0 | 131242-WSW41-MS-M-0005 | 2024-11-21 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-05 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000828 | 2024-11-21 | 2024-12-11 | 1 | NAP | Approved with Comments | 2 | "MSRA and SWP for Delivery of 2000kVA Transformer " | AWC
000828 | 01 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 1 | 131242-WSW41-MS-M-0005 | 2024-12-11 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2024-12-30 | 13 | Approved with Comments | YES | 2025-01-17 | NO | Resubmitted | 0 |  |  | 000828 | 2024-11-21 | 2024-12-11 | 1 | AWC | Approved with Comments | 2 | "MSRA and SWP for Delivery of 2000kVA Transformer " | AWC
000829 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5006 | A | 131242-WST02-DR-A-5006 | 2024-11-21 | Fire Seal Detail | Rev.0: Not approved. Please revise and resubmit. | 2024-12-19 | 2024-12-06 | 11 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000829 | 2024-11-21 | 2024-11-21 | A | NAP | Not Approved | 1 | "Fire Seal Detail" | NAP
000830 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0020 | 0 | 131242-WSW41-QA-C-0020 | 2024-11-21 | Monthly Concrete Cube Records for Structural works for September 2024 | For information. | 2024-12-19 | 2024-11-27 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000830 | 2024-11-21 | 2024-11-21 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works for September 2024" | INF
000831 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | A | 131242-WST02-DR-A-5003 | 2024-11-22 | SSN_CAT Ladder | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-08 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " | NAP
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | - | 131242-WST02-DR-A-5003 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " | NAP
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1007 | A | 131242-WST02-DR-A-1007 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2025-04-04 | 2025-04-04 | A | NAP | Not Approved | 1 | "SSN_CAT Ladder " | NAP
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1008 | A | 131242-WST02-DR-A-1008 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2025-04-04 | 2025-04-04 | A | NAP | Not Approved | 1 | "SSN_CAT Ladder " | NAP
000831 | 02 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | D | 131242-WST02-DR-A-5003 | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | 41 | Not Approved | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " | NAP
000831 | 02 | Anna | CSA | NA | PE report | NA | RT | A | NA | C | PE report-NA-RT-A-NA | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | 41 | Not Approved | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 000831 | 2025-08-19 | 2025-08-19 | C | NAP | Not Approved | 1 | "SSN_CAT Ladder " | NAP
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1002 | A | 131242-WST02-DR-A-1002 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | AWC | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 2001 | A | 131242-WST02-DR-A-2001 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | AWC | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5004 | A | 131242-WST02-DR-A-5004 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832 | 2024-11-22 | 2024-11-22 | A | AWC | Approved with Comments | 1 | "SSN Electrical Building Archi Drawing" | AWC
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5005 | A | 131242-WST02-DR-A-5005 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832 | 2024-11-22 | 2024-11-22 | A | AWC | Approved with Comments | 1 | "SSN Electrical Building Archi Drawing" | AWC
000833 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 5002 | A | 131242-WST02-DR-A-5002 | 2024-11-22 | SSN Door Window Schedule | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" | AWC
000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | B | 131242-WST02-DR-A-5002 | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" | AWC
000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5007 | A | 131242-WST02-DR-A-5007 | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2025-02-18 | 2025-02-18 | A | AWC | Approved with Comments | 1 | "SSN Door Window Schedule" | AWC
000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" | AWC
000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2025-08-19 | 2025-11-21 | A.2 | AWC | Approved with Comments | 2 | "SSN Door Window Schedule" | AWC
000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | 9 | Approved with Comments | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" | AWC
000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | 9 | Approved with Comments | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 000833 | 2025-08-19 | 2025-11-21 | A.2 | AWC | Approved with Comments | 2 | "SSN Door Window Schedule" | AWC
000834 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2024-11-22 | SSN Railing Layout | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | AWC | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
000835 | 00 | Franklin | CSA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-C-1025 | 2024-11-22 | SSN Pavement Plan | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-08 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000835&&002018 | 2024-11-22 | 2026-02-24 | A | AWC | Approved with Comments | 2 | "SSN Pavement Plan" && "C4B SSN Drain Hydraulic Calculation" | AWC
000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-S-5400 | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | 10 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1400 | A | 131242-WST02-DR-S-1400 | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | 10 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
000837 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 0 | 131242-WSD11-CL-S-0005 | 2024-11-22 | Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check | Approved | 2024-12-20 | 2024-12-06 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | APP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | APP
000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0034 | 0 | 131242-WSD11-MI-P-0034 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000838 | 2024-11-22 | 2024-11-22 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | INF
000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0035 | 0 | 131242-WSD11-MI-P-0035 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000838 | 2024-11-22 | 2024-11-22 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | INF
000839 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0020 | 0 | 131242-WSW41-MS-C-0020 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold | Approved | 2024-12-20 | 2024-12-18 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000839 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold" | APP
000840 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0021 | 0 | 131242-WSW41-MS-C-0021 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold | Approved | 2024-12-20 | 2024-12-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000840 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold" | APP
000841 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0022 | 0 | 131242-WSW41-MS-C-0022 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold | Approved | 2024-12-20 | 2024-12-18 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000841 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold" | APP
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST619 | A | 131242-WSD11-DR-S-0304_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST619 | A | 131242-WSD11-DR-S-0305_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619 | A | 131242-WSD11-DR-S-1100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619 | A | 131242-WSD11-DR-S-1101_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619 | A | 131242-WSD11-DR-S-2100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619 | A | 131242-WSD11-DR-S-3100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619 | A | 131242-WSD11-DR-S-5100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619 | A | 131242-WSD11-DR-S-5101_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619 | A | 131242-WSD11-DR-S-8002_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " | AWC
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1500_ST611 | A | 131242-WST02-DR-S-1500_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | AWC
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5500_ST611 | A | 131242-WST02-DR-S-5500_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | AWC
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5501_ST611 | A | 131242-WST02-DR-S-5501_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | AWC
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000844 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment reply | NA | 131242-WSD11-DR-S-comment reply | 2025-08-22 | THP Courtyard RC Plinth Detail | Rev.1: For Information | 2025-09-11 | 2025-09-17 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000844 | 2025-08-22 | 2025-08-22 | NA | INF | For Information | 1 | "THP Courtyard RC Plinth Detail" | INF
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1505_Superceded | A | 131242-WSD11-DR-S-1505_Superceded | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-13 | 2024-12-18 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000845 | 2024-11-25 | 2024-11-25 | A | REJ | Rejected | 1 | " THP Courtyard Equipment Anchor Bolt Details" | REJ
000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3505_Superceded | A | 131242-WSD11-DR-S-3505_Superceded | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-23 | 2024-12-18 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000845 | 2024-11-25 | 2024-11-25 | A | REJ | Rejected | 1 | " THP Courtyard Equipment Anchor Bolt Details" | REJ
000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1505 | A | 131242-WSD11-DR-S-1505 | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-08 | 2025-02-12 | 40 | Approved with Comments | YES | 2025-03-04 | NO | Resubmitted | 0 |  |  | 000845 | 2024-12-18 | 2024-12-18 | A | AWC | Approved with Comments | 1 | " THP Courtyard Equipment Anchor Bolt Details" | AWC
000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3505 | A | 131242-WSD11-DR-S-3505 | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-16 | 2025-02-12 | 40 | Approved with Comments | YES | 2025-03-04 | NO | Resubmitted | 0 |  |  | 000845 | 2024-12-18 | 2024-12-18 | A | AWC | Approved with Comments | 1 | " THP Courtyard Equipment Anchor Bolt Details" | AWC
000846 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 0 | 131242-WST02-DS-M-5481 | 2024-11-28 | Data Sheet for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 | In progress: 1). await TVU to confirm motor area (safety zone or not, Qili checking w TUV, will discuss with SO this Friday); 2). needTenwit confirm anchor bolt detail in C&S Dwg -> in 2 weeks | 000846 | 2024-11-28 | 2025-03-27 | 1 | AWC | Approved | 2 | "Data Sheet for Hyperbolic Mixer" | APP
000846 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 1 | 131242-WST02-DS-M-5481 | 2025-03-27 | Data Sheet for Hyperbolic Mixer | Rev 1: Approved | 2025-04-16 | 2025-04-27 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000846 | 2024-11-28 | 2025-03-27 | 1 | APP | Approved | 2 | "Data Sheet for Hyperbolic Mixer" | APP
000847 | 00 | Yibo/ Qili | Mech | NA | 131242 | WST02 | CL | P | 5481 | 0 | 131242-WST02-CL-P-5481 | 2024-11-28 | SSN Hyperbolic Mixer CFD | Rev 0: Not approved - Revise and Resubmit | 2024-12-27 | 2024-12-14 | 12 | Not Approved | YES | 2025-01-02 | NO | Resubmitted | 0 |  | To be handled by Process (QiLi), will be VO for revised CFD version | 000847 | 2024-11-28 | 2024-11-28 | 0 | NAP | Not Approved | 1 | "SSN Hyperbolic Mixer CFD" | NAP
000848 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0014 | 0 | 131242-WST02-VI-E-0014 | 2024-11-28 | Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  | To follow-up with HDMANN. | 000848 | 2024-11-28 | 2024-11-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" | AWC
000849 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 0 | 131242-WST02-RT-E-0007 | 2024-11-28 | SSN Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 |  | 000849 | 2024-11-28 | 2025-05-04 | 1 | AWC | Approved with Comments | 2 | "SSN Load Flow Study Report" | AWC
000849 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 1 | 131242-WST02-RT-E-0007 | 2025-05-04 | SSN Load Flow Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-22 | 2025-05-30 | 19 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 000849 | 2024-11-28 | 2025-05-04 | 1 | AWC | Approved with Comments | 2 | "SSN Load Flow Study Report" | AWC
000850 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 0 | 131242-WST02-RT-E-0008 | 2024-11-28 | SSN Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 |  | 000850 | 2024-11-28 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "SSN Short Circuit Study Report" | AWC
000850 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 1 | 131242-WST02-RT-E-0008 | 2025-05-30 | SSN Short Circuit Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000850 | 2024-11-28 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "SSN Short Circuit Study Report" | AWC
000851 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0036 | 0 | 131242-WSW41-MI-C-0036 | 2024-11-28 | CSA Meeting Minutes 0036_14112024 | For Information | 2024-12-27 | 2024-12-07 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000851 | 2024-11-28 | 2024-11-28 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0036_14112024" | INF
000852 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0013 | 0 | 131242-WSW41-RT-C-0013 | 2024-11-28 | Quarterly Safety Review Follow Up on SSN RC Works | For Information | 2024-12-27 | 2024-12-07 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000852&&001420 | 2024-11-28 | 2025-07-01 | 1 | INF | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on SSN RC Works" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
000853 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0022 | 0 | 131242-WST02-VI-I-0022 | 2024-11-28 | Vendor approval of SSN Package (Autosampler) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-27 | 2025-03-14 | 76 | Approved with Comments | YES | 2025-04-03 | NO | Resubmitted | 0 |  |  | 000853 | 2024-11-28 | 2024-11-28 | 0 | AWC | Approved with Comments | 1 | "Vendor approval of SSN Package (Autosampler) " | AWC
000854 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0003 | 0 | 131242-WST02-VI-A-0003 | 2024-11-28 | Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd. | Approved | 2024-12-27 | 2024-12-07 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000854 | 2024-11-28 | 2024-11-28 | 0 | APP | Approved | 1 | "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." | APP
000855 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004 | 2024-11-28 | Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd. | Approved | 2024-12-27 | 2024-12-05 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000855&&001327 | 2024-11-28 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " | APP
000856 | 00 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 0 | 131242-WST02-QA-A-0003 | 2024-11-29 | 2Hrs Fire rated AAC Blocks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2024-12-06 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000856 | 2024-11-29 | 2024-12-20 | 1 | NAP | Approved | 2 | "2Hrs Fire rated AAC Blocks" | APP
000856 | 01 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 1 | 131242-WST02-QA-A-0003 | 2024-12-20 | 2Hrs Fire rated AAC Blocks | Rev.1: Approved | 2025-01-10 | 2025-01-02 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000856 | 2024-11-29 | 2024-12-20 | 1 | APP | Approved | 2 | "2Hrs Fire rated AAC Blocks" | APP
000857 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 0 | 131242-WSW41-DS-I-0001 | 2024-11-29 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-30 | 2025-03-25 | 82 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000857 | 2024-11-29 | 2025-09-15 | 1 | AWC | Approved with Comments | 2 | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | AWC
000857 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 1 | 131242-WSW41-DS-I-0001 | 2025-09-15 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-10-03 | 2025-12-02 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000857 | 2024-11-29 | 2025-09-15 | 1 | AWC | Approved with Comments | 2 | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | AWC
000858 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0008 | 0 | 131242-WSW41-QA-E-0008 | 2024-11-30 | FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-12-30 | 2024-12-14 | 10 | Approved with Comments | YES | 2025-01-02 | NO | Resubmitted | 0 |  |  | 000858 | 2024-11-30 | 2024-11-30 | 0 | AWC | Approved with Comments | 1 | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5218 | A | 131242-WST02-SD-S-5218 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5219 | A | 131242-WST02-SD-S-5219 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5220 | A | 131242-WST02-SD-S-5220 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5221 | A | 131242-WST02-SD-S-5221 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5223 | A | 131242-WST02-SD-S-5223 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5224 | A | 131242-WST02-SD-S-5224 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1201 | A | 131242-WST02-SD-S-1201 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1202 | A | 131242-WST02-SD-S-1202 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1203 | A.1 | 131242-WST02-SD-S-1203 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A.1 | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1204 | A | 131242-WST02-SD-S-1204 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5212 | A | 131242-WST02-SD-S-5212 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5213 | A | 131242-WST02-SD-S-5213 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5214 | A | 131242-WST02-SD-S-5214 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5215 | A | 131242-WST02-SD-S-5215 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5216 | A | 131242-WST02-SD-S-5216 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5217 | A | 131242-WST02-SD-S-5217 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" | AWC
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1027 | A | 131242-WST02-DR-C-1027 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" | NAP
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1026 | A | 131242-WST02-DR-C-1026 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" | NAP
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5008 | A | 131242-WST02-DR-C-5008 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" | NAP
000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210 | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 4 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | APP
000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200 | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | APP
000861 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | cmmt sheet | NA | 131242-WSD11-DR-S-cmmt sheet | 2025-09-15 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-25 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000861 | 2025-09-15 | 2025-09-15 | NA | INF | For Information | 1 | "THP- Valve Pit, Sump and Kerb Detail" | INF
000862 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0018 | 0 | 131242-WSW41-PS-PM-0018 | 2024-11-30 | Monthly Progress Presentation No. 18 (1124) | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000862 | 2024-11-30 | 2024-11-30 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 18 (1124)" | INF
000863 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0018 | 0 | 131242-WSW41-MI-PM-0018 | 2024-11-30 | Monthly Progress Meeting Minutes 0018_20241113 | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000863 | 2024-11-30 | 2024-11-30 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0018_20241113" | INF
000864 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0031 | 0 | 131242-WSW41-VI-M-0031 | 2024-12-02 | Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2024-06-12 | 0 | Approved with Comments | YES | 2024-07-02 | NO | Resubmitted | 0 |  |  | 000864 | 2024-12-02 | 2024-12-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd." | AWC
000865 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 0 | 131242-WSW41-PC-W-0017 | 2024-12-02 | Payment Claim No.17 | As requested by C4BJV to reject this submittal and resubmit. | 2024-12-31 | 2024-12-03 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000865 | 2024-12-02 | 2024-12-03 | 1 | REJ | Approved | 2 | "Payment Claim No.17" | APP
000865 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 1 | 131242-WSW41-PC-W-0017 | 2024-12-03 | Payment Claim No.17 | Rev(1): Approved. Please refer to S.O. correspondence no 259 3 Dec 2024. | 2024-12-23 | 2025-01-08 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000865 | 2024-12-02 | 2024-12-03 | 1 | APP | Approved | 2 | "Payment Claim No.17" | APP
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | A | 131242-WST02-DR-EP-3008 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | A | 131242-WST02-DR-EP-3009 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | A | 131242-WST02-DR-EP-3010 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | A | 131242-WST02-DR-EP-3011 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | A | 131242-WST02-DR-EP-3012 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | A | 131242-WST02-DR-EP-3013 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | A | 131242-WST02-DR-EP-3014 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | A | 131242-WST02-DR-EP-3015 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | A | 131242-WST02-DR-EP-3016 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | A | 131242-WST02-DR-EP-3017 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | A | 131242-WST02-DR-EP-3018 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | A | 131242-WST02-DR-EP-3019 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | A | 131242-WST02-DR-EP-3020 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | A | 131242-WST02-DR-EP-3021 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | A | 131242-WST02-DR-EP-3022 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | A | 131242-WST02-DR-EP-3023 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | A | 131242-WST02-DR-EP-7110 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | A | 131242-WST02-DR-EP-7111 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | A | 131242-WST02-DR-EP-7112 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | A | 131242-WST02-DR-EP-7113 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | A | 131242-WST02-DR-EP-7114 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | A | 131242-WST02-DR-EP-7115 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | A | 131242-WST02-DR-EP-7116 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | A | 131242-WST02-DR-EP-7117 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | A | 131242-WST02-DR-EP-7118 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | A | 131242-WST02-DR-EP-7119 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | A | 131242-WST02-DR-EP-7120 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | A | 131242-WST02-DR-EP-7121 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | A | 131242-WST02-DR-EP-7122 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | A | 131242-WST02-DR-EP-7123 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | A | 131242-WST02-DR-EP-7124 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | A | 131242-WST02-DR-EP-7125 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | A | 131242-WST02-DR-EP-7126 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | A | 131242-WST02-DR-EP-7127 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | A | 131242-WST02-DR-EI-7040 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | A | 131242-WST02-DR-EI-7041 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | A | 131242-WST02-DR-EI-7042 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | A | 131242-WST02-DR-EI-7043 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | A | 131242-WST02-DR-EI-7044 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | A | 131242-WST02-DR-EI-7045 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | A | 131242-WST02-DR-EI-7046 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | A | 131242-WST02-DR-EI-7047 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | A | 131242-WST02-DR-EI-7048 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | A | 131242-WST02-DR-EI-7049 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | A | 131242-WST02-DR-EI-7050 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | A | 131242-WST02-DR-EI-7051 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | A | 131242-WST02-DR-EI-7052 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | A | 131242-WST02-DR-EI-7053 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | A | 131242-WST02-DR-EI-7054 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | A | 131242-WST02-DR-EI-7055 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | A | 131242-WST02-DR-EI-7060 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | A | 131242-WST02-DR-EI-7061 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | A | 131242-WST02-DR-EI-7062 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | A | 131242-WST02-DR-EI-7063 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | A | 131242-WST02-DR-EI-7064 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | A | 131242-WST02-DR-EI-7065 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | A | 131242-WST02-DR-EI-7066 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | A | 131242-WST02-DR-EI-7067 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | A | 131242-WST02-DR-EI-7068 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | A | 131242-WST02-DR-EI-7069 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | A | 131242-WST02-DR-EI-7070 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | A | 131242-WST02-DR-EI-7071 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | A | 131242-WST02-DR-EI-7072 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | A | 131242-WST02-DR-EI-7073 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | A | 131242-WST02-DR-EI-7074 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | A | 131242-WST02-DR-EI-7075 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | B | 131242-WST02-DR-EI-7040 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | B | 131242-WST02-DR-EI-7041 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | B | 131242-WST02-DR-EI-7042 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | B | 131242-WST02-DR-EI-7043 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | B | 131242-WST02-DR-EI-7044 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | B | 131242-WST02-DR-EI-7045 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | B | 131242-WST02-DR-EI-7046 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | B | 131242-WST02-DR-EI-7047 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | B | 131242-WST02-DR-EI-7048 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | B | 131242-WST02-DR-EI-7049 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | B | 131242-WST02-DR-EI-7050 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | B | 131242-WST02-DR-EI-7051 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | B | 131242-WST02-DR-EI-7052 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | B | 131242-WST02-DR-EI-7053 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | B | 131242-WST02-DR-EI-7054 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | B | 131242-WST02-DR-EI-7055 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | B | 131242-WST02-DR-EI-7056 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | B | 131242-WST02-DR-EI-7057 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | B | 131242-WST02-DR-EI-7058 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | B | 131242-WST02-DR-EI-7060 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | B | 131242-WST02-DR-EI-7061 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | B | 131242-WST02-DR-EI-7062 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | B | 131242-WST02-DR-EI-7063 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | B | 131242-WST02-DR-EI-7064 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | B | 131242-WST02-DR-EI-7065 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | B | 131242-WST02-DR-EI-7066 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | B | 131242-WST02-DR-EI-7067 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | B | 131242-WST02-DR-EI-7068 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | B | 131242-WST02-DR-EI-7069 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | B | 131242-WST02-DR-EI-7070 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | B | 131242-WST02-DR-EI-7071 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | B | 131242-WST02-DR-EI-7072 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | B | 131242-WST02-DR-EI-7073 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | B | 131242-WST02-DR-EI-7074 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | B | 131242-WST02-DR-EI-7075 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | B | 131242-WST02-DR-EI-7076 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | B | 131242-WST02-DR-EI-7077 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | B | 131242-WST02-DR-EI-7078 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | B | 131242-WST02-DR-EP-3012 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | B | 131242-WST02-DR-EP-3013 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | B | 131242-WST02-DR-EP-3014 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | B | 131242-WST02-DR-EP-3015 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | B | 131242-WST02-DR-EP-3016 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | B | 131242-WST02-DR-EP-3017 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | B | 131242-WST02-DR-EP-3018 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | B | 131242-WST02-DR-EP-3019 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | B | 131242-WST02-DR-EP-3020 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | B | 131242-WST02-DR-EP-3021 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | B | 131242-WST02-DR-EP-3022 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | B | 131242-WST02-DR-EP-3023 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | B | 131242-WST02-DR-EP-7110 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | B | 131242-WST02-DR-EP-7111 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | B | 131242-WST02-DR-EP-7112 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | B | 131242-WST02-DR-EP-7113 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | B | 131242-WST02-DR-EP-7114 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | B | 131242-WST02-DR-EP-7115 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | B | 131242-WST02-DR-EP-7116 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | B | 131242-WST02-DR-EP-7117 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | B | 131242-WST02-DR-EP-7118 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | B | 131242-WST02-DR-EP-7119 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | B | 131242-WST02-DR-EP-7120 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | B | 131242-WST02-DR-EP-7121 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | B | 131242-WST02-DR-EP-7122 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | B | 131242-WST02-DR-EP-7123 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | B | 131242-WST02-DR-EP-7124 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | B | 131242-WST02-DR-EP-7125 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | C | 131242-WST02-DR-EI-7040 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | C | 131242-WST02-DR-EI-7041 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | C | 131242-WST02-DR-EI-7042 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | C | 131242-WST02-DR-EI-7043 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | C | 131242-WST02-DR-EI-7044 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | C | 131242-WST02-DR-EI-7045 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | C | 131242-WST02-DR-EI-7046 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | C | 131242-WST02-DR-EI-7047 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | C | 131242-WST02-DR-EI-7048 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | C | 131242-WST02-DR-EI-7049 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | C | 131242-WST02-DR-EI-7050 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | C | 131242-WST02-DR-EI-7051 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | C | 131242-WST02-DR-EI-7052 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | C | 131242-WST02-DR-EI-7053 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | C | 131242-WST02-DR-EI-7054 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | C | 131242-WST02-DR-EI-7055 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | C | 131242-WST02-DR-EI-7056 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | C | 131242-WST02-DR-EI-7057 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | C | 131242-WST02-DR-EI-7058 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | C | 131242-WST02-DR-EI-7060 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | C | 131242-WST02-DR-EI-7061 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | C | 131242-WST02-DR-EI-7062 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | C | 131242-WST02-DR-EI-7063 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | C | 131242-WST02-DR-EI-7064 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | C | 131242-WST02-DR-EI-7065 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | C | 131242-WST02-DR-EI-7066 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | C | 131242-WST02-DR-EI-7067 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | C | 131242-WST02-DR-EI-7068 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | C | 131242-WST02-DR-EI-7069 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | C | 131242-WST02-DR-EI-7070 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | C | 131242-WST02-DR-EI-7071 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | C | 131242-WST02-DR-EI-7072 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | C | 131242-WST02-DR-EI-7073 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | C | 131242-WST02-DR-EI-7074 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | C | 131242-WST02-DR-EI-7075 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | C | 131242-WST02-DR-EI-7076 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | C | 131242-WST02-DR-EI-7077 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | C | 131242-WST02-DR-EI-7078 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | C | 131242-WST02-DR-EP-3012 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | C | 131242-WST02-DR-EP-3013 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | C | 131242-WST02-DR-EP-3014 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | C | 131242-WST02-DR-EP-3015 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | C | 131242-WST02-DR-EP-3016 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | C | 131242-WST02-DR-EP-3017 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | C | 131242-WST02-DR-EP-3018 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | C | 131242-WST02-DR-EP-3019 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | C | 131242-WST02-DR-EP-3020 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | C | 131242-WST02-DR-EP-3021 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | C | 131242-WST02-DR-EP-3022 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | C | 131242-WST02-DR-EP-3023 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | C | 131242-WST02-DR-EP-7110 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | C | 131242-WST02-DR-EP-7111 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | C | 131242-WST02-DR-EP-7112 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | C | 131242-WST02-DR-EP-7113 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | C | 131242-WST02-DR-EP-7114 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | C | 131242-WST02-DR-EP-7115 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | C | 131242-WST02-DR-EP-7116 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | C | 131242-WST02-DR-EP-7117 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | C | 131242-WST02-DR-EP-7118 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | C | 131242-WST02-DR-EP-7119 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | C | 131242-WST02-DR-EP-7120 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | C | 131242-WST02-DR-EP-7121 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | C | 131242-WST02-DR-EP-7122 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | C | 131242-WST02-DR-EP-7123 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | C | 131242-WST02-DR-EP-7124 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | C | 131242-WST02-DR-EP-7125 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | D | 131242-WST02-DR-EI-7040 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | D | 131242-WST02-DR-EI-7041 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | D | 131242-WST02-DR-EI-7042 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | D | 131242-WST02-DR-EI-7043 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | D | 131242-WST02-DR-EI-7044 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | D | 131242-WST02-DR-EI-7045 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | D | 131242-WST02-DR-EI-7046 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | D | 131242-WST02-DR-EI-7047 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | D | 131242-WST02-DR-EI-7048 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | D | 131242-WST02-DR-EI-7049 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | D | 131242-WST02-DR-EI-7050 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | D | 131242-WST02-DR-EI-7051 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | D | 131242-WST02-DR-EI-7052 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | D | 131242-WST02-DR-EI-7053 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | D | 131242-WST02-DR-EI-7054 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | D | 131242-WST02-DR-EI-7055 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | D | 131242-WST02-DR-EI-7056 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | D | 131242-WST02-DR-EI-7057 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | D | 131242-WST02-DR-EI-7058 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | D | 131242-WST02-DR-EI-7060 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | D | 131242-WST02-DR-EI-7061 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | D | 131242-WST02-DR-EI-7062 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | D | 131242-WST02-DR-EI-7063 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | D | 131242-WST02-DR-EI-7064 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | D | 131242-WST02-DR-EI-7065 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | D | 131242-WST02-DR-EI-7066 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | D | 131242-WST02-DR-EI-7067 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | D | 131242-WST02-DR-EI-7068 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | D | 131242-WST02-DR-EI-7069 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | D | 131242-WST02-DR-EI-7070 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | D | 131242-WST02-DR-EI-7071 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | D | 131242-WST02-DR-EI-7072 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | D | 131242-WST02-DR-EI-7073 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | D | 131242-WST02-DR-EI-7074 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | D | 131242-WST02-DR-EI-7075 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | D | 131242-WST02-DR-EI-7076 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | D | 131242-WST02-DR-EI-7077 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | D | 131242-WST02-DR-EI-7078 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | D | 131242-WST02-DR-EP-3012 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | D | 131242-WST02-DR-EP-3013 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | D | 131242-WST02-DR-EP-3014 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | D | 131242-WST02-DR-EP-3015 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | D | 131242-WST02-DR-EP-3016 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | D | 131242-WST02-DR-EP-3017 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | D | 131242-WST02-DR-EP-3018 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | D | 131242-WST02-DR-EP-3019 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | D | 131242-WST02-DR-EP-3020 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | D | 131242-WST02-DR-EP-3021 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | D | 131242-WST02-DR-EP-3022 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | D | 131242-WST02-DR-EP-3023 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | D | 131242-WST02-DR-EP-7110 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | D | 131242-WST02-DR-EP-7111 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | D | 131242-WST02-DR-EP-7112 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | D | 131242-WST02-DR-EP-7113 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | D | 131242-WST02-DR-EP-7114 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | D | 131242-WST02-DR-EP-7115 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | D | 131242-WST02-DR-EP-7116 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | D | 131242-WST02-DR-EP-7117 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | D | 131242-WST02-DR-EP-7118 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | D | 131242-WST02-DR-EP-7119 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | D | 131242-WST02-DR-EP-7120 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | D | 131242-WST02-DR-EP-7121 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | D | 131242-WST02-DR-EP-7122 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | D | 131242-WST02-DR-EP-7123 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | D | 131242-WST02-DR-EP-7124 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | D | 131242-WST02-DR-EP-7125 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | A | 131242-WST02-DR-EP-3038 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | A | 131242-WST02-DR-EP-3039 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | A | 131242-WST02-DR-EP-3040 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | A | 131242-WST02-DR-EP-3041 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | A | 131242-WST02-DR-EP-3042 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | A | 131242-WST02-DR-EP-3043 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | A | 131242-WST02-DR-EP-3044 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | A | 131242-WST02-DR-EP-3045 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | A | 131242-WST02-DR-EP-3046 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | A | 131242-WST02-DR-EP-3047 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | A | 131242-WST02-DR-EP-3048 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | A | 131242-WST02-DR-EP-3049 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | A | 131242-WST02-DR-EP-3050 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | A | 131242-WST02-DR-EP-3051 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | A | 131242-WST02-DR-EP-7136 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | A | 131242-WST02-DR-EP-7137 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | A | 131242-WST02-DR-EP-7138 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | A | 131242-WST02-DR-EP-7139 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | A | 131242-WST02-DR-EP-7140 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | A | 131242-WST02-DR-EP-7141 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | A | 131242-WST02-DR-EI-7120 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | A | 131242-WST02-DR-EI-7121 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | A | 131242-WST02-DR-EI-7122 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | A | 131242-WST02-DR-EI-7123 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | A | 131242-WST02-DR-EI-7124 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | A | 131242-WST02-DR-EI-7125 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | A | 131242-WST02-DR-EI-7126 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | A | 131242-WST02-DR-EI-7127 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | A | 131242-WST02-DR-EI-7128 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | A | 131242-WST02-DR-EI-7140 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | A | 131242-WST02-DR-EI-7141 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | A | 131242-WST02-DR-EI-7142 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | A | 131242-WST02-DR-EI-7143 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | A | 131242-WST02-DR-EI-7144 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | A | 131242-WST02-DR-EI-7145 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | A | 131242-WST02-DR-EI-7146 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | A | 131242-WST02-DR-EI-7147 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | A | 131242-WST02-DR-EI-7148 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | B | 131242-WST02-DR-EP-3038 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | B | 131242-WST02-DR-EP-3039 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | B | 131242-WST02-DR-EP-3040 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | B | 131242-WST02-DR-EP-3041 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | B | 131242-WST02-DR-EP-3042 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | B | 131242-WST02-DR-EP-3043 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | B | 131242-WST02-DR-EP-3044 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | B | 131242-WST02-DR-EP-3045 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | B | 131242-WST02-DR-EP-3046 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | B | 131242-WST02-DR-EP-3047 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | B | 131242-WST02-DR-EP-3048 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | B | 131242-WST02-DR-EP-3049 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | B | 131242-WST02-DR-EP-3050 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | B | 131242-WST02-DR-EP-3051 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | B | 131242-WST02-DR-EP-7136 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | B | 131242-WST02-DR-EP-7137 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | B | 131242-WST02-DR-EP-7138 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | B | 131242-WST02-DR-EP-7139 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | B | 131242-WST02-DR-EP-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | B | 131242-WST02-DR-EP-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | B | 131242-WST02-DR-EI-7120 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | B | 131242-WST02-DR-EI-7121 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | B | 131242-WST02-DR-EI-7122 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | B | 131242-WST02-DR-EI-7123 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | B | 131242-WST02-DR-EI-7124 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | B | 131242-WST02-DR-EI-7125 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | B | 131242-WST02-DR-EI-7126 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | B | 131242-WST02-DR-EI-7127 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | B | 131242-WST02-DR-EI-7128 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | B | 131242-WST02-DR-EI-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | B | 131242-WST02-DR-EI-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | B | 131242-WST02-DR-EI-7142 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | B | 131242-WST02-DR-EI-7143 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | B | 131242-WST02-DR-EI-7144 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | B | 131242-WST02-DR-EI-7145 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | B | 131242-WST02-DR-EI-7146 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | B | 131242-WST02-DR-EI-7147 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | B | 131242-WST02-DR-EI-7148 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | B | 131242-WST02-DR-EI-7149 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2025-03-28 | 2025-03-28 | B | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | C | 131242-WST02-DR-EP-3038 | 2025-08-21 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | C | 131242-WST02-DR-EP-3039 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | C | 131242-WST02-DR-EP-3040 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | C | 131242-WST02-DR-EP-3041 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | C | 131242-WST02-DR-EP-3042 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | C | 131242-WST02-DR-EP-3043 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | C | 131242-WST02-DR-EP-3044 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | C | 131242-WST02-DR-EP-3045 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | C | 131242-WST02-DR-EP-3046 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | C | 131242-WST02-DR-EP-3047 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | C | 131242-WST02-DR-EP-3048 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | C | 131242-WST02-DR-EP-3049 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | C | 131242-WST02-DR-EP-3050 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | C | 131242-WST02-DR-EP-3051 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | C | 131242-WST02-DR-EP-7136 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | C | 131242-WST02-DR-EP-7137 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | C | 131242-WST02-DR-EP-7138 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | C | 131242-WST02-DR-EP-7139 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | C | 131242-WST02-DR-EP-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | C | 131242-WST02-DR-EP-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | C | 131242-WST02-DR-EI-7120 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | C | 131242-WST02-DR-EI-7121 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | C | 131242-WST02-DR-EI-7122 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | C | 131242-WST02-DR-EI-7123 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | C | 131242-WST02-DR-EI-7124 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | C | 131242-WST02-DR-EI-7125 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | C | 131242-WST02-DR-EI-7126 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | C | 131242-WST02-DR-EI-7127 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | C | 131242-WST02-DR-EI-7128 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | C | 131242-WST02-DR-EI-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | C | 131242-WST02-DR-EI-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | C | 131242-WST02-DR-EI-7142 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | C | 131242-WST02-DR-EI-7143 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | C | 131242-WST02-DR-EI-7144 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | C | 131242-WST02-DR-EI-7145 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | C | 131242-WST02-DR-EI-7146 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | C | 131242-WST02-DR-EI-7147 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | C | 131242-WST02-DR-EI-7148 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | C | 131242-WST02-DR-EI-7149 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000867 | 2025-03-28 | 2025-03-28 | B | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | AWC
000868 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 0 | 131242-WSW41-SP-C-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-31 | 2025-01-08 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | NAP | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | APP
000868 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 1 | 131242-WSW41-SP-C-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-17 | 55 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | AWC | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | APP
000868 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 2 | 131242-WSW41-SP-C-0022 | 2025-02-20 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R2: Approved | 2025-03-12 | 2025-03-04 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | APP | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | APP
000869 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 0 | 131242-WSW41-SP-C-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R0: Not Approved. Please refer to comment sheet for resubmission | 2024-12-31 | 2025-01-08 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000869 | 2024-12-02 | 2024-12-02 | 0 | NAP | Not Approved | 2 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | NAP
000869 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 1 | 131242-WSW41-SP-C-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R1:Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-03 | 45 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000869 | 2024-12-02 | 2024-12-02 | 0 | AWC | Not Approved | 2 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | NAP
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | A | 131242-WST02-DR-EP-3024 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | A | 131242-WST02-DR-EP-3025 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | A | 131242-WST02-DR-EP-3026 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | A | 131242-WST02-DR-EP-3027 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | A | 131242-WST02-DR-EP-3028 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | A | 131242-WST02-DR-EP-3029 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | A | 131242-WST02-DR-EP-3030 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | A | 131242-WST02-DR-EP-3031 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | A | 131242-WST02-DR-EP-3032 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | A | 131242-WST02-DR-EP-3033 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | A | 131242-WST02-DR-EP-3034 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | A | 131242-WST02-DR-EP-3035 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | A | 131242-WST02-DR-EI-7080 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | A | 131242-WST02-DR-EI-7081 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | A | 131242-WST02-DR-EI-7082 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | A | 131242-WST02-DR-EI-7083 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | A | 131242-WST02-DR-EI-7084 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | A | 131242-WST02-DR-EI-7085 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | A | 131242-WST02-DR-EI-7086 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | A | 131242-WST02-DR-EI-7087 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | A | 131242-WST02-DR-EI-7088 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | A | 131242-WST02-DR-EI-7089 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | A | 131242-WST02-DR-EI-7090 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | A | 131242-WST02-DR-EI-7091 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | A | 131242-WST02-DR-EI-7100 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | A | 131242-WST02-DR-EI-7101 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | A | 131242-WST02-DR-EI-7102 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | A | 131242-WST02-DR-EI-7103 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | A | 131242-WST02-DR-EI-7104 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | A | 131242-WST02-DR-EI-7105 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | A | 131242-WST02-DR-EI-7106 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | A | 131242-WST02-DR-EI-7107 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | A | 131242-WST02-DR-EI-7108 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | A | 131242-WST02-DR-EI-7109 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | A | 131242-WST02-DR-EI-7110 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | A | 131242-WST02-DR-EI-7111 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | B | 131242-WST02-DR-EP-3024 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | B | 131242-WST02-DR-EP-3025 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | B | 131242-WST02-DR-EP-3026 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | B | 131242-WST02-DR-EP-3027 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | B | 131242-WST02-DR-EP-3028 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | B | 131242-WST02-DR-EP-3029 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | B | 131242-WST02-DR-EP-3030 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | B | 131242-WST02-DR-EP-3031 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | B | 131242-WST02-DR-EP-3032 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | B | 131242-WST02-DR-EP-3033 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | B | 131242-WST02-DR-EP-3034 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | B | 131242-WST02-DR-EP-3035 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | B | 131242-WST02-DR-EP-7126 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | B | 131242-WST02-DR-EP-7127 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | B | 131242-WST02-DR-EP-7128 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | B | 131242-WST02-DR-EP-7129 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | B | 131242-WST02-DR-EP-7130 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | B | 131242-WST02-DR-EP-7131 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | B | 131242-WST02-DR-EP-7132 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | B | 131242-WST02-DR-EP-7133 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | B | 131242-WST02-DR-EP-7134 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | B | 131242-WST02-DR-EP-7135 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | B | 131242-WST02-DR-EI-7080 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | B | 131242-WST02-DR-EI-7081 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | B | 131242-WST02-DR-EI-7082 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | B | 131242-WST02-DR-EI-7083 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | B | 131242-WST02-DR-EI-7084 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | B | 131242-WST02-DR-EI-7085 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | B | 131242-WST02-DR-EI-7086 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | B | 131242-WST02-DR-EI-7087 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | B | 131242-WST02-DR-EI-7088 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | B | 131242-WST02-DR-EI-7089 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | B | 131242-WST02-DR-EI-7090 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | B | 131242-WST02-DR-EI-7091 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | B | 131242-WST02-DR-EI-7092 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | B | 131242-WST02-DR-EI-7100 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | B | 131242-WST02-DR-EI-7101 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | B | 131242-WST02-DR-EI-7102 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | B | 131242-WST02-DR-EI-7103 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | B | 131242-WST02-DR-EI-7104 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | B | 131242-WST02-DR-EI-7105 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | B | 131242-WST02-DR-EI-7106 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | B | 131242-WST02-DR-EI-7107 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | B | 131242-WST02-DR-EI-7108 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | B | 131242-WST02-DR-EI-7109 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | B | 131242-WST02-DR-EI-7110 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | B | 131242-WST02-DR-EI-7111 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | B | 131242-WST02-DR-EI-7112 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | C | 131242-WST02-DR-EP-3024 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | C | 131242-WST02-DR-EP-3025 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | C | 131242-WST02-DR-EP-3026 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | C | 131242-WST02-DR-EP-3027 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | C | 131242-WST02-DR-EP-3028 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | C | 131242-WST02-DR-EP-3029 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | C | 131242-WST02-DR-EP-3030 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | C | 131242-WST02-DR-EP-3031 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | C | 131242-WST02-DR-EP-3032 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | C | 131242-WST02-DR-EP-3033 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | C | 131242-WST02-DR-EP-3034 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | C | 131242-WST02-DR-EP-3035 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | C | 131242-WST02-DR-EP-7126 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | C | 131242-WST02-DR-EP-7127 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | C | 131242-WST02-DR-EP-7128 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | C | 131242-WST02-DR-EP-7129 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | C | 131242-WST02-DR-EP-7130 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | C | 131242-WST02-DR-EP-7131 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | C | 131242-WST02-DR-EP-7132 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | C | 131242-WST02-DR-EP-7133 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | C | 131242-WST02-DR-EP-7134 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | C | 131242-WST02-DR-EP-7135 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | C | 131242-WST02-DR-EI-7080 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | C | 131242-WST02-DR-EI-7081 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | C | 131242-WST02-DR-EI-7082 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | C | 131242-WST02-DR-EI-7083 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | C | 131242-WST02-DR-EI-7084 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | C | 131242-WST02-DR-EI-7085 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | C | 131242-WST02-DR-EI-7086 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | C | 131242-WST02-DR-EI-7087 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | C | 131242-WST02-DR-EI-7088 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | C | 131242-WST02-DR-EI-7089 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | C | 131242-WST02-DR-EI-7090 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | C | 131242-WST02-DR-EI-7091 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | C | 131242-WST02-DR-EI-7092 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | C | 131242-WST02-DR-EI-7100 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | C | 131242-WST02-DR-EI-7101 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | C | 131242-WST02-DR-EI-7102 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | C | 131242-WST02-DR-EI-7103 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | C | 131242-WST02-DR-EI-7104 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | C | 131242-WST02-DR-EI-7105 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | C | 131242-WST02-DR-EI-7106 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | C | 131242-WST02-DR-EI-7107 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | C | 131242-WST02-DR-EI-7108 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | C | 131242-WST02-DR-EI-7109 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | C | 131242-WST02-DR-EI-7110 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | C | 131242-WST02-DR-EI-7111 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | C | 131242-WST02-DR-EI-7112 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | AWC
000871 | 00 | Thet Myo | QAQC | NA | 131242 | WSD11 | MM | S | 0001 | 0 | 131242-WSD11-MM-S-0001 | 2024-12-03 | THP Courtyard SCDF Consultation Letter | For Information | 2025-01-01 | 2024-11-14 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000871 | 2024-12-03 | 2024-12-03 | 0 | INF | For Information | 1 | "THP Courtyard SCDF Consultation Letter" | INF
000872 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0026 | 0 | 131242-WSW41-QA-M-0026 | 2024-12-04 | Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-02 | 2024-12-14 | 8 | Approved with Comments | YES | 2025-01-02 | NO | Resubmitted | 0 |  |  | 000872 | 2024-12-04 | 2024-12-04 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" | AWC
000873 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0009 | 0 | 131242-WST02-QA-E-0009 | 2024-12-04 | FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-02 | 2024-12-23 | 13 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  |  | 000873 | 2024-12-04 | 2024-12-04 | 0 | AWC | Approved with Comments | 1 | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " | AWC
000874 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 0 | 131242-WST02-CL-P-5431 | 2024-12-04 | SSN Catchpot Sizing Calculation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-02 | 2025-01-08 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | comments received on 14 Feb | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " | AWC
000874 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 1 | 131242-WST02-CL-P-5431 | 2025-03-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-28 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " | AWC
000874 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 2 | 131242-WST02-CL-P-5431 | 2025-07-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " | AWC
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | E | 131242-WST00-DR-S-8005_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | E | 131242-WST02-DR-S-0302_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0310_ST608_BCA | E | 131242-WST02-DR-S-0310_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0311_ST608_BCA | E | 131242-WST02-DR-S-0311_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0312_ST608_BCA | E | 131242-WST02-DR-S-0312_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | E | 131242-WST02-DR-S-1200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | E | 131242-WST02-DR-S-1201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | E | 131242-WST02-DR-S-1202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | E | 131242-WST02-DR-S-1203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | E | 131242-WST02-DR-S-1204_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | E | 131242-WST02-DR-S-1205_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | E | 131242-WST02-DR-S-2200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | E | 131242-WST02-DR-S-2201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | E | 131242-WST02-DR-S-2202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | E | 131242-WST02-DR-S-2203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | E | 131242-WST02-DR-S-3200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | E | 131242-WST02-DR-S-3201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | E | 131242-WST02-DR-S-3202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | E | 131242-WST02-DR-S-5200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | E | 131242-WST02-DR-S-5201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | E | 131242-WST02-DR-S-5202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | E | 131242-WST02-DR-S-5203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | E | 131242-WST02-DR-S-5204_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | E | 131242-WST02-DR-S-5205_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | E | 131242-WST02-DR-S-5206_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | E | 131242-WST02-DR-S-5207_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | E | 131242-WST02-DR-S-5208_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | E | 131242-WST02-DR-S-5209_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | INF
000876 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 0 | 131242-WST02-QA-A-0001 | 2024-12-05 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-03 | 2024-12-23 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000876 | 2024-12-05 | 2025-04-11 | 1 | AWC | Approved with Comments | 2 | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" | AWC
000876 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 1 | 131242-WST02-QA-A-0001 | 2025-04-11 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Approved with Comments | 2025-05-01 | 2025-06-09 | 41 | Approved with Comments | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 000876 | 2024-12-05 | 2025-04-11 | 1 | AWC | Approved with Comments | 2 | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" | AWC
000877 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0051 | 0 | 131242-WSW41-LT-PM-0051 | 2024-12-07 | CV of Team Member (CSEM) | Rev 0: Accepted for Information. | 2025-01-06 | 2025-03-25 | 76 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000877 | 2024-12-07 | 2024-12-07 | 0 | INF | For Information | 1 | "CV of Team Member (CSEM)" | INF
000878 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0052 | 0 | 131242-WSW41-LT-PM-0052 | 2024-12-07 | Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3) | Rev (0): Rejected. Please refer to S.O. correspondence no. 397 dated 10 Sep 25. | 2025-01-06 | 2025-09-23 | 206 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000878 | 2024-12-07 | 2024-12-07 | 0 | REJ | Rejected | 1 | "Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3)" | REJ
000879 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-IM-NA | 2024-12-09 | VCM Model Submission | For Information. | 2025-01-07 | 2024-12-23 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000879&&001888&&001941&&002009 | 2024-12-09 | 2026-02-09 | 0 | INF | For Information | 4 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | INF
000880 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5391 | 0 | 131242-WST02-CL-P-5391 | 2024-12-10 | Sampling Pump Calculation | Rev 0: Approved | 2025-01-08 | 2025-04-27 | 99 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000880 | 2024-12-10 | 2024-12-10 | 0 | APP | Approved | 1 | "Sampling Pump Calculation" | APP
000881 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 0 | 131242-WSW41-QA-M-0025 | 2024-12-10 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-08 | 2025-01-20 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000881 | 2024-12-10 | 2025-03-13 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" | APP
000881 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 1 | 131242-WSW41-QA-M-0025 | 2025-03-13 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Approved | 2025-04-02 | 2025-05-19 | 47 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000881 | 2024-12-10 | 2025-03-13 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" | APP
000882 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0005 | 0 | 131242-WST02-VI-E-0005 | 2024-12-10 | Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-08 | 2024-12-23 | 9 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  | To follow-up with Jebsen and Jessen. | 000882 | 2024-12-10 | 2024-12-10 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" | AWC
000883 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0008 | 0 | 131242-WST02-QA-A-0008 | 2024-12-10 | Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-08 | 2024-12-23 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000883 | 2024-12-10 | 2024-12-10 | 0 | APP | Approved | 1 | "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " | APP
000884 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0007 | 0 | 131242-WST02-QA-A-0007 | 2024-12-11 | Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-09 | 2024-12-23 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000884 | 2024-12-11 | 2024-12-11 | 0 | APP | Approved | 1 | "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " | APP
000885 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 0 | 131242-WSW41-QA-S-0010 | 2024-12-11 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.0: As requested by CES to reject this submission. | 2025-01-09 | 2024-12-14 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000885 | 2024-12-11 | 2024-12-18 | 1 | REJ | Approved with Comments | 2 | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" | AWC
000885 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 1 | 131242-WSW41-QA-S-0010 | 2024-12-18 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.1: Approved with comments. Please refer comment sheet for resubmission. | 2025-01-08 | 2024-12-23 | 3 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  |  | 000885 | 2024-12-11 | 2024-12-18 | 1 | AWC | Approved with Comments | 2 | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" | AWC
000886 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | I | 0006 | 0 | 131242-WSW41-VI-I-0006 | 2024-12-11 | Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-09 | 2025-01-08 | 20 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 |  |  | 000886 | 2024-12-11 | 2024-12-11 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" | AWC
000887 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0017 | 0 | 131242-WSW41-PS-HS-0017 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Sept 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2025-01-10 | 2024-12-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000887 | 2024-12-12 | 2024-12-12 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Sept 2024" | INF
000888 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0018 | 0 | 131242-WSW41-PS-HS-0018 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Oct 2024 | Rev 0: Scoring confirmed to be at 60/100 | 2025-01-10 | 2024-12-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000888 | 2024-12-12 | 2024-12-12 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Oct 2024" | INF
000889 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-01-20 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000889 | 2024-12-12 | 2024-12-12 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | AWC
000889 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 1: Approved. | 2025-01-02 | 2025-12-23 | 268 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000889 | 2024-12-12 | 2024-12-12 | 0 | APP | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | AWC
000890 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0019 | 0 | 131242-WSW41-RT-PM-0019 | 2024-12-13 | C4B Monthly Progress Report Number No.19 (11 24) | Rev. 0 - Approved with comments (see attached comment sheet / need to re-submit) | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000890 | 2024-12-13 | 2024-12-13 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.19 (11 24) " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | A | 131242-WSW41-DR-M-5201 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 | Pending vendor resubmission - Jash | 000891 | 2024-12-13 | 2025-03-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | A | 131242-WSW41-DR-M-5202 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | A | 131242-WSW41-DR-M-5203 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | A | 131242-WSW41-DR-M-5204 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | A | 131242-WSW41-DR-M-5205 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | A | 131242-WSW41-DR-M-5206 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | A | 131242-WSW41-DR-M-5207 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | A | 131242-WSW41-DR-M-5208 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | A | 131242-WSW41-DR-M-5209 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | A | 131242-WSW41-DR-M-5210 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | A | 131242-WSW41-DR-M-5211 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | A | 131242-WSW41-DR-M-5212 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | A | 131242-WSW41-DR-M-5213 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | A | 131242-WSW41-DR-M-5214 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | A | 131242-WSW41-DR-M-5215 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | A | 131242-WSW41-DR-M-5216 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | A | 131242-WSW41-DR-M-5217 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | A | 131242-WSW41-DR-M-5218 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | A | 131242-WSW41-DR-M-5219 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | A | 131242-WSW41-DR-M-5220 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | A | 131242-WSW41-DR-M-5221 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | B | 131242-WSW41-DR-M-5201 | 2025-03-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 18 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 | 2025-02-25 | Pending vendor resubmission - Jash | 000891 | 2024-12-13 | 2025-03-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | B | 131242-WSW41-DR-M-5202 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | B | 131242-WSW41-DR-M-5203 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | B | 131242-WSW41-DR-M-5204 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | B | 131242-WSW41-DR-M-5205 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | B | 131242-WSW41-DR-M-5206 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | B | 131242-WSW41-DR-M-5207 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | B | 131242-WSW41-DR-M-5208 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | B | 131242-WSW41-DR-M-5209 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | B | 131242-WSW41-DR-M-5210 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | B | 131242-WSW41-DR-M-5211 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | B | 131242-WSW41-DR-M-5212 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | B | 131242-WSW41-DR-M-5213 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | B | 131242-WSW41-DR-M-5214 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | B | 131242-WSW41-DR-M-5215 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | B | 131242-WSW41-DR-M-5216 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | B | 131242-WSW41-DR-M-5217 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | B | 131242-WSW41-DR-M-5218 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | B | 131242-WSW41-DR-M-5219 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | B | 131242-WSW41-DR-M-5220 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | B | 131242-WSW41-DR-M-5221 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5222 | A | 131242-WSW41-DR-M-5222 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5223 | A | 131242-WSW41-DR-M-5223 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5224 | A | 131242-WSW41-DR-M-5224 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5225 | A | 131242-WSW41-DR-M-5225 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5226 | A | 131242-WSW41-DR-M-5226 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5227 | A | 131242-WSW41-DR-M-5227 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " | AWC
000892 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0037 | 0 | 131242-WSW41-MI-C-0037 | 2024-12-13 | CSA Meeting Minutes 0037_28112024 | For Information | 2025-01-13 | 2024-12-30 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000892 | 2024-12-13 | 2024-12-13 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0037_28112024" | INF
000893 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0023 | 0 | 131242-WST02-VI-I-0023 | 2024-12-13 | Vendor Approval of SSN Package (Rotameter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-14 | 65 | Approved with Comments | YES | 2025-04-03 | NO | Resubmitted | 0 |  |  | 000893 | 2024-12-13 | 2024-12-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SSN Package (Rotameter)" | AWC
000894 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0050 | 0 | 131242-WSW41-LT-PM-0050 | 2024-12-13 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025. | 2025-01-13 | 2025-08-25 | 181 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000894 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | REJ
000895 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 0 | 131242-WSW41-DS-E-1390 | 2024-12-13 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2024-12-23 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000895 | 2024-12-13 | 2025-02-14 | 1 | AWC | Approved | 2 | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | APP
000895 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 1 | 131242-WSW41-DS-E-1390 | 2025-02-14 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 1: Approved. | 2025-03-06 | 2025-04-27 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000895 | 2024-12-13 | 2025-02-14 | 1 | APP | Approved | 2 | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | APP
000896 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 0 | 131242-WSW41-DS-E-1389 | 2024-12-13 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000896 | 2024-12-13 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | AWC
000896 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 1 | 131242-WSW41-DS-E-1389 | 2025-03-06 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-26 | 2025-04-27 | 37 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000896 | 2024-12-13 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | AWC
000897 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391 | 2024-12-13 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000897 | 2024-12-13 | 2025-03-11 | 0 | AWC | Approved | 2 | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | APP
000897 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391 | 2025-03-11 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 1: Approved. | 2025-03-31 | 2025-05-05 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000897 | 2024-12-13 | 2025-03-11 | 0 | APP | Approved | 2 | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | APP
000898 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023 | 2024-12-13 | MSRA and SWP for Installation of AAC Block Wall | Approved | 2025-01-13 | 2025-01-08 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000898&&001044 | 2024-12-13 | 2025-02-16 | 0 | APP | Approved | 2 | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | APP
000899 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0030 | 0 | 131242-WST02-DS-M-0030 | 2024-12-13 | Data Sheet for Blower Discharge Sliencer | Rev 0: Approved | 2025-01-13 | 2025-03-04 | 57 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000899 | 2024-12-13 | 2024-12-13 | 0 | APP | Approved | 1 | "Data Sheet for Blower Discharge Sliencer" | APP
000900 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 0 | 131242-WST02-DS-I -0002 | 2024-12-13 | Datasheet for Electromagnetic Flowmeter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-25 | 72 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000900 | 2024-12-13 | 2025-06-26 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Electromagnetic Flowmeter" | AWC
000900 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 1 | 131242-WST02-DS-I -0002 | 2025-06-26 | Datasheet for Electromagnetic Flowmeter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-16 | 2025-07-28 | 22 | Approved with Comments | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000900 | 2024-12-13 | 2025-06-26 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Electromagnetic Flowmeter" | AWC
000901 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0009 | 0 | 131242-WST02-QA-A-0009 | 2024-12-13 | Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh | For Information | 2025-01-13 | 2024-12-23 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000901 | 2024-12-13 | 2024-12-13 | 0 | INF | For Information | 1 | "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | INF
000902 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004_Withdraw | 0 | 131242-WSD11-QA-N-0004_Withdraw | 2024-12-13 | Instrument Differential Pressure Switch SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000902 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Instrument Differential Pressure Switch SAT" | REJ
000903 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005_Withdraw | 0 | 131242-WSD11-QA-N-0005_Withdraw | 2024-12-13 | Instrument Pressure Transmitter SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000903 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Instrument Pressure Transmitter SAT" | REJ
000904 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006_Withdraw | 0 | 131242-WSD11-QA-N-0006_Withdraw | 2024-12-13 | Penumatic on/ off Valve SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000904 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Penumatic on/ off Valve SAT" | REJ
000905 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002_Withdraw | 0 | 131242-WSD11-QA-N-0002_Withdraw | 2024-12-13 | Air Compresspor SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000905 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Air Compresspor SAT" | REJ
000906 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003_Withdraw | 0 | 131242-WSD11-QA-N-0003_Withdraw | 2024-12-13 | Air Dryer SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000906 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Air Dryer SAT" | REJ
000907 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 0 | 131242-WST02-RT-E-0009 | 2024-12-16 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000907 | 2024-12-16 | 2026-01-20 | 1 | AWC | Approved with Comments | 2 | "SSN Harmonics Study Report" | AWC
000907 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 1 | 131242-WST02-RT-E-0009 | 2026-01-20 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 000907 | 2024-12-16 | 2026-01-20 | 1 | PEN | Approved with Comments | 2 | "SSN Harmonics Study Report" | AWC
000908 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0004 | 0 | 131242-WSD11-RT-E-0004 | 2024-12-16 | THP Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 46 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000908 | 2024-12-16 | 2024-12-16 | 0 | AWC | Approved with Comments | 1 | "THP Harmonics Study Report" | AWC
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A | 131242-WSW41-DR-M-5128 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" | AWC
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A | 131242-WSW41-DR-M-5129 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" | AWC
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A | 131242-WSW41-DR-M-5130 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" | AWC
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A.1 | 131242-WSW41-DR-M-5128 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" | AWC
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.1 | 131242-WSW41-DR-M-5129 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" | AWC
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A.1 | 131242-WSW41-DR-M-5130 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" | AWC
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | AWC
000909 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.2 | 131242-WSW41-DR-M-5129 | 2025-06-25 | Pipe Support Standard- SWPR | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" | AWC
000910 | 00 | David | Mech | NA | 131242 | WSW41 | DS | M | 5341 | 0 | 131242-WSW41-DS-M-5341 | 2024-12-17 | Data Sheet of Auto Lubrication Unit for centrifugal pump | Rev 0: Not approved - Revise and Resubmit | 2025-01-15 | 2025-01-20 | 24 | Not Approved | YES | 2025-02-07 | NO | Resubmitted | 0 | 2025-03-28 | In Progress | 000910 | 2024-12-17 | 2024-12-17 | 0 | NAP | Not Approved | 1 | "Data Sheet of Auto Lubrication Unit for centrifugal pump" | NAP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A | 131242-WST02-DR-M-5401 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-28 | In Progress | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A | 131242-WST02-DR-M-5402 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A | 131242-WST02-DR-M-5403 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A | 131242-WST02-DR-M-5404 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A | 131242-WST02-DR-M-5405 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A | 131242-WST02-DR-M-5416 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A | 131242-WST02-DR-M-5417 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A | 131242-WST02-DR-M-5419 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A | 131242-WST02-DR-M-5420 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A.1 | 131242-WST02-DR-M-5401 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A.1 | 131242-WST02-DR-M-5402 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A.1 | 131242-WST02-DR-M-5403 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A.1 | 131242-WST02-DR-M-5404 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A.1 | 131242-WST02-DR-M-5405 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5406 | A.1 | 131242-WST02-DR-M-5406 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5407 | A.1 | 131242-WST02-DR-M-5407 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5408 | A.1 | 131242-WST02-DR-M-5408 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A.1 | 131242-WST02-DR-M-5416 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A.1 | 131242-WST02-DR-M-5417 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5418 | A.1 | 131242-WST02-DR-M-5418 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A.1 | 131242-WST02-DR-M-5419 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A.1 | 131242-WST02-DR-M-5420 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5421 | A.1 | 131242-WST02-DR-M-5421 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5422 | A.1 | 131242-WST02-DR-M-5422 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" | APP
000912 | 00 | Max | Project | NA | 131242 | WST02 | RT | S | 0001 | 0 | 131242-WST02-RT-S-0001 | 2024-12-18 | Safety Review Report for SSN Structures | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-16 | 2025-01-16 | 21 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000912 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Safety Review Report for SSN Structures" | AWC
000913 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0010 | 0 | 131242-WST02-QA-E-0010 | 2024-12-18 | FAT report for Earth cable, LV Power cable (Unwitnessed) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-02-18 | 44 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000913 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "FAT report for Earth cable, LV Power cable (Unwitnessed)" | AWC
000914 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0028 | 0 | 131242-WSD11-QA-M-0028 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 64 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000914 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI)" | AWC
000915 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0024 | 0 | 131242-WSD11-QA-M-0024 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 64 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000915 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | AWC
000916 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0013 | 0 | 131242-WSD11-CL-P-0013 | 2024-12-18 | THP G2D Plant Hydraulic Network Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-04-27 | 93 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000916 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "THP G2D Plant Hydraulic Network Calculation" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | A | 131242-WST02-DR-M-5501 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | A | 131242-WST02-DR-M-5511 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | A | 131242-WST02-DR-M-5521 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | A | 131242-WST02-DR-M-5531 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | A | 131242-WST02-DR-M-5541 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | A | 131242-WST02-DR-M-5551 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | B | 131242-WST02-DR-M-5501 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-03 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | B | 131242-WST02-DR-M-5511 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | B | 131242-WST02-DR-M-5521 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | B | 131242-WST02-DR-M-5531 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | B | 131242-WST02-DR-M-5541 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | B | 131242-WST02-DR-M-5551 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" | AWC
000918 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 0 | 131242-WST02-CL-BF-8000 | 2024-12-18 | Hydraulic Calculation (HOSEREEL) | Rev 0: Not approved - Revise and Resubmit | 2025-01-16 | 2025-01-24 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000918 | 2024-12-18 | 2025-02-19 | 1 | NAP | Approved with Comments | 2 | "Hydraulic Calculation (HOSEREEL)" | AWC
000918 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 1 | 131242-WST02-CL-BF-8000 | 2025-02-19 | Hydraulic Calculation (HOSEREEL) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-11 | 2025-03-18 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000918 | 2024-12-18 | 2025-02-19 | 1 | AWC | Approved with Comments | 2 | "Hydraulic Calculation (HOSEREEL)" | AWC
000919 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 0 | 131242-WSW41-LT-PM-0053 | 2024-12-19 | CV of Team Member (T&C Manager) | Rejected as requested by Contractor | 2025-01-17 | 2024-12-27 | 6 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000919 | 2024-12-19 | 2024-12-27 | 1 | REJ | Approved with Comments | 2 | "CV of Team Member (T&C Manager)" | AWC
000919 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 1 | 131242-WSW41-LT-PM-0053 | 2024-12-27 | CV of Team Member (T&C Manager) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-21 | 60 | Approved with Comments | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 000919 | 2024-12-19 | 2024-12-27 | 1 | AWC | Approved with Comments | 2 | "CV of Team Member (T&C Manager)" | AWC
000920 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0006 | 0 | 131242-WSW41-MS-E-0006 | 2024-12-18 | Installation of Cable Container Support System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the attached file for comments. | 2025-01-16 | 2025-12-17 | 260 | Approved with Comments | YES | 2026-01-06 | NO | Resubmitted | 0 |  |  | 000920 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Installation of Cable Container Support System" | AWC
000921 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 0 | 131242-WSW41-VI-M-2004 | 2024-12-19 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-17 | 2025-03-10 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000921 | 2024-12-19 | 2025-04-01 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | APP
000921 | 01 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 1 | 131242-WSW41-VI-M-2004 | 2025-04-01 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000921 | 2024-12-19 | 2025-04-01 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | APP
000922 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1393 | 0 | 131242-WST02-DS-E-1393 | 2024-12-19 | Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000922 | 2024-12-19 | 2024-12-19 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) " | AWC
000923 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1392 | 0 | 131242-WST02-DS-E-1392 | 2024-12-19 | Sample Board Submission for SS Cable Ladder, Accessories (United U-LI) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000923 | 2024-12-19 | 2024-12-19 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for SS Cable Ladder, Accessories (United U-LI)" | AWC
000924 | 00 | Yuen Fatt | Project | NA | 131242 | WSD11 | VI | M | 0032 | 0 | 131242-WSD11-VI-M-0032 | 2024-12-20 | Vendor Approval of Ducting - CES_Salcon Sdn Bhd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-20 | 2025-01-09 | 14 | Approved with Comments | YES | 2025-01-29 | NO | Resubmitted | 0 |  |  | 000924 | 2024-12-20 | 2024-12-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Ducting - CES_Salcon Sdn Bhd" | AWC
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5351 | A | 131242-WST02-DR-M-5351 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | AWC | Approved with Comments | 1 | "PC Pump GA Drawing " | AWC
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5361 | A | 131242-WST02-DR-M-5361 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " | PEN
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5371 | A | 131242-WST02-DR-M-5371 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " | PEN
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5381 | A | 131242-WST02-DR-M-5381 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " | PEN
000926 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0012 | 0 | 131242-WST02-VI-E-0012 | 2024-12-23 | Vendor Approval - Passive Harmonic Filter | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-01-21 | 2025-01-19 | 20 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000926 | 2024-12-23 | 2024-12-23 | 0 | REJ | Rejected | 1 | "Vendor Approval - Passive Harmonic Filter" | REJ
000927 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011 | 2024-12-23 | FAT Report for Cable Ladder 1st Batch (United ULI) | Rev 0: Approved. | 2025-01-21 | 2025-02-18 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000927&&001087 | 2024-12-23 | 2025-03-05 | 0 | APP | Approved | 2 | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" | APP
000928 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0018 | 0 | 131242-WSW41-PC-W-0018 | 2024-12-24 | Payment Claim No.18 | Rev(0): Approved. Please refer to S.O. correspondence no. 273 dated 26 Dec 2024. | 2025-01-22 | 2025-01-08 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000928 | 2024-12-24 | 2024-12-24 | 0 | APP | Approved | 1 | "Payment Claim No.18" | APP
000929 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0030 | 0 | 131242-WSW41-QA-M-0030 | 2024-12-24 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-22 | 2025-03-11 | 55 | Approved with Comments | YES | 2025-03-31 | NO | Resubmitted | 0 |  |  | 000929 | 2024-12-24 | 2024-12-24 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" | AWC
000930 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0031 | 0 | 131242-WSD11-QA-M-0031 | 2024-12-26 | Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) | Rev 0: Approved | 2025-01-23 | 2025-03-11 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000930 | 2024-12-26 | 2024-12-26 | 0 | APP | Approved | 1 | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " | APP
000931 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | A | 131242-WST02-DR-M-5601 | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-24 | 2025-03-04 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | AWC | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | APP
000931 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | B | 131242-WST02-DR-M-5601 | 2025-05-26 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 |  | 220 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | PEN | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | APP
000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0011 | 0 | 131242-WSD11-OM-M-0011 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000932 | 2024-12-27 | 2024-12-27 | 0 | INF | For Information | 1 | "O&M manual for Air Dryer and Air Compressor" | INF
000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0010 | 0 | 131242-WSD11-OM-M-0010 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000932 | 2024-12-27 | 2024-12-27 | 0 | INF | For Information | 1 | "O&M manual for Air Dryer and Air Compressor" | INF
000933 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601_WITHDRAW | A | 131242-WST02-DR-M-5601_WITHDRAW | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Rejected Submittal 931 include the same content and is already reviewed. | 2025-01-24 | 2025-03-04 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000933 | 2024-12-27 | 2024-12-27 | A | REJ | Rejected | 1 | "Screen General Arrangement Drawing" | REJ
000934 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5136 | 0 | 131242-WST02-DR-M-5136 | 2024-12-31 | Blower Name Plate Drawing | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000934 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Blower Name Plate Drawing " | APP
000935 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0010 | 0 | 131242-WST02-QA-A-0010 | 2024-12-31 | Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-01-28 | 2025-02-24 | 39 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000935 | 2024-12-31 | 2024-12-31 | 0 | AWC | Approved with Comments | 1 | "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" | AWC
000936 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0012 | 0 | 131242-WSW41-QA-E-0012 | 2024-12-31 | FAT Report for Power Cable, Control Cable, MV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-28 | 2025-01-20 | 14 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000936 | 2024-12-31 | 2024-12-31 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Power Cable, Control Cable, MV Cable" | AWC
000937 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0034 | 0 | 131242-WSW41-QA-M-0034 | 2024-12-31 | Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000937 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" | APP
000938 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0035 | 0 | 131242-WSW41-QA-M-0035 | 2024-12-31 | Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000938 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | APP
000939 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0032 | 0 | 131242-WSW41-QA-M-0032 | 2025-01-02 | QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details) | Rev 0: Approved | 2025-01-30 | 2025-04-27 | 82 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000939 | 2025-01-02 | 2025-01-02 | 0 | APP | Approved | 1 | "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" | APP
000940 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0029 | 0 | 131242-WSW41-QA-M-0029 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating | Rev 0: Approved | 2025-01-30 | 2025-04-08 | 68 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000940 | 2025-01-02 | 2025-01-02 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | APP
000941 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 0 | 131242-WSW41-QA-M-0033 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Rev 0: Not approved - Revise and Resubmit | 2025-01-30 | 2025-03-18 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000941 | 2025-01-02 | 2025-04-21 | 1 | NAP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | APP
000941 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 1 | 131242-WSW41-QA-M-0033 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Approved | 2025-05-09 | 2025-05-19 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000941 | 2025-01-02 | 2025-04-21 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | APP
000942 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 0 | 131242-WSW41-SH-M-1004 | 2025-01-02 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBC | SO comment: Please furnish GA drawings in TWRP format. (vendor not able to provide) | 000942 | 2025-01-02 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | AWC
000942 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 1 | 131242-WSW41-SH-M-1004 | 2025-06-16 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2025-09-04 | 58 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 000942 | 2025-01-02 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | AWC
000943 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | E | 0001 | 0 | 131242-WSW41-DS-E-0001 | 2025-01-03 | Datasheet for Unistrut Supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000943 | 2025-01-03 | 2025-01-03 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Unistrut Supports" | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1300 | A | 131242-WSW41-DR-E-1300 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1301 | A | 131242-WSW41-DR-E-1301 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1302 | A | 131242-WSW41-DR-E-1302 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1303 | A | 131242-WSW41-DR-E-1303 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1304 | A | 131242-WSW41-DR-E-1304 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1305 | A | 131242-WSW41-DR-E-1305 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1306 | A | 131242-WSW41-DR-E-1306 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1307 | A | 131242-WSW41-DR-E-1307 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1308 | A | 131242-WSW41-DR-E-1308 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1309 | A | 131242-WSW41-DR-E-1309 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " | AWC
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609_BCA | E | 131242-WST00-DR-S-8004_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1100__ST609_BCA | E | 131242-WST02-DR-S-1100__ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0300__ST609_BCA | E | 131242-WST02-DR-S-0300__ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609_BCA | E | 131242-WST02-DR-S-0301_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609_BCA | E | 131242-WST02-DR-S-0303_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609_BCA | E | 131242-WST02-DR-S-0304_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609_BCA | E | 131242-WST02-DR-S-0305_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609_BCA | E | 131242-WST02-DR-S-0306_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609_BCA | E | 131242-WST02-DR-S-0307_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609_BCA | E | 131242-WST02-DR-S-0308_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609_BCA | E | 131242-WST02-DR-S-0309_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609_BCA | E | 131242-WST02-DR-S-1101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609_BCA | E | 131242-WST02-DR-S-1102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609_BCA | E | 131242-WST02-DR-S-1103_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609_BCA | E | 131242-WST02-DR-S-2100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609_BCA | E | 131242-WST02-DR-S-2101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609_BCA | E | 131242-WST02-DR-S-2102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609_BCA | E | 131242-WST02-DR-S-3100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609_BCA | E | 131242-WST02-DR-S-3101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609_BCA | E | 131242-WST02-DR-S-3102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609_BCA | E | 131242-WST02-DR-S-5100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609_BCA | E | 131242-WST02-DR-S-5101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609_BCA | E | 131242-WST02-DR-S-5102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609_BCA | E | 131242-WST02-DR-S-5103_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609_BCA | E | 131242-WST02-DR-S-5104_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | D | 131242-WSW41-DR-S-8002_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | D | 131242-WSW41-DR-S-1100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | D | 131242-WSW41-DR-S-0310_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | D | 131242-WSW41-DR-S-0311_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | C | 131242-WSW41-DR-S-0312_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | C | 131242-WSW41-DR-S-0313_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | C | 131242-WSW41-DR-S-0314_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | C | 131242-WSW41-DR-S-0315_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | D | 131242-WSW41-DR-S-1101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | D | 131242-WSW41-DR-S-1102_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | D | 131242-WSW41-DR-S-1103_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | D | 131242-WSW41-DR-S-1104_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1105_ST614_BCA | D | 131242-WSW41-DR-S-1105_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000947 | 2025-01-03 | 2025-01-03 | D | INF | For Information | 1 | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1106_ST614_BCA | D | 131242-WSW41-DR-S-1106_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000947 | 2025-01-03 | 2025-01-03 | D | INF | For Information | 1 | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | D | 131242-WSW41-DR-S-2100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | D | 131242-WSW41-DR-S-2101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | D | 131242-WSW41-DR-S-3100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | D | 131242-WSW41-DR-S-5100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | D | 131242-WSW41-DR-S-5101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | D | 131242-WSW41-DR-S-5102_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | D | 131242-WSW41-DR-S-5103_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | INF
000948 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0014 | 0 | 131242-WSW41-RT-C-0014 | 2025-01-03 | Bored Piling Pile Eccentricity Reports (ECC 19 & 20) | For Information. Please refer comment sheet. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000948 | 2025-01-03 | 2025-01-03 | 0 | INF | For Information | 1 | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" | INF
000949 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 0 | 131242-WSW41-MS-E-0007 | 2025-01-03 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-01-31 | 2025-01-24 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000949 | 2025-01-03 | 2025-02-27 | 1 | NAP | Approved with Comments | 2 | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | AWC
000949 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 1 | 131242-WSW41-MS-E-0007 | 2025-02-27 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-27 | 42 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000949 | 2025-01-03 | 2025-02-27 | 1 | AWC | Approved with Comments | 2 | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | AWC
000950 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0005 | 0 | 131242-WST02-VI-A-0005 | 2025-01-03 | Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd. | Approved | 2025-01-31 | 2025-01-16 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000950 | 2025-01-03 | 2025-01-03 | 0 | APP | Approved | 1 | "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | APP
000951 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0011 | 0 | 131242-WST02-QA-A-0011 | 2025-01-04 | Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-01-31 | 2025-02-03 | 20 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000951 | 2025-01-04 | 2025-01-04 | 0 | AWC | Approved with Comments | 1 | "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" | AWC
000952 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021 | 2025-01-04 | Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024 | For information. | 2025-01-31 | 2025-01-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000825&&000952 | 2024-11-20 | 2025-01-04 | 0 | INF | For Information | 2 | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" | INF
000953 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1003 | 0 | 131242-WSW41-SH-M-1003 | 2025-01-07 | C4B Knife Gate Valve List & Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-04 | 2025-04-08 | 65 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000953 | 2025-01-07 | 2025-01-07 | 0 | AWC | Approved with Comments | 1 | "C4B Knife Gate Valve List & Datasheet" | AWC
000954 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 0 | 131242-WSW41-VI-M-1013 | 2025-01-07 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 0: Not approved - Revise and Resubmit | 2025-02-04 | 2025-02-12 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000954 | 2025-01-07 | 2025-06-17 | 2 | REJ | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | APP
000954 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 1 | 131242-WSW41-VI-M-1013 | 2025-03-27 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-04-11 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 | Pending vendor clarification - Breen | 000954 | 2025-01-07 | 2025-06-17 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | APP
000954 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 2 | 131242-WSW41-VI-M-1013 | 2025-06-17 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 2: Approved | 2025-07-07 | 2025-07-28 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000954 | 2025-01-07 | 2025-06-17 | 2 | APP | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | APP
000955 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0036 | 0 | 131242-WSW41-QA-M-0036 | 2025-01-07 | FAT/MDR Report for Side Manway (9 no;) | Rev 0: Approved | 2025-02-04 | 2025-03-25 | 55 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000955 | 2025-01-07 | 2025-01-07 | 0 | APP | Approved | 1 | "FAT/MDR Report for Side Manway (9 no;)" | APP
000956 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0051 | 0 | 131242-WSW41-CD-IM-0051 | 2025-01-08 | Submission of BIM Coordination VCM Model (Dec 2024) | For Information. Score= 71/100 | 2025-02-05 | 2025-01-24 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000956 | 2025-01-08 | 2025-01-08 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Dec 2024)" | INF
000957 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0038 | 0 | 131242-WSW41-MI-C-0038 | 2025-01-09 | CSA Meeting Minutes 0038_12122024 | For information. | 2025-02-06 | 2025-01-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000957 | 2025-01-09 | 2025-01-09 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0038_12122024" | INF
000958 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0038 | 0 | 131242-WST02-QA-M-0038 | 2025-01-09 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch) | Rev 0: Approved | 2025-02-06 | 2025-03-25 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000958 | 2025-01-09 | 2025-01-09 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" | APP
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0006 | A | 131242-WSD11-CL-S-0006 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" | AWC
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1602 | A | 131242-WSD11-DR-S-1602 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" | AWC
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5602 | A | 131242-WSD11-DR-S-5602 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007 | A | 131242-WSD11-CL-S-0007 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960&&001945 | 2025-01-10 | 2026-01-12 | 1 | AWC | Approved with Comments | 2 | "Support design for compressed Air system >2m" && "G2D Pipe Support_Report from QPD" | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600 | A | 131242-WSD11-DR-S-5600 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601 | A | 131242-WSD11-DR-S-5601 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600 | A | 131242-WSD11-DR-S-1600 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" | AWC
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601 | A | 131242-WSD11-DR-S-1601 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" | AWC
000961 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 0 | 131242-WSD11-DS-I-0004 | 2025-01-10 | Datasheet for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-05 |  | 000961 | 2025-01-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Pressure Transmitter" | AWC
000961 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 1 | 131242-WSD11-DS-I-0004 | 2025-03-17 | Datasheet for Pressure Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 37 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 000961 | 2025-01-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Pressure Transmitter" | AWC
000962 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 0 | 131242-WSD11-QA-M-0039 | 2025-01-10 | FAT report for THP Train 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-20 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | AWC | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" | REJ
000962 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 1 | 131242-WSD11-QA-M-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rejected, as requested by contractor via email dated 8 Dec 2025. They will resubmit ZIP files with clear descriptive folder names instead of individual file | 2025-12-26 | 2025-12-08 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | REJ | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" | REJ
000962 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 2 | 131242-WSD11-QA-M-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2025-12-23 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | AWC | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" | REJ
000962 | 03 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 3 | 131242-WSD11-QA-M-0039 | 2026-01-06 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | PEN | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" | REJ
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | INF
000964 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 0 | 131242-WSD11-SP-I-0004 | 2025-01-11 | Functional Design Specification (Air Compressor System) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-04 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" | AWC
000964 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 1 | 131242-WSD11-SP-I-0004 | 2025-06-04 | Functional Design Specification (Air Compressor System) | R1: Approved with comments. No resubmittal is required at this moment. The resubmittal is required only if any changes during the detailing. | 2025-06-24 | 2025-07-02 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" | AWC
000964 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 2 | 131242-WSD11-SP-I-0004 | 2025-08-12 | Functional Design Specification (Air Compressor System) | R2: Approved with comments. However, no resubmission at this stage unless there is a change to the document. | 2025-09-01 | 2025-10-08 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" | AWC
000965 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0036 | 0 | 131242-WSW41-MI-P-0036 | 2025-01-11 | Process & MEICA Meeting Minutes 0036_21112024 | For Information | 2025-02-07 | 2025-01-16 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000965 | 2025-01-11 | 2025-01-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0036_21112024" | INF
000966 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0037 | 0 | 131242-WSW41-MI-P-0037 | 2025-01-11 | Process & MEICA Meeting Minutes 0037_05122024 | For Information | 2025-02-07 | 2025-01-16 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000966 | 2025-01-11 | 2025-01-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0037_05122024" | INF
000967 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 0 | 131242-WST02-DS-I-0005 | 2025-01-11 | Datasheet for pH Transmitter & Sensor | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000967 | 2025-01-11 | 2025-08-15 | 1 | NAP | Approved with Comments | 2 | "Datasheet for pH Transmitter & Sensor " | AWC
000967 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 1 | 131242-WST02-DS-I-0005 | 2025-08-15 | Datasheet for pH Transmitter & Sensor | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-11-26 | 73 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 000967 | 2025-01-11 | 2025-08-15 | 1 | AWC | Approved with Comments | 2 | "Datasheet for pH Transmitter & Sensor " | AWC
000968 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 0 | 131242-WST02-QA-A-0012 | 2025-01-11 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-02-24 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | NAP
000968 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012 | 2025-03-10 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-14 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | NAP
000968 | 02 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012 | 2025-04-23 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.2: Not Approved. Please refer to comment sheet for resubmission | 2025-05-13 | 2025-04-28 | 3 | Not Approved | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | NAP
000969 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | I | 0005 | 0 | 131242-WSW41-QA-I-0005 | 2025-01-13 | FAT report for Power cable, Control Cable, Instrument Cable (Witness) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-02-10 | 2025-01-20 | 5 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000969 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " | AWC
000970 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0013 | 0 | 131242-WSW41-QA-E-0013 | 2025-01-13 | FAT report for SS Unistrut Support, Accessories (HDMANN) | Rev 0: Approved with comments. Resubmission not required. Please refer to attached file for comments as noted. | 2025-02-10 | 2025-03-02 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000970 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "FAT report for SS Unistrut Support, Accessories (HDMANN) " | AWC
000971 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0014 | 0 | 131242-WSW41-QA-E-0014 | 2025-01-13 | FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000971 | 2025-01-13 | 2025-01-13 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" | APP
000972 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0015 | 0 | 131242-WST02-QA-E-0015 | 2025-01-13 | FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000972 | 2025-01-13 | 2025-01-13 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" | APP
000973 | 00 | Franklin | CSA | NA | 131242 | WSW41 | CN | S | 0002 | 0 | 131242-WSW41-CN-S-0002 | 2025-01-13 | Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-10 | 2025-02-24 | 30 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000973 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | AWC
000974 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0040 | 0 | 131242-WSW41-QA-M-0040 | 2025-01-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) | Rev 0: Approved | 2025-02-11 | 2025-03-18 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000974 | 2025-01-14 | 2025-01-14 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | APP
000975 | 00 | K. Balaji | Mech | NA | 131242 | WSW41 | MS | M | 0006 | 0 | 131242-WSW41-MS-M-0006 | 2025-01-14 | Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 | Rev 0: Approved | 2025-02-11 | 2025-04-11 | 63 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000975 | 2025-01-14 | 2025-01-14 | 0 | APP | Approved | 1 | "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " | APP
000976 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 0 | 131242-WSD11-QA-M-0041 | 2025-01-15 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-12 | 2025-02-20 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | AWC | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | AWC
000976 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 1 | 131242-WSD11-QA-M-0041 | 2025-12-09 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-29 | 2025-12-23 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | AWC | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | AWC
000976 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 2 | 131242-WSD11-QA-M-0041 | 2026-01-06 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | PEN | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | AWC
000977 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0024 | 0 | 131242-WSW41-SP-C-0024 | 2025-01-15 | Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-12 | 2025-03-04 | 34 | Approved with Comments | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000977 | 2025-01-15 | 2025-01-15 | 0 | AWC | Approved with Comments | 1 | "Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd)" | AWC
000978 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0043 | 0 | 131242-WST02-QA-M-0043 | 2025-01-16 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch) | Rev 0: Approved | 2025-02-13 | 2025-03-25 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000978 | 2025-01-16 | 2025-01-16 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" | APP
000979 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0019 | 0 | 131242-WSW41-PS-PM-0019 | 2025-01-16 | Monthly Progress Presentation No. 19 (1224) | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000979 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 19 (1224)" | INF
000980 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0019 | 0 | 131242-WSW41-MI-PM-0019 | 2025-01-16 | Monthly Progress Meeting Minutes 0019_20241217 | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000980 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0019_20241217" | INF
000981 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0002 | 0 | 131242-WSW41-RT-HS-0002 | 2025-01-16 | Final Investigation Report (Incident on Leg Injury) | For Information | 2025-02-13 | 2025-12-23 | 243 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000981 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Final Investigation Report (Incident on Leg Injury)" | INF
000982 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0022 | 0 | 131242-WSW41-QA-C-0022 | 2025-01-16 | Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-02-13 | 2025-02-24 | 27 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000982 | 2025-01-16 | 2025-01-16 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" | AWC
000983 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 0 | 131242-WSD11-QA-M-0042 | 2025-01-16 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-02-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000983 | 2025-01-16 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | APP
000983 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 1 | 131242-WSD11-QA-M-0042 | 2025-12-02 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000983 | 2025-01-16 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | APP
000984 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 0 | 131242-WSW41-VI-M-1014 | 2025-01-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-01-20 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000984 | 2025-01-16 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | AWC
000984 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 1 | 131242-WSW41-VI-M-1014 | 2025-06-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-06-23 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000984 | 2025-01-16 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | AWC
000985 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0044 | 0 | 131242-WSW41-QA-M-0044 | 2025-01-17 | Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-14 | 2025-04-27 | 71 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000985 | 2025-01-17 | 2025-01-17 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " | AWC
000986 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0020 | 0 | 131242-WSW41-RT-PM-0020 | 2025-01-19 | C4B Monthly Progress Report Number No.20 (12 24) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-02-14 | 2025-02-03 | 10 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000986 | 2025-01-19 | 2025-01-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.20 (12 24) " | AWC
000987 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0024 | 0 | 131242-WSW41-MS-C-0024 | 2025-01-20 | MSRA and SWP for Waterproofing Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-17 | 2025-02-17 | 20 | Approved with Comments | YES | 2025-03-07 | NO | Resubmitted | 0 |  |  | 000987 | 2025-01-20 | 2025-01-20 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Waterproofing Work" | AWC
000988 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 0 | 131242-WSW41-VI-M-2005 | 2025-01-20 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 |  | 000988 | 2025-01-20 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | AWC
000988 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 1 | 131242-WSW41-VI-M-2005 | 2025-06-18 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-08 | 2026-01-07 | 145 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000988 | 2025-01-20 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | AWC
000989 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 0 | 131242-WSW41-VI-M-2002 | 2025-01-20 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-01-24 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | AWC
000989 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-02-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-04-02 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | AWC
000989 | 02 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-04-17 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-05-07 | 2025-05-21 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | AWC
000989 | 03 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-08-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-09-12 |  | 155 | Awaiting S.O.'s response | YES | 2025-10-10 | NO | Overdue | 0 | 2025-02-21 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | PEN | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | AWC
000990 | 00 | Prachi | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014 | 2025-01-20 | THP Steam Pressure Loss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 185 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000990&&001007 | 2025-01-20 | 2025-01-26 | 0 | APP | Approved | 2 | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" | APP
000991 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0011 | 0 | 131242-WST02-CL-P-0011 | 2025-01-20 | SSN Compressed Air Headloss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 185 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000991 | 2025-01-20 | 2025-01-20 | 0 | APP | Approved | 1 | "SSN Compressed Air Headloss Calculation" | APP
000992 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025 | 2025-01-20 | Air Compressor On Off Valve Data sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000992 | 2025-01-20 | 2025-03-07 | 0 | AWC | Approved | 2 | "Air Compressor On Off Valve Data sheet" | APP
000992 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025 | 2025-03-07 | Air Compressor On Off Valve Data sheet | Rev 1: Approved | 2025-03-27 | 2025-07-08 | 87 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000992 | 2025-01-20 | 2025-03-07 | 0 | APP | Approved | 2 | "Air Compressor On Off Valve Data sheet" | APP
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 0 | 131242-WSD11-QA-N-0005 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 0 | 131242-WSD11-QA-N-0006 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 0 | 131242-WSD11-QA-N-0009 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | AWC
000994 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 0 | 131242-WSD11-QA-N-0001 | 2025-01-20 | Commissioning Plan for THP Air Compressor System | Rev.0: Approved with Comments. Revise and resubmit. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" | AWC
000994 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 1 | 131242-WSD11-QA-N-0001 | 2025-03-06 | Commissioning Plan for THP Air Compressor System | Rev.1: Approved with Comments. Resubmittal is required | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" | AWC
000994 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 2 | 131242-WSD11-QA-N-0001 | 2025-05-10 | Commissioning Plan for THP Air Compressor System | Rev.2: Approved with Comments. Resubmittal is required | 2025-05-29 | 2025-06-04 | 17 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" | AWC
000995 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 0 | 131242-WSD11-DR-I-7209 | 2025-01-21 | THP Biosolids PMS Network Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-18 | 2025-03-31 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000995 | 2025-01-21 | 2025-04-09 | 1 | NAP | Approved with Comments | 2 | "THP Biosolids PMS Network Architecture Drawing" | AWC
000995 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 1 | 131242-WSD11-DR-I-7209 | 2025-04-09 | THP Biosolids PMS Network Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-29 | 2025-05-07 | 20 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 000995 | 2025-01-21 | 2025-04-09 | 1 | AWC | Approved with Comments | 2 | "THP Biosolids PMS Network Architecture Drawing" | AWC
000996 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 0001 | A | 131242-WSD11-DR-E-0001 | 2025-01-21 | THP Drawing Index for Cable Raceway and Room Layout | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2025-02-18 | 2025-03-13 | 37 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000996 | 2025-01-21 | 2025-01-21 | A | NAP | Not Approved | 1 | "THP Drawing Index for Cable Raceway and Room Layout" | NAP
000997 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0020 | 0 | 131242-WSD11-QA-E-0020 | 2025-01-22 | Electrical Documents for THP Train 1 & Train 2 (CAMBI) | Rev 0: Rejected. Please refer to attached file for comments. | 2025-02-19 | 2025-03-13 | 36 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000997 | 2025-01-22 | 2025-01-22 | 0 | NAP | Not Approved | 1 | "Electrical Documents for THP Train 1 & Train 2 (CAMBI)" | NAP
000998 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 0 | 131242-WSW41-QA-A-0014 | 2025-01-22 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-19 | 2025-02-24 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000998 | 2025-01-22 | 2025-03-10 | 1 | NAP | Not Approved | 2 | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " | NAP
000998 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 1 | 131242-WSW41-QA-A-0014 | 2025-03-10 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-11 | 24 | Not Approved | YES | 2025-05-01 | NO | Resubmitted | 0 |  |  | 000998 | 2025-01-22 | 2025-03-10 | 1 | NAP | Not Approved | 2 | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " | NAP
000999 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0013 | 0 | 131242-WSW41-QA-A-0013 | 2025-01-24 | Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd) | Approved | 2025-02-21 | 2025-02-24 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000999 | 2025-01-24 | 2025-01-24 | 0 | APP | Approved | 1 | "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" | APP
001000 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 0 | 131242-WSW41-SP-C-0025 | 2025-01-24 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | NAP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | APP
001000 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 1 | 131242-WSW41-SP-C-0025 | 2025-03-14 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-06 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | NAP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | APP
001000 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 2 | 131242-WSW41-SP-C-0025 | 2025-04-08 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Approved with Comments | 2025-04-28 | 2025-05-16 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | AWC | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | APP
001000 | 03 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 3 | 131242-WSW41-SP-C-0025 | 2025-06-06 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.3: Approved | 2025-06-26 | 2025-07-04 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | APP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | APP
001001 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0026 | 0 | 131242-WSW41-SP-C-0026 | 2025-01-24 | Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information. | 2025-02-21 | 2025-02-20 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001001 | 2025-01-24 | 2025-01-24 | 0 | INF | For Information | 1 | "Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32)" | INF
001002 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 0001 | A | 131242-WSD11-DR-B-0001 | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | 65 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001002 | 2025-01-26 | 2025-01-26 | A | INF | For Information | 1 | "Drawing Index (Building and Services Mech.)" | INF
001002 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | B | 0001 | A | 131242-WST02-DR-B-0001 | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | 65 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001002 | 2025-01-26 | 2025-01-26 | A | PEN | Awaiting S.O.'s response | 1 | "Drawing Index (Building and Services Mech.)" | PEN
001003 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0054 | 0 | 131242-WSW41-LT-PM-0054 | 2025-01-26 | CV of Team member (Senior Planning Engineer) | Rev. 0 - Approved | 2025-02-21 | 2025-02-07 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001003 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "CV of Team member (Senior Planning Engineer)" | APP
001004 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0021 | 0 | 131242-WST02-QA-E-0021 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001004 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI)" | APP
001005 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1394 | 0 | 131242-WST02-DS-E-1394 | 2025-01-26 | Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-03-02 | 25 | Approved with Comments | YES | 2025-03-20 | NO | Resubmitted | 0 |  |  | 001005 | 2025-01-26 | 2025-01-26 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd)" | AWC
001006 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 0 | 131242-WSD11-MS-N-0001 | 2025-01-26 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-21 | 2025-02-07 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001006 | 2025-01-26 | 2025-05-19 | 1 | AWC | Approved with Comments | 2 | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | AWC
001006 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 1 | 131242-WSD11-MS-N-0001 | 2025-05-19 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-06 | 2025-07-02 | 32 | Approved with Comments | YES | 2025-07-22 | NO | Resubmitted | 0 |  |  | 001006 | 2025-01-26 | 2025-05-19 | 1 | AWC | Approved with Comments | 2 | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | AWC
001007 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014 | 2025-01-26 | Process Gas Hydraulic Calculation | Rev 0: Approved. Please furnish PE Endorsement. | 2025-02-21 | 2025-10-06 | 180 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000990&&001007 | 2025-01-20 | 2025-01-26 | 0 | APP | Approved | 2 | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" | APP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | A | 131242-WST02-SD-A-1010 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | A | 131242-WST02-SD-A-1011 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | A | 131242-WST02-SD-A-1012 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | A | 131242-WST02-SD-A-1013 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | A | 131242-WST02-SD-A-3006 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | A | 131242-WST02-SD-A-3007 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | A | 131242-WST02-SD-A-3008 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | A | 131242-WST02-SD-A-3009 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | A | 131242-WST02-SD-A-3010 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | A | 131242-WST02-SD-A-3011 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | A | 131242-WST02-SD-A-3012 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | A | 131242-WST02-SD-A-3013 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST00 | DR | S | 0001 | A | 131242-WST00-DR-S-0001 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-01-26 | A | NAP | Not Approved | 1 | "Shop Drawings for Lintel and Stiffener " | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-10 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | B | 131242-WST02-SD-A-3007 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | B | 131242-WST02-SD-A-3008 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | B | 131242-WST02-SD-A-3009 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | B | 131242-WST02-SD-A-3010 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | A | 0001_supporting docs | 1 | 131242-WSW41-QA-A-0001_supporting docs | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-03-21 | 2025-03-21 | 1 | NAP | Not Approved | 1 | "Shop Drawings for Block Wall" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | C | 131242-WST02-SD-A-1010 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | C | 131242-WST02-SD-A-1011 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | C | 131242-WST02-SD-A-1012 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | C | 131242-WST02-SD-A-1013 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | C | 131242-WST02-SD-A-3006 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | C | 131242-WST02-SD-A-3007 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | C | 131242-WST02-SD-A-3008 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | C | 131242-WST02-SD-A-3009 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | C | 131242-WST02-SD-A-3010 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | C | 131242-WST02-SD-A-3011 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | C | 131242-WST02-SD-A-3012 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | C | 131242-WST02-SD-A-3013 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617_BCA | B | 131242-WSD11-DR-S-0300_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617_BCA | B | 131242-WSD11-DR-S-0301_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST617_BCA | B | 131242-WSD11-DR-S-0302_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_ST617_BCA | B | 131242-WSD11-DR-S-0303_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST617_BCA | B | 131242-WSD11-DR-S-0304_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST617_BCA | B | 131242-WSD11-DR-S-0305_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617_BCA | B | 131242-WSD11-DR-S-1000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617_BCA | B | 131242-WSD11-DR-S-1001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617_BCA | B | 131242-WSD11-DR-S-1002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617_BCA | B | 131242-WSD11-DR-S-1003_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617_BCA | B | 131242-WSD11-DR-S-2000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617_BCA | B | 131242-WSD11-DR-S-2001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617_BCA | B | 131242-WSD11-DR-S-3000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617_BCA | B | 131242-WSD11-DR-S-3001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617_BCA | B | 131242-WSD11-DR-S-3002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617_BCA | B | 131242-WSD11-DR-S-5000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617_BCA | B | 131242-WSD11-DR-S-5001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617_BCA | B | 131242-WSD11-DR-S-5002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617_BCA | B | 131242-WSD11-DR-S-5003_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617_BCA | B | 131242-WSD11-DR-S-5004_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617_BCA | B | 131242-WSD11-DR-S-5005_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617_BCA | B | 131242-WSD11-DR-S-5006_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617_BCA | B | 131242-WSD11-DR-S-8000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " | AWC
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001011 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0006 | 0 | 131242-WSD11-QA-I-0006 | 2025-01-26 | Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-21 | 2025-04-11 | 54 | Not Approved | YES | 2025-05-01 | NO | Resubmitted | 0 |  |  | 001011 | 2025-01-26 | 2025-01-26 | 0 | NAP | Not Approved | 1 | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" | NAP
001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7001 | A | 131242-WSD11-DR-BE-7001 | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | 47 | Rejected | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001012 | 2025-01-26 | 2025-01-26 | A | REJ | Rejected | 1 | "THP Compartmentalization Lighting and Ventilation Fan" | REJ
001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1005 | A | 131242-WSD11-DR-EL-1005 | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | 47 | Rejected | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001012 | 2025-01-26 | 2025-01-26 | A | REJ | Rejected | 1 | "THP Compartmentalization Lighting and Ventilation Fan" | REJ
001013 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0019 | 0 | 131242-WST02-QA-E-0019 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001013 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " | APP
001014 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 0 | 131242-WSW41-QA-E-0016 | 2025-01-26 | ITP for Lightning Protection System Installation | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file and incorporate minor comments. | 2025-02-21 | 2025-03-13 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001014 | 2025-01-26 | 2025-03-14 | 1 | AWC | Approved | 2 | "ITP for Lightning Protection System Installation" | APP
001014 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 1 | 131242-WSW41-QA-E-0016 | 2025-03-14 | ITP for Lightning Protection System Installation | Rev 1: Approved. | 2025-04-03 | 2025-05-07 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001014 | 2025-01-26 | 2025-03-14 | 1 | APP | Approved | 2 | "ITP for Lightning Protection System Installation" | APP
001015 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0010 | 0 | 131242-WSW41-VI-S-0010 | 2025-02-03 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-03 | 2025-02-20 | 13 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001015 | 2025-02-03 | 2025-02-03 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." | AWC
001016 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0019 | 0 | 131242-WSW41-PC-W-0019 | 2025-02-03 | Payment Claim No.19 | Rev (0): Approved. Please refer to S.O. Correspondence no. 291 dated 5 Feb 2025. | 2025-03-03 | 2025-02-17 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001016 | 2025-02-03 | 2025-02-03 | 0 | APP | Approved | 1 | "Payment Claim No.19" | APP
001017 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BH | 7000 | A | 131242-WSD11-DR-BH-7000 | 2025-02-03 | THP Protected Corridor Fan Control Circuit Diagram | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-03-03 | 2025-04-27 | 60 | Rejected | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001017 | 2025-02-03 | 2025-02-03 | A | REJ | Rejected | 1 | "THP Protected Corridor Fan Control Circuit Diagram" | REJ
001018 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 0 | 131242-WSD11-QA-M-0047 | 2025-02-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-03 | 2025-03-25 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001018 | 2025-02-03 | 2025-07-03 | 1 | AWC | Approved | 2 | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | APP
001018 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 1 | 131242-WSD11-QA-M-0047 | 2025-07-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 1: Approved | 2025-07-23 | 2025-12-23 | 123 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001018 | 2025-02-03 | 2025-07-03 | 1 | APP | Approved | 2 | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | APP
001019 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0045 | 0 | 131242-WSW41-QA-M-0045 | 2025-02-03 | WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd | Rev 0: For Information | 2025-03-03 | 2025-04-27 | 60 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001019 | 2025-02-03 | 2025-02-03 | 0 | INF | For Information | 1 | "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | INF
001020 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 0 | 131242-WST02-DS-E-1395 | 2025-02-04 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-04 | 2025-03-02 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001020 | 2025-02-04 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | AWC
001020 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 1 | 131242-WST02-DS-E-1395 | 2025-03-14 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 36 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 001020 | 2025-02-04 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | AWC
001021 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0048 | 0 | 131242-WST02-QA-M-0048 | 2025-02-05 | FAT Report for Air Blowers (Aerzen) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 34 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001021 | 2025-02-05 | 2025-02-05 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Air Blowers (Aerzen)" | AWC
001022 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0016 | 0 | 131242-WSW41-QA-A-0016 | 2025-02-06 | Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-06 | 2025-02-18 | 8 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 001022 | 2025-02-06 | 2025-02-06 | 0 | AWC | Approved with Comments | 1 | "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | AWC
001023 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025 | 2025-02-07 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-03-02 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | NAP
001023 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025 | 2025-03-10 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Approved with Comments | 2025-03-28 | 2025-06-11 | 67 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | AWC | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | NAP
001024 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0023 | 0 | 131242-WSW41-QA-C-0023 | 2025-02-07 | Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024 | For information. | 2025-03-07 | 2025-02-18 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001024 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" | INF
001025 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0015 | 0 | 131242-WST02-QA-A-0015 | 2025-02-07 | Sample Board Submission for Roof Waterproofing (G-Concept) | For information. Please provide technical data sheet for the proposed system and submit shop drawings for approval. | 2025-03-07 | 2025-02-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001025 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "Sample Board Submission for Roof Waterproofing (G-Concept)" | INF
001026 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1014 | 0 | 131242-WST02-SD-A-1014 | 2025-02-07 | Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-02-24 | 11 | Not Approved | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | A | 131242-WSD11-DR-EI-7040 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | A | 131242-WSD11-DR-EI-7041 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | A | 131242-WSD11-DR-EI-7042 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | A | 131242-WSD11-DR-EI-7043 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | A | 131242-WSD11-DR-EI-7044 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | A | 131242-WSD11-DR-EI-7045 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | A | 131242-WSD11-DR-EI-7046 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | A | 131242-WSD11-DR-EI-7047 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | A | 131242-WSD11-DR-EI-7048 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | A | 131242-WSD11-DR-EI-7049 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | A | 131242-WSD11-DR-EI-7050 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | A | 131242-WSD11-DR-EI-7060 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | A | 131242-WSD11-DR-EI-7061 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | A | 131242-WSD11-DR-EI-7062 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | A | 131242-WSD11-DR-EI-7063 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | A | 131242-WSD11-DR-EI-7064 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | A | 131242-WSD11-DR-EI-7065 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | A | 131242-WSD11-DR-EI-7066 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | A | 131242-WSD11-DR-EI-7067 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | A | 131242-WSD11-DR-EI-7068 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | A | 131242-WSD11-DR-EI-7069 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | A | 131242-WSD11-DR-EI-7070 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | A | 131242-WSD11-DR-EP-3014 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | A | 131242-WSD11-DR-EP-3015 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | A | 131242-WSD11-DR-EP-3016 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | A | 131242-WSD11-DR-EP-3017 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | A | 131242-WSD11-DR-EP-3018 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | A | 131242-WSD11-DR-EP-3019 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | A | 131242-WSD11-DR-EP-3020 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | A | 131242-WSD11-DR-EP-3021 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | A | 131242-WSD11-DR-EP-3022 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | A | 131242-WSD11-DR-EP-3023 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | A | 131242-WSD11-DR-EP-3024 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | A | 131242-WSD11-DR-EP-3025 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | A | 131242-WSD11-DR-EP-3026 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | A | 131242-WSD11-DR-EP-3027 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | A | 131242-WSD11-DR-EP-7110 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | A | 131242-WSD11-DR-EP-7111 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | A | 131242-WSD11-DR-EP-7112 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | A | 131242-WSD11-DR-EP-7113 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | A | 131242-WSD11-DR-EP-7114 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | A | 131242-WSD11-DR-EP-7115 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | A | 131242-WSD11-DR-EP-7116 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | A | 131242-WSD11-DR-EP-7117 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | A | 131242-WSD11-DR-EP-7118 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | A | 131242-WSD11-DR-EP-7119 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | B | 131242-WSD11-DR-EI-7040 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | B | 131242-WSD11-DR-EI-7041 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | B | 131242-WSD11-DR-EI-7042 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | B | 131242-WSD11-DR-EI-7043 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | B | 131242-WSD11-DR-EI-7044 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | B | 131242-WSD11-DR-EI-7045 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | B | 131242-WSD11-DR-EI-7046 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | B | 131242-WSD11-DR-EI-7047 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | B | 131242-WSD11-DR-EI-7048 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | B | 131242-WSD11-DR-EI-7049 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | B | 131242-WSD11-DR-EI-7050 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | B | 131242-WSD11-DR-EI-7060 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | B | 131242-WSD11-DR-EI-7061 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | B | 131242-WSD11-DR-EI-7062 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | B | 131242-WSD11-DR-EI-7063 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | B | 131242-WSD11-DR-EI-7064 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | B | 131242-WSD11-DR-EI-7065 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | B | 131242-WSD11-DR-EI-7066 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | B | 131242-WSD11-DR-EI-7067 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | B | 131242-WSD11-DR-EI-7068 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | B | 131242-WSD11-DR-EI-7069 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | B | 131242-WSD11-DR-EI-7070 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | B | 131242-WSD11-DR-EP-3014 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | B | 131242-WSD11-DR-EP-3015 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | B | 131242-WSD11-DR-EP-3016 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | B | 131242-WSD11-DR-EP-3017 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | B | 131242-WSD11-DR-EP-3018 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | B | 131242-WSD11-DR-EP-3019 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | B | 131242-WSD11-DR-EP-3020 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | B | 131242-WSD11-DR-EP-3021 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | B | 131242-WSD11-DR-EP-3022 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | B | 131242-WSD11-DR-EP-3023 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | B | 131242-WSD11-DR-EP-3024 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | B | 131242-WSD11-DR-EP-3025 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | B | 131242-WSD11-DR-EP-3026 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | B | 131242-WSD11-DR-EP-3027 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | B | 131242-WSD11-DR-EP-7110 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | B | 131242-WSD11-DR-EP-7111 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | B | 131242-WSD11-DR-EP-7112 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | B | 131242-WSD11-DR-EP-7113 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | B | 131242-WSD11-DR-EP-7114 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | B | 131242-WSD11-DR-EP-7115 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | B | 131242-WSD11-DR-EP-7116 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | B | 131242-WSD11-DR-EP-7117 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | B | 131242-WSD11-DR-EP-7118 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | B | 131242-WSD11-DR-EP-7119 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | C | 131242-WSD11-DR-EI-7040 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | C | 131242-WSD11-DR-EI-7041 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | C | 131242-WSD11-DR-EI-7042 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | C | 131242-WSD11-DR-EI-7043 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | C | 131242-WSD11-DR-EI-7044 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | C | 131242-WSD11-DR-EI-7045 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | C | 131242-WSD11-DR-EI-7046 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | C | 131242-WSD11-DR-EI-7047 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | C | 131242-WSD11-DR-EI-7048 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | C | 131242-WSD11-DR-EI-7049 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | C | 131242-WSD11-DR-EI-7050 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | C | 131242-WSD11-DR-EI-7060 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | C | 131242-WSD11-DR-EI-7061 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | C | 131242-WSD11-DR-EI-7062 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | C | 131242-WSD11-DR-EI-7063 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | C | 131242-WSD11-DR-EI-7064 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | C | 131242-WSD11-DR-EI-7065 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | C | 131242-WSD11-DR-EI-7066 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | C | 131242-WSD11-DR-EI-7067 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | C | 131242-WSD11-DR-EI-7068 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | C | 131242-WSD11-DR-EI-7069 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | C | 131242-WSD11-DR-EI-7070 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | C | 131242-WSD11-DR-EP-3014 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | C | 131242-WSD11-DR-EP-3015 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | C | 131242-WSD11-DR-EP-3016 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | C | 131242-WSD11-DR-EP-3017 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | C | 131242-WSD11-DR-EP-3018 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | C | 131242-WSD11-DR-EP-3019 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | C | 131242-WSD11-DR-EP-3020 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | C | 131242-WSD11-DR-EP-3021 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | C | 131242-WSD11-DR-EP-3022 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | C | 131242-WSD11-DR-EP-3023 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | C | 131242-WSD11-DR-EP-3024 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | C | 131242-WSD11-DR-EP-3025 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | C | 131242-WSD11-DR-EP-3026 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | C | 131242-WSD11-DR-EP-3027 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | C | 131242-WSD11-DR-EP-7110 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | C | 131242-WSD11-DR-EP-7111 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | C | 131242-WSD11-DR-EP-7112 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | C | 131242-WSD11-DR-EP-7113 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | C | 131242-WSD11-DR-EP-7114 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | C | 131242-WSD11-DR-EP-7115 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | C | 131242-WSD11-DR-EP-7116 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | C | 131242-WSD11-DR-EP-7117 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | C | 131242-WSD11-DR-EP-7118 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | C | 131242-WSD11-DR-EP-7119 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" | AWC
001028 | 00 | Zora | CSA | NA | 131242 | NA | NA | NA | FOR INFORMATION | 0 | 131242-NA-NA-NA-FOR INFORMATION | 2025-02-07 | BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters | For information. | 2025-03-07 | 2025-02-18 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001028 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters " | INF
001029 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 0 | 131242-WSW41-QA-M-0037 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Rev 0: Not approved - Revise and Resubmit | 2025-03-07 | 2025-03-25 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001029 | 2025-02-07 | 2025-04-21 | 1 | NAP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | APP
001029 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 1 | 131242-WSW41-QA-M-0037 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Approved | 2025-05-09 | 2025-05-12 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001029 | 2025-02-07 | 2025-04-21 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | APP
001030 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 0 | 131242-WSW41-QA-M-0046 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001030 | 2025-02-07 | 2025-06-18 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | APP
001030 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 1 | 131242-WSW41-QA-M-0046 | 2025-06-18 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-08 | 2025-09-08 | 58 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001030 | 2025-02-07 | 2025-06-18 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | APP
001031 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0009 | 0 | 131242-WST02-CL-P-0009 | 2025-02-07 | SSN Energy Consumption Computation | Rev 0: For Information | 2025-03-07 | 2025-10-06 | 171 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001031 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | " SSN Energy Consumption Computation" | INF
001032 | 00 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 0 | 131242-WST02-SP-P-0002 | 2025-02-07 | SSN Aeration Blower Control Philosophy | Rev0: approved with comments, resubmission is required. | 2025-03-07 | 2025-03-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001032 | 2025-02-07 | 2025-06-04 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blower Control Philosophy" | AWC
001032 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 1 | 131242-WST02-SP-P-0002 | 2025-06-04 | SSN Aeration Blower Control Philosophy | Rev1: approved with comments, resubmission is required. | 2025-06-24 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | NO | Resubmitted | 0 |  |  | 001032 | 2025-02-07 | 2025-06-04 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blower Control Philosophy" | AWC
001033 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 0 | 131242-WSD11-VI-I-0004 | 2025-02-10 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-10 | 2025-02-13 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-05 |  | 001033 | 2025-02-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | AWC
001033 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 1 | 131242-WSD11-VI-I-0004 | 2025-03-17 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001033 | 2025-02-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | AWC
001034 | 00 | Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052 | 2025-02-10 | Submission of BIM Coordination VCM Model (Jan 2025) | For Information. Score= 70/100 | 2025-03-10 | 2025-02-20 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000163&&001034 | 2025-02-10 | 2025-12-16 | 0 | INF | Approved with Comments | 2 | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | AWC
001035 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0049 | 0 | 131242-WSD11-QA-M-0049 | 2025-02-10 | FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch) | Rev 0: Approved | 2025-03-10 | 2025-03-25 | 31 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001035 | 2025-02-10 | 2025-02-10 | 0 | APP | Approved | 1 | "FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch)" | APP
001036 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | A | 0017 | 0 | 131242-WST02-QA-A-0017 | 2025-02-11 | Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | For information. | 2025-03-11 | 2025-02-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001036 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | INF
001037 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0055 | 0 | 131242-WSW41-LT-PM-0055 | 2025-02-11 | EOT Notice Letter for ST617 & ST619 | Rev (0): For Information. Please refer to S.O. correspondence no. 327 dated 14 April 2025. | 2025-03-11 | 2025-04-27 | 54 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001037 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "EOT Notice Letter for ST617 & ST619" | INF
001038 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0004 | 0 | 131242-WSW41-PO-E-0004 | 2025-02-11 | Unppriced PO for YHW | Rev 0: For Information. | 2025-03-11 | 2025-03-13 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001038 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "Unppriced PO for YHW" | INF
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A | 131242-WSD11-DR-B-1003 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.2 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A1 | 131242-WSD11-DR-BH-3000 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A1 | 131242-WSD11-DR-BH-1000 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A1 | 131242-WSD11-DR-BH-1001 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A1 | 131242-WSD11-DR-BH-1002 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | CL | BH | 8000 | 0 | 131242-WSD11-CL-BH-8000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-06-04 | 2025-06-04 | 0 | AWC | Approved with Comments | 1 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A.2 | 131242-WSD11-DR-B-1003 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.2 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A.3 | 131242-WSD11-DR-BH-3000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A.3 | 131242-WSD11-DR-BH-1000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A.3 | 131242-WSD11-DR-BH-1001 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A.3 | 131242-WSD11-DR-BH-1002 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" | AWC
001040 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 0 | 131242-WSD11-QA-E-0023 | 2025-02-12 | FAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. | 2025-03-12 | 2025-03-13 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001040 | 2025-02-12 | 2025-03-27 | 1 | AWC | Approved with Comments | 2 | "FAT Report for WSD11-MCC-0101A&B" | AWC
001040 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 1 | 131242-WSD11-QA-E-0023 | 2025-03-27 | FAT Report for WSD11-MCC-0101A&B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-05-07 | 29 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001040 | 2025-02-12 | 2025-03-27 | 1 | AWC | Approved with Comments | 2 | "FAT Report for WSD11-MCC-0101A&B" | AWC
001041 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 0 | 131242-WSW41-QA-M-0051 | 2025-02-13 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Rev 0: Not approved - Revise and Resubmit | 2025-03-13 | 2025-02-18 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001041 | 2025-02-13 | 2025-03-24 | 1 | NAP | Approved | 2 | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | APP
001041 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 1 | 131242-WSW41-QA-M-0051 | 2025-03-24 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Approved | 2025-04-11 | 2025-05-19 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001041 | 2025-02-13 | 2025-03-24 | 1 | APP | Approved | 2 | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | APP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | NAP
001043 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 0 | 131242-WSW41-VI-M-1007 | 2025-02-14 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-04-05 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001043 | 2025-02-14 | 2025-06-09 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | AWC
001043 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 1 | 131242-WSW41-VI-M-1007 | 2025-06-09 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 | 9 | Approved with Comments | YES | 2025-07-10 | NO | Resubmitted | 0 |  |  | 001043 | 2025-02-14 | 2025-06-09 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | AWC
001044 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023 | 2025-02-16 | MSRA, SWP for Site Wide Pipe Rack Installation | Approved | 2025-03-14 | 2025-12-17 | 217 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000898&&001044 | 2024-12-13 | 2025-02-16 | 0 | APP | Approved | 2 | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | APP
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | INF
001046 | 00 | Jun | HSE | NA | 131242 | WSW41 | MS | E | 0008 | 0 | 131242-WSW41-MS-E-0008 | 2025-02-17 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-03-17 | 20 | Approved with Comments | YES | 2025-04-04 | NO | Resubmitted | 0 |  |  | 001046 | 2025-02-17 | 2025-02-17 | 0 | AWC | Approved with Comments | 1 | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" | AWC
001047 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0021 | 0 | 131242-WSW41-RT-PM-0021 | 2025-02-17 | C4B Monthly Progress Report Number No.21 (01 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-03-17 | 2025-03-13 | 18 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001047 | 2025-02-17 | 2025-02-17 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.21 (01 25) " | AWC
001048 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0020 | 0 | 131242-WSW41-PS-PM-0020 | 2025-02-18 | Monthly Progress Presentation No. 20 (0125) | Rev. 0 - For Information | 2025-03-18 | 2025-02-18 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001048 | 2025-02-18 | 2025-02-18 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 20 (0125)" | INF
001049 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0020 | 0 | 131242-WSW41-MI-PM-0020 | 2025-02-18 | Monthly Progress Meeting Minutes 0020_20250122 | Rev. 0 - For Information | 2025-03-18 | 2025-02-24 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001049 | 2025-02-18 | 2025-02-18 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0020_20250122" | INF
001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-A-1014 | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | 17 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | A | 131242-WST02-SD-A-3014 | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | 17 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | NAP | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001051 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 0 | 131242-WST02-DS-M-5601 | 2025-02-18 | Data Sheet for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-03-04 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001051 | 2025-02-18 | 2025-04-01 | 1 | AWC | Approved | 2 | "Data Sheet for Parabolic Screen" | APP
001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 1 | 131242-WST02-DS-M-5601 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001051 | 2025-02-18 | 2025-04-01 | 1 | APP | Approved | 2 | "Data Sheet for Parabolic Screen" | APP
001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | F | 131242-WST02-DR-M-5601 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | APP | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | APP
001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3203 | A | 131242-WST02-DR-E-3203 | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | 35 | Not Approved | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 001052 | 2025-02-18 | 2025-02-18 | A | NAP | Not Approved | 1 | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | NAP
001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3204 | A | 131242-WST02-DR-E-3204 | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | 35 | Not Approved | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 001052 | 2025-02-18 | 2025-02-18 | A | NAP | Not Approved | 1 | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | NAP
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_BCA | B | 131242-WSD11-DR-S-0300_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_BCA | B | 131242-WSD11-DR-S-0301_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_BCA | B | 131242-WSD11-DR-S-0302_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_BCA | B | 131242-WSD11-DR-S-0303_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_BCA | B | 131242-WSD11-DR-S-0304_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_BCA | B | 131242-WSD11-DR-S-0305_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_BCA | B | 131242-WSD11-DR-S-1000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_BCA | B | 131242-WSD11-DR-S-1001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_BCA | B | 131242-WSD11-DR-S-1002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_BCA | B | 131242-WSD11-DR-S-1003_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_BCA | B | 131242-WSD11-DR-S-2000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_BCA | B | 131242-WSD11-DR-S-2001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_BCA | B | 131242-WSD11-DR-S-3000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_BCA | B | 131242-WSD11-DR-S-3001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_BCA | B | 131242-WSD11-DR-S-3002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_BCA | B | 131242-WSD11-DR-S-5000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_BCA | B | 131242-WSD11-DR-S-5001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_BCA | B | 131242-WSD11-DR-S-5002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_BCA | B | 131242-WSD11-DR-S-5003_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_BCA | B | 131242-WSD11-DR-S-5004_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_BCA | B | 131242-WSD11-DR-S-5005_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_BCA | B | 131242-WSD11-DR-S-5006_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_BCA | B | 131242-WSD11-DR-S-8000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" | INF
001054 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0018 | 0 | 131242-WSW41-QA-A-0018 | 2025-02-18 | Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works | Rev.0:Approved. Please submit MSRA. | 2025-03-18 | 2025-02-24 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001054 | 2025-02-18 | 2025-02-18 | 0 | APP | Approved | 1 | "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" | APP
001055 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0022 | 0 | 131242-WSW41-QA-E-0022 | 2025-02-18 | Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001055 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | AWC
001056 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0017 | 0 | 131242-WSW41-QA-E-0017 | 2025-02-18 | Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001056 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" | AWC
001057 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0018 | 0 | 131242-WSW41-QA-E-0018 | 2025-02-18 | Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001057 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" | AWC
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007_ST620_BCA | 1 | 131242-WSD11-CL-S-0007_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058 | 2025-02-19 | 2025-02-19 | 1 | INF | For Information | 1 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001059 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0050 | 0 | 131242-WST02-QA-M-0050 | 2025-02-19 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch) | Rev 0: Approved | 2025-03-19 | 2025-04-27 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001059 | 2025-02-19 | 2025-02-19 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" | APP
001060 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0052 | 0 | 131242-WSD11-QA-M-0052 | 2025-02-19 | Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-02 | 30 | Approved with Comments | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001060 | 2025-02-19 | 2025-02-19 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system" | AWC
001061 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 0 | 131242-WSD11-QA-E-0024 | 2025-02-20 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-20 | 2025-02-25 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | NAP | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | REJ
001061 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 1 | 131242-WSD11-QA-E-0024 | 2025-03-10 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-02 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | REJ
001061 | 02 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 2 | 131242-WSD11-QA-E-0024 | 2025-04-11 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-05-01 | 2025-05-12 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | REJ
001061 | 03 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 3 | 131242-WSD11-QA-E-0024 | 2025-05-02 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-05-12 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | REJ
001061 | 04 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 4 | 131242-WSD11-QA-E-0024 | 2025-06-28 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 4: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-07-17 | 2025-07-23 | 17 | Rejected | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | REJ | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | REJ
001062 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0007 | 0 | 131242-WSD11-QA-I-0007 | 2025-02-20 | Inspection and Test plan for THP air Compressor System Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-03-20 | 2025-05-30 | 71 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001062 | 2025-02-20 | 2025-02-20 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test plan for THP air Compressor System Pressure Transmitter " | AWC
001063 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | E | 0001 | A | 131242-WST02-DR-E-0001 | 2025-02-21 | SSN Drawing Index (Cable Tray Layout) | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-03-21 | 2025-05-06 | 52 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001063 | 2025-02-21 | 2025-02-21 | A | REJ | Rejected | 1 | "SSN Drawing Index (Cable Tray Layout)" | REJ
001064 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 0001 | A | 131242-WST02-DR-I-0001 | 2025-02-21 | SSN Drawing Index (Instrument Layout) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-21 | 2025-05-07 | 53 | Not Approved | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001064 | 2025-02-21 | 2025-02-21 | A | NAP | Not Approved | 1 | "SSN Drawing Index (Instrument Layout)" | NAP
001065 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0053 | 0 | 131242-WSD11-QA-M-0053 | 2025-02-21 | Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton) | Rev 0: Approved | 2025-03-21 | 2025-04-02 | 28 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001065 | 2025-02-21 | 2025-02-21 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton)" | APP
001066 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0026 | 0 | 131242-WSW41-VI-M-0026 | 2025-02-21 | Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-21 | 2025-04-02 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001066 | 2025-02-21 | 2025-02-21 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks)" | AWC
001067 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0026 | 0 | 131242-WSD11-DS-M-0026 | 2025-02-21 | Data Sheet for Steam Sparger G2D Inlet Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-21 | 2025-04-28 | 46 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 001067 | 2025-02-21 | 2025-02-21 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Steam Sparger G2D Inlet Control Valve" | AWC
001068 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025 | 2025-02-24 | MSRA, SWP for Box Out Concreting | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-24 | 2025-03-18 | 16 | Not Approved | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | NAP
001068 | 01 | Kumar | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025 | 2025-03-28 | MSRA, SWP for Box Out Concreting | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-04-15 | 12 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | NAP
001069 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0013 | 0 | 131242-WSW41-PO-M-0013 | 2025-02-24 | Unpriced PO for CSEL Pipes (MUSG) | Rev 0: For Information. | 2025-03-24 | 2025-03-27 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001069 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for CSEL Pipes (MUSG)" | INF
001070 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0005 | 0 | 131242-WSW41-PO-E-0005 | 2025-02-24 | Unpriced PO for Cable Raceway (United-U Li) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001070 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (United-U Li) " | INF
001071 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0006 | 0 | 131242-WSW41-PO-E-0006 | 2025-02-24 | Unpriced PO for Cable Raceway (Jebsen & Jessen) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001071 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" | INF
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0039 | 0 | 131242-WSW41-MI-C-0039 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | INF
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0040 | 0 | 131242-WSW41-MI-C-0040 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | INF
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0041 | 0 | 131242-WSW41-MI-C-0041 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | INF
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A | 131242-WSD11-DR-BF-7000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 2 | "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | AWC
001074 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0025 | 0 | 131242-WSD11-QA-E-0025 | 2025-02-26 | FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch | Rev 0: Approved. | 2025-03-26 | 2025-05-06 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001074 | 2025-02-26 | 2025-02-26 | 0 | APP | Approved | 1 | "FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch" | APP
001075 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0020 | 0 | 131242-WST02-QA-A-0020 | 2025-02-27 | Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd) | For Information | 2025-03-27 | 2025-04-11 | 31 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001075 | 2025-02-27 | 2025-02-27 | 0 | APP | Approved | 1 | "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" | APP
001076 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8000 | 0 | 131242-WST02-CL-BH-8000 | 2025-02-27 | Fan Static Load Calculation (SSN Electrical Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-25 | 18 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001076 | 2025-02-27 | 2025-02-27 | 0 | AWC | Approved with Comments | 1 | "Fan Static Load Calculation (SSN Electrical Building)" | AWC
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | INF
001078 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 0 | 131242-WST02-QA-A-0019 | 2025-02-28 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-06 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001078 | 2025-02-28 | 2025-04-09 | 1 | NAP | Not Approved | 2 | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" | NAP
001078 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 1 | 131242-WST02-QA-A-0019 | 2025-04-09 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-29 | 2025-05-27 | 34 | Not Approved | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001078 | 2025-02-28 | 2025-04-09 | 1 | NAP | Not Approved | 2 | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" | NAP
001079 | 00 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5751 | 0 | 131242-WST02-CL-P-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Calculations | Rev 0: Approved | 2025-03-28 | 2025-04-28 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001079 | 2025-02-28 | 2025-02-28 | 0 | APP | Approved | 1 | "C4B SSN Pressure Reducing Valve Calculations" | APP
001080 | 00 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 0 | 131242-WST02-DS-M-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-28 | 41 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 001080 | 2025-02-28 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "C4B SSN Pressure Reducing Valve Datasheet" | AWC
001080 | 01 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 1 | 131242-WST02-DS-M-5751 | 2025-07-07 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 52 |  |  | 001080 | 2025-02-28 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "C4B SSN Pressure Reducing Valve Datasheet" | AWC
001081 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 0 | 131242-WSD11-VI-M-0003 | 2025-03-03 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-31 | 2025-03-04 | 1 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001081 | 2025-03-03 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | AWC
001081 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 1 | 131242-WSD11-VI-M-0003 | 2025-03-14 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-02 | 13 | Approved with Comments | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001081 | 2025-03-03 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | AWC
001082 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | S | 0010 | 0 | 131242-WST02-VI-S-0010 | 2025-03-03 | Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-31 | 2025-04-02 | 22 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001082 | 2025-03-03 | 2025-03-03 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." | NAP
001083 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0024 | 0 | 131242-WSD11-DS-M-0024 | 2025-03-04 | Ring Circulation Pump Data Sheet | Rev 0: Approved | 2025-04-01 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001083 | 2025-03-04 | 2025-03-04 | 0 | APP | Approved | 1 | "Ring Circulation Pump Data Sheet" | APP
001084 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0028 | 0 | 131242-WSD11-CL-P-0028 | 2025-03-04 | Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-07-08 | 90 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001084 | 2025-03-04 | 2025-03-04 | 0 | AWC | Approved with Comments | 1 | "Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation" | AWC
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 0301 | A1 | 131242-WSW41-SD-S-0301 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1101 | A1 | 131242-WSW41-SD-S-1101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1102 | A1 | 131242-WSW41-SD-S-1102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1103 | A1 | 131242-WSW41-SD-S-1103 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1104 | A1 | 131242-WSW41-SD-S-1104 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1105 | A1 | 131242-WSW41-SD-S-1105 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1106 | A1 | 131242-WSW41-SD-S-1106 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1107 | A1 | 131242-WSW41-SD-S-1107 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1108 | A1 | 131242-WSW41-SD-S-1108 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2100 | A1 | 131242-WSW41-SD-S-2100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2101 | A1 | 131242-WSW41-SD-S-2101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2102 | A1 | 131242-WSW41-SD-S-2102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3100 | A1 | 131242-WSW41-SD-S-3100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 000581&&001085&&001906 | 2024-07-23 | 2025-12-17 | X | NAP | Not Approved | 3 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3101 | A1 | 131242-WSW41-SD-S-3101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5100 | A1 | 131242-WSW41-SD-S-5100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5101 | A1 | 131242-WSW41-SD-S-5101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5102 | A1 | 131242-WSW41-SD-S-5102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5103 | A1 | 131242-WSW41-SD-S-5103 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5104 | A1 | 131242-WSW41-SD-S-5104 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5105 | A1 | 131242-WSW41-SD-S-5105 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5106 | A1 | 131242-WSW41-SD-S-5106 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | NAP
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 8002 | A1 | 131242-WSW41-SD-S-8002 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001086 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0055 | 0 | 131242-WST02-QA-M-0055 | 2025-03-04 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch) | Rev 0: Approved | 2025-04-01 | 2025-04-30 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001086 | 2025-03-04 | 2025-03-04 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" | APP
001087 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011 | 2025-03-05 | FAT report for Cable Ladder 1st batch (United ULI) | For information | 2025-04-02 | 2025-05-05 | 43 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000927&&001087 | 2024-12-23 | 2025-03-05 | 0 | APP | Approved | 2 | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" | APP
001088 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0033 | 0 | 131242-WSD11-VI-M-0033 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001088 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED" | REJ
001089 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0034 | 0 | 131242-WSD11-VI-M-0034 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001089 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD " | REJ
001090 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0035 | 0 | 131242-WSD11-VI-M-0035 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001090 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES" | REJ
001091 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0054 | 0 | 131242-WSW41-QA-M-0054 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-03-25 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001091 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL)" | AWC
001092 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0028 | 0 | 131242-WSD11-DS-M-0028 | 2025-03-06 | Manual Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001092 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "Manual Gate Valve Data Sheet (Cambi Supply)" | APP
001093 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0029 | 0 | 131242-WSD11-DS-M-0029 | 2025-03-06 | Manual Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001093 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "Manual Ball Valve Data Sheet (Cambi Supply)" | APP
001094 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0030 | 0 | 131242-WSD11-DS-M-0030 | 2025-03-06 | Manual Globe Valve Data Sheet (Cambi Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 88 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001094 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Manual Globe Valve Data Sheet (Cambi Supply)" | AWC
001095 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1395 | 0 | 131242-WSW41-DS-E-1395 | 2025-03-06 | Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) | Rev 0: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001095 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) " | AWC
001096 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0056 | 0 | 131242-WST02-QA-M-0056 | 2025-03-06 | FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved | 2025-04-03 | 2025-03-21 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001096 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | APP
001097 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0026 | 0 | 131242-WSD11-QA-I-0026 | 2025-03-06 | FAT report for Pressure transmitter (Air compressor) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-05-30 | 61 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001097 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "FAT report for Pressure transmitter (Air compressor)" | AWC
001098 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0014 | 0 | 131242-WSW41-PO-M-0014 | 2025-03-06 | Unpriced PO for HDPE Pipes (AGRU) | Rev 0 for information | 2025-04-03 | 2025-03-27 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001098 | 2025-03-06 | 2025-03-06 | 0 | INF | For Information | 1 | "Unpriced PO for HDPE Pipes (AGRU) " | INF
001099 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 0 | 131242-WST02-CD-I-0009 | 2025-03-06 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " | AWC
001099 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 1 | 131242-WST02-CD-I-0009 | 2025-06-16 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " | AWC
001099 | 02 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 2 | 131242-WST02-CD-I-0009 | 2025-08-19 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-23 | 25 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " | AWC
001100 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 0 | 131242-WST02-CD-I-0008 | 2025-03-06 | SSN Aeration Blowers I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001100 | 2025-03-06 | 2025-07-11 | 1 | NAP | Approved with Comments | 2 | "SSN Aeration Blowers I/O List" | AWC
001100 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 1 | 131242-WST02-CD-I-0008 | 2025-07-11 | SSN Aeration Blowers I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001100 | 2025-03-06 | 2025-07-11 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blowers I/O List" | AWC
001101 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0011 | 0 | 131242-WST02-RT-E-0011 | 2025-03-07 | SSN Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 43 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001101 | 2025-03-07 | 2025-03-07 | 0 | AWC | Approved with Comments | 1 | "SSN Motor Starting Study Report " | AWC
001102 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0006 | 0 | 131242-WSD11-RT-E-0006 | 2025-03-07 | THP Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 43 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001102 | 2025-03-07 | 2025-03-07 | 0 | AWC | Approved with Comments | 1 | "THP Motor Starting Study Report " | AWC
001103 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0032 | 0 | 131242-WSD11-DS-M-0032 | 2025-03-07 | ON OFF Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001103 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Gate Valve Data Sheet (Cambi Supply)" | APP
001104 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0033 | 0 | 131242-WSD11-DS-M-0033 | 2025-03-07 | ON OFF Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001104 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve Data Sheet (Cambi Supply)" | APP
001105 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0034 | 0 | 131242-WSD11-DS-M-0034 | 2025-03-07 | ON OFF Ball Valve PN25 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001105 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve PN25 Data Sheet (Cambi Supply)" | APP
001106 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0035 | 0 | 131242-WSD11-DS-M-0035 | 2025-03-07 | ON OFF Ball Valve PN40 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001106 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve PN40 Data Sheet (Cambi Supply)" | APP
001107 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0022 | 0 | 131242-WSW41-RT-PM-0022 | 2025-03-10 | C4B Monthly Progress Report Number No.22 (02 25) | Rev. 0 - Approved with comments (need to re-submit / see attached comment sheet) | 2025-04-07 | 2025-03-27 | 13 | Approved with Comments | YES | 2025-04-16 | NO | Resubmitted | 0 |  |  | 001107 | 2025-03-10 | 2025-03-10 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.22 (02 25) " | AWC
001108 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 0 | 131242-WST02-VI-B-0003 | 2025-03-10 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001108 | 2025-03-10 | 2025-08-22 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" | AWC
001108 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 1 | 131242-WST02-VI-B-0003 | 2025-08-22 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-11 |  | 156 | Awaiting S.O.'s response | YES | 2025-10-09 | NO | Overdue | 0 |  |  | 001108 | 2025-03-10 | 2025-08-22 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" | AWC
001109 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 0 | 131242-WST02-VI-B-0002 | 2025-03-10 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001109 | 2025-03-10 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" | AWC
001109 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 1 | 131242-WST02-VI-B-0002 | 2025-04-18 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-08 | 2025-05-06 | 12 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001109 | 2025-03-10 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" | AWC
001110 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0053 | 0 | 131242-WSW41-CD-IM-0053 | 2025-03-10 | Submission of BIM Coordination VCM Model (Feb 2025) | For information. | 2025-04-07 | 2025-03-25 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001110 | 2025-03-10 | 2025-03-10 | 0 | INF | For Information | 1 | " Submission of BIM Coordination VCM Model (Feb 2025) " | INF
001111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0020 | 0 | 131242-WSW41-PC-W-0020 | 2025-03-10 | Payment Claim No.20 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-04-07 | 2025-04-27 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001111 | 2025-03-10 | 2025-03-10 | 0 | INF | For Information | 1 | "Payment Claim No.20" | INF
001112 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 0 | 131242-WST02-DR-I-7209 | 2025-03-10 | SSN PMS Network Architecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-07 | 2025-05-07 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001112 | 2025-03-10 | 2025-08-07 | 1 | NAP | Approved with Comments | 2 | "SSN PMS Network Architecture Drawings" | AWC
001112 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 1 | 131242-WST02-DR-I-7209 | 2025-08-07 | SSN PMS Network Architecture Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | 55 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001112 | 2025-03-10 | 2025-08-07 | 1 | AWC | Approved with Comments | 2 | "SSN PMS Network Architecture Drawings" | AWC
001113 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 0 | 131242-WST02-VI-BP-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-04-07 | 2025-03-28 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | NAP | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | NAP
001113 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 1 | 131242-WST02-VI-BP-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-03-28 | 2025-05-29 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | NAP | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | NAP
001113 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 2 | 131242-WST02-VI-BP-0001 | 2026-02-05 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2026-02-25 |  | 37 | Awaiting S.O.'s response | YES | 2026-03-25 | NO | Overdue | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | PEN | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | NAP
001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-A-3015 | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | 16 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001114&&001356 | 2025-03-11 | 2025-06-12 | A | NAP | Not Approved | 2 | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | NAP
001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1015 | A | 131242-WST02-SD-A-1015 | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | 16 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001114 | 2025-03-11 | 2025-03-11 | A | NAP | Not Approved | 1 | "Shop Drawings for Siphonic System (Fast Flow)" | NAP
001115 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0007 | 0 | 131242-WSW41-PO-E-0007 | 2025-03-11 | Unpriced PO for Cable Support System (Jiangsu HDMann) | Rev 0: For Information. | 2025-04-08 | 2025-04-27 | 34 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001115 | 2025-03-11 | 2025-03-11 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Support System (Jiangsu HDMann) " | INF
001116 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0057 | 0 | 131242-WSD11-QA-M-0057 | 2025-03-12 | FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-09 | 2025-03-21 | 7 | Approved with Comments | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001116 | 2025-03-12 | 2025-03-12 | 0 | AWC | Approved with Comments | 1 | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " | AWC
001117 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 0 | 131242-WST02-CD-I-0010 | 2025-03-12 | SSN -RIO PANEL 0202- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-09 | 2025-04-22 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001117 | 2025-03-12 | 2025-06-18 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0202- I/O List" | AWC
001117 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 1 | 131242-WST02-CD-I-0010 | 2025-06-18 | SSN -RIO PANEL 0202- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-02 | 54 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001117 | 2025-03-12 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0202- I/O List" | AWC
001118 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2007 | 0 | 131242-WSW41-VI-M-2007 | 2025-03-12 | Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-07-08 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001118 | 2025-03-12 | 2025-03-12 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain" | AWC
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_LTA_NPKS | A | 131242-WSD11-DR-A-1002_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" | NAP
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_LTA_NPKS | A | 131242-WSD11-DR-A-1003_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" | NAP
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_LTA_NPKS | A | 131242-WSD11-DR-A-1004_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" | NAP
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_LTA_NPKS | A | 131242-WSD11-DR-A-2000_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" | NAP
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_LTA_NPKS | A | 131242-WSD11-DR-A-3000_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_PUB | A | 131242-WSD11-DR-A-1002_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_PUB | A | 131242-WSD11-DR-A-1003_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_PUB | A | 131242-WSD11-DR-A-1004_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_PUB | A | 131242-WSD11-DR-A-2000_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" | NAP
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_PUB | A | 131242-WSD11-DR-A-3000_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_NEA | A | 131242-WSD11-DR-A-1002_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_NEA | A | 131242-WSD11-DR-A-1003_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_NEA | A | 131242-WSD11-DR-A-1004_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_NEA | A | 131242-WSD11-DR-A-2000_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" | NAP
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_NEA | A | 131242-WSD11-DR-A-3000_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" | NAP
001122 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0056 | 0 | 131242-WSW41-LT-PM-0056 | 2025-03-13 | NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings | For Information. Please refer to S.O. correspondence no. 353 dated 28 May 2025. | 2025-04-10 | 2025-08-25 | 117 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001122 | 2025-03-13 | 2025-03-13 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings" | INF
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | A | 131242-WST02-DR-M-5484 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | A | 131242-WST02-DR-M-5481 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | A | 131242-WST02-DR-M-5482 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | A | 131242-WST02-DR-M-5483 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | B | 131242-WST02-DR-M-5484 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | B | 131242-WST02-DR-M-5481 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | B | 131242-WST02-DR-M-5482 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | B | 131242-WST02-DR-M-5483 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | AWC
001124 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 5483 | 0 | 131242-WSD11-QA-M-5483 | 2025-03-14 | Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON) | Rev 0: Approved | 2025-04-11 | 2025-07-08 | 82 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001124 | 2025-03-14 | 2025-03-14 | 0 | APP | Approved | 1 | "Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON)" | APP
001125 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2003 | 0 | 131242-WSW41-VI-M-2003 | 2025-03-14 | Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-11 | 2025-04-27 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001125 | 2025-03-14 | 2025-03-14 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen)" | AWC
001126 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0026 | 0 | 131242-WSW41-MS-C-0026 | 2025-03-14 | SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd. | R0: As communicated, CES would like to withdraw the submittal as CES has no intention to use the proposed materials for grouting. Hence, this submittal is rejected and no resubmission is required. | 2025-04-11 | 2025-06-04 | 58 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001126 | 2025-03-14 | 2025-03-14 | 0 | REJ | Rejected | 1 | "SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd." | REJ
001127 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0005 | 0 | 131242-WSD11-DS-I-0005 | 2025-03-17 | Datasheet for Differential Pressure Switch (Compressed Air System) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-14 | 2025-07-10 | 83 | Approved with Comments | YES | 2025-07-30 | NO | Resubmitted | 0 |  |  | 001127 | 2025-03-17 | 2025-03-17 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Differential Pressure Switch (Compressed Air System)" | AWC
001128 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0019 | 0 | 131242-WSW41-PS-HS-0019 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Nov 2024 | Rev 0: Scoring confirmed to be at 70/100 | 2025-04-14 | 2025-03-25 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001128 | 2025-03-17 | 2025-03-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for Nov 2024" | APP
001129 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0005 | 0 | 131242-WST02-VI-B-0005 | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-03-25 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001129 | 2025-03-18 | 2025-03-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | AWC
001129 | 01 | Yuen Fatt | Project | NA | 131242 | NA | NA | NA | Cmt reply sheet | NA | 131242-NA-NA-NA-Cmt reply sheet | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 1: Approved | 2025-04-07 | 2025-05-06 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001129 | 2025-03-18 | 2025-03-18 | NA | APP | Approved | 1 | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | APP
001130 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0020 | 0 | 131242-WSW41-PS-HS-0020 | 2025-03-18 | Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025 | Rev 0: Noted for information | 2025-04-15 | 2025-03-25 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001130 | 2025-03-18 | 2025-03-18 | 0 | APP | Approved | 1 | "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | APP
001131 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 0 | 131242-WST02-RT-S-0002 | 2025-03-18 | Safety Review Report for Sitewide Pipe Rack | Approved with Comments | 2025-04-15 | 2025-05-13 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001131 | 2025-03-18 | 2025-06-18 | 1 | AWC | Approved | 2 | "Safety Review Report for Sitewide Pipe Rack" | APP
001131 | 01 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 1 | 131242-WST02-RT-S-0002 | 2025-06-18 | Safety Review Report for Sitewide Pipe Rack | R1: Approved | 2025-07-08 | 2025-07-07 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001131 | 2025-03-18 | 2025-06-18 | 1 | APP | Approved | 2 | "Safety Review Report for Sitewide Pipe Rack" | APP
001132 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 0 | 131242-WST02-QA-EI-0026 | 2025-03-18 | FAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-05-07 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001132 | 2025-03-18 | 2025-05-23 | 1 | AWC | Approved | 2 | "FAT Procedure for LVSG Panels (Sunlight)" | APP
001132 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 1 | 131242-WST02-QA-EI-0026 | 2025-05-23 | FAT Procedure for LVSG Panels (Sunlight) | Rev 1: Approved. | 2025-06-12 | 2025-07-14 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001132 | 2025-03-18 | 2025-05-23 | 1 | APP | Approved | 2 | "FAT Procedure for LVSG Panels (Sunlight)" | APP
001133 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0027 | 0 | 131242-WST02-QA-EI-0027 | 2025-03-18 | FAT Procedure for MDB Panels (Sunlight) | Approved with Comments | 2025-04-15 | 2025-05-21 | 46 | Approved with Comments | YES | 2025-06-10 | NO | Resubmitted | 0 |  |  | 001133 | 2025-03-18 | 2025-03-18 | 0 | AWC | Approved with Comments | 1 | " FAT Procedure for MDB Panels (Sunlight)" | AWC
001134 | 00 | Max | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 0 | 131242-WSD11-RT-S-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-12 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001134 | 2025-03-18 | 2025-03-18 | 0 | NAP | Not Approved | 2 | "Report of DFS (GUIDE 3) for THP Trains Installation" | NAP
001134 | 01 | Htet Nu | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 1 | 131242-WSD11-RT-S-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-07 | 2025-07-17 | 87 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001134 | 2025-03-18 | 2025-03-18 | 0 | AWC | Not Approved | 2 | "Report of DFS (GUIDE 3) for THP Trains Installation" | NAP
001135 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5801 | A | 131242-WST02-DS-M-5801 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | 82 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001135 | 2025-03-20 | 2025-03-20 | A | AWC | Approved with Comments | 1 | "SSN Spray Nozzle datasheet and drawing" | AWC
001135 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5801 | 0 | 131242-WST02-DR-M-5801 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | 82 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001135 | 2025-03-20 | 2025-03-20 | 0 | AWC | Approved with Comments | 1 | "SSN Spray Nozzle datasheet and drawing" | AWC
001136 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | A | 5000 | A | 131242-WSW41-DR-A-5000 | 2025-03-20 | Sitewide Piperack Handrail and Cad Ladder Layout and Details | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 34 | Not Approved | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001136 | 2025-03-20 | 2025-03-20 | A | NAP | Not Approved | 1 | "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | NAP
001137 | 00 | Radha | QAQC | NA | 131101 | WSW41 | MM | C | 0002 | 0 | 131101-WSW41-MM-C-0002 | 2025-03-20 | Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 34 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001137 | 2025-03-20 | 2025-03-20 | 0 | AWC | Approved with Comments | 1 | "Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall)" | AWC
001138 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0028 | 0 | 131242-WSW41-QA-E-0028 | 2025-03-20 | FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI) | Approved | 2025-04-17 | 2025-05-06 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001138 | 2025-03-20 | 2025-03-20 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" | APP
001139 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 0 | 131242-WSW41-VI-M-2006 | 2025-03-20 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-04-05 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001139 | 2025-03-20 | 2025-05-05 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | AWC
001139 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 1 | 131242-WSW41-VI-M-2006 | 2025-05-05 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | 235 | Awaiting S.O.'s response | YES | 2025-06-20 | NO | Overdue | 0 |  |  | 001139 | 2025-03-20 | 2025-05-05 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | A | 131242-WST02-DR-EI-7160 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | A | 131242-WST02-DR-EI-7161 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | A | 131242-WST02-DR-EI-7162 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | A | 131242-WST02-DR-EI-7163 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | A | 131242-WST02-DR-EI-7164 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | A | 131242-WST02-DR-EI-7165 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | A | 131242-WST02-DR-EI-7166 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | A | 131242-WST02-DR-EI-7167 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | A | 131242-WST02-DR-EI-7180 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | A | 131242-WST02-DR-EI-7181 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | A | 131242-WST02-DR-EI-7182 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | A | 131242-WST02-DR-EI-7183 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | A | 131242-WST02-DR-EI-7184 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | A | 131242-WST02-DR-EI-7185 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | A | 131242-WST02-DR-EI-7186 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | A | 131242-WST02-DR-EI-7187 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | A | 131242-WST02-DR-EP-3052 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | A | 131242-WST02-DR-EP-3053 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | A | 131242-WST02-DR-EP-3054 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | A | 131242-WST02-DR-EP-3055 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | A | 131242-WST02-DR-EP-3056 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | A | 131242-WST02-DR-EP-3057 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | A | 131242-WST02-DR-EP-3058 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | A | 131242-WST02-DR-EP-3059 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | A | 131242-WST02-DR-EP-3060 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | A | 131242-WST02-DR-EP-3061 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | A | 131242-WST02-DR-EP-3062 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | A | 131242-WST02-DR-EP-3063 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | A | 131242-WST02-DR-EP-3064 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | A | 131242-WST02-DR-EP-3065 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | A | 131242-WST02-DR-EP-7142 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | A | 131242-WST02-DR-EP-7143 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | A | 131242-WST02-DR-EP-7144 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | A | 131242-WST02-DR-EP-7145 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | A | 131242-WST02-DR-EP-7146 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | A | 131242-WST02-DR-EP-7147 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | B | 131242-WST02-DR-EI-7160 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | B | 131242-WST02-DR-EI-7161 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | B | 131242-WST02-DR-EI-7162 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | B | 131242-WST02-DR-EI-7163 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | B | 131242-WST02-DR-EI-7164 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | B | 131242-WST02-DR-EI-7165 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | B | 131242-WST02-DR-EI-7166 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | B | 131242-WST02-DR-EI-7167 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | B | 131242-WST02-DR-EI-7180 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | B | 131242-WST02-DR-EI-7181 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | B | 131242-WST02-DR-EI-7182 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | B | 131242-WST02-DR-EI-7183 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | B | 131242-WST02-DR-EI-7184 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | B | 131242-WST02-DR-EI-7185 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | B | 131242-WST02-DR-EI-7186 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | B | 131242-WST02-DR-EI-7187 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | B | 131242-WST02-DR-EP-3052 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | B | 131242-WST02-DR-EP-3053 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | B | 131242-WST02-DR-EP-3054 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | B | 131242-WST02-DR-EP-3055 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | B | 131242-WST02-DR-EP-3056 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | B | 131242-WST02-DR-EP-3057 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | B | 131242-WST02-DR-EP-3058 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | B | 131242-WST02-DR-EP-3059 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | B | 131242-WST02-DR-EP-3060 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | B | 131242-WST02-DR-EP-3061 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | B | 131242-WST02-DR-EP-3062 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | B | 131242-WST02-DR-EP-3063 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | B | 131242-WST02-DR-EP-3064 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | B | 131242-WST02-DR-EP-3065 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | B | 131242-WST02-DR-EP-7142 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | B | 131242-WST02-DR-EP-7143 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | B | 131242-WST02-DR-EP-7144 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | B | 131242-WST02-DR-EP-7145 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | B | 131242-WST02-DR-EP-7146 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | B | 131242-WST02-DR-EP-7147 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | AWC
001141 | 00 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 0 | 131242-WST02-VI-I-0024 | 2025-03-21 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-18 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001141 | 2025-03-21 | 2025-04-30 | 1 | NAP | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | AWC
001141 | 01 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 1 | 131242-WST02-VI-I-0024 | 2025-04-30 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-04 | 25 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 001141 | 2025-03-21 | 2025-04-30 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | AWC
001142 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 0 | 131242-WST02-CD-I-0011 | 2025-03-21 | SSN -RIO PANEL 0401- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-22 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001142 | 2025-03-21 | 2025-06-25 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0401- I/O List" | AWC
001142 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 1 | 131242-WST02-CD-I-0011 | 2025-06-25 | SSN -RIO PANEL 0401- I/O List | Rev 1: Approved with Comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-15 | 58 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001142 | 2025-03-21 | 2025-06-25 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0401- I/O List" | AWC
001143 | 00 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 0 | 131242-WSD11-MS-M-0007 | 2025-03-21 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Not approved - Revise and Resubmit. Refer to comments provided during MSRA briefing meeting dated 28th March 2025 and 4 April 2025. | 2025-04-18 | 2025-04-05 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001143 | 2025-03-21 | 2025-04-10 | 1 | NAP | Approved | 2 | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " | APP
001143 | 01 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 1 | 131242-WSD11-MS-M-0007 | 2025-04-10 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Approved | 2025-04-30 | 2025-05-21 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001143 | 2025-03-21 | 2025-04-10 | 1 | APP | Approved | 2 | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " | APP
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | B | 131242-WST02-DR-IP-1051 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | B | 131242-WST02-DR-IP-1052 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | B | 131242-WST02-DR-IP-1053 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | B | 131242-WST02-DR-IP-1054 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | B | 131242-WST02-DR-IP-1055 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | B | 131242-WST02-DR-IP-1056 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | B | 131242-WST02-DR-IP-1057 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | B | 131242-WST02-DR-IP-1058 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | B | 131242-WST02-DR-IP-1059 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | B | 131242-WST02-DR-IP-1060 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | B | 131242-WST02-DR-IP-1061 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | B | 131242-WST02-DR-IP-1062 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | B | 131242-WST02-DR-IP-1063 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | B | 131242-WST02-DR-IP-1064 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | B | 131242-WST02-DR-IP-1065 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | B | 131242-WST02-DR-IP-1066 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | B | 131242-WST02-DR-IP-1067 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | B | 131242-WST02-DR-IP-1068 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | B | 131242-WST02-DR-IP-1069 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | B | 131242-WST02-DR-IP-1070 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | B | 131242-WST02-DR-IP-1071 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | B | 131242-WST02-DR-IP-1072 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | B | 131242-WST02-DR-IP-1073 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | B | 131242-WST02-DR-IP-1074 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | B | 131242-WST02-DR-IP-1075 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | C | 131242-WST02-DR-IP-1051 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | C | 131242-WST02-DR-IP-1052 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | C | 131242-WST02-DR-IP-1053 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | C | 131242-WST02-DR-IP-1054 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | C | 131242-WST02-DR-IP-1055 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | C | 131242-WST02-DR-IP-1056 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | C | 131242-WST02-DR-IP-1057 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | C | 131242-WST02-DR-IP-1058 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | C | 131242-WST02-DR-IP-1059 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | C | 131242-WST02-DR-IP-1060 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | C | 131242-WST02-DR-IP-1061 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | C | 131242-WST02-DR-IP-1062 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | C | 131242-WST02-DR-IP-1063 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | C | 131242-WST02-DR-IP-1064 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | C | 131242-WST02-DR-IP-1065 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | C | 131242-WST02-DR-IP-1066 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | C | 131242-WST02-DR-IP-1067 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | C | 131242-WST02-DR-IP-1068 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | C | 131242-WST02-DR-IP-1069 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | C | 131242-WST02-DR-IP-1070 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | C | 131242-WST02-DR-IP-1071 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | C | 131242-WST02-DR-IP-1072 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | C | 131242-WST02-DR-IP-1073 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | C | 131242-WST02-DR-IP-1074 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | C | 131242-WST02-DR-IP-1075 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" | AWC
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | B | 131242-WST02-DR-IP-1151 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | B | 131242-WST02-DR-IP-1152 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | B | 131242-WST02-DR-IP-1153 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | B | 131242-WST02-DR-IP-1154 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | B | 131242-WST02-DR-IP-1155 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | B | 131242-WST02-DR-IP-1156 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | B | 131242-WST02-DR-IP-1157 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | B | 131242-WST02-DR-IP-1158 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | B | 131242-WST02-DR-IP-1159 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | B | 131242-WST02-DR-IP-1160 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | B | 131242-WST02-DR-IP-1161 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | B | 131242-WST02-DR-IP-1162 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | B | 131242-WST02-DR-IP-1163 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | B | 131242-WST02-DR-IP-1164 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | B | 131242-WST02-DR-IP-1165 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | B | 131242-WST02-DR-IP-1166 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | B | 131242-WST02-DR-IP-1167 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | B | 131242-WST02-DR-IP-1168 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | B | 131242-WST02-DR-IP-1169 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | B | 131242-WST02-DR-IP-1170 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | B | 131242-WST02-DR-IP-1171 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | B | 131242-WST02-DR-IP-1172 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | B | 131242-WST02-DR-IP-1173 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | B | 131242-WST02-DR-IP-1174 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | B | 131242-WST02-DR-IP-1175 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | B | 131242-WST02-DR-IP-1176 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | B | 131242-WST02-DR-IP-1177 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | B | 131242-WST02-DR-IP-1178 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | B | 131242-WST02-DR-IP-1179 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | B | 131242-WST02-DR-IP-1180 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | B | 131242-WST02-DR-IP-1181 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | B | 131242-WST02-DR-IP-1182 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | B | 131242-WST02-DR-IP-1183 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | B | 131242-WST02-DR-IP-1184 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | B | 131242-WST02-DR-IP-1185 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | B | 131242-WST02-DR-IP-1186 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | B | 131242-WST02-DR-IP-1187 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | B | 131242-WST02-DR-IP-1188 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | B | 131242-WST02-DR-IP-1189 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | B | 131242-WST02-DR-IP-1190 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | B | 131242-WST02-DR-IP-1191 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | B | 131242-WST02-DR-IP-1192 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | B | 131242-WST02-DR-IP-1193 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | B | 131242-WST02-DR-IP-1194 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | B | 131242-WST02-DR-IP-1195 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | B | 131242-WST02-DR-IP-1196 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | B | 131242-WST02-DR-IP-1197 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | B | 131242-WST02-DR-IP-1198 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | B | 131242-WST02-DR-IP-1199 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | B | 131242-WST02-DR-IP-1200 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | B | 131242-WST02-DR-IP-1201 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | B | 131242-WST02-DR-IP-1202 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | B | 131242-WST02-DR-IP-1203 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | B | 131242-WST02-DR-IP-1204 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | B | 131242-WST02-DR-IP-1205 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | B | 131242-WST02-DR-IP-1206 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | B | 131242-WST02-DR-IP-1207 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | B | 131242-WST02-DR-IP-1208 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | B | 131242-WST02-DR-IP-1209 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | B | 131242-WST02-DR-IP-1210 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | B | 131242-WST02-DR-IP-1211 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | B | 131242-WST02-DR-IP-1212 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | B | 131242-WST02-DR-IP-1213 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | B | 131242-WST02-DR-IP-1214 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | B | 131242-WST02-DR-IP-1215 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | B | 131242-WST02-DR-IP-1216 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | B | 131242-WST02-DR-IP-1217 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | B | 131242-WST02-DR-IP-1218 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | B | 131242-WST02-DR-IP-1219 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | B | 131242-WST02-DR-IP-1220 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | B | 131242-WST02-DR-IP-1221 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | B | 131242-WST02-DR-IP-1222 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | B | 131242-WST02-DR-IP-1223 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | B | 131242-WST02-DR-IP-1224 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | B | 131242-WST02-DR-IP-1225 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | B | 131242-WST02-DR-IP-1226 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | B | 131242-WST02-DR-IP-1227 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | B | 131242-WST02-DR-IP-1228 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | B | 131242-WST02-DR-IP-1229 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | B | 131242-WST02-DR-IP-1230 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | B | 131242-WST02-DR-IP-1231 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | B | 131242-WST02-DR-IP-1232 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | B | 131242-WST02-DR-IP-1233 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | B | 131242-WST02-DR-IP-1234 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | B | 131242-WST02-DR-IP-1235 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | B | 131242-WST02-DR-IP-1236 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | B | 131242-WST02-DR-IP-1237 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | B | 131242-WST02-DR-IP-1238 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | B | 131242-WST02-DR-IP-1239 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | B | 131242-WST02-DR-IP-1240 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | B | 131242-WST02-DR-IP-1241 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | B | 131242-WST02-DR-IP-1242 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | B | 131242-WST02-DR-IP-1243 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | B | 131242-WST02-DR-IP-1244 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | B | 131242-WST02-DR-IP-1245 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | B | 131242-WST02-DR-IP-1246 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | B | 131242-WST02-DR-IP-1247 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | B | 131242-WST02-DR-IP-1248 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | B | 131242-WST02-DR-IP-1249 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | B | 131242-WST02-DR-IP-1250 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | B | 131242-WST02-DR-IP-1251 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | B | 131242-WST02-DR-IP-1252 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | B | 131242-WST02-DR-IP-1253 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | B | 131242-WST02-DR-IP-1254 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | B | 131242-WST02-DR-IP-1255 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | B | 131242-WST02-DR-IP-1256 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | B | 131242-WST02-DR-IP-1257 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | B | 131242-WST02-DR-IP-1258 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | B | 131242-WST02-DR-IP-1259 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | B | 131242-WST02-DR-IP-1260 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | B | 131242-WST02-DR-IP-1261 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | B | 131242-WST02-DR-IP-1262 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | B | 131242-WST02-DR-IP-1263 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | B | 131242-WST02-DR-IP-1264 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | B | 131242-WST02-DR-IP-1265 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | B | 131242-WST02-DR-IP-1266 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | B | 131242-WST02-DR-IP-1267 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | B | 131242-WST02-DR-IP-1268 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | B | 131242-WST02-DR-IP-1269 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | B | 131242-WST02-DR-IP-1270 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | B | 131242-WST02-DR-IP-1271 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | B | 131242-WST02-DR-IP-1272 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | B | 131242-WST02-DR-IP-1273 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | B | 131242-WST02-DR-IP-1274 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | B | 131242-WST02-DR-IP-1275 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | B | 131242-WST02-DR-IP-1276 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | B | 131242-WST02-DR-IP-1277 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | B | 131242-WST02-DR-IP-1278 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | B | 131242-WST02-DR-IP-1279 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | B | 131242-WST02-DR-IP-1280 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | B | 131242-WST02-DR-IP-1281 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | B | 131242-WST02-DR-IP-1282 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | B | 131242-WST02-DR-IP-1283 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | B | 131242-WST02-DR-IP-1284 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | B | 131242-WST02-DR-IP-1285 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | B | 131242-WST02-DR-IP-1286 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | B | 131242-WST02-DR-IP-1287 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | B | 131242-WST02-DR-IP-1288 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | B | 131242-WST02-DR-IP-1289 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | B | 131242-WST02-DR-IP-1290 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | B | 131242-WST02-DR-IP-1291 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | B | 131242-WST02-DR-IP-1292 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | B | 131242-WST02-DR-IP-1293 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | B | 131242-WST02-DR-IP-1294 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | B | 131242-WST02-DR-IP-1295 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | B | 131242-WST02-DR-IP-1296 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | B | 131242-WST02-DR-IP-1297 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | B | 131242-WST02-DR-IP-1298 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | B | 131242-WST02-DR-IP-1299 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | C | 131242-WST02-DR-IP-1151 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | C | 131242-WST02-DR-IP-1152 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | C | 131242-WST02-DR-IP-1153 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | C | 131242-WST02-DR-IP-1154 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | C | 131242-WST02-DR-IP-1155 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | C | 131242-WST02-DR-IP-1156 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | C | 131242-WST02-DR-IP-1157 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | C | 131242-WST02-DR-IP-1158 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | C | 131242-WST02-DR-IP-1159 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | C | 131242-WST02-DR-IP-1160 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | C | 131242-WST02-DR-IP-1161 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | C | 131242-WST02-DR-IP-1162 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | C | 131242-WST02-DR-IP-1163 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | C | 131242-WST02-DR-IP-1164 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | C | 131242-WST02-DR-IP-1165 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | C | 131242-WST02-DR-IP-1166 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | C | 131242-WST02-DR-IP-1167 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | C | 131242-WST02-DR-IP-1168 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | C | 131242-WST02-DR-IP-1169 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | C | 131242-WST02-DR-IP-1170 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | C | 131242-WST02-DR-IP-1171 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | C | 131242-WST02-DR-IP-1172 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | C | 131242-WST02-DR-IP-1173 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | C | 131242-WST02-DR-IP-1174 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | C | 131242-WST02-DR-IP-1175 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | C | 131242-WST02-DR-IP-1176 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | C | 131242-WST02-DR-IP-1177 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | C | 131242-WST02-DR-IP-1178 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | C | 131242-WST02-DR-IP-1179 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | C | 131242-WST02-DR-IP-1180 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | C | 131242-WST02-DR-IP-1181 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | C | 131242-WST02-DR-IP-1182 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | C | 131242-WST02-DR-IP-1183 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | C | 131242-WST02-DR-IP-1184 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | C | 131242-WST02-DR-IP-1185 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | C | 131242-WST02-DR-IP-1186 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | C | 131242-WST02-DR-IP-1187 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | C | 131242-WST02-DR-IP-1188 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | C | 131242-WST02-DR-IP-1189 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | C | 131242-WST02-DR-IP-1190 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | C | 131242-WST02-DR-IP-1191 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | C | 131242-WST02-DR-IP-1192 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | C | 131242-WST02-DR-IP-1193 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | C | 131242-WST02-DR-IP-1194 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | C | 131242-WST02-DR-IP-1195 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | C | 131242-WST02-DR-IP-1196 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | C | 131242-WST02-DR-IP-1197 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | C | 131242-WST02-DR-IP-1198 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | C | 131242-WST02-DR-IP-1199 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | C | 131242-WST02-DR-IP-1200 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | C | 131242-WST02-DR-IP-1201 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | C | 131242-WST02-DR-IP-1202 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | C | 131242-WST02-DR-IP-1203 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | C | 131242-WST02-DR-IP-1204 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | C | 131242-WST02-DR-IP-1205 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | C | 131242-WST02-DR-IP-1206 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | C | 131242-WST02-DR-IP-1207 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | C | 131242-WST02-DR-IP-1208 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | C | 131242-WST02-DR-IP-1209 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | C | 131242-WST02-DR-IP-1210 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | C | 131242-WST02-DR-IP-1211 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | C | 131242-WST02-DR-IP-1212 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | C | 131242-WST02-DR-IP-1213 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | C | 131242-WST02-DR-IP-1214 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | C | 131242-WST02-DR-IP-1215 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | C | 131242-WST02-DR-IP-1216 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | C | 131242-WST02-DR-IP-1217 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | C | 131242-WST02-DR-IP-1218 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | C | 131242-WST02-DR-IP-1219 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | C | 131242-WST02-DR-IP-1220 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | C | 131242-WST02-DR-IP-1221 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | C | 131242-WST02-DR-IP-1222 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | C | 131242-WST02-DR-IP-1223 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | C | 131242-WST02-DR-IP-1224 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | C | 131242-WST02-DR-IP-1225 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | C | 131242-WST02-DR-IP-1226 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | C | 131242-WST02-DR-IP-1227 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | C | 131242-WST02-DR-IP-1228 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | C | 131242-WST02-DR-IP-1229 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | C | 131242-WST02-DR-IP-1230 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | C | 131242-WST02-DR-IP-1231 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | C | 131242-WST02-DR-IP-1232 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | C | 131242-WST02-DR-IP-1233 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | C | 131242-WST02-DR-IP-1234 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | C | 131242-WST02-DR-IP-1235 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | C | 131242-WST02-DR-IP-1236 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | C | 131242-WST02-DR-IP-1237 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | C | 131242-WST02-DR-IP-1238 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | C | 131242-WST02-DR-IP-1239 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | C | 131242-WST02-DR-IP-1240 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | C | 131242-WST02-DR-IP-1241 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | C | 131242-WST02-DR-IP-1242 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | C | 131242-WST02-DR-IP-1243 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | C | 131242-WST02-DR-IP-1244 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | C | 131242-WST02-DR-IP-1245 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | C | 131242-WST02-DR-IP-1246 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | C | 131242-WST02-DR-IP-1247 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | C | 131242-WST02-DR-IP-1248 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | C | 131242-WST02-DR-IP-1249 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | C | 131242-WST02-DR-IP-1250 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | C | 131242-WST02-DR-IP-1251 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | C | 131242-WST02-DR-IP-1252 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | C | 131242-WST02-DR-IP-1253 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | C | 131242-WST02-DR-IP-1254 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | C | 131242-WST02-DR-IP-1255 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | C | 131242-WST02-DR-IP-1256 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | C | 131242-WST02-DR-IP-1257 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | C | 131242-WST02-DR-IP-1258 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | C | 131242-WST02-DR-IP-1259 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | C | 131242-WST02-DR-IP-1260 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | C | 131242-WST02-DR-IP-1261 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | C | 131242-WST02-DR-IP-1262 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | C | 131242-WST02-DR-IP-1263 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | C | 131242-WST02-DR-IP-1264 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | C | 131242-WST02-DR-IP-1265 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | C | 131242-WST02-DR-IP-1266 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | C | 131242-WST02-DR-IP-1267 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | C | 131242-WST02-DR-IP-1268 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | C | 131242-WST02-DR-IP-1269 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | C | 131242-WST02-DR-IP-1270 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | C | 131242-WST02-DR-IP-1271 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | C | 131242-WST02-DR-IP-1272 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | C | 131242-WST02-DR-IP-1273 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | C | 131242-WST02-DR-IP-1274 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | C | 131242-WST02-DR-IP-1275 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | C | 131242-WST02-DR-IP-1276 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | C | 131242-WST02-DR-IP-1277 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | C | 131242-WST02-DR-IP-1278 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | C | 131242-WST02-DR-IP-1279 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | C | 131242-WST02-DR-IP-1280 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | C | 131242-WST02-DR-IP-1281 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | C | 131242-WST02-DR-IP-1282 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | C | 131242-WST02-DR-IP-1283 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | C | 131242-WST02-DR-IP-1284 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | C | 131242-WST02-DR-IP-1285 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | C | 131242-WST02-DR-IP-1286 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | C | 131242-WST02-DR-IP-1287 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | C | 131242-WST02-DR-IP-1288 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | C | 131242-WST02-DR-IP-1289 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | C | 131242-WST02-DR-IP-1290 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | C | 131242-WST02-DR-IP-1291 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | C | 131242-WST02-DR-IP-1292 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | C | 131242-WST02-DR-IP-1293 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | C | 131242-WST02-DR-IP-1294 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | C | 131242-WST02-DR-IP-1295 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | C | 131242-WST02-DR-IP-1296 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | C | 131242-WST02-DR-IP-1297 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | C | 131242-WST02-DR-IP-1298 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | C | 131242-WST02-DR-IP-1299 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" | NAP
001149 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | B | 1397 | 0 | 131242-WSW41-DS-B-1397 | 2025-03-21 | Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance) | Approved | 2025-04-18 | 2025-05-25 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001149 | 2025-03-21 | 2025-03-21 | 0 | APP | Approved | 1 | "Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance)" | APP
001150 | 00 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 0 | 131242-WSD11-RT-S-0002 | 2025-03-24 | Report of Project Safety Review for THP Trains Installation | Approved with Comments | 2025-04-21 | 2025-05-13 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" | AWC
001150 | 01 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 1 | 131242-WSD11-RT-S-0002 | 2025-06-18 | Report of Project Safety Review for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-08 | 2025-07-04 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" | AWC
001150 | 02 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 2 | 131242-WSD11-RT-S-0002 | 2025-09-03 | Report of Project Safety Review for THP Trains Installation | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-10-14 | 29 | Approved with Comments | YES | 2025-11-03 | NO | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" | AWC
001151 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0059 | 0 | 131242-WSW41-QA-M-0059 | 2025-03-24 | FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch) | NA | 2025-04-21 | 2025-09-02 | 116 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001151 | 2025-03-24 | 2025-03-24 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" | AWC
001152 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0028 | 0 | 131242-WSW41-SP-C-0028 | 2025-03-24 | Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) | Approved | 2025-04-21 | 2025-05-09 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001152 | 2025-03-24 | 2025-03-24 | 0 | APP | Approved | 1 | "Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) " | APP
001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | CL | S | 0003 | 0 | 131242-WST02-CL-S-0003 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001153 | 2025-03-24 | 2025-03-24 | 0 | APP | Approved | 1 | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" | APP
001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | DR | S | 5603 | A.3 | 131242-WST02-DR-S-5603 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001153&&001528 | 2025-03-24 | 2025-07-24 | A | APP | Not Approved | 2 | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | NAP
001154 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 0 | 131242-WST02-VI-BF-0001 | 2025-03-24 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-04-21 | 2025-05-06 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | NAP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | APP
001154 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 1 | 131242-WST02-VI-BF-0001 | 2025-06-04 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-06-24 | 2025-07-08 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | NAP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | APP
001154 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 2 | 131242-WST02-VI-BF-0001 | 2025-08-12 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-09-01 | 2026-01-05 | 104 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | APP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | APP
001155 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 0 | 131242-WST02-CD-I-0012 | 2025-03-24 | SSN -RIO PANEL 0203- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-21 | 2025-04-27 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001155 | 2025-03-24 | 2025-06-25 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0203- I/O List " | AWC
001155 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 1 | 131242-WST02-CD-I-0012 | 2025-06-25 | SSN -RIO PANEL 0203- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-02 | 49 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001155 | 2025-03-24 | 2025-06-25 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0203- I/O List " | AWC
001156 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | A | 0005 | 0 | 131242-WSW41-MS-A-0005 | 2025-03-24 | MSRA for Waterproofing Works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-21 | 2025-04-15 | 16 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001156 | 2025-03-24 | 2025-03-24 | 0 | NAP | Not Approved | 1 | "MSRA for Waterproofing Works" | NAP
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | A | 131242-WST02-DR-EI-7200 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | A | 131242-WST02-DR-EI-7201 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | A | 131242-WST02-DR-EI-7202 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | A | 131242-WST02-DR-EI-7203 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | A | 131242-WST02-DR-EI-7204 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | A | 131242-WST02-DR-EI-7205 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | A | 131242-WST02-DR-EI-7206 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | A | 131242-WST02-DR-EI-7207 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | A | 131242-WST02-DR-EI-7208 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | A | 131242-WST02-DR-EI-7209 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | A | 131242-WST02-DR-EI-7220 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | A | 131242-WST02-DR-EI-7221 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | A | 131242-WST02-DR-EI-7222 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | A | 131242-WST02-DR-EI-7223 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | A | 131242-WST02-DR-EI-7224 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | A | 131242-WST02-DR-EI-7225 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | A | 131242-WST02-DR-EI-7226 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | A | 131242-WST02-DR-EI-7227 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | A | 131242-WST02-DR-EI-7228 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | A | 131242-WST02-DR-EI-7229 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | A | 131242-WST02-DR-EP-3066 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | A | 131242-WST02-DR-EP-3067 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | A | 131242-WST02-DR-EP-3068 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | A | 131242-WST02-DR-EP-3069 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | A | 131242-WST02-DR-EP-3070 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | A | 131242-WST02-DR-EP-3071 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | A | 131242-WST02-DR-EP-3072 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | A | 131242-WST02-DR-EP-3073 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | A | 131242-WST02-DR-EP-3074 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | A | 131242-WST02-DR-EP-3075 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | A | 131242-WST02-DR-EP-3076 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | A | 131242-WST02-DR-EP-3077 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | A | 131242-WST02-DR-EP-3078 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | A | 131242-WST02-DR-EP-3079 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | A | 131242-WST02-DR-EP-7148 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | A | 131242-WST02-DR-EP-7149 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | A | 131242-WST02-DR-EP-7150 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | A | 131242-WST02-DR-EP-7151 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | A | 131242-WST02-DR-EP-7152 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | A | 131242-WST02-DR-EP-7153 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | A | 131242-WST02-DR-EP-7154 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | A | 131242-WST02-DR-EP-7155 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | B | 131242-WST02-DR-EI-7200 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | B | 131242-WST02-DR-EI-7201 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | B | 131242-WST02-DR-EI-7202 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | B | 131242-WST02-DR-EI-7203 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | B | 131242-WST02-DR-EI-7204 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | B | 131242-WST02-DR-EI-7205 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | B | 131242-WST02-DR-EI-7206 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | B | 131242-WST02-DR-EI-7207 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | B | 131242-WST02-DR-EI-7208 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | B | 131242-WST02-DR-EI-7209 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | B | 131242-WST02-DR-EI-7220 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | B | 131242-WST02-DR-EI-7221 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | B | 131242-WST02-DR-EI-7222 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | B | 131242-WST02-DR-EI-7223 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | B | 131242-WST02-DR-EI-7224 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | B | 131242-WST02-DR-EI-7225 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | B | 131242-WST02-DR-EI-7226 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | B | 131242-WST02-DR-EI-7227 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | B | 131242-WST02-DR-EI-7228 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | B | 131242-WST02-DR-EI-7229 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | B | 131242-WST02-DR-EP-3066 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | B | 131242-WST02-DR-EP-3067 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | B | 131242-WST02-DR-EP-3068 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | B | 131242-WST02-DR-EP-3069 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | B | 131242-WST02-DR-EP-3070 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | B | 131242-WST02-DR-EP-3071 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | B | 131242-WST02-DR-EP-3072 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | B | 131242-WST02-DR-EP-3073 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | B | 131242-WST02-DR-EP-3074 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | B | 131242-WST02-DR-EP-3075 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | B | 131242-WST02-DR-EP-3076 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | B | 131242-WST02-DR-EP-3077 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | B | 131242-WST02-DR-EP-3078 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | B | 131242-WST02-DR-EP-3079 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | B | 131242-WST02-DR-EP-7148 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | B | 131242-WST02-DR-EP-7149 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | B | 131242-WST02-DR-EP-7150 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | B | 131242-WST02-DR-EP-7151 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | B | 131242-WST02-DR-EP-7152 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | B | 131242-WST02-DR-EP-7153 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | B | 131242-WST02-DR-EP-7154 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | B | 131242-WST02-DR-EP-7155 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | AWC
001158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0010 | 0 | 131242-WST02-RT-E-0010 | 2025-03-25 | SSN Protection Coordination Study Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-22 | 2025-05-27 | 45 | Approved with Comments | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001158 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "SSN Protection Coordination Study Report" | AWC
001159 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0005 | 0 | 131242-WSD11-RT-E-0005 | 2025-03-25 | THP Protection Coordination Study Report | : Rev 0: Approved with comments. To revise and resubmit | 2025-04-22 | 2025-05-27 | 45 | Approved with Comments | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001159 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "THP Protection Coordination Study Report" | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7201 | A | 131242-WSD11-DR-I-7201 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7202 | A | 131242-WSD11-DR-I-7202 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7203 | A | 131242-WSD11-DR-I-7203 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7204 | A | 131242-WSD11-DR-I-7204 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " | AWC
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7205 | A | 131242-WSD11-DR-I-7205 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " | AWC
001161 | 00 | Charles | CSA | NA | 131242 | WSW41 | MS | A | 0001 | 0 | 131242-WSW41-MS-A-0001 | 2025-03-25 | MSRA and SWP for MEICA OPENING on Block-wall | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | 15 | Approved with Comments | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001161 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for MEICA OPENING on Block-wall " | AWC
001162 | 00 | N.Kumar | CSA | NA | 131242 | WSW41 | MS | C | 0027 | 0 | 131242-WSW41-MS-C-0027 | 2025-03-25 | Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | 15 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001162 | 2025-03-25 | 2025-03-25 | 0 | NAP | Not Approved | 1 | "Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) " | NAP
001163 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0008 | 0 | 131242-WSW41-PO-E-0008 | 2025-03-25 | Unpriced PO for Cable Raceway (Jiangsu HDMann) | Rev 0: For information. | 2025-04-22 | 2025-05-06 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001163 | 2025-03-25 | 2025-03-25 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" | INF
001164 | 00 | Aaron | CSA | NA | 131242 | WSW41 | VI | A | 0005 | 0 | 131242-WSW41-VI-A-0005 | 2025-03-25 | Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd) | R0: Approved | 2025-04-22 | 2025-04-15 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001164 | 2025-03-25 | 2025-03-25 | 0 | APP | Approved | 1 | "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" | APP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | A | 131242-WST02-DR-IC-3001 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | A | 131242-WST02-DR-IC-3002 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | A | 131242-WST02-DR-IC-3003 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | A | 131242-WST02-DR-IC-3004 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | A | 131242-WST02-DR-IC-3005 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | A | 131242-WST02-DR-IC-3006 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | A | 131242-WST02-DR-IC-3007 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | A | 131242-WST02-DR-IC-3008 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | A | 131242-WST02-DR-IC-3009 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | A | 131242-WST02-DR-IC-3010 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | A | 131242-WST02-DR-IC-3011 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | A | 131242-WST02-DR-IC-3012 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | A | 131242-WST02-DR-IC-3013 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | A | 131242-WST02-DR-IC-3014 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | A | 131242-WST02-DR-IC-3015 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | A | 131242-WST02-DR-IC-3016 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | A | 131242-WST02-DR-IC-3017 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | A | 131242-WST02-DR-IC-3018 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | A | 131242-WST02-DR-IC-3019 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | A | 131242-WST02-DR-IC-3020 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | A | 131242-WST02-DR-IC-3021 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | A | 131242-WST02-DR-IC-3022 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | A | 131242-WST02-DR-IC-3023 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | A | 131242-WST02-DR-IC-3024 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | B | 131242-WST02-DR-IC-3001 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | B | 131242-WST02-DR-IC-3002 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | B | 131242-WST02-DR-IC-3003 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | B | 131242-WST02-DR-IC-3004 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | B | 131242-WST02-DR-IC-3005 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | B | 131242-WST02-DR-IC-3006 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | B | 131242-WST02-DR-IC-3007 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | B | 131242-WST02-DR-IC-3008 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | B | 131242-WST02-DR-IC-3009 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | B | 131242-WST02-DR-IC-3010 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | B | 131242-WST02-DR-IC-3011 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | B | 131242-WST02-DR-IC-3012 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | B | 131242-WST02-DR-IC-3013 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | B | 131242-WST02-DR-IC-3014 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | B | 131242-WST02-DR-IC-3015 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | B | 131242-WST02-DR-IC-3016 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | B | 131242-WST02-DR-IC-3017 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | B | 131242-WST02-DR-IC-3018 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | B | 131242-WST02-DR-IC-3019 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | B | 131242-WST02-DR-IC-3020 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | B | 131242-WST02-DR-IC-3021 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | B | 131242-WST02-DR-IC-3022 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | B | 131242-WST02-DR-IC-3023 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | B | 131242-WST02-DR-IC-3024 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | NAP
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | A | 131242-WST02-DR-IP-2101 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | A | 131242-WST02-DR-IP-2102 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | A | 131242-WST02-DR-IP-2103 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | A | 131242-WST02-DR-IP-2104 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | A | 131242-WST02-DR-IP-2105 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | A | 131242-WST02-DR-IP-2106 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | A | 131242-WST02-DR-IP-2107 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | A | 131242-WST02-DR-IP-2108 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | A | 131242-WST02-DR-IP-2109 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | A | 131242-WST02-DR-IP-2110 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | A | 131242-WST02-DR-IP-2111 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | A | 131242-WST02-DR-IP-2112 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | A | 131242-WST02-DR-IP-2113 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | A | 131242-WST02-DR-IP-2114 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | A | 131242-WST02-DR-IP-2115 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | A | 131242-WST02-DR-IP-2116 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | A | 131242-WST02-DR-IP-2117 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | A | 131242-WST02-DR-IP-2118 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2119 | A | 131242-WST02-DR-IP-2119 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-03-25 | A | NAP | Not Approved | 1 | "SSN Panel (FIOP) - GA & Wiring Drawings" | NAP
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2120 | A | 131242-WST02-DR-IP-2120 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-03-25 | A | NAP | Not Approved | 1 | "SSN Panel (FIOP) - GA & Wiring Drawings" | NAP
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | D | 131242-WST02-DR-IP-2101 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-02 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | D | 131242-WST02-DR-IP-2102 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | D | 131242-WST02-DR-IP-2103 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | D | 131242-WST02-DR-IP-2104 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | D | 131242-WST02-DR-IP-2105 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | D | 131242-WST02-DR-IP-2106 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | D | 131242-WST02-DR-IP-2107 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | D | 131242-WST02-DR-IP-2108 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | D | 131242-WST02-DR-IP-2109 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | D | 131242-WST02-DR-IP-2110 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | D | 131242-WST02-DR-IP-2111 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | D | 131242-WST02-DR-IP-2112 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | D | 131242-WST02-DR-IP-2113 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | D | 131242-WST02-DR-IP-2114 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | D | 131242-WST02-DR-IP-2115 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | D | 131242-WST02-DR-IP-2116 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | D | 131242-WST02-DR-IP-2117 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | D | 131242-WST02-DR-IP-2118 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" | AWC
001167 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 0 | 131242-WSD11-DS-I-0006 | 2025-03-25 | Datasheet for Electromagnetic Flow Meter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-07-10 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001167 | 2025-03-25 | 2025-10-16 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Electromagnetic Flow Meter " | AWC
001167 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 1 | 131242-WSD11-DS-I-0006 | 2025-10-16 | Datasheet for Electromagnetic Flow Meter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-27 | 30 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001167 | 2025-03-25 | 2025-10-16 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Electromagnetic Flow Meter " | AWC
001168 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0006 | 0 | 131242-WST02-VI-A-0006 | 2025-03-26 | Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd. | Approved | 2025-04-23 | 2025-04-11 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001168 | 2025-03-26 | 2025-03-26 | 0 | APP | Approved | 1 | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." | APP
001169 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0058 | 0 | 131242-WSW41-LT-PM-0058 | 2025-03-26 | Consent to Potential Acquisition of CES Construction by OKH | For Information | 2025-04-23 | 2025-04-05 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001169 | 2025-03-26 | 2025-03-26 | 0 | INF | For Information | 1 | "Consent to Potential Acquisition of CES Construction by OKH " | INF
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 0 | 131242-WST02-CL-P-5701 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 0 | 131242-WST02-CL-P-5702 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 0 | 131242-WST02-CL-P-5703 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 0 | 131242-WST02-DS-M-5701 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 0 | 131242-WST02-DS-M-5702 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 0 | 131242-WST02-DS-M-5703 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 1 | 131242-WST02-CL-P-5701 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 1 | 131242-WST02-CL-P-5702 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 1 | 131242-WST02-CL-P-5703 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 1 | 131242-WST02-DS-M-5701 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 1 | 131242-WST02-DS-M-5702 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 1 | 131242-WST02-DS-M-5703 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" | AWC
001171 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 0 | 131242-WSD11-DS-I-0007 | 2025-03-27 | Datasheet for Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001171 | 2025-03-27 | 2025-10-16 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Level Transmitter" | AWC
001171 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 1 | 131242-WSD11-DS-I-0007 | 2025-10-16 | Datasheet for Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-05 | 14 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001171 | 2025-03-27 | 2025-10-16 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Level Transmitter" | AWC
001172 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 0 | 131242-WST02-DS-M-5391 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | 1 | AWC | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" | AWC
001172 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | A | 131242-WST02-DR-M-5391 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | B | AWC | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" | AWC
001172 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 1 | 131242-WST02-DS-M-5391 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-06 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | 1 | PEN | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" | AWC
001172 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | B | 131242-WST02-DR-M-5391 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | B | PEN | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" | AWC
001173 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 0 | 131242-WSD11-DS-I-0011 | 2025-03-27 | Datasheet for Temperature Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | NAP | Not Approved | 3 | "Datasheet for Temperature Transmitter " | NAP
001173 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1_Superceded | 131242-WSD11-DS-I-0011 | 2025-10-27 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2025-11-14 | 2025-12-09 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | NAP | Not Approved | 3 | "Datasheet for Temperature Transmitter " | NAP
001173 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1 | 131242-WSD11-DS-I-0011 | 2026-01-21 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2026-02-10 |  | 48 | Awaiting S.O.'s response | YES | 2026-03-10 | NO | Overdue | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | PEN | Not Approved | 3 | "Datasheet for Temperature Transmitter " | NAP
001174 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029 | 2025-03-27 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-24 | 2025-06-17 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001174 | 2025-03-27 | 2025-07-10 | 0 | AWC | Approved with Comments | 2 | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " | AWC
001174 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029 | 2025-07-10 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached filed for comments. | 2025-07-30 | 2025-07-17 | 5 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001174 | 2025-03-27 | 2025-07-10 | 0 | AWC | Approved with Comments | 2 | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " | AWC
001175 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0060 | 0 | 131242-WSW41-QA-M-0060 | 2025-03-27 | FAT Report for Compressor Pipe support in Bio solid building | NA | 2025-04-24 | 2025-09-02 | 113 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001175 | 2025-03-27 | 2025-03-27 | 0 | AWC | Approved with Comments | 1 | " FAT Report for Compressor Pipe support in Bio solid building" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | A | 131242-WST02-DR-IP-1025 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | A | 131242-WST02-DR-IP-1026 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | A | 131242-WST02-DR-IP-1027 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | A | 131242-WST02-DR-IP-1028 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | A | 131242-WST02-DR-IP-1029 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | A | 131242-WST02-DR-IP-1030 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | A | 131242-WST02-DR-IP-1031 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | A | 131242-WST02-DR-IP-1032 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | A | 131242-WST02-DR-IP-1033 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | A | 131242-WST02-DR-IP-1034 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | A | 131242-WST02-DR-IP-1035 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | A | 131242-WST02-DR-IP-1036 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | A | 131242-WST02-DR-IP-1037 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | A | 131242-WST02-DR-IP-1038 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | A | 131242-WST02-DR-IP-1039 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | A | 131242-WST02-DR-IP-1040 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | A | 131242-WST02-DR-IP-1041 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | A | 131242-WST02-DR-IP-1042 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | A | 131242-WST02-DR-IP-1043 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | A | 131242-WST02-DR-IP-1044 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | A | 131242-WST02-DR-IP-1045 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | A | 131242-WST02-DR-IP-1046 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | A | 131242-WST02-DR-IP-1901 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | A | 131242-WST02-DR-IP-1902 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | A | 131242-WST02-DR-IP-1903 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | A | 131242-WST02-DR-IP-1904 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | A | 131242-WST02-DR-IP-1905 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | A | 131242-WST02-DR-IP-1906 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | A | 131242-WST02-DR-IP-1907 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | A | 131242-WST02-DR-IP-1908 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | A | 131242-WST02-DR-IP-1909 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | A | 131242-WST02-DR-IP-1910 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | A | 131242-WST02-DR-IP-1911 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | A | 131242-WST02-DR-IP-1912 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | A | 131242-WST02-DR-IP-1913 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | A | 131242-WST02-DR-IP-1914 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | A | 131242-WST02-DR-IP-1915 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | A | 131242-WST02-DR-IP-1916 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | A | 131242-WST02-DR-IP-1917 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | A | 131242-WST02-DR-IP-1918 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | A | 131242-WST02-DR-IP-1919 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | A | 131242-WST02-DR-IP-1920 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | A | 131242-WST02-DR-IP-1921 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | A | 131242-WST02-DR-IP-1922 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | A | 131242-WST02-DR-IP-1923 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | A | 131242-WST02-DR-IP-1924 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | A | 131242-WST02-DR-IP-1925 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | A | 131242-WST02-DR-IP-1926 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | A | 131242-WST02-DR-IP-1927 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | A | 131242-WST02-DR-IP-1928 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | A | 131242-WST02-DR-IP-1929 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | A | 131242-WST02-DR-IP-1930 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | A | 131242-WST02-DR-IP-1931 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | A | 131242-WST02-DR-IP-1932 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | A | 131242-WST02-DR-IP-1933 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | A | 131242-WST02-DR-IP-1934 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | A | 131242-WST02-DR-IP-1935 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | A | 131242-WST02-DR-IP-1936 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | A | 131242-WST02-DR-IP-1937 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | A | 131242-WST02-DR-IP-1938 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | A | 131242-WST02-DR-IP-1939 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | A | 131242-WST02-DR-IP-1940 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | AWC
001178 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0061 | 0 | 131242-WSD11-QA-M-0061 | 2025-03-28 | Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI) | NA | 2025-04-25 | 2025-09-08 | 116 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001178 | 2025-03-28 | 2025-03-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI)" | AWC
001179 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 0 | 131242-WSD11-DS-I-0008 | 2025-04-01 | Datasheet for Pressure Transmitter | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001179 | 2025-04-01 | 2025-10-16 | 1 | NAP | Not Approved | 2 | "Datasheet for Pressure Transmitter" | NAP
001179 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 1 | 131242-WSD11-DS-I-0008 | 2025-10-16 | Datasheet for Pressure Transmitter | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-12-02 | 33 | Not Approved | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001179 | 2025-04-01 | 2025-10-16 | 1 | NAP | Not Approved | 2 | "Datasheet for Pressure Transmitter" | NAP
001180 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 0 | 131242-WSD11-DS-I-0009 | 2025-04-01 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001180 | 2025-04-01 | 2025-09-10 | 1 | NAP | Not Approved | 2 | "Datasheet for Tuning Fork Level Switch " | NAP
001180 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 1 | 131242-WSD11-DS-I-0009 | 2025-09-10 | Datasheet for Tuning Fork Level Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-09-30 | 2025-12-02 | 59 | Not Approved | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001180 | 2025-04-01 | 2025-09-10 | 1 | NAP | Not Approved | 2 | "Datasheet for Tuning Fork Level Switch " | NAP
001181 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 0 | 131242-WSD11-DS-I-0010 | 2025-04-01 | Datasheet for Pressure Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | NAP | Not Approved | 3 | "Datasheet for Pressure Switch" | NAP
001181 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 1 | 131242-WSD11-DS-I-0010 | 2025-09-10 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-30 | 2025-12-02 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | NAP | Not Approved | 3 | "Datasheet for Pressure Switch" | NAP
001181 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 2 | 131242-WSD11-DS-I-0010 | 2026-01-30 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-19 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | PEN | Not Approved | 3 | "Datasheet for Pressure Switch" | NAP
001182 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1017 | 0 | 131242-WSW41-VI-M-1017 | 2025-04-01 | Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-29 | 2025-06-23 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001182 | 2025-04-01 | 2025-04-01 | 0 | AWC | Approved with Comments | 1 | "Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe)" | AWC
001183 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 0 | 131242-WSW41-SH-M-1007 | 2025-04-01 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Rev 0: Not approved - Revise and Resubmit | 2025-04-29 | 2025-06-23 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001183 | 2025-04-01 | 2025-07-22 | 1 | NAP | Approved | 2 | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | APP
001183 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 1 | 131242-WSW41-SH-M-1007 | 2025-07-22 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Approved | 2025-08-11 | 2025-08-01 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001183 | 2025-04-01 | 2025-07-22 | 1 | APP | Approved | 2 | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | APP
001184 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0061 | 0 | 131242-WSW41-QA-M-0061 | 2025-04-02 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch) | Approved | 2025-04-30 | 2025-05-21 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001184 | 2025-04-02 | 2025-04-02 | 0 | APP | Approved | 1 | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch)" | APP
001185 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0062 | 0 | 131242-WSW41-QA-M-0062 | 2025-04-02 | FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch) | NA | 2025-04-30 | 2025-09-02 | 109 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001185 | 2025-04-02 | 2025-04-02 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch)" | AWC
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A1 | 131242-WST02-DR-A-1000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A1 | 131242-WST02-DR-A-1001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A1 | 131242-WST02-DR-A-1002_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A1 | 131242-WST02-DR-A-1003_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A1 | 131242-WST02-DR-A-1004_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A1 | 131242-WST02-DR-A-1006_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A1 | 131242-WST02-DR-A-1009_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A1 | 131242-WST02-DR-A-2000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A1 | 131242-WST02-DR-A-2001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A1 | 131242-WST02-DR-A-2002_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A1 | 131242-WST02-DR-A-2003_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A | 131242-WST02-DR-A-2007_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A | 131242-WST02-DR-A-3000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_BCA_BP | A1 | 131242-WST02-DR-A-9000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2025-04-02 | A1 | NAP | Not Approved | 1 | "SSN BCA BP Submission" | NAP
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_BCA_BP | A1 | 131242-WST02-DR-A-9001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2025-04-02 | A1 | NAP | Not Approved | 1 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | NAP | Not Approved | 3 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | NAP | Not Approved | 3 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | PEN | Not Approved | 3 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" | NAP
001187 | 00 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 0 | 131242-WSD11-VI-S-0001 | 2025-04-03 | Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001187 | 2025-04-03 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" | AWC
001187 | 01 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 1 | 131242-WSD11-VI-S-0001 | 2025-04-18 | Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Approved with Comments | 2025-05-08 | 2025-05-16 | 20 | Approved with Comments | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001187 | 2025-04-03 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" | AWC
001188 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 0 | 131242-WST02-MM-E-0001 | 2025-04-03 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 0: Rejected. To revise and resubmit. | 2025-05-01 | 2025-05-30 | 41 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001188 | 2025-04-03 | 2025-07-22 | 1 | REJ | Not Approved | 2 | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " | NAP
001188 | 01 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 1 | 131242-WST02-MM-E-0001 | 2025-07-22 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 1: Not Approved. To revise and resubmit. Refer to the comment sheet, after incorporating comments, please submit hardcopy to S.O. prior to resubmission. | 2025-08-11 | 2025-10-01 | 51 | Not Approved | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001188 | 2025-04-03 | 2025-07-22 | 1 | NAP | Not Approved | 2 | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " | NAP
001189 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0002 | 0 | 131242-WST02-MM-E-0002 | 2025-04-03 | Memo-Installation Letter of TMS for Sivacon S8 | Rev 0: Accepted for Information | 2025-05-01 | 2025-05-05 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001189 | 2025-04-03 | 2025-04-03 | 0 | INF | For Information | 1 | "Memo-Installation Letter of TMS for Sivacon S8" | INF
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7201 | A | 131242-WST02-DR-I-7201 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | AWC | Approved with Comments | 1 | "SSN UPSDB SLD " | AWC
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7202 | A | 131242-WST02-DR-I-7202 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7203 | A | 131242-WST02-DR-I-7203 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7204 | A | 131242-WST02-DR-I-7204 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7205 | A | 131242-WST02-DR-I-7205 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7206 | A | 131242-WST02-DR-I-7206 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7207 | A | 131242-WST02-DR-I-7207 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7208 | A | 131242-WST02-DR-I-7208 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " | PEN
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | A | 131242-WST02-DR-IP-1941 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | A | 131242-WST02-DR-IP-1942 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | A | 131242-WST02-DR-IP-1943 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | A | 131242-WST02-DR-IP-1944 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | A | 131242-WST02-DR-IP-1945 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | A | 131242-WST02-DR-IP-1946 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | A | 131242-WST02-DR-IP-1947 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | A | 131242-WST02-DR-IP-1948 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | A | 131242-WST02-DR-IP-1949 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | A | 131242-WST02-DR-IP-1950 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | A | 131242-WST02-DR-IP-1951 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | A | 131242-WST02-DR-IP-1952 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | A | 131242-WST02-DR-IP-1953 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | A | 131242-WST02-DR-IP-1954 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | A | 131242-WST02-DR-IP-1955 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | A | 131242-WST02-DR-IP-1956 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | A | 131242-WST02-DR-IP-1957 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | A | 131242-WST02-DR-IP-1958 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | A | 131242-WST02-DR-IP-1959 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | A | 131242-WST02-DR-IP-1960 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | A | 131242-WST02-DR-IP-1961 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | A | 131242-WST02-DR-IP-1962 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | A | 131242-WST02-DR-IP-1963 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | A | 131242-WST02-DR-IP-1964 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | A | 131242-WST02-DR-IP-1965 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | A | 131242-WST02-DR-IP-1966 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | A | 131242-WST02-DR-IP-1967 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | A | 131242-WST02-DR-IP-1968 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | A | 131242-WST02-DR-IP-1969 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | A | 131242-WST02-DR-IP-1970 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | A | 131242-WST02-DR-IP-1971 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | A | 131242-WST02-DR-IP-1972 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | A | 131242-WST02-DR-IP-1973 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | A | 131242-WST02-DR-IP-1974 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | A | 131242-WST02-DR-IP-1975 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | A | 131242-WST02-DR-IP-2021 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | A | 131242-WST02-DR-IP-2022 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | A | 131242-WST02-DR-IP-2023 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | A | 131242-WST02-DR-IP-2024 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | A | 131242-WST02-DR-IP-2025 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | A | 131242-WST02-DR-IP-2026 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | A | 131242-WST02-DR-IP-2027 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | A | 131242-WST02-DR-IP-2028 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | A | 131242-WST02-DR-IP-2029 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | A | 131242-WST02-DR-IP-2030 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | A | 131242-WST02-DR-IP-2031 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | A | 131242-WST02-DR-IP-2032 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | A | 131242-WST02-DR-IP-2033 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | A | 131242-WST02-DR-IP-2034 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | A | 131242-WST02-DR-IP-2035 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | A | 131242-WST02-DR-IP-2036 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | A | 131242-WST02-DR-IP-2037 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | A | 131242-WST02-DR-IP-2038 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | A | 131242-WST02-DR-IP-2039 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | A | 131242-WST02-DR-IP-2040 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | A | 131242-WST02-DR-IP-2041 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | A | 131242-WST02-DR-IP-2042 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | A | 131242-WST02-DR-IP-2043 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | A | 131242-WST02-DR-IP-2044 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | A | 131242-WST02-DR-IP-2045 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | A | 131242-WST02-DR-IP-2046 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | A | 131242-WST02-DR-IP-2047 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | A | 131242-WST02-DR-IP-2048 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | A | 131242-WST02-DR-IP-2049 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | A | 131242-WST02-DR-IP-2050 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | A | 131242-WST02-DR-IP-2051 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | A | 131242-WST02-DR-IP-2052 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | A | 131242-WST02-DR-IP-2053 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | A | 131242-WST02-DR-IP-2054 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | A | 131242-WST02-DR-IP-2055 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | A | 131242-WST02-DR-IP-2056 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | A | 131242-WST02-DR-IP-2061 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | A | 131242-WST02-DR-IP-2062 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | A | 131242-WST02-DR-IP-2063 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | A | 131242-WST02-DR-IP-2064 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | A | 131242-WST02-DR-IP-2065 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | A | 131242-WST02-DR-IP-2066 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | A | 131242-WST02-DR-IP-2067 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | A | 131242-WST02-DR-IP-2068 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | A | 131242-WST02-DR-IP-2069 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | A | 131242-WST02-DR-IP-2070 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | A | 131242-WST02-DR-IP-2071 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | A | 131242-WST02-DR-IP-2072 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | A | 131242-WST02-DR-IP-2073 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | A | 131242-WST02-DR-IP-2074 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | A | 131242-WST02-DR-IP-2075 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | A | 131242-WST02-DR-IP-2076 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | A | 131242-WST02-DR-IP-2077 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | A | 131242-WST02-DR-IP-2078 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | A | 131242-WST02-DR-IP-2079 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | A | 131242-WST02-DR-IP-2080 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | A | 131242-WST02-DR-IP-2081 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | A | 131242-WST02-DR-IP-2082 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | A | 131242-WST02-DR-IP-2083 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-28 | 2025-09-23 | 55 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | A | 131242-WST02-DR-IP-1981 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | A | 131242-WST02-DR-IP-1982 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | A | 131242-WST02-DR-IP-1983 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | A | 131242-WST02-DR-IP-1984 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | A | 131242-WST02-DR-IP-1985 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | A | 131242-WST02-DR-IP-1986 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | A | 131242-WST02-DR-IP-1987 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | A | 131242-WST02-DR-IP-1988 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | A | 131242-WST02-DR-IP-1989 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | A | 131242-WST02-DR-IP-1990 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | A | 131242-WST02-DR-IP-1991 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | A | 131242-WST02-DR-IP-1992 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | A | 131242-WST02-DR-IP-1993 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | A | 131242-WST02-DR-IP-1994 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | A | 131242-WST02-DR-IP-1995 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | A | 131242-WST02-DR-IP-1996 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | A | 131242-WST02-DR-IP-1997 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | A | 131242-WST02-DR-IP-1998 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | A | 131242-WST02-DR-IP-1999 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | A | 131242-WST02-DR-IP-2000 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | A | 131242-WST02-DR-IP-2001 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | A | 131242-WST02-DR-IP-2002 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | A | 131242-WST02-DR-IP-2003 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | A | 131242-WST02-DR-IP-2004 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | A | 131242-WST02-DR-IP-2005 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | A | 131242-WST02-DR-IP-2006 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | A | 131242-WST02-DR-IP-2007 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | A | 131242-WST02-DR-IP-2008 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | A | 131242-WST02-DR-IP-2009 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | A | 131242-WST02-DR-IP-2010 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | A | 131242-WST02-DR-IP-2011 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | A | 131242-WST02-DR-IP-2012 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | A | 131242-WST02-DR-IP-2013 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | A | 131242-WST02-DR-IP-2014 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | A | 131242-WST02-DR-IP-2015 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | A | 131242-WST02-DR-IP-2016 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | AWC
001195 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 0 | 131242-WSW41-SH-M-1006 | 2025-04-03 | Manual Butterfly Valve | Rev 0: Not approved - Revise and Resubmit | 2025-05-01 | 2025-06-23 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | NAP | Approved with Comments | 3 | "Manual Butterfly Valve " | AWC
001195 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 1 | 131242-WSW41-SH-M-1006 | 2025-08-06 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-08-26 | 2025-09-04 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | AWC | Approved with Comments | 3 | "Manual Butterfly Valve " | AWC
001195 | 02 | Joo Kwan | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 2 | 131242-WSW41-SH-M-1006 | 2025-11-26 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | PEN | Approved with Comments | 3 | "Manual Butterfly Valve " | AWC
001196 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0021 | 0 | 131242-WSW41-QA-A-0021 | 2025-04-03 | Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | 8 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001196 | 2025-04-03 | 2025-04-03 | 0 | NAP | Not Approved | 1 | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" | NAP
001197 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0003 | 0 | 131242-WSW41-MS-A-0003 | 2025-04-03 | MSRA and SWP for Plastering and Skim Coat | Rev.0: Approved with comments. No resubmission is required. | 2025-05-01 | 2025-05-12 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001197 | 2025-04-03 | 2025-04-03 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Plastering and Skim Coat " | AWC
001198 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0004 | 0 | 131242-WSW41-MS-A-0004 | 2025-04-03 | MSRA and SWP for Floor Screeding and Tiles Laying | Rev.0: Approved with comments. | 2025-05-01 | 2025-05-12 | 27 | Approved with Comments | YES | 2025-05-30 | NO | Resubmitted | 0 |  |  | 001198 | 2025-04-03 | 2025-04-03 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Floor Screeding and Tiles Laying " | AWC
001199 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0068 | 0 | 131242-WST02-QA-M-0068 | 2025-04-03 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) | NA | 2025-05-01 | 2025-09-08 | 112 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001199 | 2025-04-03 | 2025-04-03 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) " | APP
001200 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 0 | 131242-WSW41-VI-M-0028 | 2025-04-03 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Approved with Comments | 2025-05-01 | 2025-05-21 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001200 | 2025-04-03 | 2025-07-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | AWC
001200 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 1 | 131242-WSW41-VI-M-0028 | 2025-07-02 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-22 | 2026-01-07 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001200 | 2025-04-03 | 2025-07-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | AWC
001201 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1015 | 0 | 131242-WSW41-VI-M-1015 | 2025-04-04 | Preliminary design and Vendor Approval – Strainer (Bliss) | Rev 0: Not approved - Revise and Resubmit | 2025-05-02 | 2025-06-23 | 56 | Not Approved | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001201 | 2025-04-04 | 2025-04-04 | 0 | NAP | Not Approved | 1 | "Preliminary design and Vendor Approval – Strainer (Bliss)" | NAP
001202 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0059 | 0 | 131242-WSW41-LT-PM-0059 | 2025-04-04 | Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors | Rev (0): Received for information. Please refer to S.O. correspondence no. 399 dated 10 Sep 2025. | 2025-05-02 | 2025-09-23 | 122 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001202 | 2025-04-04 | 2025-04-04 | 0 | INF | For Information | 1 | "Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors" | INF
001203 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0007 | 0 | 131242-WSW41-MS-A-0007 | 2025-04-07 | MSRA, SWP for Door Installation | Approved | 2025-05-05 | 2025-04-15 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001203 | 2025-04-07 | 2025-04-07 | 0 | APP | Approved | 1 | "MSRA, SWP for Door Installation" | APP
001204 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0021 | 0 | 131242-WSW41-PC-W-0021 | 2025-04-07 | Payment Claim No.21 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-05-05 | 2025-04-27 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001204 | 2025-04-07 | 2025-04-07 | 0 | INF | For Information | 1 | "Payment Claim No.21" | INF
001205 | 00 | N. Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0024 | 0 | 131242-WSW41-QA-C-0024 | 2025-04-07 | Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) | Approved with Comments | 2025-05-05 | 2025-06-04 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001205 | 2025-04-07 | 2025-04-07 | 0 | AWC | Approved with Comments | 1 | "Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) " | AWC
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7000 | A | 131242-WSW41-DR-EI-7000 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7001 | A | 131242-WSW41-DR-EI-7001 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7002 | A | 131242-WSW41-DR-EI-7002 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3000 | A | 131242-WSW41-DR-EP-3000 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3001 | A | 131242-WSW41-DR-EP-3001 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3002 | A | 131242-WSW41-DR-EP-3002 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3003 | A | 131242-WSW41-DR-EP-3003 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3004 | A | 131242-WSW41-DR-EP-3004 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3005 | A | 131242-WSW41-DR-EP-3005 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" | REJ
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | B | 131242-WSD11-DR-EI-7400 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | B | 131242-WSD11-DR-EI-7401 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | B | 131242-WSD11-DR-EI-7402 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | B | 131242-WSD11-DR-EP-3180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | B | 131242-WSD11-DR-EP-3181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | B | 131242-WSD11-DR-EP-3182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | B | 131242-WSD11-DR-EP-3183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | B | 131242-WSD11-DR-EP-3184 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | B | 131242-WSD11-DR-EP-3185 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | B | 131242-WSD11-DR-EP-3186 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | B | 131242-WSD11-DR-EP-3187 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | B | 131242-WSD11-DR-EP-3188 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | B | 131242-WSD11-DR-EP-7180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | B | 131242-WSD11-DR-EP-7181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | B | 131242-WSD11-DR-EP-7182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | B | 131242-WSD11-DR-EP-7183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | B | 131242-WST02-DR-EI-7400 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | B | 131242-WST02-DR-EI-7401 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | B | 131242-WST02-DR-EI-7402 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | B | 131242-WST02-DR-EP-3180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | B | 131242-WST02-DR-EP-3181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | B | 131242-WST02-DR-EP-3182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | B | 131242-WST02-DR-EP-3183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | B | 131242-WST02-DR-EP-3184 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | B | 131242-WST02-DR-EP-3185 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | B | 131242-WST02-DR-EP-3186 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | B | 131242-WST02-DR-EP-3187 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | B | 131242-WST02-DR-EP-3188 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | B | 131242-WST02-DR-EP-7180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | B | 131242-WST02-DR-EP-7181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | B | 131242-WST02-DR-EP-7182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | B | 131242-WST02-DR-EP-7183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | C | 131242-WSD11-DR-EI-7400 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | C | 131242-WSD11-DR-EI-7401 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | C | 131242-WSD11-DR-EI-7402 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | C | 131242-WSD11-DR-EP-3180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | C | 131242-WSD11-DR-EP-3181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | C | 131242-WSD11-DR-EP-3182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | C | 131242-WSD11-DR-EP-3183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | C | 131242-WSD11-DR-EP-3184 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | C | 131242-WSD11-DR-EP-3185 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | C | 131242-WSD11-DR-EP-3186 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | C | 131242-WSD11-DR-EP-3187 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | C | 131242-WSD11-DR-EP-3188 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | C | 131242-WSD11-DR-EP-7180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | C | 131242-WSD11-DR-EP-7181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | C | 131242-WSD11-DR-EP-7182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | C | 131242-WSD11-DR-EP-7183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | C | 131242-WST02-DR-EI-7400 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | C | 131242-WST02-DR-EI-7401 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | C | 131242-WST02-DR-EI-7402 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | C | 131242-WST02-DR-EP-3180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | C | 131242-WST02-DR-EP-3181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | C | 131242-WST02-DR-EP-3182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | C | 131242-WST02-DR-EP-3183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | C | 131242-WST02-DR-EP-3184 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | C | 131242-WST02-DR-EP-3185 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | C | 131242-WST02-DR-EP-3186 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | C | 131242-WST02-DR-EP-3187 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | C | 131242-WST02-DR-EP-3188 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | C | 131242-WST02-DR-EP-7180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | C | 131242-WST02-DR-EP-7181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | C | 131242-WST02-DR-EP-7182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | C | 131242-WST02-DR-EP-7183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" | AWC
001207 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 0 | 131242-WSW41-MS-C-0028 | 2025-04-07 | MSRA SWP for Concrete Coring | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-05 | 2025-05-12 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001207 | 2025-04-07 | 2025-05-18 | 1 | NAP | Approved with Comments | 2 | "MSRA SWP for Concrete Coring " | AWC
001207 | 01 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 1 | 131242-WSW41-MS-C-0028 | 2025-05-18 | MSRA SWP for Concrete Coring | Rev.1: Approved with Comments: Please refer to comment sheet for resubmission. | 2025-06-05 | 2025-06-13 | 19 | Approved with Comments | YES | 2025-07-03 | NO | Resubmitted | 0 |  |  | 001207 | 2025-04-07 | 2025-05-18 | 1 | AWC | Approved with Comments | 2 | "MSRA SWP for Concrete Coring " | AWC
001208 | 00 | Aaron | CSA | NA | 131242 | WSW41 | SD | S | - | 0 | 131242-WSW41-SD-S-- | 2025-04-08 | Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614) | R0: For Information. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-06-30 | 59 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001208 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | "Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614)" | INF
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1101 | A | 131242-WST02-SD-S-1101 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1102 | A | 131242-WST02-SD-S-1102 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2100 | A | 131242-WST02-SD-S-2100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2103 | A | 131242-WST02-SD-S-2103 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3100 | A | 131242-WST02-SD-S-3100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5100 | A | 131242-WST02-SD-S-5100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | NAP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5101 | A | 131242-WST02-SD-S-5101 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | NAP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5105 | A | 131242-WST02-SD-S-5105 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8004 | A | 131242-WST02-SD-S-8004 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" | NAP
001210 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0054 | 0 | 131242-WSW41-CD-IM-0054 | 2025-04-08 | Submission of BIM Coordination VCM Model (Mar 2025) | For Information. Score= 71/100 | 2025-05-06 | 2025-04-27 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001210 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | " Submission of BIM Coordination VCM Model (Mar 2025) " | INF
001211 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0015 | 0 | 131242-WSW41-PO-M-0015 | 2025-04-08 | Unpriced LOA for MEICA installer (Cyclect Engineering) | Rev 0: For Information | 2025-05-06 | 2025-10-06 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001211 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | "Unpriced LOA for MEICA installer (Cyclect Engineering)" | INF
001212 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0023 | 0 | 131242-WSW41-RT-PM-0023 | 2025-04-09 | C4B Monthly Progress Report Number No.23 (03 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-05-07 | 2025-04-27 | 13 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001212 | 2025-04-09 | 2025-04-09 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.23 (03 25) " | AWC
001213 | 00 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 0 | 131242-WSD11-CD-I-0005 | 2025-04-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 | 2025-04-27 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001213&&001440 | 2025-04-09 | 2025-07-07 | 0 | NAP | Approved with Comments | 3 | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | AWC
001213 | 01 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 1 | 131242-WSD11-CD-I-0005 | 2025-05-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 1: Approved with comments. To revise and resubmit. | 2025-05-29 | 2025-06-17 | 27 | Approved with Comments | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 001213&&001440 | 2025-04-09 | 2025-07-07 | 0 | AWC | Approved with Comments | 3 | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | AWC
001214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0016 | 0 | 131242-WSW41-PO-M-0016 | 2025-04-09 | Unpriced LOA for Fire Protection System | Rev 0: For Information | 2025-05-07 | 2025-10-06 | 128 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001214 | 2025-04-09 | 2025-04-09 | 0 | INF | For Information | 1 | "Unpriced LOA for Fire Protection System" | INF
001215 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0063 | 0 | 131242-WSD11-QA-M-0063 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3 | Approved | 2025-05-07 | 2025-05-21 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001215 | 2025-04-09 | 2025-04-09 | 0 | APP | Approved | 1 | "Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3" | APP
001216 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0067 | 0 | 131242-WSD11-QA-M-0067 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 | Rev 0: Approved | 2025-05-07 | 2025-10-06 | 128 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001216 | 2025-04-09 | 2025-04-09 | 0 | APP | Approved | 1 | "Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 " | APP
001217 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0029 | 0 | 131242-WSW41-QA-EI-0029 | 2025-04-10 | FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch | Approved | 2025-05-08 | 2025-05-12 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001217 | 2025-04-10 | 2025-04-10 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" | APP
001218 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 1008 | 0 | 131242-WSW41-SH-M-1008 | 2025-04-10 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 0: Not approved - Revise and Resubmit | 2025-05-08 | 2025-06-23 | 52 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001218 | 2025-04-10 | 2025-04-10 | 0 | NAP | Not Approved | 1 | "ON OFF Butterfly Valve Data sheet (OVS)" | NAP
001218 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | SH | M | 1008 | 1 | 131242-WST02-SH-M-1008 | 2025-07-11 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-31 | 2025-09-04 | 39 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001218 | 2025-07-11 | 2025-07-11 | 1 | AWC | Approved with Comments | 1 | "ON OFF Butterfly Valve Data sheet (OVS)" | AWC
001219 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 0 | 131242-WST02-QA-BS-0001 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-05-08 | 2025-05-25 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | NAP
001219 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 1 | 131242-WST02-QA-BS-0001 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-07-22 | 2025-08-06 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | NAP
001219 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 2 | 131242-WST02-QA-BS-0001 | 2025-08-19 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-08-28 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | NAP
001219 | 03 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 3 | 131242-WST02-QA-BS-0001 | 2025-10-07 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-27 | 2025-12-05 | 43 | Not Approved | YES | 2025-12-25 | NO | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | NAP
001220 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0065 | 0 | 131242-WSW41-QA-M-0065 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve | Approved | 2025-05-08 | 2025-05-21 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001220 | 2025-04-10 | 2025-04-10 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve" | APP
001221 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0025 | 0 | 131242-WSW41-QA-C-0025 | 2025-04-11 | Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces | Approved with Comments | 2025-05-09 | 2025-05-09 | 20 | Approved with Comments | YES | 2025-05-29 | NO | Resubmitted | 0 |  |  | 001221 | 2025-04-11 | 2025-04-11 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" | AWC
001222 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0021 | 0 | 131242-WSW41-PS-HS-0021 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Dec 2024 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001222 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Dec 2024" | INF
001223 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0022 | 0 | 131242-WSW41-PS-HS-0022 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Jan 2025 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001223 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jan 2025" | INF
001224 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0023 | 0 | 131242-WSW41-PS-HS-0023 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Feb 2025 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001224 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Feb 2025" | INF
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0042 | 0 | 131242-WSW41-MI-C-0042 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | INF
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0043 | 0 | 131242-WSW41-MI-C-0043 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | INF
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0044 | 0 | 131242-WSW41-MI-C-0044 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | INF
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0045 | 0 | 131242-WSW41-MI-C-0045 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | INF
001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5200 | A | 131242-WSW41-DR-S-5200 | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001226&&001586 | 2025-04-14 | 2025-08-13 | E | NAP | Not Approved | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "SWPR _Platform A and B- Cat ladders" | NAP
001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | A | 131242-WSW41-DR-S-1210 | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001226 | 2025-04-14 | 2025-09-15 | B | NAP | Rejected | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | REJ
001226 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | B | 131242-WSD11-DR-S-5200 | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | REJ | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | APP
001226 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | B | 131242-WSW41-DR-S-1210 | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001226 | 2025-04-14 | 2025-09-15 | B | REJ | Rejected | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | REJ
001227 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 0 | 131242-WSW41-MS-EI-0011 | 2025-04-14 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-12 | 2025-05-30 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001227 | 2025-04-14 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" | AWC
001227 | 01 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 1 | 131242-WSW41-MS-EI-0011 | 2025-12-08 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2026-02-20 | 54 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001227 | 2025-04-14 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" | AWC
001228 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 0 | 131242-WSW41-SP-C-0029 | 2025-04-16 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-14 | 2025-05-07 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001228 | 2025-04-16 | 2025-06-27 | 1 | AWC | Approved | 2 | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | APP
001228 | 01 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 1 | 131242-WSW41-SP-C-0029 | 2025-06-27 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R1: Approved | 2025-07-17 | 2025-07-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001228 | 2025-04-16 | 2025-06-27 | 1 | APP | Approved | 2 | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | APP
001229 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 0 | 131242-WST02-DS-I-0006 | 2025-04-16 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001229 | 2025-04-16 | 2025-12-08 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Tuning Fork Level Switch " | AWC
001229 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 1 | 131242-WST02-DS-I-0006 | 2025-12-08 | Datasheet for Tuning Fork Level Switch | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-26 | 2026-02-09 | 45 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001229 | 2025-04-16 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Tuning Fork Level Switch " | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | B | 131242-WSD11-DR-IP-3001 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | B | 131242-WSD11-DR-IP-3002 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | B | 131242-WSD11-DR-IP-3003 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | B | 131242-WSD11-DR-IP-3004 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | B | 131242-WSD11-DR-IP-3005 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | B | 131242-WSD11-DR-IP-3006 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | B | 131242-WSD11-DR-IP-3007 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | B | 131242-WSD11-DR-IP-3008 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | B | 131242-WSD11-DR-IP-3009 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | B | 131242-WSD11-DR-IP-3010 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | B | 131242-WSD11-DR-IP-3011 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | B | 131242-WSD11-DR-IP-3012 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | B | 131242-WSD11-DR-IP-3013 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | B | 131242-WSD11-DR-IP-3014 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | B | 131242-WSD11-DR-IP-3015 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | B | 131242-WSD11-DR-IP-3016 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | B | 131242-WSD11-DR-IP-3017 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | B | 131242-WSD11-DR-IP-3018 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | B | 131242-WSD11-DR-IP-3019 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | B | 131242-WSD11-DR-IP-3020 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | B | 131242-WSD11-DR-IP-3021 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | B | 131242-WSD11-DR-IP-3022 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | B | 131242-WSD11-DR-IP-3023 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | B | 131242-WSD11-DR-IP-3024 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | B | 131242-WSD11-DR-IP-3025 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3026 | B | 131242-WSD11-DR-IP-3026 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3027 | B | 131242-WSD11-DR-IP-3027 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3028 | B | 131242-WSD11-DR-IP-3028 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" | AWC
001231 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 0 | 131242-WST02-DS-I-0007 | 2025-04-16 | Datasheet for Radar Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-05-14 | 2025-06-30 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001231 | 2025-04-16 | 2025-07-22 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Radar Level Transmitter " | AWC
001231 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 1 | 131242-WST02-DS-I-0007 | 2025-07-22 | Datasheet for Radar Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-08-06 | 11 | Approved with Comments | YES | 2025-08-26 | NO | Resubmitted | 0 |  |  | 001231 | 2025-04-16 | 2025-07-22 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Radar Level Transmitter " | AWC
001232 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0070 | 0 | 131242-WSD11-QA-M-0070 | 2025-04-17 | MSRA & SWP for NDT Activities | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-05-15 | 2025-10-06 | 122 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001232 | 2025-04-17 | 2025-04-17 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP for NDT Activities " | AWC
001233 | 00 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 0 | 131242-WST02-BQ-I-0005 | 2025-04-17 | SSN ICA Cable List | Not Approved - Revise and resubmit | 2025-05-15 | 2025-06-11 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001233 | 2025-04-17 | 2025-10-28 | 1 | NAP | Not Approved | 2 | "SSN ICA Cable List " | NAP
001233 | 01 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 1 | 131242-WST02-BQ-I-0005 | 2025-10-28 | SSN ICA Cable List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2026-01-26 | 64 | Not Approved | YES | 2026-02-13 | NO | Resubmitted | 0 |  |  | 001233 | 2025-04-17 | 2025-10-28 | 1 | NAP | Not Approved | 2 | "SSN ICA Cable List " | NAP
001234 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 0 | 131242-WST02-DS-BS-0003 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 0: Not approved - Revise and Resubmit | 2025-05-15 | 2025-05-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | NAP | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | AWC
001234 | 01 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 1 | 131242-WST02-DS-BS-0003 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 1: Not approved - Revise and Resubmit | 2025-05-07 | 2025-05-25 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | NAP | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | AWC
001234 | 02 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 2 | 131242-WST02-DS-BS-0003 | 2025-06-06 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-26 | 2025-07-04 | 20 | Approved with Comments | YES | 2025-07-24 | NO | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | AWC | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | AWC
001235 | 00 | Balaji | EICA | NA | 131242 | WSW41 | DR | IP | 1001 | A | 131242-WSW41-DR-IP-1001 | 2025-04-18 | Panel Base Frame Drawing | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-05-16 | 2025-06-11 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001235 | 2025-04-18 | 2025-04-18 | A | INF | For Information | 1 | "Panel Base Frame Drawing" | INF
001236 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | DS | C | 0001 | 0 | 131242-WST02-DS-C-0001 | 2025-04-18 | Epoxy Coating System | Approved | 2025-05-16 | 2025-06-04 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001236 | 2025-04-18 | 2025-04-18 | 0 | APP | Approved | 1 | "Epoxy Coating System" | APP
001237 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0030 | 0 | 131242-WSW41-QA-C-0030 | 2025-04-21 | Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps) | For Information | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001237 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | INF
001238 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0029 | 0 | 131242-WSW41-QA-C-0029 | 2025-04-21 | Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing | For Information | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001238 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" | INF
001239 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0028 | 0 | 131242-WSW41-QA-C-0028 | 2025-04-21 | Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports) | For information | 2025-05-19 | 2025-06-04 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001239 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | INF
001240 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0027 | 0 | 131242-WSW41-QA-C-0027 | 2025-04-21 | Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps) | For Information | 2025-05-19 | 2025-05-30 | 29 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001240 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" | INF
001241 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0026 | 0 | 131242-WSW41-QA-C-0026 | 2025-04-21 | Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024 | For information | 2025-05-19 | 2025-05-16 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001241 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | INF
001242 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0021 | 0 | 131242-WSW41-PS-PM-0021 | 2025-04-21 | Monthly Progress Presentation No. 21 (0225) | For information and record. | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001242 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 21 (0225)" | INF
001243 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0021 | 0 | 131242-WSW41-MI-PM-0021 | 2025-04-21 | Monthly Progress Meeting Minutes 0021_20250226 | For information and record. | 2025-05-19 | 2025-05-07 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001243 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0021_20250226" | INF
001244 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0022 | 0 | 131242-WSW41-PS-PM-0022 | 2025-04-21 | Monthly Progress Presentation No. 22 (0325) | For information and record. | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001244 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 22 (0325)" | INF
001245 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0022 | 0 | 131242-WSW41-MI-PM-0022 | 2025-04-21 | Monthly Progress Meeting Minutes 0022_20250324 | For information and record | 2025-05-19 | 2025-05-07 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001245 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0022_20250324" | INF
001246 | 00 | Danapal | QAQC | NA | 131242 | WSD11 | QA | I | 0009 | 0 | 131242-WSD11-QA-I-0009 | 2025-04-22 | FAT report for MCP panel WSD11-006-MCP-1000 | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-11 | 36 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001246 | 2025-04-22 | 2025-04-22 | 0 | AWC | Approved with Comments | 1 | "FAT report for MCP panel WSD11-006-MCP-1000 " | AWC
001247 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0005 | 0 | 131242-WSD11-VI-I-0005 | 2025-04-22 | Vendor Approval for THP Electromagnetic Flowmeters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-30 | 49 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001247 | 2025-04-22 | 2025-04-22 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval for THP Electromagnetic Flowmeters" | AWC
001248 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0046 | 0 | 131242-WSW41-MI-C-0046 | 2025-04-22 | CSA Meeting Minutes 0046_17042025 | For information. | 2025-05-20 | 2025-05-30 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001248 | 2025-04-22 | 2025-04-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0046_17042025" | INF
001249 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0060 | 0 | 131242-WSW41-LT-PM-0060 | 2025-04-23 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building | Rev (0): Rejected. Please refer to S.O. correspondence no. 355 dated 3 June 2025. | 2025-05-21 | 2025-08-22 | 87 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001249 | 2025-04-23 | 2025-04-23 | 0 | REJ | Rejected | 1 | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building " | REJ
001250 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 0 | 131242-WSD11-QA-M-0066 | 2025-04-24 | FAT report for THP Sludge cooler B Stage 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-07-02 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001250 | 2025-04-24 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler B Stage 1" | APP
001250 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 1 | 131242-WSD11-QA-M-0066 | 2025-12-02 | FAT report for THP Sludge cooler B Stage 1 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001250 | 2025-04-24 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler B Stage 1" | APP
001251 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | C | 0031 | 0 | 131242-WST02-MS-C-0031 | 2025-04-24 | MSRA, SWP for Water Testing of Liquid Retaining Structure | Approved with Comments | 2025-05-22 | 2025-06-02 | 27 | Approved with Comments | YES | 2025-06-20 | NO | Resubmitted | 0 |  |  | 001251 | 2025-04-24 | 2025-04-24 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Water Testing of Liquid Retaining Structure" | AWC
001252 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0004 | 0 | 131242-WST02-DS-BS-0004 | 2025-04-25 | Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance | Not Approved - Revise and resubmit | 2025-05-23 | 2025-05-25 | 21 | Not Approved | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001252 | 2025-04-25 | 2025-04-25 | 0 | NAP | Not Approved | 1 | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " | NAP
001253 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | E | 0030 | 0 | 131242-WSW41-QA-E-0030 | 2025-04-25 | FAT Report for Control Cable and Power Cables | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-05-30 | 25 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001253 | 2025-04-25 | 2025-04-25 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Control Cable and Power Cables" | AWC
001254 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | BQ | I | 0001 | 0 | 131242-WSD11-BQ-I-0001 | 2025-04-25 | THP ICA Cable List | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-06-11 | 33 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001254 | 2025-04-25 | 2025-04-25 | 0 | AWC | Approved with Comments | 1 | " THP ICA Cable List" | AWC
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618_BCA | 0 | 131242-WSD11-DR-S-0302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618_BCA | C | 131242-WSD11-DR-S-1300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618_BCA | C | 131242-WSD11-DR-S-1301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618_BCA | C | 131242-WSD11-DR-S-1302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618_BCA | C | 131242-WSD11-DR-S-1303_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618_BCA | C | 131242-WSD11-DR-S-1304_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618_BCA | C | 131242-WSD11-DR-S-1305_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1306_ST618_BCA | C | 131242-WSD11-DR-S-1306_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618_BCA | C | 131242-WSD11-DR-S-2300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618_BCA | C | 131242-WSD11-DR-S-3300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618_BCA | C | 131242-WSD11-DR-S-3301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255 | 2025-04-25 | 2025-04-25 | C | INF | For Information | 1 | "ST618 WD Response For THP Train Cambi Structures" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618_BCA | C | 131242-WSD11-DR-S-5300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618_BCA | C | 131242-WSD11-DR-S-5301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618_BCA | C | 131242-WSD11-DR-S-5302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618_BCA | C | 131242-WSD11-DR-S-5303_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618_BCA | C | 131242-WSD11-DR-S-5304_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618_BCA | C | 131242-WSD11-DR-S-5305_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618_BCA | C | 131242-WSD11-DR-S-5306_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618_BCA | C | 131242-WSD11-DR-S-5307_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618_BCA | C | 131242-WSD11-DR-S-5308_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618_BCA | C | 131242-WSD11-DR-S-5309_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618_BCA | C | 131242-WSD11-DR-S-5310_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5311_ST618_BCA | C | 131242-WSD11-DR-S-5311_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5312_ST618_BCA | C | 131242-WSD11-DR-S-5312_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5313_ST618_BCA | C | 131242-WSD11-DR-S-5313_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5314_ST618_BCA | C | 131242-WSD11-DR-S-5314_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5315_ST618_BCA | C | 131242-WSD11-DR-S-5315_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5316_ST618_BCA | C | 131242-WSD11-DR-S-5316_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001256 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 0 | 131242-WSD11-QA-M-0069 | 2025-04-28 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-26 | 2025-07-02 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001256 | 2025-04-28 | 2025-12-04 | 1 | AWC | Approved | 2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" | APP
001256 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 1 | 131242-WSD11-QA-M-0069 | 2025-12-04 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 1: Approved | 2025-12-24 | 2025-12-23 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001256 | 2025-04-28 | 2025-12-04 | 1 | APP | Approved | 2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" | APP
001257 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 0 | 131242-WSW41-QA-M-0068 | 2025-04-29 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-08-01 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001257 | 2025-04-29 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | AWC
001257 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 1 | 131242-WSW41-QA-M-0068 | 2025-08-25 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-09-12 | 2025-12-23 | 86 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001257 | 2025-04-29 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | AWC
001258 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0073 | 0 | 131242-WST02-QA-M-0073 | 2025-04-29 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-06-23 | 39 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001258 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | AWC
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5731 | 0 | 131242-WST02-DS-M-5731 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | AWC
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5732 | 0 | 131242-WST02-DS-M-5732 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | AWC
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5733 | 0 | 131242-WST02-DS-M-5733 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | AWC
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5734 | 0 | 131242-WST02-DS-M-5734 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | AWC
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5735 | 0 | 131242-WST02-DS-M-5735 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | AWC
001260 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 0 | 131242-WST02-QA-BS-0005 | 2025-04-30 | Inspection and test Plan for fire protection system | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-28 | 2025-05-30 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001260 | 2025-04-30 | 2025-07-04 | 1 | AWC | Approved | 2 | "Inspection and test Plan for fire protection system " | APP
001260 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 1 | 131242-WST02-QA-BS-0005 | 2025-07-04 | Inspection and test Plan for fire protection system | R1: Approved | 2025-07-24 | 2025-12-29 | 126 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001260 | 2025-04-30 | 2025-07-04 | 1 | APP | Approved | 2 | "Inspection and test Plan for fire protection system " | APP
001261 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 0 | 131242-WSD11-QA-M-0071 | 2025-04-30 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-28 | 2025-07-02 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001261 | 2025-04-30 | 2025-12-03 | 1 | AWC | Approved | 2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | APP
001261 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 1 | 131242-WSD11-QA-M-0071 | 2025-12-03 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 1: Approved | 2025-12-23 | 2025-12-23 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001261 | 2025-04-30 | 2025-12-03 | 1 | APP | Approved | 2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | APP
001262 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 0 | 131242-WST02-QA-BS-0006 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-05-30 | 2025-05-30 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001262 | 2025-05-02 | 2025-07-05 | 1 | AWC | Approved with Comments | 2 | "Inspection and test Plan and Factory Acceptance Test for Public Address System" | AWC
001262 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 1 | 131242-WST02-QA-BS-0006 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-07-24 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-21 | NO | Overdue | 0 |  |  | 001262 | 2025-05-02 | 2025-07-05 | 1 | PEN | Approved with Comments | 2 | "Inspection and test Plan and Factory Acceptance Test for Public Address System" | AWC
001263 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 0 | 131242-WST02-QA-BS-0007 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001263 | 2025-05-02 | 2025-07-07 | 1 | AWC | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " | APP
001263 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 1 | 131242-WST02-QA-BS-0007 | 2025-07-07 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R1: Approved | 2025-07-25 | 2025-12-29 | 125 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001263 | 2025-05-02 | 2025-07-07 | 1 | APP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " | APP
001264 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | I | 0011 | 0 | 131242-WSW41-QA-I-0011 | 2025-05-02 | Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-05-30 | 2025-06-30 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001264 | 2025-05-02 | 2025-05-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | AWC
001265 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0030 | 0 | 131242-WSW41-MS-C-0030 | 2025-05-04 | Application of Novolac Epoxy Coating | R0: Approved | 2025-05-30 | 2025-05-30 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001265 | 2025-05-04 | 2025-05-04 | 0 | APP | Approved | 1 | "Application of Novolac Epoxy Coating " | APP
001266 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | E | 0014 | 0 | 131242-WSW41-MS-E-0014 | 2025-05-04 | MSRA for Protection Relay Replacement Works | Rev 0: Rejected. Resubmission not required, refer to attached file for comments to note | 2025-05-30 | 2025-06-17 | 31 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001266 | 2025-05-04 | 2025-05-04 | 0 | REJ | Rejected | 1 | "MSRA for Protection Relay Replacement Works " | REJ
001267 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0031 | 0 | 131242-WSW41-QA-C-0031 | 2025-05-04 | Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 | For Information | 2025-05-30 | 2025-06-09 | 25 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001267 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " | INF
001268 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 0 | 131242-WST02-QA-BS-0008 | 2025-05-04 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001268 | 2025-05-04 | 2025-07-05 | 1 | NAP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" | APP
001268 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 1 | 131242-WST02-QA-BS-0008 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-24 | 2025-09-23 | 56 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001268 | 2025-05-04 | 2025-07-05 | 1 | APP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" | APP
001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5487 | 0 | 131242-WST02-DS-M-5487 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | 194 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001269 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | INF
001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5487 | 0 | 131242-WST02-DR-M-5487 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | 194 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001269 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | INF
001270 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0059 | 0 | 131242-WST02-CD-IM-0059 | 2025-05-09 | Submission of BIM Coordination VCM Model (Apr 2025) | For Information | 2025-06-06 | 2025-05-29 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001270 | 2025-05-09 | 2025-05-09 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Apr 2025) " | INF
001271 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0080 | 0 | 131242-WST02-QA-M-0080 | 2025-05-09 | FAT Report for Discharge Transfer Pumps (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-07-01 | 37 | Approved with Comments | YES | 2025-07-21 | NO | Resubmitted | 0 |  |  | 001271 | 2025-05-09 | 2025-05-09 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Discharge Transfer Pumps (KSB)" | AWC
001272 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0077 | 0 | 131242-WSD11-QA-M-0077 | 2025-05-09 | Final FAT report for THP train 1 & Train 2 Feed pumps | Rev 0: Approved | 2025-06-06 | 2025-07-02 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001272 | 2025-05-09 | 2025-05-09 | 0 | APP | Approved | 1 | "Final FAT report for THP train 1 & Train 2 Feed pumps" | APP
001273 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0075 | 0 | 131242-WSW41-QA-M-0075 | 2025-05-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen) | Rev 0: Approved | 2025-06-06 | 2025-07-14 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001273 | 2025-05-09 | 2025-05-09 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen)" | APP
001274 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0004 | 0 | 131242-WSD11-VI-M-0004 | 2025-05-10 | Preliminary Design and Vendor Approval Document for Steam Equiptment Package | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001274 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" | AWC
001275 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0016 | 0 | 131242-WSD11-CL-P-0016 | 2025-05-10 | HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard | Rev 0: Approved | 2025-06-06 | 2025-07-04 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001275 | 2025-05-10 | 2025-05-10 | 0 | APP | Approved | 1 | "HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard" | APP
001276 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0040 | 0 | 131242-WSD11-DS-M-0040 | 2025-05-10 | THP HWR Bypass Control Valve | Approved with Comments | 2025-06-06 | 2025-05-21 | 7 | Approved with Comments | YES | 2025-06-10 | NO | Resubmitted | 0 |  |  | 001276 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "THP HWR Bypass Control Valve" | AWC
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5721 | 0 | 131242-WST02-DS-M-5721 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | AWC
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5722 | 0 | 131242-WST02-DS-M-5722 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | AWC
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5723 | 0 | 131242-WST02-DS-M-5723 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | AWC
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5724 | 0 | 131242-WST02-DS-M-5724 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | AWC
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5725 | 0 | 131242-WST02-DS-M-5725 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | AWC
001278 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0032 | 0 | 131242-WSW41-QA-C-0032 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Mar 2024 | For information | 2025-06-10 | 2025-05-20 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001278 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" | INF
001279 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0033 | 0 | 131242-WSW41-QA-C-0033 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Apr 2024 | For Information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001279 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" | INF
001280 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0034 | 0 | 131242-WSW41-QA-C-0034 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024 | For Information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001280 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" | INF
001281 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 0 | 131242-WSW41-QA-M-0082 | 2025-05-13 | FAT report for THP Sludge cooler D Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-07-02 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001281 | 2025-05-13 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler D Stage 2" | APP
001281 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 1 | 131242-WSW41-QA-M-0082 | 2025-12-02 | FAT report for THP Sludge cooler D Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001281 | 2025-05-13 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler D Stage 2" | APP
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620 | E | 131242-WSD11-DR-S-1600_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" | INF
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620 | E | 131242-WSD11-DR-S-1601_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" | INF
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620 | E | 131242-WSD11-DR-S-5600_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" | INF
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620 | E | 131242-WSD11-DR-S-5601_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" | INF
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5602_ST620 | E | 131242-WSD11-DR-S-5602_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" | INF
001283 | 00 | Aaron | CSA | NA | New WD | NA | NA | NA | NA | NA | New WD -NA-NA-NA-NA | 2025-05-13 | NEW WD from BCA for ST618 - THP Train Cambi Structures | For information | 2025-06-10 | 2025-05-21 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001283 | 2025-05-13 | 2025-05-13 | NA | INF | For Information | 1 | "NEW WD from BCA for ST618 - THP Train Cambi Structures" | INF
001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011 | E | 131242-WST02-DR-S-1011 | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | 34 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001284&&001656 | 2025-05-13 | 2025-09-08 | A.1 | AWC | Not Approved | 2 | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | NAP
001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004 | E | 131242-WST02-DR-S-7004 | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | 34 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001284 | 2025-05-13 | 2025-05-13 | E | AWC | Approved with Comments | 1 | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | AWC
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1203 | F | 131242-WST02-DR-S-1203 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1204 | F | 131242-WST02-DR-S-1204 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 2202 | F | 131242-WST02-DR-S-2202 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3202 | F | 131242-WST02-DR-S-3202 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5205 | F | 131242-WST02-DR-S-5205 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5206 | F | 131242-WST02-DR-S-5206 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5207 | F | 131242-WST02-DR-S-5207 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5208 | F | 131242-WST02-DR-S-5208 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" | INF
001286 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0009 | 0 | 131242-WSW41-PO-E-0009 | 2025-05-13 | Unpriced PO for Accessories for Lighting Protection (SkyPRO) | For information | 2025-06-10 | 2025-05-20 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001286 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" | INF
001287 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0017 | 0 | 131242-WSW41-PO-M-0017 | 2025-05-13 | Unpriced LOA for Electric Hoist (Helmsion Engineering) | Rev 0: For Information Only. | 2025-06-10 | 2025-11-21 | 138 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001287 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " | INF
001288 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0078 | 0 | 131242-WSW41-QA-M-0078 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) | NA | 2025-06-10 | 2025-09-08 | 84 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001288 | 2025-05-13 | 2025-05-13 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) " | APP
001289 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0079 | 0 | 131242-WSW41-QA-M-0079 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-08-01 | 58 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001289 | 2025-05-13 | 2025-05-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve" | AWC
001290 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0022 | 0 | 131242-WSW41-PC-W-0022 | 2025-05-13 | Payment Claim No.22 | Rev (0): Approved. Please refer to S.O. correspondence no. 350 date 16 May 2025. | 2025-06-10 | 2025-08-22 | 73 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001290 | 2025-05-13 | 2025-05-13 | 0 | APP | Approved | 1 | "Payment Claim No.22" | APP
001291 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0024 | 0 | 131242-WSW41-RT-PM-0024 | 2025-05-13 | C4B Monthly Progress Report Number No.24 (04 25) | Approved with Comments No resubmission is required | 2025-06-10 | 2025-05-16 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001291 | 2025-05-13 | 2025-05-13 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.24 (04 25)" | AWC
001292 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0035 | 0 | 131242-WSW41-QA-C-0035 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 | For information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001292 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " | INF
001293 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0036 | 0 | 131242-WSW41-QA-C-0036 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024 | For information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001293 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" | INF
001294 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0037 | 0 | 131242-WSW41-QA-C-0037 | 2025-05-14 | Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025 | For information | 2025-06-11 | 2025-06-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001294 | 2025-05-14 | 2025-05-14 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" | INF
001295 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0030 | 0 | 131242-WSW41-SP-C-0030 | 2025-05-14 | Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information | 2025-06-11 | 2025-06-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001295 | 2025-05-14 | 2025-05-14 | 0 | INF | For Information | 1 | "Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) " | INF
001296 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BS | 0001 | 0 | 131242-WST02-DS-BS-0001 | 2025-05-15 | Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001296 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" | AWC
001297 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0002 | 0 | 131242-WST02-DS-BF-0002 | 2025-05-15 | Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001297 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" | AWC
001298 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0003 | 0 | 131242-WST02-DS-BF-0003 | 2025-05-15 | Data Sheets for Clean Gas System | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001298 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | " Data Sheets for Clean Gas System" | AWC
001299 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | 0 | 131242-WST02-DR-BF-5000 | 2025-05-15 | Typical installation drawing for PA & Fire Alarm System | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001299&&001306 | 2025-05-15 | 2025-05-18 | A | AWC | Approved | 2 | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" | APP
001300 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0030 | 0 | 131242-WST02-QA-E-0030 | 2025-05-15 | Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-12 | 2025-06-09 | 17 | Approved with Comments | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001300 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " | AWC
001301 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | BS | 1398 | 0 | 131242-WST02-DS-BS-1398 | 2025-05-15 | Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance) | Rev 0: For Information | 2025-06-12 | 2025-06-23 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001301 | 2025-05-15 | 2025-05-15 | 0 | INF | For Information | 1 | "Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance)" | INF
001302 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0038 | 0 | 131242-WSW41-QA-C-0038 | 2025-05-18 | Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025 | For Information | 2025-06-13 | 2025-06-04 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001302 | 2025-05-18 | 2025-05-18 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025" | INF
001303 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0031 | 0 | 131242-WSW41-QA-E-0031 | 2025-05-18 | FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN) | Rev 0: Approved | 2025-06-13 | 2025-05-29 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001303 | 2025-05-18 | 2025-05-18 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" | APP
001304 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0012 | 0 | 131242-WSW41-QA-I-0012 | 2025-05-18 | Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-13 | 2025-07-14 | 40 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001304 | 2025-05-18 | 2025-05-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | AWC
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 41 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | AWC
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | AWC
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7004 | A | 131242-WST02-DR-BF-7004 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" | AWC
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7005 | A | 131242-WST02-DR-BF-7005 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" | AWC
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7104 | A | 131242-WST02-DR-BF-7104 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" | AWC
001306 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | A | 131242-WST02-DR-BF-5000 | 2025-05-18 | Typical Installation drawing For PA & Fire Alarm | Approved | 2025-06-13 | 2025-06-30 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001299&&001306 | 2025-05-15 | 2025-05-18 | A | APP | Approved | 2 | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" | APP
001307 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | NA | NA | Fabrication drawing-NA-NA-NA-NA | 2025-05-18 | ST609 SSN-PR001 Fabrication Drawing and Model | For information. Subject mentioned 'model' however no models were included in the submittal. Also, all drawings are not as per TWRP standard, including file naming and title block. | 2025-06-13 | 2025-08-05 | 56 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001307&&001364&&001365&&001366 | 2025-05-18 | 2025-06-12 | NA | INF | For Information | 4 | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | INF
001308 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 0 | 131242-WSD11-CL-P-0017 | 2025-05-19 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001308 | 2025-05-19 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "G1 Booster Pump Hydraulics Calculation " | AWC
001308 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 1 | 131242-WSD11-CL-P-0017 | 2025-08-25 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-12 |  | 155 | Awaiting S.O.'s response | YES | 2025-10-10 | NO | Overdue | 0 |  |  | 001308 | 2025-05-19 | 2025-08-25 | 1 | PEN | Approved with Comments | 2 | "G1 Booster Pump Hydraulics Calculation " | AWC
001309 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 0 | 131242-WSD11-CL-P-0018 | 2025-05-19 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001309 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "G2D Booster Pump Hydraulics Calculation " | AWC
001309 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 1 | 131242-WSD11-CL-P-0018 | 2025-07-28 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | 175 | Awaiting S.O.'s response | YES | 2025-09-12 | NO | Overdue | 0 |  |  | 001309 | 2025-05-19 | 2025-07-28 | 1 | PEN | Approved with Comments | 2 | "G2D Booster Pump Hydraulics Calculation " | AWC
001310 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 0 | 131242-WST02-DS-M-5711 | 2025-05-19 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-05-30 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001310 | 2025-05-19 | 2025-07-15 | 1 | AWC | Approved with Comments | 2 | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | AWC
001310 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 1 | 131242-WST02-DS-M-5711 | 2025-07-15 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 001310 | 2025-05-19 | 2025-07-15 | 1 | PEN | Approved with Comments | 2 | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | AWC
001311 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 0 | 131242-WSD11-RT-P-0004 | 2025-05-19 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-02 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001311 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "H2S Dispersion Simulation And Risk Assessement Report" | AWC
001311 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 1 | 131242-WSD11-RT-P-0004 | 2025-07-28 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-15 | 2025-09-24 | 42 | Approved with Comments | YES | 2025-10-14 | NO | Resubmitted | 0 |  |  | 001311 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "H2S Dispersion Simulation And Risk Assessement Report" | AWC
001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501 | A | 131242-WSD11-DR-S-3501 | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001312&&001363 | 2025-05-19 | 2025-06-12 | F | NAP | Not Approved | 2 | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | NAP
001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501_Endorsed | - | 131242-WSD11-DR-S-3501_Endorsed | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001312 | 2025-05-19 | 2025-05-19 | - | NAP | Not Approved | 1 | "Revised Design of THP Steel Structure Plinths" | NAP
001312 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | Comment reply | NA | 131242-WSD11-DR-S-Comment reply | 2025-08-22 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-09-17 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001312 | 2025-08-22 | 2025-08-22 | NA | INF | For Information | 1 | "Revised Design of THP Steel Structure Plinths" | INF
001313 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0013 | 0 | 131242-WSW41-QA-I-0013 | 2025-05-20 | Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-17 | 2025-07-14 | 39 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001313 | 2025-05-20 | 2025-05-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | AWC
001314 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2008 | 0 | 131242-WSW41-VI-M-2008 | 2025-05-20 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-17 | 2025-06-20 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001314 | 2025-05-20 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Solenoid Valve " | AWC
001314 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2008 | 1 | 131242-WSW41-VI-M-2008 | 2025-07-28 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | 175 | Awaiting S.O.'s response | YES | 2025-09-12 | NO | Overdue | 0 |  |  | 001314 | 2025-05-20 | 2025-07-28 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Solenoid Valve " | AWC
001315 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 0 | 131242-WSD11-QA-M-0081 | 2025-05-23 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-02 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001315 | 2025-05-23 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT Report for THP Sludge Cooler C Stage 2" | APP
001315 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 1 | 131242-WSD11-QA-M-0081 | 2025-12-02 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001315 | 2025-05-23 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT Report for THP Sludge Cooler C Stage 2" | APP
001316 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0074 | 0 | 131242-WSW41-QA-M-0074 | 2025-05-23 | Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson) | NA | 2025-06-20 | 2025-09-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001316 | 2025-05-23 | 2025-05-23 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson)" | APP
001317 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0031 | 0 | 131242-WSD11-QA-E-0031 | 2025-05-23 | SAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-23 | 43 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001317 | 2025-05-23 | 2025-05-23 | 0 | AWC | Approved with Comments | 1 | "SAT Report for WSD11-MCC-0101A&B" | AWC
001318 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0002 | 0 | 131242-WST02-OM-M-0002 | 2025-05-26 | O&M Manual for Aeration Blower | NA | 2025-06-23 |  | 220 | Awaiting S.O.'s response | YES | 2025-07-11 | NO | Overdue | 0 |  |  | 001318 | 2025-05-26 | 2025-05-26 | 0 | PEN | Awaiting S.O.'s response | 1 | "O&M Manual for Aeration Blower" | PEN
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | A | 131242-WST02-DR-M-5624 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | NAP | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" | NAP
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | A | 131242-WST02-DR-M-5625 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | NAP | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" | NAP
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5624 | 0 | 131242-WST02-DS-M-5624 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-05-26 | 0 | NAP | Not Approved | 1 | "Data Sheet and Drawing for Davit Crane" | NAP
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5625 | 0 | 131242-WST02-DS-M-5625 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-05-26 | 0 | NAP | Not Approved | 1 | "Data Sheet and Drawing for Davit Crane" | NAP
001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | B | 131242-WST02-DR-M-5624 | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | PEN | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" | NAP
001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | B | 131242-WST02-DR-M-5625 | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | PEN | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" | NAP
001320 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 0 | 131242-WSW41-QA-M-0083 | 2025-05-26 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-23 | 2025-07-31 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001320 | 2025-05-26 | 2025-10-01 | 1 | AWC | Approved with Comments | 2 | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | AWC
001320 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 1 | 131242-WSW41-QA-M-0083 | 2025-10-01 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 |  | 128 | Awaiting S.O.'s response | YES | 2025-11-18 | NO | Overdue | 0 |  |  | 001320 | 2025-05-26 | 2025-10-01 | 1 | PEN | Approved with Comments | 2 | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | AWC
001321 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0032 | 0 | 131242-WSW41-MS-C-0032 | 2025-05-26 | MSRA and SWP for RC Sub & Super-Structural Work (TechGems) | Rev 0: Approved | 2025-06-23 | 2025-06-20 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001321 | 2025-05-26 | 2025-05-26 | 0 | APP | Approved | 1 | "MSRA and SWP for RC Sub & Super-Structural Work (TechGems)" | APP
001322 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | MS | M | 0008 | 0 | 131242-WSD11-MS-M-0008 | 2025-05-27 | Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building | Rev 0: Approved | 2025-06-24 | 2025-08-11 | 54 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001322 | 2025-05-27 | 2025-05-27 | 0 | APP | Approved | 1 | "Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building " | APP
001323 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0084 | 0 | 131242-WST02-QA-M-0084 | 2025-05-28 | FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank) | Rev 0: Approved | 2025-06-25 | 2025-07-02 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001323 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank)" | APP
001324 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0085 | 0 | 131242-WSD11-QA-M-0085 | 2025-05-28 | FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps | Rev 0: Approved | 2025-06-25 | 2025-07-04 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001324 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps" | APP
001325 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002 | 2025-05-28 | Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000781&&001325 | 2024-10-26 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " | APP
001326 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | CL | A | 0002 | 0 | 131242-WST02-CL-A-0002 | 2025-05-28 | Siphonic System Schematic and Calculation | Approved | 2025-06-25 | 2025-07-09 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001326 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "Siphonic System Schematic and Calculation" | APP
001327 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004 | 2025-05-28 | Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000855&&001327 | 2024-11-28 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " | APP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1541 | A | 131242-WSD11-DR-IP-1541 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1542 | A | 131242-WSD11-DR-IP-1542 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1543 | A | 131242-WSD11-DR-IP-1543 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1544 | A | 131242-WSD11-DR-IP-1544 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1545 | A | 131242-WSD11-DR-IP-1545 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1546 | A | 131242-WSD11-DR-IP-1546 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1547 | A | 131242-WSD11-DR-IP-1547 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1548 | A | 131242-WSD11-DR-IP-1548 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1549 | A | 131242-WSD11-DR-IP-1549 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1550 | A | 131242-WSD11-DR-IP-1550 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1551 | A | 131242-WSD11-DR-IP-1551 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1552 | A | 131242-WSD11-DR-IP-1552 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1553 | A | 131242-WSD11-DR-IP-1553 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1554 | A | 131242-WSD11-DR-IP-1554 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1555 | A | 131242-WSD11-DR-IP-1555 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1556 | A | 131242-WSD11-DR-IP-1556 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1557 | A | 131242-WSD11-DR-IP-1557 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1091 | A | 131242-WSD11-DR-IP-1091 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1092 | A | 131242-WSD11-DR-IP-1092 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1093 | A | 131242-WSD11-DR-IP-1093 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1094 | A | 131242-WSD11-DR-IP-1094 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1095 | A | 131242-WSD11-DR-IP-1095 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1096 | A | 131242-WSD11-DR-IP-1096 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1097 | A | 131242-WSD11-DR-IP-1097 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1098 | A | 131242-WSD11-DR-IP-1098 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1099 | A | 131242-WSD11-DR-IP-1099 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1100 | A | 131242-WSD11-DR-IP-1100 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1101 | A | 131242-WSD11-DR-IP-1101 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1102 | A | 131242-WSD11-DR-IP-1102 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1103 | A | 131242-WSD11-DR-IP-1103 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1104 | A | 131242-WSD11-DR-IP-1104 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1105 | A | 131242-WSD11-DR-IP-1105 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1106 | A | 131242-WSD11-DR-IP-1106 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1107 | A | 131242-WSD11-DR-IP-1107 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1108 | A | 131242-WSD11-DR-IP-1108 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1109 | A | 131242-WSD11-DR-IP-1109 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1110 | A | 131242-WSD11-DR-IP-1110 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1111 | A | 131242-WSD11-DR-IP-1111 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1112 | A | 131242-WSD11-DR-IP-1112 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1113 | A | 131242-WSD11-DR-IP-1113 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1114 | A | 131242-WSD11-DR-IP-1114 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1115 | A | 131242-WSD11-DR-IP-1115 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1116 | A | 131242-WSD11-DR-IP-1116 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1117 | A | 131242-WSD11-DR-IP-1117 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1118 | A | 131242-WSD11-DR-IP-1118 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1119 | A | 131242-WSD11-DR-IP-1119 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1120 | A | 131242-WSD11-DR-IP-1120 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1121 | A | 131242-WSD11-DR-IP-1121 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1122 | A | 131242-WSD11-DR-IP-1122 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1123 | A | 131242-WSD11-DR-IP-1123 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1124 | A | 131242-WSD11-DR-IP-1124 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1125 | A | 131242-WSD11-DR-IP-1125 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1031 | A | 131242-WSD11-DR-IP-1031 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1032 | A | 131242-WSD11-DR-IP-1032 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1033 | A | 131242-WSD11-DR-IP-1033 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1034 | A | 131242-WSD11-DR-IP-1034 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1035 | A | 131242-WSD11-DR-IP-1035 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1036 | A | 131242-WSD11-DR-IP-1036 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1037 | A | 131242-WSD11-DR-IP-1037 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1038 | A | 131242-WSD11-DR-IP-1038 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1039 | A | 131242-WSD11-DR-IP-1039 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1040 | A | 131242-WSD11-DR-IP-1040 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1041 | A | 131242-WSD11-DR-IP-1041 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1042 | A | 131242-WSD11-DR-IP-1042 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1043 | A | 131242-WSD11-DR-IP-1043 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1044 | A | 131242-WSD11-DR-IP-1044 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1045 | A | 131242-WSD11-DR-IP-1045 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1046 | A | 131242-WSD11-DR-IP-1046 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1047 | A | 131242-WSD11-DR-IP-1047 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1048 | A | 131242-WSD11-DR-IP-1048 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1049 | A | 131242-WSD11-DR-IP-1049 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1050 | A | 131242-WSD11-DR-IP-1050 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1051 | A | 131242-WSD11-DR-IP-1051 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1052 | A | 131242-WSD11-DR-IP-1052 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1053 | A | 131242-WSD11-DR-IP-1053 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1054 | A | 131242-WSD11-DR-IP-1054 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1055 | A | 131242-WSD11-DR-IP-1055 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1056 | A | 131242-WSD11-DR-IP-1056 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1057 | A | 131242-WSD11-DR-IP-1057 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1058 | A | 131242-WSD11-DR-IP-1058 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1059 | A | 131242-WSD11-DR-IP-1059 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1060 | A | 131242-WSD11-DR-IP-1060 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1061 | A | 131242-WSD11-DR-IP-1061 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1062 | A | 131242-WSD11-DR-IP-1062 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1063 | A | 131242-WSD11-DR-IP-1063 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1064 | A | 131242-WSD11-DR-IP-1064 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1065 | A | 131242-WSD11-DR-IP-1065 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" | NAP
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | A | 131242-WSD11-DR-IP-1001 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | A | 131242-WSD11-DR-IP-1002 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | A | 131242-WSD11-DR-IP-1003 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | A | 131242-WSD11-DR-IP-1004 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | A | 131242-WSD11-DR-IP-1005 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | A | 131242-WSD11-DR-IP-1006 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | A | 131242-WSD11-DR-IP-1007 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | A | 131242-WSD11-DR-IP-1008 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | A | 131242-WSD11-DR-IP-1009 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1010 | A | 131242-WSD11-DR-IP-1010 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1011 | A | 131242-WSD11-DR-IP-1011 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1012 | A | 131242-WSD11-DR-IP-1012 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1013 | A | 131242-WSD11-DR-IP-1013 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1014 | A | 131242-WSD11-DR-IP-1014 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1015 | A | 131242-WSD11-DR-IP-1015 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1016 | A | 131242-WSD11-DR-IP-1016 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1017 | A | 131242-WSD11-DR-IP-1017 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1018 | A | 131242-WSD11-DR-IP-1018 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1019 | A | 131242-WSD11-DR-IP-1019 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1020 | A | 131242-WSD11-DR-IP-1020 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | A | 131242-WSD11-DR-IP-3001 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | A | 131242-WSD11-DR-IP-3002 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | A | 131242-WSD11-DR-IP-3003 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | A | 131242-WSD11-DR-IP-3004 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | A | 131242-WSD11-DR-IP-3005 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | A | 131242-WSD11-DR-IP-3006 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | A | 131242-WSD11-DR-IP-3007 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | A | 131242-WSD11-DR-IP-3008 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | A | 131242-WSD11-DR-IP-3009 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | A | 131242-WSD11-DR-IP-3010 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | A | 131242-WSD11-DR-IP-3011 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | A | 131242-WSD11-DR-IP-3012 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | A | 131242-WSD11-DR-IP-3013 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | A | 131242-WSD11-DR-IP-3014 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | A | 131242-WSD11-DR-IP-3015 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | A | 131242-WSD11-DR-IP-3016 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | A | 131242-WSD11-DR-IP-3017 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | A | 131242-WSD11-DR-IP-3018 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | A | 131242-WSD11-DR-IP-3019 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | A | 131242-WSD11-DR-IP-3020 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | A | 131242-WSD11-DR-IP-3021 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | A | 131242-WSD11-DR-IP-3022 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | A | 131242-WSD11-DR-IP-3023 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | A | 131242-WSD11-DR-IP-3024 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | A | 131242-WSD11-DR-IP-3025 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | B | 131242-WSD11-DR-IP-1001 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | B | 131242-WSD11-DR-IP-1002 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | B | 131242-WSD11-DR-IP-1003 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | B | 131242-WSD11-DR-IP-1004 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | B | 131242-WSD11-DR-IP-1005 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | B | 131242-WSD11-DR-IP-1006 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | B | 131242-WSD11-DR-IP-1007 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | B | 131242-WSD11-DR-IP-1008 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | B | 131242-WSD11-DR-IP-1009 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1010 | B | 131242-WSD11-DR-IP-1010 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1011 | B | 131242-WSD11-DR-IP-1011 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1012 | B | 131242-WSD11-DR-IP-1012 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1013 | B | 131242-WSD11-DR-IP-1013 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1014 | B | 131242-WSD11-DR-IP-1014 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1015 | B | 131242-WSD11-DR-IP-1015 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1016 | B | 131242-WSD11-DR-IP-1016 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1017 | B | 131242-WSD11-DR-IP-1017 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1018 | B | 131242-WSD11-DR-IP-1018 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1019 | B | 131242-WSD11-DR-IP-1019 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1020 | B | 131242-WSD11-DR-IP-1020 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1021 | B | 131242-WSD11-DR-IP-1021 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-10-28 | 2025-10-28 | B | AWC | Approved with Comments | 1 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1022 | B | 131242-WSD11-DR-IP-1022 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-10-28 | 2025-10-28 | B | AWC | Approved with Comments | 1 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1023 | B | 131242-WSD11-DR-IP-1023 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-10-28 | 2025-10-28 | B | AWC | Approved with Comments | 1 | "THP ICA GA & Wiring drawings" | AWC
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1024 | B | 131242-WSD11-DR-IP-1024 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-10-28 | 2025-10-28 | B | AWC | Approved with Comments | 1 | "THP ICA GA & Wiring drawings" | AWC
001329 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0023 | 0 | 131242-WSW41-PC-W-0023 | 2025-05-30 | Payment Claim No.23 | Rev(0): Approved. Please refer to S.O. correspondence no. 354 dated 30 May 2025. | 2025-06-27 | 2025-06-02 | 1 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001329 | 2025-05-30 | 2025-05-30 | 0 | APP | Approved | 1 | "Payment Claim No.23" | APP
001330 | 00 | Karthik | EICA | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-05-30 | THP ICA GA & Wiring Drawings | Rev 0: For Information. No resubmission required. | 2025-06-27 | 2025-12-05 | 135 | For Information | NO |  | YES | Resubmitted | 0 |  | Dublicate submission. Please refer to 1328. | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | INF | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001331 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0013 | 0 | 131242-WST02-CD-I-0013 | 2025-05-30 | Electrical Signal List for SSN -LVSG-0101A/0101B | Not Approved - Revise and resubmit | 2025-06-27 | 2025-06-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001331 | 2025-05-30 | 2025-06-09 | 1 | NAP | Approved with Comments | 2 | "Electrical Signal List for SSN -LVSG-0101A/0101B" | AWC
001331 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0013 | 1 | 131242-WST02-CD-I-0013 | 2025-06-09 | Electrical Signal List for SSN -LVSG-0101A/0101B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-30 | 15 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001331 | 2025-05-30 | 2025-06-09 | 1 | AWC | Approved with Comments | 2 | "Electrical Signal List for SSN -LVSG-0101A/0101B" | AWC
001332 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0086 | 0 | 131242-WSW41-QA-M-0086 | 2025-05-30 | FAT Report for CSEL piping DN 750mm (2nd batch) | NA | 2025-06-27 | 2025-09-02 | 67 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001332 | 2025-05-30 | 2025-05-30 | 0 | APP | Approved | 1 | "FAT Report for CSEL piping DN 750mm (2nd batch)" | APP
001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001 | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001333&&001547 | 2025-05-30 | 2025-10-28 | A | NAP | Approved with Comments | 3 | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | AWC
001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7010 | A | 131242-WST02-DR-I-7010 | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | NAP
001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7011 | A | 131242-WST02-DR-I-7011 | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | NAP
001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7001 | B | 131242-WST02-DR-II-7001 | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | NAP | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7010 | B | 131242-WST02-DR-II-7010 | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | NAP | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7011 | B | 131242-WST02-DR-II-7011 | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | NAP | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7001 | C | 131242-WST02-DR-II-7001 | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | 22 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | AWC | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7010 | C | 131242-WST02-DR-II-7010 | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | 22 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | AWC | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7011 | C | 131242-WST02-DR-II-7011 | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | 22 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001333 | 2025-08-25 | 2025-10-27 | C | AWC | Approved with Comments | 2 | "SSN Over All Network Archtecture Drawings" | AWC
001334 | 00 | Bryan | Mech | NA | 131242 | WSD11 | MS | C | 0007 | 0 | 131242-WSD11-MS-C-0007 | 2025-05-30 | Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Approved | 2025-06-27 | 2025-12-29 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001334 | 2025-05-30 | 2025-05-30 | 0 | APP | Approved | 1 | "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | APP
001335 | 00 | Jun | EICA | NA | 131242 | WSW41 | MM | E | 0003 | 0 | 131242-WSW41-MM-E-0003 | 2025-05-30 | Memo-Appointment of LEW Representatives | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 | 15 | Approved with Comments | YES | 2025-07-10 | NO | Resubmitted | 0 |  |  | 001335 | 2025-05-30 | 2025-05-30 | 0 | AWC | Approved with Comments | 1 | "Memo-Appointment of LEW Representatives" | AWC
001336 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0014 | 0 | 131242-WSW41-QA-I-0014 | 2025-05-30 | FAT Report for Radar Level Transmitter 1st Batch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-27 | 2025-07-14 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001336 | 2025-05-30 | 2025-07-22 | 1 | NAP | Approved with Comments | 2 | "FAT Report for Radar Level Transmitter 1st Batch " | AWC
001336 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0014 | 1 | 131242-WSW41-QA-I-0014 | 2025-07-22 | FAT Report for Radar Level Transmitter 1st Batch | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-08-06 | 11 | Approved with Comments | YES | 2025-08-26 | NO | Resubmitted | 0 |  |  | 001336 | 2025-05-30 | 2025-07-22 | 1 | AWC | Approved with Comments | 2 | "FAT Report for Radar Level Transmitter 1st Batch " | AWC
001337 | 00 | K Balaji | Const; | NA | 131242 | WSW41 | MS | M | 0008 | 0 | 131242-WSW41-MS-M-0008 | 2025-05-30 | Method Statement & Risk Assessment for Piping Installation at SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-08-11 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001337 | 2025-05-30 | 2025-12-05 | 1 | AWC | Approved with Comments | 2 | "Method Statement & Risk Assessment for Piping Installation at SWPR" | AWC
001337 | 01 | K Balaji | Const; | NA | 131242 | WSW41 | MS | M | 0008 | 1 | 131242-WSW41-MS-M-0008 | 2025-12-05 | Method Statement & Risk Assessment for Piping Installation at SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-25 | 2025-12-29 | 16 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001337 | 2025-05-30 | 2025-12-05 | 1 | AWC | Approved with Comments | 2 | "Method Statement & Risk Assessment for Piping Installation at SWPR" | AWC
001338 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0015 | 0 | 131242-WST02-QA-I-0015 | 2025-06-03 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001338 | 2025-06-03 | 2025-08-21 | 1 | NAP | Approved with Comments | 2 | "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | AWC
001338 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0015 | 1 | 131242-WST02-QA-I-0015 | 2025-08-21 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-10 | 2025-09-02 | 8 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001338 | 2025-06-03 | 2025-08-21 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | AWC
001339 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0018 | 0 | 131242-WSW41-QA-I-0018 | 2025-06-03 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-17 | 32 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001339&&001357 | 2025-06-03 | 2025-06-12 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | AWC
001340 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0016 | 0 | 131242-WSW41-QA-I-0016 | 2025-06-03 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-20 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001340 | 2025-06-03 | 2025-08-25 | 1 | NAP | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | AWC
001340 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0016 | 1 | 131242-WSW41-QA-I-0016 | 2025-08-25 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-09-02 | 6 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001340 | 2025-06-03 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | AWC
001341 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 0 | 131242-WSW41-QA-M-0076 | 2025-06-03 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2025-07-01 | 2025-08-01 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001341 | 2025-06-03 | 2025-09-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | AWC
001341 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 1 | 131242-WSW41-QA-M-0076 | 2025-08-27 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2025-09-16 | 2025-09-02 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001341 | 2025-06-03 | 2025-09-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | AWC
001341 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 2 | 131242-WSW41-QA-M-0076 | 2025-09-17 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-07 | 2025-12-23 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001341 | 2025-06-03 | 2025-09-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | AWC
001342 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0017 | 0 | 131242-WSW41-QA-I-0017 | 2025-06-03 | FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-06-20 | 13 | Approved with Comments | YES | 2025-07-10 | NO | Resubmitted | 0 |  |  | 001342 | 2025-06-03 | 2025-06-03 | 0 | AWC | Approved with Comments | 1 | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" | AWC
001343 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0019 | 0 | 131242-WSW41-QA-I-0019 | 2025-06-04 | Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-02 | 2025-08-04 | 43 | Approved with Comments | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001343 | 2025-06-04 | 2025-06-04 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" | AWC
001344 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0072 | 0 | 131242-WSW41-QA-M-0072 | 2025-06-04 | Vendor Manufacturing Inspection Test Plan for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 | 2025-07-14 | 28 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001344 | 2025-06-04 | 2025-06-04 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Parabolic Screen" | AWC
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0011 | 0 | 131242-WST02-OM-M-0011 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0012 | 0 | 131242-WST02-OM-M-0012 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0013 | 0 | 131242-WST02-OM-M-0013 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0014 | 0 | 131242-WST02-OM-M-0014 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0015 | 0 | 131242-WST02-OM-M-0015 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0016 | 0 | 131242-WST02-OM-M-0016 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | 211 | Awaiting S.O.'s response | YES | 2025-07-24 | NO | Overdue | 0 |  |  | 001345 | 2025-06-06 | 2025-06-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | PEN
001346 | 00 | Yibo | Mech | NA | 131242 | WST02 | CL | M | 5624 | 0 | 131242-WST02-CL-M-5624 | 2025-06-06 | Crane Calculation for Davit Crane 1and 2 | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2026-02-27 | 190 | Not Approved | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001346 | 2025-06-06 | 2025-06-06 | 0 | NAP | Not Approved | 1 | "Crane Calculation for Davit Crane 1and 2" | NAP
001346 | 00 | Yibo | Mech | NA | 131242 | WST02 | CL | M | 5625 | 0 | 131242-WST02-CL-M-5625 | 2025-06-06 | Crane Calculation for Davit Crane 1and 2 | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2026-02-27 | 190 | Not Approved | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001346 | 2025-06-06 | 2025-06-06 | 0 | NAP | Not Approved | 1 | "Crane Calculation for Davit Crane 1and 2" | NAP
001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5620 | A | 131242-WST02-DR-M-5620 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001347 | 2025-06-06 | 2025-09-29 | B | AWC | Approved with Comments | 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5622 | A | 131242-WST02-DR-M-5622 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001347 | 2025-06-06 | 2025-09-29 | B | AWC | Approved with Comments | 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5620 | 0 | 131242-WST02-DS-M-5620 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001347 | 2025-06-06 | 2025-06-06 | 0 | AWC | Approved with Comments | 1 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5622 | 0 | 131242-WST02-DS-M-5622 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001347 | 2025-06-06 | 2025-06-06 | 0 | AWC | Approved with Comments | 1 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001347 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5620 | B | 131242-WST02-DR-M-5620 | 2025-09-29 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-10-17 |  | 130 | Awaiting S.O.'s response | YES | 2025-11-14 | NO | Overdue | 0 |  |  | 001347 | 2025-06-06 | 2025-09-29 | B | PEN | Approved with Comments | 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001347 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5622 | B | 131242-WST02-DR-M-5622 | 2025-09-29 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-10-17 |  | 130 | Awaiting S.O.'s response | YES | 2025-11-14 | NO | Overdue | 0 |  |  | 001347 | 2025-06-06 | 2025-09-29 | B | PEN | Approved with Comments | 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | AWC
001348 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | C | 0022 | 0 | 131242-WST02-QA-C-0022 | 2025-06-06 | Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-07-28 | 36 | Approved with Comments | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001348 | 2025-06-06 | 2025-06-06 | 0 | AWC | Approved with Comments | 1 | "Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) " | AWC
001349 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0060 | 0 | 131242-WST02-CD-IM-0060 | 2025-06-09 | Submission of BIM Coordination VCM Model (May 2025) | For Information | 2025-07-07 | 2025-06-30 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001349 | 2025-06-09 | 2025-06-09 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (May 2025) " | INF
001350 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CD | I | 0001 | 0 | 131242-WSW41-CD-I-0001 | 2025-06-10 | Electrical Signal List for MCC - TYPICAL | NA | 2025-07-08 |  | 209 | Awaiting S.O.'s response | YES | 2025-07-18 | NO | Overdue | 0 |  |  | 001350&&001467 | 2025-06-10 | 2025-07-25 | 1 | PEN | Approved with Comments | 2 | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " | AWC
001351 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5101 | A | 131242-WSD11-DR-I-5101 | 2025-06-10 | Hookup Drawing for PIT at Air Receiver | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-12-09 | 130 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001351 | 2025-06-10 | 2025-06-10 | A | AWC | Approved with Comments | 1 | "Hookup Drawing for PIT at Air Receiver " | AWC
001352 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5102 | A | 131242-WSD11-DR-I-5102 | 2025-06-10 | Hook up Drawing for PDSH - CAS | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-12-09 | 130 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001352&&001904 | 2025-06-10 | 2025-12-16 | B | AWC | Approved with Comments | 2 | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | AWC
001353 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0025 | 0 | 131242-WST02-VI-I-0025 | 2025-06-10 | Vendor Approval of SSN Package - Magnetic Level Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-23 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001353 | 2025-06-10 | 2025-11-05 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of SSN Package - Magnetic Level Gauge" | AWC
001353 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0025 | 1 | 131242-WST02-VI-I-0025 | 2025-11-05 | Vendor Approval of SSN Package - Magnetic Level Gauge | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-11-26 | 15 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001353 | 2025-06-10 | 2025-11-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package - Magnetic Level Gauge" | AWC
001354 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0061 | 0 | 131242-WSW41-LT-PM-0061 | 2025-06-11 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025 | For Information. Please refer to S.O. correspondence no. 380 dated 30 July 2025. | 2025-07-09 | 2025-08-25 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001354 | 2025-06-11 | 2025-06-11 | 0 | INF | For Information | 1 | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025" | INF
001355 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0025 | 0 | 131242-WSW41-RT-PM-0025 | 2025-06-12 | C4B Monthly Progress Report Number No.25 (05 25) | Approved with comments which to be addressed in the next MPR submission. | 2025-07-10 | 2025-07-20 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001355 | 2025-06-12 | 2025-06-12 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.25 (05 25)" | AWC
001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | A | 131242-WST02-SD-A-3014 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | NAP | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-A-3015 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001114&&001356 | 2025-03-11 | 2025-06-12 | A | NAP | Not Approved | 2 | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | NAP
001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-A-1014 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | B | 131242-WST02-SD-A-3014 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-02 | 2025-07-11 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | NAP | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | A | 131242-WST02-SD-A-3016 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-11 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001356&&001367 | 2025-06-12 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | AWC
001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | A | 131242-WST02-SD-A-3017 | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-11 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001356&&001530 | 2025-06-12 | 2025-08-27 | C | NAP | Approved with Comments | 4 | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | AWC
001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | B | 131242-WST02-SD-A-1014 | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | AWC | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | C | 131242-WST02-SD-A-3014 | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-27 | 2025-08-04 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | AWC | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | B | 131242-WST02-SD-A-3016 | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001356&&001367 | 2025-06-12 | 2025-08-27 | C | AWC | Approved with Comments | 5 | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | AWC
001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | B | 131242-WST02-SD-A-3017 | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001356&&001530 | 2025-06-12 | 2025-08-27 | C | AWC | Approved with Comments | 4 | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | AWC
001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | C | 131242-WST02-SD-A-1014 | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | 28 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 147 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | AWC | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | D | 131242-WST02-SD-A-3014 | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | 28 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 147 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | AWC | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | AWC
001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | C | 131242-WST02-SD-A-3016 | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | 28 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 6 |  |  | 001356&&001367 | 2025-06-12 | 2025-08-27 | C | AWC | Approved with Comments | 5 | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | AWC
001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | C | 131242-WST02-SD-A-3017 | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | 28 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001356&&001530 | 2025-06-12 | 2025-08-27 | C | AWC | Approved with Comments | 4 | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | AWC
001357 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0018 | 0 | 131242-WSW41-QA-I-0018 | 2025-06-12 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-10 | 2025-07-14 | 22 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001339&&001357 | 2025-06-03 | 2025-06-12 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | AWC
001358 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0087 | 0 | 131242-WSW41-QA-M-0087 | 2025-06-12 | FAT Report for Spray Nozzles | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-10 | 2025-07-23 | 29 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001358 | 2025-06-12 | 2025-06-12 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Spray Nozzles" | AWC
001359 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 0 | 131242-WST02-VI-B-0004 | 2025-06-12 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001359 | 2025-06-12 | 2025-11-13 | 2 | NAP | Not Approved | 3 | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | NAP
001359 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 1 | 131242-WST02-VI-B-0004 | 2025-07-22 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-11 | 2025-10-10 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001359 | 2025-06-12 | 2025-11-13 | 2 | NAP | Not Approved | 3 | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | NAP
001359 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 2 | 131242-WST02-VI-B-0004 | 2025-11-13 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-03 | 2025-12-29 | 32 | Not Approved | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001359 | 2025-06-12 | 2025-11-13 | 2 | NAP | Not Approved | 3 | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | NAP
001360 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | BS | 1399 | 0 | 131242-WST02-DS-BS-1399 | 2025-06-12 | Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) | R0: Approve with comments. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-08 | 18 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001360 | 2025-06-12 | 2025-06-12 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) " | AWC
001361 | 00 | Dhanapal | QAQC | NA | 131424 | WSD11 | QA | I | 0020 | 0 | 131424-WSD11-QA-I-0020 | 2025-06-12 | FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-12-23 | 138 | Approved with Comments | YES | 2026-01-12 | NO | Resubmitted | 0 |  |  | 001361 | 2025-06-12 | 2025-06-12 | 0 | AWC | Approved with Comments | 1 | "FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module)" | AWC
001362 | 00 | Dhanapal | QAQC | NA | 131424 | WSD11 | QA | I | 0021 | 0 | 131424-WSD11-QA-I-0021 | 2025-06-12 | FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-07-10 | 2025-12-09 | 128 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001362 | 2025-06-12 | 2025-06-12 | 0 | NAP | Not Approved | 1 | "FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA)" | NAP
001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | F | 131242-WSD11-DR-S-1500 | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | NAP | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | F | 131242-WSD11-DR-S-1501 | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | NAP | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | F | 131242-WSD11-DR-S-3500 | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | NAP | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501 | F | 131242-WSD11-DR-S-3501 | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001312&&001363 | 2025-05-19 | 2025-06-12 | F | NAP | Not Approved | 2 | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | NAP
001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | G | 131242-WSD11-DR-S-1500 | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-11 | 2025-09-24 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | G | 131242-WSD11-DR-S-1501 | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-19 | 2025-09-24 | 23 | Approved with Comments | YES | 2025-10-14 | NO | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | G | 131242-WSD11-DR-S-3500 | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-19 | 2025-09-24 | 23 | Approved with Comments | YES | 2025-10-14 | NO | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | G | 131242-WSD11-DR-S-1500 | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | 78 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | G | 131242-WSD11-DR-S-1501 | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | 78 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | G | 131242-WSD11-DR-S-3500 | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | 78 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | AWC
001364 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | NA | NA | Fabrication drawing-NA-NA-NA-NA | 2025-06-12 | ST609-SSN-PR002 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | 76 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001307&&001364&&001365&&001366 | 2025-05-18 | 2025-06-12 | NA | INF | For Information | 4 | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | INF
001365 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | NA | NA | Fabrication drawing-NA-NA-NA-NA | 2025-06-12 | ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | 76 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001307&&001364&&001365&&001366 | 2025-05-18 | 2025-06-12 | NA | INF | For Information | 4 | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | INF
001366 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | NA | NA | Fabrication drawing-NA-NA-NA-NA | 2025-06-12 | ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | 76 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001307&&001364&&001365&&001366 | 2025-05-18 | 2025-06-12 | NA | INF | For Information | 4 | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | INF
001367 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1016 | A | 131242-WST02-SD-A-1016 | 2025-06-12 | Raised Floor Shop Drawings submission (Momentum) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001367 | 2025-06-12 | 2025-07-24 | B | NAP | Approved with Comments | 2 | "Raised Floor Shop Drawings submission (Momentum)" | AWC
001367 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | A | 131242-WST02-SD-A-3016 | 2025-06-12 | Raised Floor Shop Drawings submission (Momentum) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001356&&001367 | 2025-06-12 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | AWC
001367 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1016 | B | 131242-WST02-SD-A-1016 | 2025-07-24 | Raised Floor Shop Drawings submission (Momentum) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-01 | 6 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001367 | 2025-06-12 | 2025-07-24 | B | AWC | Approved with Comments | 2 | "Raised Floor Shop Drawings submission (Momentum)" | AWC
001367 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | B | 131242-WST02-SD-A-3016 | 2025-07-24 | Raised Floor Shop Drawings submission (Momentum) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-01 | 6 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001356&&001367 | 2025-06-12 | 2025-08-27 | C | AWC | Approved with Comments | 5 | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | AWC
001368 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0016 | 0 | 131242-WST02-VI-E-0016 | 2025-06-12 | Vendor Approval for Active Harmonic Filter (DANFOSS) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-07-04 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001368 | 2025-06-12 | 2025-08-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for Active Harmonic Filter (DANFOSS)" | AWC
001368 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0016 | 1 | 131242-WST02-VI-E-0016 | 2025-08-05 | Vendor Approval for Active Harmonic Filter (DANFOSS) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001368 | 2025-06-12 | 2025-08-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for Active Harmonic Filter (DANFOSS)" | AWC
001369 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | BQ | E | 0001 | 0 | 131242-WSW41-BQ-E-0001 | 2025-06-12 | Electrical As Built Drawing List | Rev 0: Not Approved. To revise and resubmit. | 2025-07-10 | 2025-07-23 | 29 | Not Approved | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001369 | 2025-06-12 | 2025-06-12 | 0 | NAP | Not Approved | 1 | "Electrical As Built Drawing List" | NAP
001370 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5701 | A | 131242-WST02-DR-M-5701 | 2025-06-12 | General Arrangement for TCI Flow Control valve | NA | 2025-07-10 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 001370 | 2025-06-12 | 2025-06-12 | A | PEN | Awaiting S.O.'s response | 1 | "General Arrangement for TCI Flow Control valve" | PEN
001371 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5702 | A | 131242-WST02-DR-M-5702 | 2025-06-12 | General Arrangement for DC Partial Bypass Line Flow Control Valve | NA | 2025-07-10 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 001371 | 2025-06-12 | 2025-06-12 | A | PEN | Awaiting S.O.'s response | 1 | "General Arrangement for DC Partial Bypass Line Flow Control Valve" | PEN
001372 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5703 | A | 131242-WST02-DR-M-5703 | 2025-06-12 | General Arrangement for Lamella Clarifier Flow Control Valve | NA | 2025-07-10 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 001372 | 2025-06-12 | 2025-06-12 | A | PEN | Awaiting S.O.'s response | 1 | "General Arrangement for Lamella Clarifier Flow Control Valve" | PEN
001373 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5711 | A | 131242-WST02-DR-M-5711 | 2025-06-12 | General Arrangement for IRIS Diaphragm Flow Control Valve | NA | 2025-07-10 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 001373 | 2025-06-12 | 2025-06-12 | A | PEN | Awaiting S.O.'s response | 1 | "General Arrangement for IRIS Diaphragm Flow Control Valve" | PEN
001374 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5602 | A | 131242-WST02-DR-M-5602 | 2025-06-16 | GA Drawing for Static Screen - Plinth Opening & Seal plate | NA | 2025-07-14 |  | 205 | Awaiting S.O.'s response | YES | 2025-08-01 | NO | Overdue | 0 |  |  | 001374 | 2025-06-16 | 2025-06-16 | A | PEN | Awaiting S.O.'s response | 1 | "GA Drawing for Static Screen - Plinth Opening & Seal plate" | PEN
001375 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0041 | 0 | 131242-WSD11-DS-M-0041 | 2025-06-16 | G1 Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-07-14 | 2025-07-08 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001375 | 2025-06-16 | 2025-08-25 | 1 | NAP | Approved with Comments | 2 | "G1 Booster Pump Data Sheet" | AWC
001375 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0041 | 1 | 131242-WSD11-DS-M-0041 | 2025-08-25 | G1 Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-09-12 | 2025-09-08 | 10 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001375 | 2025-06-16 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "G1 Booster Pump Data Sheet" | AWC