001376 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5751 | A | 131242-WST02-DR-M-5751 | 2025-06-16 | GA for SSN G2D PRV | NA | 2025-07-14 |  | 205 | Awaiting S.O.'s response | YES | 2025-08-01 | NO | Overdue | 0 |  |  | 001376 | 2025-06-16 | 2025-06-16 | A | PEN | Awaiting S.O.'s response | 1 | "GA for SSN G2D PRV" | PEN
001377 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5103 | A | 131242-WSD11-DR-I-5103 | 2025-06-16 | Hook-up Drawing for Pressure Transmitter (HS) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-12-10 | 127 | Not Approved | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001377 | 2025-06-16 | 2025-06-16 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Pressure Transmitter (HS)" | NAP
001378 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0011 | 0 | 131242-WST02-DS-I-0011 | 2025-06-16 | Data sheet for Autosampler | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-10-24 | 94 | Approved with Comments | YES | 2025-11-13 | NO | Resubmitted | 0 |  |  | 001378 | 2025-06-16 | 2025-06-16 | 0 | AWC | Approved with Comments | 1 | "Data sheet for Autosampler" | AWC
001379 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0008 | 0 | 131242-WST02-DS-I-0008 | 2025-06-16 | Data sheet for Capacitive Level Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-11-05 | 102 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001379 | 2025-06-16 | 2025-06-16 | 0 | AWC | Approved with Comments | 1 | "Data sheet for Capacitive Level Switch" | AWC
001380 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0009 | 0 | 131242-WST02-DS-I-0009 | 2025-06-16 | Datasheet for Thermal Mass Flowmeter | NA | 2025-07-14 | 2025-09-24 | 72 | Approved with Comments | YES | 2025-10-14 | NO | Resubmitted | 0 |  |  | 001380 | 2025-06-16 | 2025-06-16 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Thermal Mass Flowmeter" | AWC
001381 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0042 | 0 | 131242-WSD11-DS-M-0042 | 2025-06-16 | G2D Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-07-14 | 2025-07-08 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001381 | 2025-06-16 | 2025-08-22 | 1 | NAP | Approved with Comments | 2 | "G2D Booster Pump Data Sheet" | AWC
001381 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0042 | 1 | 131242-WSD11-DS-M-0042 | 2025-08-22 | G2D Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-09-11 | 2025-09-08 | 11 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001381 | 2025-06-16 | 2025-08-22 | 1 | AWC | Approved with Comments | 2 | "G2D Booster Pump Data Sheet" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1221 | A | 131242-WSD11-DR-IP-1221 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1222 | A | 131242-WSD11-DR-IP-1222 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1223 | A | 131242-WSD11-DR-IP-1223 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1224 | A | 131242-WSD11-DR-IP-1224 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1225 | A | 131242-WSD11-DR-IP-1225 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1226 | A | 131242-WSD11-DR-IP-1226 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1227 | A | 131242-WSD11-DR-IP-1227 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1228 | A | 131242-WSD11-DR-IP-1228 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1229 | A | 131242-WSD11-DR-IP-1229 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1230 | A | 131242-WSD11-DR-IP-1230 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1231 | A | 131242-WSD11-DR-IP-1231 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1232 | A | 131242-WSD11-DR-IP-1232 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1233 | A | 131242-WSD11-DR-IP-1233 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1234 | A | 131242-WSD11-DR-IP-1234 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1235 | A | 131242-WSD11-DR-IP-1235 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1236 | A | 131242-WSD11-DR-IP-1236 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1237 | A | 131242-WSD11-DR-IP-1237 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1238 | A | 131242-WSD11-DR-IP-1238 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1239 | A | 131242-WSD11-DR-IP-1239 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1240 | A | 131242-WSD11-DR-IP-1240 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1241 | A | 131242-WSD11-DR-IP-1241 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1242 | A | 131242-WSD11-DR-IP-1242 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1243 | A | 131242-WSD11-DR-IP-1243 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1244 | A | 131242-WSD11-DR-IP-1244 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1245 | A | 131242-WSD11-DR-IP-1245 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1246 | A | 131242-WSD11-DR-IP-1246 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1247 | A | 131242-WSD11-DR-IP-1247 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1248 | A | 131242-WSD11-DR-IP-1248 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1249 | A | 131242-WSD11-DR-IP-1249 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1250 | A | 131242-WSD11-DR-IP-1250 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1251 | A | 131242-WSD11-DR-IP-1251 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1252 | A | 131242-WSD11-DR-IP-1252 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1253 | A | 131242-WSD11-DR-IP-1253 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1254 | A | 131242-WSD11-DR-IP-1254 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1255 | A | 131242-WSD11-DR-IP-1255 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1256 | A | 131242-WSD11-DR-IP-1256 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1257 | A | 131242-WSD11-DR-IP-1257 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1258 | A | 131242-WSD11-DR-IP-1258 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1259 | A | 131242-WSD11-DR-IP-1259 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1260 | A | 131242-WSD11-DR-IP-1260 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1261 | A | 131242-WSD11-DR-IP-1261 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1262 | A | 131242-WSD11-DR-IP-1262 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1263 | A | 131242-WSD11-DR-IP-1263 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1264 | A | 131242-WSD11-DR-IP-1264 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1265 | A | 131242-WSD11-DR-IP-1265 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1266 | A | 131242-WSD11-DR-IP-1266 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1267 | A | 131242-WSD11-DR-IP-1267 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1268 | A | 131242-WSD11-DR-IP-1268 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1269 | A | 131242-WSD11-DR-IP-1269 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1270 | A | 131242-WSD11-DR-IP-1270 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1271 | A | 131242-WSD11-DR-IP-1271 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1272 | A | 131242-WSD11-DR-IP-1272 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1273 | A | 131242-WSD11-DR-IP-1273 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1274 | A | 131242-WSD11-DR-IP-1274 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1275 | A | 131242-WSD11-DR-IP-1275 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1276 | A | 131242-WSD11-DR-IP-1276 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1277 | A | 131242-WSD11-DR-IP-1277 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1278 | A | 131242-WSD11-DR-IP-1278 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1279 | A | 131242-WSD11-DR-IP-1279 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1280 | A | 131242-WSD11-DR-IP-1280 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1281 | A | 131242-WSD11-DR-IP-1281 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1282 | A | 131242-WSD11-DR-IP-1282 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1283 | A | 131242-WSD11-DR-IP-1283 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1284 | A | 131242-WSD11-DR-IP-1284 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1285 | A | 131242-WSD11-DR-IP-1285 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1286 | A | 131242-WSD11-DR-IP-1286 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1287 | A | 131242-WSD11-DR-IP-1287 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1288 | A | 131242-WSD11-DR-IP-1288 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1289 | A | 131242-WSD11-DR-IP-1289 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1290 | A | 131242-WSD11-DR-IP-1290 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1291 | A | 131242-WSD11-DR-IP-1291 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1292 | A | 131242-WSD11-DR-IP-1292 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1293 | A | 131242-WSD11-DR-IP-1293 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1294 | A | 131242-WSD11-DR-IP-1294 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1295 | A | 131242-WSD11-DR-IP-1295 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1296 | A | 131242-WSD11-DR-IP-1296 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1297 | A | 131242-WSD11-DR-IP-1297 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1298 | A | 131242-WSD11-DR-IP-1298 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1299 | A | 131242-WSD11-DR-IP-1299 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1300 | A | 131242-WSD11-DR-IP-1300 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1301 | A | 131242-WSD11-DR-IP-1301 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1302 | A | 131242-WSD11-DR-IP-1302 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1303 | A | 131242-WSD11-DR-IP-1303 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1304 | A | 131242-WSD11-DR-IP-1304 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1305 | A | 131242-WSD11-DR-IP-1305 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1306 | A | 131242-WSD11-DR-IP-1306 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1307 | A | 131242-WSD11-DR-IP-1307 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1308 | A | 131242-WSD11-DR-IP-1308 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1309 | A | 131242-WSD11-DR-IP-1309 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1310 | A | 131242-WSD11-DR-IP-1310 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1311 | A | 131242-WSD11-DR-IP-1311 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1312 | A | 131242-WSD11-DR-IP-1312 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1313 | A | 131242-WSD11-DR-IP-1313 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1314 | A | 131242-WSD11-DR-IP-1314 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1315 | A | 131242-WSD11-DR-IP-1315 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1316 | A | 131242-WSD11-DR-IP-1316 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1317 | A | 131242-WSD11-DR-IP-1317 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1318 | A | 131242-WSD11-DR-IP-1318 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1319 | A | 131242-WSD11-DR-IP-1319 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1320 | A | 131242-WSD11-DR-IP-1320 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1321 | A | 131242-WSD11-DR-IP-1321 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1322 | A | 131242-WSD11-DR-IP-1322 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1323 | A | 131242-WSD11-DR-IP-1323 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1324 | A | 131242-WSD11-DR-IP-1324 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1325 | A | 131242-WSD11-DR-IP-1325 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1326 | A | 131242-WSD11-DR-IP-1326 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1327 | A | 131242-WSD11-DR-IP-1327 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1328 | A | 131242-WSD11-DR-IP-1328 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1329 | A | 131242-WSD11-DR-IP-1329 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1330 | A | 131242-WSD11-DR-IP-1330 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1331 | A | 131242-WSD11-DR-IP-1331 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1332 | A | 131242-WSD11-DR-IP-1332 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1333 | A | 131242-WSD11-DR-IP-1333 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1334 | A | 131242-WSD11-DR-IP-1334 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1335 | A | 131242-WSD11-DR-IP-1335 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1336 | A | 131242-WSD11-DR-IP-1336 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1337 | A | 131242-WSD11-DR-IP-1337 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1338 | A | 131242-WSD11-DR-IP-1338 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1339 | A | 131242-WSD11-DR-IP-1339 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1351 | A | 131242-WSD11-DR-IP-1351 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1352 | A | 131242-WSD11-DR-IP-1352 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1353 | A | 131242-WSD11-DR-IP-1353 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1354 | A | 131242-WSD11-DR-IP-1354 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1355 | A | 131242-WSD11-DR-IP-1355 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1356 | A | 131242-WSD11-DR-IP-1356 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1357 | A | 131242-WSD11-DR-IP-1357 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1358 | A | 131242-WSD11-DR-IP-1358 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1359 | A | 131242-WSD11-DR-IP-1359 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1360 | A | 131242-WSD11-DR-IP-1360 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1361 | A | 131242-WSD11-DR-IP-1361 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1362 | A | 131242-WSD11-DR-IP-1362 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1363 | A | 131242-WSD11-DR-IP-1363 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1364 | A | 131242-WSD11-DR-IP-1364 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1365 | A | 131242-WSD11-DR-IP-1365 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1366 | A | 131242-WSD11-DR-IP-1366 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1367 | A | 131242-WSD11-DR-IP-1367 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1368 | A | 131242-WSD11-DR-IP-1368 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1369 | A | 131242-WSD11-DR-IP-1369 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1370 | A | 131242-WSD11-DR-IP-1370 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1371 | A | 131242-WSD11-DR-IP-1371 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1372 | A | 131242-WSD11-DR-IP-1372 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1373 | A | 131242-WSD11-DR-IP-1373 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1374 | A | 131242-WSD11-DR-IP-1374 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1375 | A | 131242-WSD11-DR-IP-1375 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1376 | A | 131242-WSD11-DR-IP-1376 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1377 | A | 131242-WSD11-DR-IP-1377 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1378 | A | 131242-WSD11-DR-IP-1378 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1379 | A | 131242-WSD11-DR-IP-1379 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1380 | A | 131242-WSD11-DR-IP-1380 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1381 | A | 131242-WSD11-DR-IP-1381 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1382 | A | 131242-WSD11-DR-IP-1382 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1383 | A | 131242-WSD11-DR-IP-1383 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1384 | A | 131242-WSD11-DR-IP-1384 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1385 | A | 131242-WSD11-DR-IP-1385 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1386 | A | 131242-WSD11-DR-IP-1386 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1387 | A | 131242-WSD11-DR-IP-1387 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1388 | A | 131242-WSD11-DR-IP-1388 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1389 | A | 131242-WSD11-DR-IP-1389 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1390 | A | 131242-WSD11-DR-IP-1390 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1391 | A | 131242-WSD11-DR-IP-1391 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1392 | A | 131242-WSD11-DR-IP-1392 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1393 | A | 131242-WSD11-DR-IP-1393 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1394 | A | 131242-WSD11-DR-IP-1394 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1395 | A | 131242-WSD11-DR-IP-1395 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1396 | A | 131242-WSD11-DR-IP-1396 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1397 | A | 131242-WSD11-DR-IP-1397 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1398 | A | 131242-WSD11-DR-IP-1398 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1399 | A | 131242-WSD11-DR-IP-1399 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1400 | A | 131242-WSD11-DR-IP-1400 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1401 | A | 131242-WSD11-DR-IP-1401 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1402 | A | 131242-WSD11-DR-IP-1402 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1403 | A | 131242-WSD11-DR-IP-1403 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1404 | A | 131242-WSD11-DR-IP-1404 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1405 | A | 131242-WSD11-DR-IP-1405 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1406 | A | 131242-WSD11-DR-IP-1406 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1407 | A | 131242-WSD11-DR-IP-1407 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1408 | A | 131242-WSD11-DR-IP-1408 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1409 | A | 131242-WSD11-DR-IP-1409 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1410 | A | 131242-WSD11-DR-IP-1410 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1411 | A | 131242-WSD11-DR-IP-1411 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1412 | A | 131242-WSD11-DR-IP-1412 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1413 | A | 131242-WSD11-DR-IP-1413 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1414 | A | 131242-WSD11-DR-IP-1414 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1415 | A | 131242-WSD11-DR-IP-1415 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1416 | A | 131242-WSD11-DR-IP-1416 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1417 | A | 131242-WSD11-DR-IP-1417 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1418 | A | 131242-WSD11-DR-IP-1418 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1419 | A | 131242-WSD11-DR-IP-1419 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1420 | A | 131242-WSD11-DR-IP-1420 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1421 | A | 131242-WSD11-DR-IP-1421 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1422 | A | 131242-WSD11-DR-IP-1422 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1423 | A | 131242-WSD11-DR-IP-1423 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1424 | A | 131242-WSD11-DR-IP-1424 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1425 | A | 131242-WSD11-DR-IP-1425 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1426 | A | 131242-WSD11-DR-IP-1426 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1427 | A | 131242-WSD11-DR-IP-1427 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1428 | A | 131242-WSD11-DR-IP-1428 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1429 | A | 131242-WSD11-DR-IP-1429 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1430 | A | 131242-WSD11-DR-IP-1430 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1431 | A | 131242-WSD11-DR-IP-1431 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1432 | A | 131242-WSD11-DR-IP-1432 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1433 | A | 131242-WSD11-DR-IP-1433 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1434 | A | 131242-WSD11-DR-IP-1434 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1435 | A | 131242-WSD11-DR-IP-1435 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1436 | A | 131242-WSD11-DR-IP-1436 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1437 | A | 131242-WSD11-DR-IP-1437 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1438 | A | 131242-WSD11-DR-IP-1438 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1439 | A | 131242-WSD11-DR-IP-1439 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1440 | A | 131242-WSD11-DR-IP-1440 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1441 | A | 131242-WSD11-DR-IP-1441 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1442 | A | 131242-WSD11-DR-IP-1442 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1443 | A | 131242-WSD11-DR-IP-1443 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1444 | A | 131242-WSD11-DR-IP-1444 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1445 | A | 131242-WSD11-DR-IP-1445 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1446 | A | 131242-WSD11-DR-IP-1446 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1447 | A | 131242-WSD11-DR-IP-1447 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1448 | A | 131242-WSD11-DR-IP-1448 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1449 | A | 131242-WSD11-DR-IP-1449 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1450 | A | 131242-WSD11-DR-IP-1450 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1451 | A | 131242-WSD11-DR-IP-1451 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1452 | A | 131242-WSD11-DR-IP-1452 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1453 | A | 131242-WSD11-DR-IP-1453 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1454 | A | 131242-WSD11-DR-IP-1454 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1455 | A | 131242-WSD11-DR-IP-1455 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1456 | A | 131242-WSD11-DR-IP-1456 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1457 | A | 131242-WSD11-DR-IP-1457 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1458 | A | 131242-WSD11-DR-IP-1458 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1459 | A | 131242-WSD11-DR-IP-1459 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1460 | A | 131242-WSD11-DR-IP-1460 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1461 | A | 131242-WSD11-DR-IP-1461 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1462 | A | 131242-WSD11-DR-IP-1462 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1463 | A | 131242-WSD11-DR-IP-1463 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1464 | A | 131242-WSD11-DR-IP-1464 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1465 | A | 131242-WSD11-DR-IP-1465 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1466 | A | 131242-WSD11-DR-IP-1466 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1467 | A | 131242-WSD11-DR-IP-1467 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1468 | A | 131242-WSD11-DR-IP-1468 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1469 | A | 131242-WSD11-DR-IP-1469 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1470 | A | 131242-WSD11-DR-IP-1470 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1151 | A | 131242-WSD11-DR-IP-1151 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1152 | A | 131242-WSD11-DR-IP-1152 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1153 | A | 131242-WSD11-DR-IP-1153 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1154 | A | 131242-WSD11-DR-IP-1154 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1155 | A | 131242-WSD11-DR-IP-1155 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1156 | A | 131242-WSD11-DR-IP-1156 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1157 | A | 131242-WSD11-DR-IP-1157 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1158 | A | 131242-WSD11-DR-IP-1158 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1159 | A | 131242-WSD11-DR-IP-1159 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1160 | A | 131242-WSD11-DR-IP-1160 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1161 | A | 131242-WSD11-DR-IP-1161 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1162 | A | 131242-WSD11-DR-IP-1162 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1163 | A | 131242-WSD11-DR-IP-1163 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1164 | A | 131242-WSD11-DR-IP-1164 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1165 | A | 131242-WSD11-DR-IP-1165 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1166 | A | 131242-WSD11-DR-IP-1166 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1167 | A | 131242-WSD11-DR-IP-1167 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1168 | A | 131242-WSD11-DR-IP-1168 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1169 | A | 131242-WSD11-DR-IP-1169 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1170 | A | 131242-WSD11-DR-IP-1170 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1171 | A | 131242-WSD11-DR-IP-1171 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1172 | A | 131242-WSD11-DR-IP-1172 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1173 | A | 131242-WSD11-DR-IP-1173 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1174 | A | 131242-WSD11-DR-IP-1174 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1175 | A | 131242-WSD11-DR-IP-1175 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1176 | A | 131242-WSD11-DR-IP-1176 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1177 | A | 131242-WSD11-DR-IP-1177 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1178 | A | 131242-WSD11-DR-IP-1178 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1179 | A | 131242-WSD11-DR-IP-1179 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1180 | A | 131242-WSD11-DR-IP-1180 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1181 | A | 131242-WSD11-DR-IP-1181 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1182 | A | 131242-WSD11-DR-IP-1182 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1183 | A | 131242-WSD11-DR-IP-1183 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1184 | A | 131242-WSD11-DR-IP-1184 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1185 | A | 131242-WSD11-DR-IP-1185 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1186 | A | 131242-WSD11-DR-IP-1186 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1187 | A | 131242-WSD11-DR-IP-1187 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1188 | A | 131242-WSD11-DR-IP-1188 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1189 | A | 131242-WSD11-DR-IP-1189 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1190 | A | 131242-WSD11-DR-IP-1190 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1191 | A | 131242-WSD11-DR-IP-1191 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1192 | A | 131242-WSD11-DR-IP-1192 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1193 | A | 131242-WSD11-DR-IP-1193 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1194 | A | 131242-WSD11-DR-IP-1194 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1195 | A | 131242-WSD11-DR-IP-1195 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1196 | A | 131242-WSD11-DR-IP-1196 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1197 | A | 131242-WSD11-DR-IP-1197 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1198 | A | 131242-WSD11-DR-IP-1198 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1199 | A | 131242-WSD11-DR-IP-1199 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1481 | A | 131242-WSD11-DR-IP-1481 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1482 | A | 131242-WSD11-DR-IP-1482 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1483 | A | 131242-WSD11-DR-IP-1483 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1484 | A | 131242-WSD11-DR-IP-1484 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1485 | A | 131242-WSD11-DR-IP-1485 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1486 | A | 131242-WSD11-DR-IP-1486 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1487 | A | 131242-WSD11-DR-IP-1487 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1488 | A | 131242-WSD11-DR-IP-1488 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1489 | A | 131242-WSD11-DR-IP-1489 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1490 | A | 131242-WSD11-DR-IP-1490 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1491 | A | 131242-WSD11-DR-IP-1491 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1492 | A | 131242-WSD11-DR-IP-1492 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1493 | A | 131242-WSD11-DR-IP-1493 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1494 | A | 131242-WSD11-DR-IP-1494 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1495 | A | 131242-WSD11-DR-IP-1495 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1496 | A | 131242-WSD11-DR-IP-1496 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1497 | A | 131242-WSD11-DR-IP-1497 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1498 | A | 131242-WSD11-DR-IP-1498 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1499 | A | 131242-WSD11-DR-IP-1499 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1500 | A | 131242-WSD11-DR-IP-1500 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1501 | A | 131242-WSD11-DR-IP-1501 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1502 | A | 131242-WSD11-DR-IP-1502 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1503 | A | 131242-WSD11-DR-IP-1503 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1504 | A | 131242-WSD11-DR-IP-1504 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1505 | A | 131242-WSD11-DR-IP-1505 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1506 | A | 131242-WSD11-DR-IP-1506 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1507 | A | 131242-WSD11-DR-IP-1507 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1508 | A | 131242-WSD11-DR-IP-1508 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1509 | A | 131242-WSD11-DR-IP-1509 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1510 | A | 131242-WSD11-DR-IP-1510 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1511 | A | 131242-WSD11-DR-IP-1511 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1512 | A | 131242-WSD11-DR-IP-1512 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1513 | A | 131242-WSD11-DR-IP-1513 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1514 | A | 131242-WSD11-DR-IP-1514 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1515 | A | 131242-WSD11-DR-IP-1515 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1516 | A | 131242-WSD11-DR-IP-1516 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1517 | A | 131242-WSD11-DR-IP-1517 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1518 | A | 131242-WSD11-DR-IP-1518 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1519 | A | 131242-WSD11-DR-IP-1519 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1520 | A | 131242-WSD11-DR-IP-1520 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1521 | A | 131242-WSD11-DR-IP-1521 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1522 | A | 131242-WSD11-DR-IP-1522 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1523 | A | 131242-WSD11-DR-IP-1523 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1524 | A | 131242-WSD11-DR-IP-1524 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1525 | A | 131242-WSD11-DR-IP-1525 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1526 | A | 131242-WSD11-DR-IP-1526 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1527 | A | 131242-WSD11-DR-IP-1527 | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | NAP | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1221 | B | 131242-WSD11-DR-IP-1221 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1222 | B | 131242-WSD11-DR-IP-1222 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1223 | B | 131242-WSD11-DR-IP-1223 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1224 | B | 131242-WSD11-DR-IP-1224 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1225 | B | 131242-WSD11-DR-IP-1225 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1226 | B | 131242-WSD11-DR-IP-1226 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1227 | B | 131242-WSD11-DR-IP-1227 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1228 | B | 131242-WSD11-DR-IP-1228 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1229 | B | 131242-WSD11-DR-IP-1229 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1230 | B | 131242-WSD11-DR-IP-1230 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1231 | B | 131242-WSD11-DR-IP-1231 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1232 | B | 131242-WSD11-DR-IP-1232 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1233 | B | 131242-WSD11-DR-IP-1233 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1234 | B | 131242-WSD11-DR-IP-1234 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1235 | B | 131242-WSD11-DR-IP-1235 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1236 | B | 131242-WSD11-DR-IP-1236 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1237 | B | 131242-WSD11-DR-IP-1237 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1238 | B | 131242-WSD11-DR-IP-1238 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1239 | B | 131242-WSD11-DR-IP-1239 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1240 | B | 131242-WSD11-DR-IP-1240 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1241 | B | 131242-WSD11-DR-IP-1241 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1242 | B | 131242-WSD11-DR-IP-1242 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1243 | B | 131242-WSD11-DR-IP-1243 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1244 | B | 131242-WSD11-DR-IP-1244 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1245 | B | 131242-WSD11-DR-IP-1245 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1246 | B | 131242-WSD11-DR-IP-1246 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1247 | B | 131242-WSD11-DR-IP-1247 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1248 | B | 131242-WSD11-DR-IP-1248 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1249 | B | 131242-WSD11-DR-IP-1249 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1250 | B | 131242-WSD11-DR-IP-1250 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1251 | B | 131242-WSD11-DR-IP-1251 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1252 | B | 131242-WSD11-DR-IP-1252 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1253 | B | 131242-WSD11-DR-IP-1253 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1254 | B | 131242-WSD11-DR-IP-1254 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1255 | B | 131242-WSD11-DR-IP-1255 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1256 | B | 131242-WSD11-DR-IP-1256 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1257 | B | 131242-WSD11-DR-IP-1257 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1258 | B | 131242-WSD11-DR-IP-1258 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1259 | B | 131242-WSD11-DR-IP-1259 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1260 | B | 131242-WSD11-DR-IP-1260 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1261 | B | 131242-WSD11-DR-IP-1261 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1262 | B | 131242-WSD11-DR-IP-1262 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1263 | B | 131242-WSD11-DR-IP-1263 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1264 | B | 131242-WSD11-DR-IP-1264 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1265 | B | 131242-WSD11-DR-IP-1265 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1266 | B | 131242-WSD11-DR-IP-1266 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1267 | B | 131242-WSD11-DR-IP-1267 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1268 | B | 131242-WSD11-DR-IP-1268 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1269 | B | 131242-WSD11-DR-IP-1269 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1270 | B | 131242-WSD11-DR-IP-1270 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1271 | B | 131242-WSD11-DR-IP-1271 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1272 | B | 131242-WSD11-DR-IP-1272 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1273 | B | 131242-WSD11-DR-IP-1273 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1274 | B | 131242-WSD11-DR-IP-1274 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1275 | B | 131242-WSD11-DR-IP-1275 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1276 | B | 131242-WSD11-DR-IP-1276 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1277 | B | 131242-WSD11-DR-IP-1277 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1278 | B | 131242-WSD11-DR-IP-1278 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1279 | B | 131242-WSD11-DR-IP-1279 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1280 | B | 131242-WSD11-DR-IP-1280 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1281 | B | 131242-WSD11-DR-IP-1281 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1282 | B | 131242-WSD11-DR-IP-1282 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1283 | B | 131242-WSD11-DR-IP-1283 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1284 | B | 131242-WSD11-DR-IP-1284 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1285 | B | 131242-WSD11-DR-IP-1285 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1286 | B | 131242-WSD11-DR-IP-1286 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1287 | B | 131242-WSD11-DR-IP-1287 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1288 | B | 131242-WSD11-DR-IP-1288 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1289 | B | 131242-WSD11-DR-IP-1289 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1290 | B | 131242-WSD11-DR-IP-1290 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1291 | B | 131242-WSD11-DR-IP-1291 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1292 | B | 131242-WSD11-DR-IP-1292 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1293 | B | 131242-WSD11-DR-IP-1293 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1294 | B | 131242-WSD11-DR-IP-1294 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1295 | B | 131242-WSD11-DR-IP-1295 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1296 | B | 131242-WSD11-DR-IP-1296 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1297 | B | 131242-WSD11-DR-IP-1297 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1298 | B | 131242-WSD11-DR-IP-1298 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1299 | B | 131242-WSD11-DR-IP-1299 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1300 | B | 131242-WSD11-DR-IP-1300 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1301 | B | 131242-WSD11-DR-IP-1301 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1302 | B | 131242-WSD11-DR-IP-1302 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1303 | B | 131242-WSD11-DR-IP-1303 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1304 | B | 131242-WSD11-DR-IP-1304 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1305 | B | 131242-WSD11-DR-IP-1305 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1306 | B | 131242-WSD11-DR-IP-1306 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1307 | B | 131242-WSD11-DR-IP-1307 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1308 | B | 131242-WSD11-DR-IP-1308 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1309 | B | 131242-WSD11-DR-IP-1309 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1310 | B | 131242-WSD11-DR-IP-1310 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1311 | B | 131242-WSD11-DR-IP-1311 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1312 | B | 131242-WSD11-DR-IP-1312 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1313 | B | 131242-WSD11-DR-IP-1313 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1314 | B | 131242-WSD11-DR-IP-1314 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1315 | B | 131242-WSD11-DR-IP-1315 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1316 | B | 131242-WSD11-DR-IP-1316 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1317 | B | 131242-WSD11-DR-IP-1317 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1318 | B | 131242-WSD11-DR-IP-1318 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1319 | B | 131242-WSD11-DR-IP-1319 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1320 | B | 131242-WSD11-DR-IP-1320 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1321 | B | 131242-WSD11-DR-IP-1321 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1322 | B | 131242-WSD11-DR-IP-1322 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1323 | B | 131242-WSD11-DR-IP-1323 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1324 | B | 131242-WSD11-DR-IP-1324 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1325 | B | 131242-WSD11-DR-IP-1325 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1326 | B | 131242-WSD11-DR-IP-1326 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1327 | B | 131242-WSD11-DR-IP-1327 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1328 | B | 131242-WSD11-DR-IP-1328 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1329 | B | 131242-WSD11-DR-IP-1329 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1330 | B | 131242-WSD11-DR-IP-1330 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1331 | B | 131242-WSD11-DR-IP-1331 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1332 | B | 131242-WSD11-DR-IP-1332 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1333 | B | 131242-WSD11-DR-IP-1333 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1334 | B | 131242-WSD11-DR-IP-1334 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1335 | B | 131242-WSD11-DR-IP-1335 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1336 | B | 131242-WSD11-DR-IP-1336 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1337 | B | 131242-WSD11-DR-IP-1337 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1338 | B | 131242-WSD11-DR-IP-1338 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1339 | B | 131242-WSD11-DR-IP-1339 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1351 | B | 131242-WSD11-DR-IP-1351 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1352 | B | 131242-WSD11-DR-IP-1352 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1353 | B | 131242-WSD11-DR-IP-1353 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1354 | B | 131242-WSD11-DR-IP-1354 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1355 | B | 131242-WSD11-DR-IP-1355 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1356 | B | 131242-WSD11-DR-IP-1356 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1357 | B | 131242-WSD11-DR-IP-1357 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1358 | B | 131242-WSD11-DR-IP-1358 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1359 | B | 131242-WSD11-DR-IP-1359 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1360 | B | 131242-WSD11-DR-IP-1360 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1361 | B | 131242-WSD11-DR-IP-1361 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1362 | B | 131242-WSD11-DR-IP-1362 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1363 | B | 131242-WSD11-DR-IP-1363 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1364 | B | 131242-WSD11-DR-IP-1364 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1365 | B | 131242-WSD11-DR-IP-1365 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1366 | B | 131242-WSD11-DR-IP-1366 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1367 | B | 131242-WSD11-DR-IP-1367 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1368 | B | 131242-WSD11-DR-IP-1368 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1369 | B | 131242-WSD11-DR-IP-1369 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1370 | B | 131242-WSD11-DR-IP-1370 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1371 | B | 131242-WSD11-DR-IP-1371 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1372 | B | 131242-WSD11-DR-IP-1372 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1373 | B | 131242-WSD11-DR-IP-1373 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1374 | B | 131242-WSD11-DR-IP-1374 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1375 | B | 131242-WSD11-DR-IP-1375 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1376 | B | 131242-WSD11-DR-IP-1376 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1377 | B | 131242-WSD11-DR-IP-1377 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1378 | B | 131242-WSD11-DR-IP-1378 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1379 | B | 131242-WSD11-DR-IP-1379 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1380 | B | 131242-WSD11-DR-IP-1380 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1381 | B | 131242-WSD11-DR-IP-1381 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1382 | B | 131242-WSD11-DR-IP-1382 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1383 | B | 131242-WSD11-DR-IP-1383 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1384 | B | 131242-WSD11-DR-IP-1384 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1385 | B | 131242-WSD11-DR-IP-1385 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1386 | B | 131242-WSD11-DR-IP-1386 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1387 | B | 131242-WSD11-DR-IP-1387 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1388 | B | 131242-WSD11-DR-IP-1388 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1389 | B | 131242-WSD11-DR-IP-1389 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1390 | B | 131242-WSD11-DR-IP-1390 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1391 | B | 131242-WSD11-DR-IP-1391 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1392 | B | 131242-WSD11-DR-IP-1392 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1393 | B | 131242-WSD11-DR-IP-1393 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1394 | B | 131242-WSD11-DR-IP-1394 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1395 | B | 131242-WSD11-DR-IP-1395 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1396 | B | 131242-WSD11-DR-IP-1396 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1397 | B | 131242-WSD11-DR-IP-1397 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1398 | B | 131242-WSD11-DR-IP-1398 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1399 | B | 131242-WSD11-DR-IP-1399 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1400 | B | 131242-WSD11-DR-IP-1400 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1401 | B | 131242-WSD11-DR-IP-1401 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1402 | B | 131242-WSD11-DR-IP-1402 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1403 | B | 131242-WSD11-DR-IP-1403 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1404 | B | 131242-WSD11-DR-IP-1404 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1405 | B | 131242-WSD11-DR-IP-1405 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1406 | B | 131242-WSD11-DR-IP-1406 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1407 | B | 131242-WSD11-DR-IP-1407 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1408 | B | 131242-WSD11-DR-IP-1408 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1409 | B | 131242-WSD11-DR-IP-1409 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1410 | B | 131242-WSD11-DR-IP-1410 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1411 | B | 131242-WSD11-DR-IP-1411 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1412 | B | 131242-WSD11-DR-IP-1412 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1413 | B | 131242-WSD11-DR-IP-1413 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1414 | B | 131242-WSD11-DR-IP-1414 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1415 | B | 131242-WSD11-DR-IP-1415 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1416 | B | 131242-WSD11-DR-IP-1416 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1417 | B | 131242-WSD11-DR-IP-1417 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1418 | B | 131242-WSD11-DR-IP-1418 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1419 | B | 131242-WSD11-DR-IP-1419 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1420 | B | 131242-WSD11-DR-IP-1420 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1421 | B | 131242-WSD11-DR-IP-1421 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1422 | B | 131242-WSD11-DR-IP-1422 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1423 | B | 131242-WSD11-DR-IP-1423 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1424 | B | 131242-WSD11-DR-IP-1424 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1425 | B | 131242-WSD11-DR-IP-1425 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1426 | B | 131242-WSD11-DR-IP-1426 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1427 | B | 131242-WSD11-DR-IP-1427 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1428 | B | 131242-WSD11-DR-IP-1428 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1429 | B | 131242-WSD11-DR-IP-1429 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1430 | B | 131242-WSD11-DR-IP-1430 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1431 | B | 131242-WSD11-DR-IP-1431 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1432 | B | 131242-WSD11-DR-IP-1432 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1433 | B | 131242-WSD11-DR-IP-1433 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1434 | B | 131242-WSD11-DR-IP-1434 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1435 | B | 131242-WSD11-DR-IP-1435 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1436 | B | 131242-WSD11-DR-IP-1436 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1437 | B | 131242-WSD11-DR-IP-1437 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1438 | B | 131242-WSD11-DR-IP-1438 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1439 | B | 131242-WSD11-DR-IP-1439 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1440 | B | 131242-WSD11-DR-IP-1440 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1441 | B | 131242-WSD11-DR-IP-1441 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1442 | B | 131242-WSD11-DR-IP-1442 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1443 | B | 131242-WSD11-DR-IP-1443 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1444 | B | 131242-WSD11-DR-IP-1444 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1445 | B | 131242-WSD11-DR-IP-1445 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1446 | B | 131242-WSD11-DR-IP-1446 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1447 | B | 131242-WSD11-DR-IP-1447 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1448 | B | 131242-WSD11-DR-IP-1448 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1449 | B | 131242-WSD11-DR-IP-1449 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1450 | B | 131242-WSD11-DR-IP-1450 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1451 | B | 131242-WSD11-DR-IP-1451 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1452 | B | 131242-WSD11-DR-IP-1452 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1453 | B | 131242-WSD11-DR-IP-1453 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1454 | B | 131242-WSD11-DR-IP-1454 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1455 | B | 131242-WSD11-DR-IP-1455 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1456 | B | 131242-WSD11-DR-IP-1456 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1457 | B | 131242-WSD11-DR-IP-1457 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1458 | B | 131242-WSD11-DR-IP-1458 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1459 | B | 131242-WSD11-DR-IP-1459 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1460 | B | 131242-WSD11-DR-IP-1460 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1461 | B | 131242-WSD11-DR-IP-1461 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1462 | B | 131242-WSD11-DR-IP-1462 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1463 | B | 131242-WSD11-DR-IP-1463 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1464 | B | 131242-WSD11-DR-IP-1464 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1465 | B | 131242-WSD11-DR-IP-1465 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1466 | B | 131242-WSD11-DR-IP-1466 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1467 | B | 131242-WSD11-DR-IP-1467 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1468 | B | 131242-WSD11-DR-IP-1468 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1469 | B | 131242-WSD11-DR-IP-1469 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1470 | B | 131242-WSD11-DR-IP-1470 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1151 | B | 131242-WSD11-DR-IP-1151 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1152 | B | 131242-WSD11-DR-IP-1152 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1153 | B | 131242-WSD11-DR-IP-1153 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1154 | B | 131242-WSD11-DR-IP-1154 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1155 | B | 131242-WSD11-DR-IP-1155 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1156 | B | 131242-WSD11-DR-IP-1156 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1157 | B | 131242-WSD11-DR-IP-1157 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1158 | B | 131242-WSD11-DR-IP-1158 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1159 | B | 131242-WSD11-DR-IP-1159 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1160 | B | 131242-WSD11-DR-IP-1160 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1161 | B | 131242-WSD11-DR-IP-1161 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1162 | B | 131242-WSD11-DR-IP-1162 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1163 | B | 131242-WSD11-DR-IP-1163 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1164 | B | 131242-WSD11-DR-IP-1164 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1165 | B | 131242-WSD11-DR-IP-1165 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1166 | B | 131242-WSD11-DR-IP-1166 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1167 | B | 131242-WSD11-DR-IP-1167 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1168 | B | 131242-WSD11-DR-IP-1168 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1169 | B | 131242-WSD11-DR-IP-1169 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1170 | B | 131242-WSD11-DR-IP-1170 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1171 | B | 131242-WSD11-DR-IP-1171 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1172 | B | 131242-WSD11-DR-IP-1172 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1173 | B | 131242-WSD11-DR-IP-1173 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1174 | B | 131242-WSD11-DR-IP-1174 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1175 | B | 131242-WSD11-DR-IP-1175 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1176 | B | 131242-WSD11-DR-IP-1176 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1177 | B | 131242-WSD11-DR-IP-1177 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1178 | B | 131242-WSD11-DR-IP-1178 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1179 | B | 131242-WSD11-DR-IP-1179 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1180 | B | 131242-WSD11-DR-IP-1180 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1181 | B | 131242-WSD11-DR-IP-1181 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1182 | B | 131242-WSD11-DR-IP-1182 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1183 | B | 131242-WSD11-DR-IP-1183 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1184 | B | 131242-WSD11-DR-IP-1184 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1185 | B | 131242-WSD11-DR-IP-1185 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1186 | B | 131242-WSD11-DR-IP-1186 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1187 | B | 131242-WSD11-DR-IP-1187 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1188 | B | 131242-WSD11-DR-IP-1188 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1189 | B | 131242-WSD11-DR-IP-1189 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1190 | B | 131242-WSD11-DR-IP-1190 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1191 | B | 131242-WSD11-DR-IP-1191 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1192 | B | 131242-WSD11-DR-IP-1192 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1193 | B | 131242-WSD11-DR-IP-1193 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1194 | B | 131242-WSD11-DR-IP-1194 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1195 | B | 131242-WSD11-DR-IP-1195 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1196 | B | 131242-WSD11-DR-IP-1196 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1197 | B | 131242-WSD11-DR-IP-1197 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1198 | B | 131242-WSD11-DR-IP-1198 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1199 | B | 131242-WSD11-DR-IP-1199 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1481 | B | 131242-WSD11-DR-IP-1481 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1482 | B | 131242-WSD11-DR-IP-1482 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1483 | B | 131242-WSD11-DR-IP-1483 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1484 | B | 131242-WSD11-DR-IP-1484 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1485 | B | 131242-WSD11-DR-IP-1485 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1486 | B | 131242-WSD11-DR-IP-1486 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1487 | B | 131242-WSD11-DR-IP-1487 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1488 | B | 131242-WSD11-DR-IP-1488 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1489 | B | 131242-WSD11-DR-IP-1489 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1490 | B | 131242-WSD11-DR-IP-1490 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1491 | B | 131242-WSD11-DR-IP-1491 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1492 | B | 131242-WSD11-DR-IP-1492 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1493 | B | 131242-WSD11-DR-IP-1493 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1494 | B | 131242-WSD11-DR-IP-1494 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1495 | B | 131242-WSD11-DR-IP-1495 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1496 | B | 131242-WSD11-DR-IP-1496 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1497 | B | 131242-WSD11-DR-IP-1497 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1498 | B | 131242-WSD11-DR-IP-1498 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1499 | B | 131242-WSD11-DR-IP-1499 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1500 | B | 131242-WSD11-DR-IP-1500 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1501 | B | 131242-WSD11-DR-IP-1501 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1502 | B | 131242-WSD11-DR-IP-1502 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1503 | B | 131242-WSD11-DR-IP-1503 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1504 | B | 131242-WSD11-DR-IP-1504 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1505 | B | 131242-WSD11-DR-IP-1505 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1506 | B | 131242-WSD11-DR-IP-1506 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1507 | B | 131242-WSD11-DR-IP-1507 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1508 | B | 131242-WSD11-DR-IP-1508 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1509 | B | 131242-WSD11-DR-IP-1509 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1510 | B | 131242-WSD11-DR-IP-1510 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1511 | B | 131242-WSD11-DR-IP-1511 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1512 | B | 131242-WSD11-DR-IP-1512 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1513 | B | 131242-WSD11-DR-IP-1513 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1514 | B | 131242-WSD11-DR-IP-1514 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1515 | B | 131242-WSD11-DR-IP-1515 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1516 | B | 131242-WSD11-DR-IP-1516 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1517 | B | 131242-WSD11-DR-IP-1517 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1518 | B | 131242-WSD11-DR-IP-1518 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1519 | B | 131242-WSD11-DR-IP-1519 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1520 | B | 131242-WSD11-DR-IP-1520 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1521 | B | 131242-WSD11-DR-IP-1521 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1522 | B | 131242-WSD11-DR-IP-1522 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1523 | B | 131242-WSD11-DR-IP-1523 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1524 | B | 131242-WSD11-DR-IP-1524 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1525 | B | 131242-WSD11-DR-IP-1525 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1526 | B | 131242-WSD11-DR-IP-1526 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1527 | B | 131242-WSD11-DR-IP-1527 | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | 14 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001382 | 2025-06-16 | 2025-08-13 | B | AWC | Approved with Comments | 2 | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | AWC
001383 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5201 | 0 | 131242-WSD11-DR-M-5201 | 2025-06-16 | GA for Bypass Control Valve 1 | NA | 2025-07-14 |  | 205 | Awaiting S.O.'s response | YES | 2025-08-01 | NO | Overdue | 0 |  |  | 001383 | 2025-06-16 | 2025-06-16 | 0 | PEN | Awaiting S.O.'s response | 1 | "GA for Bypass Control Valve 1" | PEN
001384 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5202 | 0 | 131242-WSD11-DR-M-5202 | 2025-06-16 | GA for Bypass Control Valve 2 | NA | 2025-07-14 |  | 205 | Awaiting S.O.'s response | YES | 2025-08-01 | NO | Overdue | 0 |  |  | 001384 | 2025-06-16 | 2025-06-16 | 0 | PEN | Awaiting S.O.'s response | 1 | "GA for Bypass Control Valve 2" | PEN
001385 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0089 | 0 | 131242-WSD11-QA-M-0089 | 2025-06-16 | FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report | NA | 2025-07-14 | 2025-09-08 | 60 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001385 | 2025-06-16 | 2025-06-16 | 0 | APP | Approved | 1 | "FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report" | APP
001386 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0088 | 0 | 131242-WSD11-QA-M-0088 | 2025-06-18 | FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch) | NA | 2025-07-16 | 2025-09-02 | 54 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001386 | 2025-06-18 | 2025-06-18 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch)" | AWC
001387 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | BS | 0009 | 0 | 131242-WSW41-QA-BS-0009 | 2025-06-18 | Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-16 | 2025-07-14 | 18 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001387 | 2025-06-18 | 2025-06-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation)" | AWC
001388 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0003 | 0 | 131242-WSD11-RT-S-0003 | 2025-06-18 | Project Safety Review Report for THP Installation | Approved | 2025-07-16 | 2025-08-25 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001388 | 2025-06-18 | 2025-06-18 | 0 | APP | Approved | 1 | "Project Safety Review Report for THP Installation" | APP
001389 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0090 | 0 | 131242-WSW41-QA-M-0090 | 2025-06-18 | FAT Report for Top Manway (900x900mm & 400x400mm) | NA | 2025-07-16 | 2025-09-02 | 54 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001389 | 2025-06-18 | 2025-06-18 | 0 | APP | Approved | 1 | "FAT Report for Top Manway (900x900mm & 400x400mm) " | APP
001390 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0014 | 0 | 131242-WST02-CD-I-0014 | 2025-06-18 | Electrical Signal List for SSN -MCC-1001A/1001B | Rev 0: Rejected. Refer to attached file for comments. | 2025-07-16 | 2025-07-16 | 20 | Rejected | YES | 2025-08-05 | NO | Resubmitted | 0 |  |  | 001390 | 2025-06-18 | 2025-06-18 | 0 | REJ | Rejected | 1 | "Electrical Signal List for SSN -MCC-1001A/1001B " | REJ
001391 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8002 | 0 | 131242-WST02-CL-BF-8002 | 2025-06-19 | Trust Block Calculation Report for Fire Hydrant | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-17 | 2025-06-30 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001391 | 2025-06-19 | 2025-07-11 | 0 | NAP | Approved with Comments | 2 | "Trust Block Calculation Report for Fire Hydrant " && "Thrust Block Calculation Report for Fire Hydrant " | AWC
001391 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8002 | 0 | 131242-WST02-CL-BF-8002 | 2025-07-11 | Thrust Block Calculation Report for Fire Hydrant | R1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-31 | 2025-12-29 | 121 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001391 | 2025-06-19 | 2025-07-11 | 0 | AWC | Approved with Comments | 2 | "Trust Block Calculation Report for Fire Hydrant " && "Thrust Block Calculation Report for Fire Hydrant " | AWC
001392 | 00 | Muthu | BIM | NA | 131242 | WSW41 | MS | IM | 0001 | 0 | 131242-WSW41-MS-IM-0001 | 2025-06-19 | Laser Scanning Method of Statement | NA | 2025-07-17 |  | 202 | Awaiting S.O.'s response | YES | 2025-08-06 | NO | Overdue | 0 |  |  | 001392 | 2025-06-19 | 2025-06-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Laser Scanning Method of Statement " | PEN
001393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0001 | 0 | 131242-WSD11-RT-EL-0001 | 2025-06-20 | THP Protected Corridor Lux Simulation Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-07-18 | 2025-08-11 | 36 | Approved with Comments | YES | 2025-08-29 | NO | Resubmitted | 0 |  |  | 001393 | 2025-06-20 | 2025-06-20 | 0 | AWC | Approved with Comments | 1 | "THP Protected Corridor Lux Simulation Report" | AWC
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5002_URA | A | 131242-WSD11-DR-A-5002_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001394 | 2025-06-23 | 2025-06-23 | A | NAP | Not Approved | 1 | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5003_URA | A | 131242-WSD11-DR-A-5003_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001394 | 2025-06-23 | 2025-06-23 | A | NAP | Not Approved | 1 | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5004_URA | A | 131242-WSD11-DR-A-5004_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001394 | 2025-06-23 | 2025-06-23 | A | NAP | Not Approved | 1 | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | 25 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | NAP
001395 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0022 | 0 | 131242-WST02-QA-EI-0022 | 2025-06-23 | Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-21 | 2025-07-14 | 15 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001395 | 2025-06-23 | 2025-06-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector" | AWC
001396 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0023 | 0 | 131242-WST02-QA-I-0023 | 2025-06-23 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-21 | 2025-07-14 | 15 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001396&&001891 | 2025-06-23 | 2025-12-09 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | AWC
001397 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | M | 0091 | 0 | 131242-WST02-QA-M-0091 | 2025-06-23 | FAT Report for Progressive Cavity Pumps (NETZSCH) | Rev 0: Approved | 2025-07-21 | 2025-07-23 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001397 | 2025-06-23 | 2025-06-23 | 0 | APP | Approved | 1 | "FAT Report for Progressive Cavity Pumps (NETZSCH)" | APP
001398 | 00 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 0 | 131242-WSW41-MS-BS-0001 | 2025-06-23 | MSRA, SWP for fire protection services | Approved | 2025-07-21 | 2025-08-06 | 32 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001398 | 2025-06-23 | 2026-02-13 | 2 | APP | Approved | 3 | "MSRA, SWP for fire protection services " | APP
001398 | 01 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 1 | 131242-WSW41-MS-BS-0001 | 2025-12-04 | MSRA, SWP for fire protection services | Approved | 2025-12-24 | 2025-12-17 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001398 | 2025-06-23 | 2026-02-13 | 2 | APP | Approved | 3 | "MSRA, SWP for fire protection services " | APP
001398 | 02 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 2 | 131242-WSW41-MS-BS-0001 | 2026-02-13 | MSRA, SWP for fire protection services | Approved | 2026-03-05 |  | 31 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 001398 | 2025-06-23 | 2026-02-13 | 2 | PEN | Approved | 3 | "MSRA, SWP for fire protection services " | APP
001399 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0033 | 0 | 131242-WSW41-MS-C-0033 | 2025-06-23 | MSRA SWP for Wet blasting Linabond Works | R0: Approved | 2025-07-21 | 2025-06-30 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001399 | 2025-06-23 | 2025-06-23 | 0 | APP | Approved | 1 | "MSRA SWP for Wet blasting Linabond Works" | APP
001400 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0047 | 0 | 131242-WSW41-MI-C-0047 | 2025-06-23 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | For information | 2025-07-21 | 2025-07-04 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001400 | 2025-06-23 | 2025-06-23 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | INF
001400 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0048 | 0 | 131242-WSW41-MI-C-0048 | 2025-06-23 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | For information | 2025-07-21 | 2025-07-04 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001400 | 2025-06-23 | 2025-06-23 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | INF
001401 | 00 | Jun | EICA | NA | 131242 | WSW41 | VI | E | 0025 | 0 | 131242-WSW41-VI-E-0025 | 2025-06-23 | Vendor Approval for Lighting and Small Power Material (Hong An) | Rev 0: Rejected. To resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-07-20 | 20 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001401 | 2025-06-23 | 2025-08-14 | 1 | REJ | Approved with Comments | 2 | "Vendor Approval for Lighting and Small Power Material (Hong An)" | AWC
001401 | 01 | Jun | EICA | NA | 131242 | WSW41 | VI | E | 0025 | 1 | 131242-WSW41-VI-E-0025 | 2025-08-14 | Vendor Approval for Lighting and Small Power Material (Hong An) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-03 | 2025-09-03 | 14 | Approved with Comments | YES | 2025-09-23 | NO | Resubmitted | 0 |  |  | 001401 | 2025-06-23 | 2025-08-14 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for Lighting and Small Power Material (Hong An)" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 0 | 131242-WST02-DR-BH-1002 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 0 | 131242-WST02-DR-BH-1003 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 0 | 131242-WST02-DR-BH-1004 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 0 | 131242-WST02-DR-BH-1005 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 0 | 131242-WST02-DR-BH-1006 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 0 | 131242-WST02-DR-BH-1007 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 0 | 131242-WST02-DR-BH-1008 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 0 | 131242-WST02-DR-BH-1009 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 0 | 131242-WST02-DR-BH-1010 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 0 | 131242-WST02-DR-BH-1011 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 0 | 131242-WST02-DR-BH-1012 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 0 | 131242-WST02-DR-BH-1013 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 0 | 131242-WST02-DR-BH-1014 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 0 | 131242-WST02-DR-BH-1015 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 0 | 131242-WST02-DR-BH-1016 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 0 | 131242-WST02-DR-BH-1017 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 0 | 131242-WST02-DR-BH-1018 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 0 | 131242-WST02-DR-BH-1019 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 0 | 131242-WST02-DR-BH-1020 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 0 | 131242-WST02-DR-BH-1022 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 0 | 131242-WST02-DR-BH-1023 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 0 | 131242-WST02-DR-BH-1024 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 0 | 131242-WST02-DR-BH-1021 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | NAP | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | AWC | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1025 | 1 | 131242-WST02-DR-BH-1025 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1026 | 1 | 131242-WST02-DR-BH-1026 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1027 | 1 | 131242-WST02-DR-BH-1027 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1028 | 1 | 131242-WST02-DR-BH-1028 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1029 | 1 | 131242-WST02-DR-BH-1029 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1030 | 1 | 131242-WST02-DR-BH-1030 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1031 | 1 | 131242-WST02-DR-BH-1031 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1032 | 1 | 131242-WST02-DR-BH-1032 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1033 | 1 | 131242-WST02-DR-BH-1033 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1034 | 1 | 131242-WST02-DR-BH-1034 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | 14 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | AWC | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-06-23 | 2026-02-04 | 1 | PEN | Approved with Comments | 4 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1025 | 1 | 131242-WST02-DR-BH-1025 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1026 | 1 | 131242-WST02-DR-BH-1026 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1027 | 1 | 131242-WST02-DR-BH-1027 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1028 | 1 | 131242-WST02-DR-BH-1028 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1029 | 1 | 131242-WST02-DR-BH-1029 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1030 | 1 | 131242-WST02-DR-BH-1030 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1031 | 1 | 131242-WST02-DR-BH-1031 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1032 | 1 | 131242-WST02-DR-BH-1032 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1033 | 1 | 131242-WST02-DR-BH-1033 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1034 | 1 | 131242-WST02-DR-BH-1034 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 35 |  |  | 001402 | 2025-11-21 | 2026-02-04 | 1 | PEN | Approved with Comments | 2 | "ACMV LCP GA & Wiring Drawing" | AWC
001403 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 0 | 131242-WST02-QA-M-0092 | 2025-06-23 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-08-01 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001403 | 2025-06-23 | 2026-01-08 | 3 | AWC | Approved | 4 | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | APP
001403 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 1 | 131242-WST02-QA-M-0092 | 2025-09-09 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-29 | 2025-11-10 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001403 | 2025-06-23 | 2026-01-08 | 3 | AWC | Approved | 4 | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | APP
001403 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 2 | 131242-WST02-QA-M-0092 | 2025-11-10 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-23 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001403 | 2025-06-23 | 2026-01-08 | 3 | AWC | Approved | 4 | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | APP
001403 | 03 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 3 | 131242-WST02-QA-M-0092 | 2026-01-08 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 3: Approved | 2026-01-28 | 2030-01-01 | 1038 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001403 | 2025-06-23 | 2026-01-08 | 3 | APP | Approved | 4 | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | APP
001404 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PO | M | 0023 | 0 | 131242-WSW41-PO-M-0023 | 2025-06-23 | Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB) | Rev 0: For Information | 2025-07-21 | 2025-07-31 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001404 | 2025-06-23 | 2025-06-23 | 0 | INF | For Information | 1 | "Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB)" | INF
001405 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PO | M | 0024 | 0 | 131242-WSW41-PO-M-0024 | 2025-06-23 | Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv) | Rev 0: For Information Only. | 2025-07-21 | 2025-11-24 | 110 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001405 | 2025-06-23 | 2025-06-23 | 0 | INF | For Information | 1 | "Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv)" | INF
001406 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0010 | 0 | 131242-WST02-DS-I-0010 | 2025-06-25 | Datasheet for Temperature Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-23 | 2025-10-06 | 73 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001406 | 2025-06-25 | 2025-06-25 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Temperature Transmitter" | AWC
001407 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0043 | 0 | 131242-WSD11-DS-M-0043 | 2025-06-25 | Steam Safety Relief Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-23 | 2025-07-08 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001407 | 2025-06-25 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Steam Safety Relief Valve Datasheet" | AWC
001407 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0043 | 1 | 131242-WSD11-DS-M-0043 | 2025-10-23 | Steam Safety Relief Valve Datasheet | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-12 | 2026-01-07 | 54 | Approved with Comments | YES | 2026-01-27 | NO | Resubmitted | 0 |  |  | 001407 | 2025-06-25 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Steam Safety Relief Valve Datasheet" | AWC
001408 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0044 | 0 | 131242-WSD11-DS-M-0044 | 2025-06-25 | Steam Strainer Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-23 | 2025-07-08 | 9 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001408 | 2025-06-25 | 2025-06-25 | 0 | AWC | Approved with Comments | 1 | "Steam Strainer Data Sheet" | AWC
001409 | 00 | Jun | EICA | NA | 131242 | WST02 | MS | E | 0015 | 0 | 131242-WST02-MS-E-0015 | 2025-06-26 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-24 | 2025-08-20 | 39 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001409 | 2025-06-26 | 2025-06-26 | 0 | AWC | Approved with Comments | 1 | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building" | AWC
001410 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5104 | A | 131242-WSD11-DR-I-5104 | 2025-06-26 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001410 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | NAP
001410 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5105 | A | 131242-WSD11-DR-I-5105 | 2025-06-26 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001410 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | NAP
001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5106 | A | 131242-WSD11-DR-I-5106 | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001411 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | NAP
001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5107 | A | 131242-WSD11-DR-I-5107 | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001411 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | NAP
001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5108 | A | 131242-WSD11-DR-I-5108 | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001411 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | NAP
001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5109 | A | 131242-WSD11-DR-I-5109 | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | 118 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001411 | 2025-06-26 | 2025-06-26 | A | NAP | Not Approved | 1 | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | NAP
001412 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PC | W | 0024 | 0 | 131242-WSW41-PC-W-0024 | 2025-06-27 | Payment Claim No.24 | Rev (0): Approved. Please refer to S.O. correspondence no. 366 dated 30 June 2025. | 2025-07-25 | 2025-07-08 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001412 | 2025-06-27 | 2025-06-27 | 0 | APP | Approved | 1 | " Payment Claim No.24" | APP
001413 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | S | 0001 | 0 | 131242-WSW41-QA-S-0001 | 2025-06-27 | ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission | For Information | 2025-07-25 | 2025-08-07 | 29 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001413 | 2025-06-27 | 2025-06-27 | 0 | INF | For Information | 1 | "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" | INF
001414 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0024 | 0 | 131242-WST02-QA-A-0024 | 2025-06-27 | Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-25 | 2025-07-04 | 5 | Approved with Comments | YES | 2025-07-24 | NO | Resubmitted | 0 |  |  | 001414 | 2025-06-27 | 2025-06-27 | 0 | AWC | Approved with Comments | 1 | "Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction)" | AWC
001415 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0023 | 0 | 131242-WST02-QA-A-0023 | 2025-06-27 | Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-25 | 2025-07-28 | 21 | Approved with Comments | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001415 | 2025-06-27 | 2025-06-27 | 0 | AWC | Approved with Comments | 1 | "Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd)" | AWC
001416 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0015 | 0 | 131242-WSW41-RT-C-0015 | 2025-06-27 | Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report | For Information. Please submit pile ecc report with licensed surveyor endorsement. | 2025-07-25 | 2025-07-14 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001416 | 2025-06-27 | 2025-06-27 | 0 | INF | For Information | 1 | "Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report " | INF
001417 | 00 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0003 | 0 | 131242-WST02-MS-M-0003 | 2025-06-28 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-08-11 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001417 | 2025-06-28 | 2025-08-29 | 1 | AWC | Approved with Comments | 2 | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | AWC
001417 | 01 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0003 | 1 | 131242-WST02-MS-M-0003 | 2025-08-29 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-18 | 2025-12-29 | 86 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001417 | 2025-06-28 | 2025-08-29 | 1 | AWC | Approved with Comments | 2 | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | AWC
001418 | 00 | Aaron | CSA | NA | NA | NA | NA | NA | NA | NA | NA-NA-NA-NA-NA | 2025-07-01 | Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement | R0: Not Approved. Please refer to comment sheet for submission. | 2025-07-29 | 2025-07-28 | 19 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001418&&002022&&002023&&002024 | 2025-07-01 | 2025-07-01 | NA | NAP | Not Approved | 4 | "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | NAP
001419 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0004 | 0 | 131242-WSD11-RT-S-0004 | 2025-07-01 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-16 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001419 | 2025-07-01 | 2025-09-03 | 1 | NAP | Not Approved | 2 | "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" | NAP
001419 | 01 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0004 | 1 | 131242-WSD11-RT-S-0004 | 2025-09-03 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | R1: Not Approved. Please refer to comment sheet for resubmission | 2025-09-23 | 2025-10-06 | 23 | Not Approved | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001419 | 2025-07-01 | 2025-09-03 | 1 | NAP | Not Approved | 2 | "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" | NAP
001420 | 00 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0012 | 1 | 131242-WSW41-RT-C-0012 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | 9 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000790&&001420 | 2024-10-30 | 2025-07-01 | 1 | AWC | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
001420 | 00 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0013 | 1 | 131242-WSW41-RT-C-0013 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | 9 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000852&&001420 | 2024-11-28 | 2025-07-01 | 1 | AWC | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on SSN RC Works" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
001420 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0003 | 0 | 131242-WST02-RT-S-0003 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | 9 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001420 | 2025-07-01 | 2025-07-01 | 0 | AWC | Approved with Comments | 1 | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
001420 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0005 | 0 | 131242-WSD11-RT-S-0005 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | 9 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001420 | 2025-07-01 | 2025-07-01 | 0 | AWC | Approved with Comments | 1 | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | AWC
001421 | 00 | Aaron | CSA | NA | WD | WSW41 | NA | NA | NA | NA | WD-WSW41-NA-NA-NA | 2025-07-01 | C4B ST621 (Site Wide Pipe Rack) - BCA WD | For information | 2025-07-29 | 2025-07-28 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001421 | 2025-07-01 | 2025-07-01 | NA | INF | For Information | 1 | "C4B ST621 (Site Wide Pipe Rack) - BCA WD" | INF
001422 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0094 | 0 | 131242-WSW41-QA-M-0094 | 2025-07-02 | FAT Report for Parabolic Screen | NA | 2025-07-30 | 2025-09-08 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001422 | 2025-07-02 | 2025-07-02 | 0 | APP | Approved | 1 | "FAT Report for Parabolic Screen" | APP
001423 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0093 | 0 | 131242-WSW41-QA-M-0093 | 2025-07-02 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch) | NA | 2025-07-30 | 2025-09-02 | 44 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001423 | 2025-07-02 | 2025-07-02 | 0 | APP | Approved | 1 | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch)" | APP
001424 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0010 | 0 | 131242-WST02-QA-BS-0010 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services) | R0: Approve with comments. Please refer to comment sheet for resubmission. | 2025-07-30 | 2025-08-19 | 34 | Approved with Comments | YES | 2025-09-08 | NO | Resubmitted | 0 |  |  | 001424 | 2025-07-02 | 2025-07-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | AWC
001425 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0011 | 0 | 131242-WST02-QA-BS-0011 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-30 | 2025-08-19 | 34 | Not Approved | YES | 2025-09-08 | NO | Resubmitted | 0 |  |  | 001425 | 2025-07-02 | 2025-07-02 | 0 | NAP | Not Approved | 1 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | NAP
001426 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | B | 1401 | 0 | 131242-WST02-DS-B-1401 | 2025-07-02 | Sample board Submission for PA Conduit ,Saddle,Junction box | For information | 2025-07-30 | 2025-08-19 | 34 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001426 | 2025-07-02 | 2025-07-02 | 0 | INF | For Information | 1 | "Sample board Submission for PA Conduit ,Saddle,Junction box" | INF
001427 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0024 | 0 | 131242-WST02-QA-I-0024 | 2025-07-02 | Vendor Manufacturing Inspection test plan for Pressure Gauges | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-07-14 | 8 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001427 | 2025-07-02 | 2025-07-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan for Pressure Gauges " | AWC
001428 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | BF | 0002 | 0 | 131242-WST02-VI-BF-0002 | 2025-07-02 | Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik | NA | 2025-07-30 |  | 193 | Awaiting S.O.'s response | YES | 2025-08-11 | NO | Overdue | 0 |  |  | 001428&&001431 | 2025-07-02 | 2025-07-03 | 0 | PEN | Awaiting S.O.'s response | 2 | "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" | PEN
001429 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0039 | 0 | 131242-WSW41-QA-C-0039 | 2025-07-02 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025 | For information | 2025-07-30 | 2025-07-17 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001429 | 2025-07-02 | 2025-07-02 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025" | INF
001430 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0006 | 0 | 131242-WSD11-CD-I-0006 | 2025-07-02 | THP RIO Panel 002A I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-10-24 | 82 | Approved with Comments | YES | 2025-11-13 | NO | Resubmitted | 0 |  |  | 001430 | 2025-07-02 | 2025-07-02 | 0 | AWC | Approved with Comments | 1 | "THP RIO Panel 002A I/O List" | AWC
001431 | 00 | Yuen Fatt | BS | NA | 131242 | WST02 | VI | BF | 0002 | 0 | 131242-WST02-VI-BF-0002 | 2025-07-03 | Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik | NA | 2025-07-31 |  | 192 | Awaiting S.O.'s response | YES | 2025-08-20 | NO | Overdue | 0 |  |  | 001428&&001431 | 2025-07-02 | 2025-07-03 | 0 | PEN | Awaiting S.O.'s response | 2 | "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" | PEN
001432 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0018 | 0 | 131242-WSW41-VI-E-0018 | 2025-07-04 | Vendor Approval for Distribution Boards (ZPA) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-01 | 2025-07-17 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001432 | 2025-07-04 | 2025-08-21 | 1 | NAP | Approved | 2 | "Vendor Approval for Distribution Boards (ZPA)" | APP
001432 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0018 | 1 | 131242-WSW41-VI-E-0018 | 2025-08-21 | Vendor Approval for Distribution Boards (ZPA) | Rev 1: Approved. | 2025-09-10 | 2025-10-01 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001432 | 2025-07-04 | 2025-08-21 | 1 | APP | Approved | 2 | "Vendor Approval for Distribution Boards (ZPA)" | APP
001433 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0031 | 0 | 131242-WSW41-SP-C-0031 | 2025-07-04 | Material Submission - Steel Structure Base Plate Grouting (Sanhe) | Approved | 2025-08-01 | 2025-07-17 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001433 | 2025-07-04 | 2025-07-04 | 0 | APP | Approved | 1 | "Material Submission - Steel Structure Base Plate Grouting (Sanhe)" | APP
001434 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0007 | 0 | 131242-WST02-VI-A-0007 | 2025-07-04 | VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD. | R0: Approved with comments. Pleas refer to comment sheet. | 2025-08-01 | 2025-07-14 | 6 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001434 | 2025-07-04 | 2025-07-04 | 0 | AWC | Approved with Comments | 1 | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." | AWC
001435 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0096 | 0 | 131242-WSW41-QA-M-0096 | 2025-07-05 | Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton) | NA | 2025-08-01 | 2025-09-08 | 45 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001435 | 2025-07-05 | 2025-07-05 | 0 | AWC | Approved with Comments | 1 | "Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton)" | AWC
001436 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0032 | 0 | 131242-WSW41-SP-C-0032 | 2025-07-05 | Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-01 | 2025-07-28 | 15 | Not Approved | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 001436&&001660 | 2025-07-05 | 2025-09-09 | 0 | NAP | Not Approved | 2 | "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" && "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" | NAP
001437 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0015 | 0 | 131242-WSW41-VI-E-0015 | 2025-07-07 | Vendor Approval for Distribution Boards (GSM) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-07-17 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001437 | 2025-07-07 | 2025-10-01 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval for Distribution Boards (GSM)" | AWC
001437 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0015 | 1 | 131242-WSW41-VI-E-0015 | 2025-10-01 | Vendor Approval for Distribution Boards (GSM) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2025-10-15 | 10 | Approved with Comments | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 001437 | 2025-07-07 | 2025-10-01 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for Distribution Boards (GSM)" | AWC
001438 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 0 | 131242-WSD11-VI-E-0017 | 2025-07-07 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 0: Rejected. To revise and submit. Refer to attached file for comments. | 2025-08-04 | 2025-09-02 | 41 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001438 | 2025-07-07 | 2026-02-24 | 2 | REJ | Not Approved | 3 | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | NAP
001438 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 1 | 131242-WSD11-VI-E-0017 | 2025-10-01 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 1: Not Approved. To revise and submit. Refer to attached file for comments. | 2025-10-21 | 2025-10-15 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001438 | 2025-07-07 | 2026-02-24 | 2 | NAP | Not Approved | 3 | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | NAP
001438 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 2 | 131242-WSD11-VI-E-0017 | 2026-02-24 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 1: Not Approved. To revise and submit. Refer to attached file for comments. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 001438 | 2025-07-07 | 2026-02-24 | 2 | PEN | Not Approved | 3 | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | NAP
001439 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0031 | 0 | 131242-WSW41-QA-EI-0031 | 2025-07-07 | FAT report for LVSG Panels (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-07-17 | 8 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001439 | 2025-07-07 | 2025-07-07 | 0 | AWC | Approved with Comments | 1 | "FAT report for LVSG Panels (Sunlight)" | AWC
001440 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 0 | 131242-WSD11-CD-I-0005 | 2025-07-07 | THP RIO Panel 0101 I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-08-06 | 22 | Approved with Comments | YES | 2025-08-26 | NO | Resubmitted | 0 |  |  | 001213&&001440 | 2025-04-09 | 2025-07-07 | 0 | AWC | Approved with Comments | 3 | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | AWC
001441 | 00 | Mohan | EICA | NA | 131242 | WST02 | QA | M | 0097 | 0 | 131242-WST02-QA-M-0097 | 2025-07-07 | FAT Report for SSN Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-08-01 | 19 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001441 | 2025-07-07 | 2025-07-07 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SSN Flow Control Valve (KSB)" | AWC
001442 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0008 | 0 | 131242-WSD11-CD-I-0008 | 2025-07-07 | THP RIO Panel 001A-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-07 | 66 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001442 | 2025-07-07 | 2025-07-07 | 0 | AWC | Approved with Comments | 1 | "THP RIO Panel 001A-I/O list" | AWC
001443 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0009 | 0 | 131242-WSD11-CD-I-0009 | 2025-07-07 | THP RIO Panel 001B-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-07 | 66 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001443 | 2025-07-07 | 2025-07-07 | 0 | AWC | Approved with Comments | 1 | "THP RIO Panel 001B-I/O list" | AWC
001444 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0007 | 0 | 131242-WSD11-CD-I-0007 | 2025-07-07 | THP RIO Panel 002B-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-24 | 79 | Approved with Comments | YES | 2025-11-13 | NO | Resubmitted | 0 |  |  | 001444 | 2025-07-07 | 2025-07-07 | 0 | AWC | Approved with Comments | 1 | "THP RIO Panel 002B-I/O list" | AWC
001445 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5024 | A | 131242-WSD11-DR-M-5024 | 2025-07-07 | GA for G2D Booster Pump | NA | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 0 |  |  | 001445 | 2025-07-07 | 2025-07-07 | A | PEN | Awaiting S.O.'s response | 1 | "GA for G2D Booster Pump" | PEN
001446 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0025 | 0 | 131242-WSW41-QA-I-0025 | 2025-07-08 | Vendor Manufacturing Inspection Test Plan for pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-08-05 | 2025-12-09 | 110 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001446 | 2025-07-08 | 2025-07-08 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for pH Analyser" | AWC
001447 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0026 | 0 | 131242-WSW41-QA-I-0026 | 2025-07-08 | Factory Acceptance Test Report for pH Analyser | Contractor requests to reject, email attached. | 2025-08-05 | 2025-07-11 | 3 | Rejected | YES | 2025-07-31 | NO | Resubmitted | 0 |  |  | 001447 | 2025-07-08 | 2025-07-08 | 0 | REJ | Rejected | 1 | "Factory Acceptance Test Report for pH Analyser" | REJ
001448 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0033 | 0 | 131242-WSW41-QA-EI-0033 | 2025-07-08 | FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-17 | 7 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001448 | 2025-07-08 | 2025-07-08 | 0 | AWC | Approved with Comments | 1 | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" | AWC
001449 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0034 | 0 | 131242-WSW41-QA-E-0034 | 2025-07-08 | Site Acceptance Test Procedure for 22KV HV Cable | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-23 | 11 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001449 | 2025-07-08 | 2025-07-08 | 0 | AWC | Approved with Comments | 1 | "Site Acceptance Test Procedure for 22KV HV Cable" | AWC
001450 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0035 | 0 | 131242-WSW41-QA-E-0035 | 2025-07-08 | Inspection and Test Plan for Cable Laying, Installation, Testing and Termination | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-23 | 11 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001450 | 2025-07-08 | 2025-07-08 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " | AWC
001451 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0098 | 0 | 131242-WSW41-QA-M-0098 | 2025-07-08 | FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite) | NA | 2025-08-05 | 2025-09-02 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001451 | 2025-07-08 | 2025-07-08 | 0 | APP | Approved | 1 | "FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite)" | APP
001452 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0061 | 0 | 131242-WST02-CD-IM-0061 | 2025-07-08 | VCM Submission for 2025-06 | For Information. Please refer to the comment sheet. | 2025-08-05 | 2025-07-30 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001452 | 2025-07-08 | 2025-07-08 | 0 | INF | For Information | 1 | "VCM Submission for 2025-06" | INF
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1551 | C | 131242-WST02-DR-IP-1551 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1552 | C | 131242-WST02-DR-IP-1552 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1553 | C | 131242-WST02-DR-IP-1553 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1554 | C | 131242-WST02-DR-IP-1554 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1555 | C | 131242-WST02-DR-IP-1555 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1556 | C | 131242-WST02-DR-IP-1556 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1557 | C | 131242-WST02-DR-IP-1557 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1558 | C | 131242-WST02-DR-IP-1558 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1559 | C | 131242-WST02-DR-IP-1559 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1560 | C | 131242-WST02-DR-IP-1560 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1561 | C | 131242-WST02-DR-IP-1561 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1562 | C | 131242-WST02-DR-IP-1562 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1563 | C | 131242-WST02-DR-IP-1563 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1564 | C | 131242-WST02-DR-IP-1564 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1565 | C | 131242-WST02-DR-IP-1565 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1566 | C | 131242-WST02-DR-IP-1566 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1567 | C | 131242-WST02-DR-IP-1567 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1568 | C | 131242-WST02-DR-IP-1568 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1569 | C | 131242-WST02-DR-IP-1569 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1570 | C | 131242-WST02-DR-IP-1570 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1571 | C | 131242-WST02-DR-IP-1571 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1572 | C | 131242-WST02-DR-IP-1572 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1573 | C | 131242-WST02-DR-IP-1573 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1574 | C | 131242-WST02-DR-IP-1574 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1575 | C | 131242-WST02-DR-IP-1575 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1576 | C | 131242-WST02-DR-IP-1576 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1577 | C | 131242-WST02-DR-IP-1577 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1578 | C | 131242-WST02-DR-IP-1578 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1579 | C | 131242-WST02-DR-IP-1579 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1580 | C | 131242-WST02-DR-IP-1580 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1581 | C | 131242-WST02-DR-IP-1581 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1582 | C | 131242-WST02-DR-IP-1582 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1583 | C | 131242-WST02-DR-IP-1583 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1584 | C | 131242-WST02-DR-IP-1584 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1585 | C | 131242-WST02-DR-IP-1585 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1586 | C | 131242-WST02-DR-IP-1586 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1587 | C | 131242-WST02-DR-IP-1587 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1588 | C | 131242-WST02-DR-IP-1588 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1589 | C | 131242-WST02-DR-IP-1589 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1590 | C | 131242-WST02-DR-IP-1590 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1591 | C | 131242-WST02-DR-IP-1591 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1592 | C | 131242-WST02-DR-IP-1592 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1593 | C | 131242-WST02-DR-IP-1593 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1594 | C | 131242-WST02-DR-IP-1594 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1595 | C | 131242-WST02-DR-IP-1595 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1596 | C | 131242-WST02-DR-IP-1596 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1597 | C | 131242-WST02-DR-IP-1597 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1598 | C | 131242-WST02-DR-IP-1598 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1599 | C | 131242-WST02-DR-IP-1599 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1600 | C | 131242-WST02-DR-IP-1600 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1601 | C | 131242-WST02-DR-IP-1601 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1602 | C | 131242-WST02-DR-IP-1602 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1603 | C | 131242-WST02-DR-IP-1603 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1604 | C | 131242-WST02-DR-IP-1604 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1605 | C | 131242-WST02-DR-IP-1605 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1606 | C | 131242-WST02-DR-IP-1606 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1607 | C | 131242-WST02-DR-IP-1607 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1608 | C | 131242-WST02-DR-IP-1608 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1609 | C | 131242-WST02-DR-IP-1609 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1610 | C | 131242-WST02-DR-IP-1610 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1611 | C | 131242-WST02-DR-IP-1611 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1612 | C | 131242-WST02-DR-IP-1612 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1613 | C | 131242-WST02-DR-IP-1613 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1614 | C | 131242-WST02-DR-IP-1614 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1615 | C | 131242-WST02-DR-IP-1615 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1616 | C | 131242-WST02-DR-IP-1616 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1617 | C | 131242-WST02-DR-IP-1617 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1618 | C | 131242-WST02-DR-IP-1618 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1619 | C | 131242-WST02-DR-IP-1619 | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | 89 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001453 | 2025-07-08 | 2025-07-08 | C | AWC | Approved with Comments | 1 | "SSN RIO - 203 GA & Wiring Diagram" | AWC
001454 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0040 | 0 | 131242-WSW41-QA-C-0040 | 2025-07-09 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-06 | 2025-08-07 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001454 | 2025-07-09 | 2025-08-18 | 1 | NAP | Approved with Comments | 2 | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " | AWC
001454 | 01 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0040 | 1 | 131242-WSW41-QA-C-0040 | 2025-08-18 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | R1: Approved with comments. Please refer to comment sheet for resubmission | 2025-09-05 | 2025-10-13 | 40 | Approved with Comments | YES | 2025-10-31 | NO | Resubmitted | 0 |  |  | 001454 | 2025-07-09 | 2025-08-18 | 1 | AWC | Approved with Comments | 2 | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " | AWC
001455 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0019 | 0 | 131242-WSD11-VI-E-0019 | 2025-07-09 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-06 | 2025-09-02 | 39 | Not Approved | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001455 | 2025-07-09 | 2025-07-09 | 0 | NAP | Not Approved | 1 | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA)" | NAP
001456 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0045 | 0 | 131242-WSD11-QA-M-0045 | 2025-07-10 | Steam Motorized Valve Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-07 | 2025-09-04 | 40 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001456 | 2025-07-10 | 2025-07-10 | 0 | AWC | Approved with Comments | 1 | " Steam Motorized Valve Data Sheet" | AWC
001457 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0099 | 0 | 131242-WSD11-QA-M-0099 | 2025-07-10 | FAT Report for THP Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-07 | 2025-08-01 | 16 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001457 | 2025-07-10 | 2025-07-10 | 0 | AWC | Approved with Comments | 1 | " FAT Report for THP Flow Control Valve (KSB)" | AWC
001458 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600 | 2025-07-11 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-08-01 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | NAP | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001458 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5602 | A | 131242-WST02-SD-S-5602 | 2025-07-11 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-08-01 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458&&001589 | 2025-07-11 | 2025-08-13 | A | NAP | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | AWC
001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.3 | 131242-WST02-SD-S-8600 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | NAP | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3001 | A.3 | 131242-WST02-SD-S-3001 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | NAP | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1002 | A.3 | 131242-WST02-SD-S-1002 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | NAP | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1003 | A.3 | 131242-WST02-SD-S-1003 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | NAP | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.5 | 131242-WST02-SD-S-8600 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | 4 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | AWC | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3001 | A.5 | 131242-WST02-SD-S-3001 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | 4 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | AWC | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1002 | A.5 | 131242-WST02-SD-S-1002 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | 4 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | AWC | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1003 | A.5 | 131242-WST02-SD-S-1003 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | 4 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 001458 | 2025-08-13 | 2025-08-22 | A.5 | AWC | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" | AWC
001459 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | ST610 | NA | 131242-WST02-DR-C-ST610 | 2025-07-10 | Valve Chamber Design for SSN- Portable Water Line | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-09-17 | 49 | Not Approved | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 001459 | 2025-07-10 | 2025-11-28 | NA | NAP | Approved with Comments | 2 | "Valve Chamber Design for SSN- Portable Water Line" | AWC
001459 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | C | ST610 | NA | 131242-WST02-DR-C-ST610 | 2025-11-28 | Valve Chamber Design for SSN- Portable Water Line | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-18 | 2026-01-15 | 34 | Approved with Comments | YES | 2026-02-04 | NO | Resubmitted | 52 |  |  | 001459 | 2025-07-10 | 2025-11-28 | NA | AWC | Approved with Comments | 2 | "Valve Chamber Design for SSN- Portable Water Line" | AWC
001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611 | A | 131242-WST02-DR-S-5600_ST611 | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | INF | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611 | A | 131242-WST02-DR-S-1601_ST611 | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | INF | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611 | A | 131242-WST02-DR-S-5601_ST611 | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | INF | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611 | A | 131242-WST02-DR-S-1600_ST611 | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | INF | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001461 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0041 | 0 | 131242-WSW41-QA-C-0041 | 2025-07-11 | Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025 | For Information | 2025-08-08 | 2025-08-05 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001461 | 2025-07-11 | 2025-07-11 | 0 | INF | For Information | 1 | "Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025" | INF
001462 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | ST607 | - | 131242-WST02-DR-S-ST607 | 2025-07-11 | Updated Drawings ST607 - SSN Water Tank | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-10-23 | 74 | Not Approved | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001462 | 2025-07-11 | 2025-07-11 | - | NAP | Not Approved | 1 | " Updated Drawings ST607 - SSN Water Tank" | NAP
001463 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0027 | 0 | 131242-WST02-QA-I-0027 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for Conductive Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-08-15 | 25 | Approved with Comments | YES | 2025-09-04 | NO | Resubmitted | 0 |  |  | 001463&&001476 | 2025-07-11 | 2025-07-14 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" && "Factory Acceptance Test Report for Pressure Gauges" | AWC
001464 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0100 | 0 | 131242-WST02-QA-M-0100 | 2025-07-11 | FAT Report for EQ Tank Transfer Pumps (KSB) | Rev 0: Approved | 2025-08-08 | 2025-08-11 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001464 | 2025-07-11 | 2025-07-11 | 0 | APP | Approved | 1 | " FAT Report for EQ Tank Transfer Pumps (KSB)" | APP
001465 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0029 | 0 | 131242-WST02-QA-I-0029 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-08-08 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001465 | 2025-07-11 | 2025-07-11 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | AWC
001466 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0026 | 0 | 131242-WST02-QA-I-0026 | 2025-07-11 | Factory Acceptance Test Report for Conductivity Analyser | NA | 2025-08-08 | 2025-08-26 | 32 | Approved with Comments | YES | 2025-09-15 | NO | Resubmitted | 0 |  |  | 001466 | 2025-07-11 | 2025-07-11 | 0 | AWC | Approved with Comments | 1 | " Factory Acceptance Test Report for Conductivity Analyser" | AWC
001467 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | CD | I | 0015 | 0 | 131242-WST02-CD-I-0015 | 2025-07-11 | Electrical Signal List for SSN -MCC-0102A/0102B | Rev 0: Rejected. Refer to attached file for comments. | 2025-08-08 | 2025-07-16 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001467 | 2025-07-11 | 2025-07-11 | 0 | REJ | Rejected | 1 | "Electrical Signal List for SSN -MCC-0102A/0102B " | REJ
001467 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | CD | I | 0001 | 1 | 131242-WSW41-CD-I-0001 | 2025-07-25 | Electrical Signal List for SSN -MCC-0102A/0102B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. Please update and amend the Prolog document title to "Electrical Signal List for MCC-TYPICAL". | 2025-08-14 | 2025-10-01 | 48 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 7 |  |  | 001350&&001467 | 2025-06-10 | 2025-07-25 | 1 | AWC | Approved with Comments | 2 | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " | AWC
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7213 | A | 131242-WST02-DR-IP-7213 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7214 | A | 131242-WST02-DR-IP-7214 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7215 | A | 131242-WST02-DR-IP-7215 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7210 | A | 131242-WST02-DR-IP-7210 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7211 | A | 131242-WST02-DR-IP-7211 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7212 | A | 131242-WST02-DR-IP-7212 | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | 107 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001468 | 2025-07-11 | 2025-07-11 | A | NAP | Not Approved | 1 | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | NAP
001469 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0030 | 0 | 131242-WST02-QA-I-0030 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-08-15 | 25 | Approved with Comments | YES | 2025-09-04 | NO | Resubmitted | 0 |  |  | 001469 | 2025-07-11 | 2025-07-11 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical" | AWC
001470 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1016 | 0 | 131242-WSW41-VI-M-1016 | 2025-07-11 | Preliminary design and Vendor Approval for Strainer (Spirax) | Approved | 2025-08-08 | 2025-08-01 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001470 | 2025-07-11 | 2025-07-11 | 0 | APP | Approved | 1 | " Preliminary design and Vendor Approval for Strainer (Spirax)" | APP
001471 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0026 | 0 | 131242-WSW41-RT-PM-0026 | 2025-07-12 | C4B Monthly Progress Report Number No.26 (06 25) | Approved with comments which will be addressed in the next MPR submission. | 2025-08-08 | 2025-08-04 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001471 | 2025-07-12 | 2025-07-12 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.26 (06 25)" | AWC
001472 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0031 | 0 | 131242-WST02-QA-I-0031 | 2025-07-14 | Vendor Manufacturing Inspection Test Plan for Temperature Transmitters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-06 | 60 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001472 | 2025-07-14 | 2025-07-14 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Temperature Transmitters" | AWC
001473 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5025 | A | 131242-WSD11-DR-M-5025 | 2025-07-14 | GA for G1 Booster Pump | NA | 2025-08-11 |  | 185 | Awaiting S.O.'s response | YES | 2025-08-29 | NO | Overdue | 0 |  |  | 001473 | 2025-07-14 | 2025-07-14 | A | PEN | Awaiting S.O.'s response | 1 | "GA for G1 Booster Pump" | PEN
001474 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0033 | 0 | 131242-WST02-QA-I-0033 | 2025-07-14 | Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-06 | 60 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001474 | 2025-07-14 | 2025-07-14 | 0 | AWC | Approved with Comments | 1 | " Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter" | AWC
001475 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0034 | 0 | 131242-WST02-QA-I-0034 | 2025-07-14 | Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-12-09 | 106 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001475 | 2025-07-14 | 2025-07-14 | 0 | AWC | Approved with Comments | 1 | " Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter" | AWC
001476 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0027 | 0 | 131242-WST02-QA-I-0027 | 2025-07-14 | Factory Acceptance Test Report for Pressure Gauges | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-15 | 67 | Approved with Comments | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 001463&&001476 | 2025-07-11 | 2025-07-14 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" && "Factory Acceptance Test Report for Pressure Gauges" | AWC
001477 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0062 | 0 | 131242-WSW41-LT-PM-0062 | 2025-07-15 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building | Rev (0): Rejected. Please refer to S.O. correspondence no. 386 dated 13 Aug 2025. | 2025-08-12 | 2025-08-22 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001477 | 2025-07-15 | 2025-07-15 | 0 | REJ | Rejected | 1 | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building" | REJ
001478 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0035 | 0 | 131242-WST02-QA-I-0035 | 2025-07-16 | Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-12-10 | 105 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001478 | 2025-07-16 | 2025-07-16 | 0 | AWC | Approved with Comments | 1 | " Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector" | AWC
001479 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0036 | 0 | 131242-WST02-QA-I-0036 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-10-24 | 72 | Approved with Comments | YES | 2025-11-13 | NO | Resubmitted | 0 |  |  | 001479&&001480 | 2025-07-16 | 2025-07-16 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | AWC
001480 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0036 | 0 | 131242-WST02-QA-I-0036 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | Rev 0: Rejected. No resubmission required. | 2025-08-13 | 2025-12-09 | 104 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001479&&001480 | 2025-07-16 | 2025-07-16 | 0 | REJ | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | AWC
001481 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0032 | 0 | 131242-WST02-QA-I-0032 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-11-05 | 80 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001481&&001554 | 2025-07-16 | 2025-08-04 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" && "SAT Procedure for LVSG Panels (Sunlight)" | AWC
001482 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5130 | C | 131242-WSD11-SD-S-5130 | 2025-07-16 | Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-12 | 19 | Not Approved | YES | 2025-09-01 | NO | Resubmitted | 0 |  | QPD design drawing | 001482 | 2025-07-16 | 2025-07-16 | C | NAP | Not Approved | 1 | "Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing" | NAP
001483 | 00 | Aaron | CSA | NA | Mock up Drawing | NA | NA | NA | NA | NA | Mock up Drawing-NA-NA-NA-NA | 2025-07-16 | Aluminum Railing (Mock-up) Drawing | Rev 0: Approved with comments. Please refer comment sheet for resubmission. | 2025-08-13 | 2025-08-14 | 21 | Approved with Comments | YES | 2025-09-03 | NO | Resubmitted | 0 |  |  | 001483 | 2025-07-16 | 2025-07-16 | NA | AWC | Approved with Comments | 1 | "Aluminum Railing (Mock-up) Drawing" | AWC
001484 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0039 | 0 | 131242-WST02-QA-I-0039 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-10-23 | 71 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001484 | 2025-07-16 | 2025-07-16 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN)" | AWC
001485 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0024 | 0 | 131242-WSW41-PS-HS-0024 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Mar 2025 | NA | 2025-08-14 | 2025-09-11 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001485 | 2025-07-17 | 2025-07-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for Mar 2025" | APP
001486 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0025 | 0 | 131242-WSW41-PS-HS-0025 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Apr 2025 | NA | 2025-08-14 | 2025-09-11 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001486 | 2025-07-17 | 2025-07-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for Apr 2025" | APP
001487 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0026 | 0 | 131242-WSW41-PS-HS-0026 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for May 2025 | NA | 2025-08-14 | 2025-09-11 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001487 | 2025-07-17 | 2025-07-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for May 2025" | APP
001488 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0027 | 0 | 131242-WSW41-PS-HS-0027 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Jun 2025 | NA | 2025-08-14 | 2025-09-11 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001488 | 2025-07-17 | 2025-07-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for Jun 2025" | APP
001489 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0037 | 0 | 131242-WST02-QA-I-0037 | 2025-07-21 | Factory Acceptance Test Report for Auto Sampler | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-10-24 | 69 | Approved with Comments | YES | 2025-11-13 | NO | Resubmitted | 0 |  |  | 001489 | 2025-07-21 | 2025-07-21 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Auto Sampler" | AWC
001490 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0038 | 0 | 131242-WST02-QA-I-0038 | 2025-07-21 | Factory Acceptance Test Report for TSS Analyser - Optical | NA | 2025-08-18 | 2025-08-26 | 26 | Approved with Comments | YES | 2025-09-15 | NO | Resubmitted | 0 |  |  | 001490 | 2025-07-21 | 2025-07-21 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for TSS Analyser - Optical" | AWC
001491 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0040 | 0 | 131242-WSW41-QA-I-0040 | 2025-07-21 | Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand | Rev 0: Accepted for Information. No resubmission required. | 2025-08-18 | 2025-12-09 | 101 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001491 | 2025-07-21 | 2025-07-21 | 0 | INF | For Information | 1 | "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" | INF
001492 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0036 | 0 | 131242-WST02-QA-E-0036 | 2025-07-21 | Inspection Test Plan for Transformer | Approved | 2025-08-18 | 2025-08-01 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001492 | 2025-07-21 | 2025-07-21 | 0 | APP | Approved | 1 | "Inspection Test Plan for Transformer" | APP
001493 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0101 | 0 | 131242-WSD11-QA-M-0101 | 2025-07-21 | FAT Report for Desuperheater (Cambi) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-08-18 | 2025-11-23 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001493 | 2025-07-21 | 2025-07-21 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Desuperheater (Cambi)" | AWC
001494 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0037 | 0 | 131242-WST02-QA-E-0037 | 2025-07-21 | Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) | Approved | 2025-08-18 | 2025-08-01 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001494 | 2025-07-21 | 2025-07-21 | 0 | APP | Approved | 1 | "Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) " | APP
001495 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0102 | 0 | 131242-WSD11-QA-M-0102 | 2025-07-21 | Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line | NA | 2025-08-18 | 2025-09-08 | 35 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001495 | 2025-07-21 | 2025-07-21 | 0 | AWC | Approved with Comments | 1 | "Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line" | AWC
001496 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0014 | 0 | 131242-WST02-DS-I-0014 | 2025-07-22 | Datasheet for Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-19 | 2025-08-15 | 18 | Approved with Comments | YES | 2025-09-04 | NO | Resubmitted | 0 |  |  | 001496 | 2025-07-22 | 2025-07-22 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Conductivity Analyser" | AWC
001497 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1018 | 0 | 131242-WSW41-VI-M-1018 | 2025-07-22 | Preliminary design and Vendor Approval - Strainer (Asahi, Agru) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-08-19 | 2025-08-01 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001497 | 2025-07-22 | 2025-07-22 | 0 | AWC | Approved with Comments | 1 | "Preliminary design and Vendor Approval - Strainer (Asahi, Agru)" | AWC
001498 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | B | 131242-WST02-SD-S-5003 | 2025-07-22 | ST617 THP-PF-02 Shop Drawing Submission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-12-10 | 101 | Not Approved | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001498&&001698&&001803 | 2025-07-22 | 2026-02-09 | A.5 | NAP | Not Approved | 3 | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001499 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | A | 0008 | 0 | 131242-WST02-MS-A-0008 | 2025-07-22 | MSRA, SWP for Waterproofing Works (Electrical Building Roof) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-01 | 8 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001499 | 2025-07-22 | 2025-07-22 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Waterproofing Works (Electrical Building Roof)" | AWC
001500 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0010 | 0 | 131242-WSW41-PO-E-0010 | 2025-07-22 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001500 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" | REJ
001500 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0001 | 0 | 131242-WSW41-PO-I-0001 | 2025-08-01 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | For Information | 2025-08-29 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001500 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" | INF
001501 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0011 | 0 | 131242-WSW41-PO-E-0011 | 2025-07-22 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Disciplin | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001501 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | REJ
001501 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0002 | 0 | 131242-WSW41-PO-I-0002 | 2025-08-22 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | Accepted for information | 2025-09-11 | 2025-12-05 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001501 | 2025-08-22 | 2025-08-22 | 0 | INF | For Information | 1 | "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | INF
001502 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0012 | 0 | 131242-WSW41-PO-E-0012 | 2025-07-22 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001502 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | REJ
001502 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0003 | 0 | 131242-WSW41-PO-I-0003 | 2025-08-01 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001502 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | INF
001503 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0013 | 0 | 131242-WSW41-PO-E-0013 | 2025-07-22 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001503 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" | REJ
001503 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0004 | 0 | 131242-WSW41-PO-I-0004 | 2025-08-01 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001503 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" | INF
001504 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0014 | 0 | 131242-WSW41-PO-E-0014 | 2025-07-22 | Unpriced PO for Capacitive Level Switch (IFM) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001504 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Capacitive Level Switch (IFM)" | REJ
001504 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0005 | 0 | 131242-WSW41-PO-I-0005 | 2025-08-01 | Unpriced PO for Capacitive Level Switch (IFM) | Rev 0: Accepted for Information. | 2025-08-21 | 2025-12-05 | 90 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001504 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Capacitive Level Switch (IFM)" | INF
001505 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0015 | 0 | 131242-WSW41-PO-E-0015 | 2025-07-22 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001505 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | REJ
001505 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0006 | 0 | 131242-WSW41-PO-I-0006 | 2025-08-01 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001505 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | INF
001506 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0016 | 0 | 131242-WSW41-PO-E-0016 | 2025-07-22 | Unpriced PO for Pressure Gauge (Baumer) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001506 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Pressure Gauge (Baumer) " | REJ
001506 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0007 | 0 | 131242-WSW41-PO-I-0007 | 2025-08-01 | Unpriced PO for Pressure Gauge (Baumer) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001506 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Pressure Gauge (Baumer) " | INF
001507 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0017 | 0 | 131242-WSW41-PO-E-0017 | 2025-07-22 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001507 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | REJ
001507 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0008 | 0 | 131242-WSW41-PO-I-0008 | 2025-08-01 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001507 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | INF
001508 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0018_Superceded | 0 | 131242-WSW41-PO-E-0018_Superceded | 2025-07-22 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001508 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | REJ
001508 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0009 | 0 | 131242-WSW41-PO-I-0009 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001508 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | INF
001509 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0019 | 0 | 131242-WSW41-PO-E-0019 | 2025-07-22 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001509 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Pressure Transmitter (Emerson)" | REJ
001509 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0010 | 0 | 131242-WSW41-PO-I-0010 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Emerson) | For Information | 2025-08-21 | 2025-08-11 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001509 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Pressure Transmitter (Emerson)" | INF
001510 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0020 | 0 | 131242-WSW41-PO-E-0020 | 2025-07-22 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001510 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Pressure Transmitter (Emerson)" | REJ
001510 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0011 | 0 | 131242-WSW41-PO-I-0011 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 1: Not Approved. Wrong PO reference. To revise and resubmit. | 2025-08-21 | 2025-12-15 | 96 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001510 | 2025-08-01 | 2025-08-01 | 0 | NAP | Not Approved | 1 | "Unpriced PO for Pressure Transmitter (Emerson)" | NAP
001511 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0021 | 0 | 131242-WSW41-PO-E-0021 | 2025-07-22 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | 7 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001511 | 2025-07-22 | 2025-07-22 | 0 | REJ | Rejected | 1 | "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | REJ
001511 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0012 | 1 | 131242-WSW41-PO-I-0012 | 2025-08-01 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-05 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001511 | 2025-08-01 | 2025-08-01 | 1 | INF | For Information | 1 | "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | INF
001512 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0001 | 0 | 131242-WSW41-PO-M-0001 | 2025-07-22 | Unpriced PO for Knife Gate Valve (Jash Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001512 | 2025-07-22 | 2025-07-22 | 0 | INF | For Information | 1 | "Unpriced PO for Knife Gate Valve (Jash Engineering)" | INF
001513 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0002 | 0 | 131242-WSW41-PO-M-0002 | 2025-07-22 | Unpriced PO for Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-04 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001513 | 2025-07-22 | 2025-07-22 | 0 | INF | For Information | 1 | "Unpriced PO for Ball Valve (OVS Engineering)" | INF
001514 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0003 | 0 | 131242-WSW41-PO-M-0003 | 2025-07-22 | Unpriced PO for Non-return Check Valve (Breen International) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001514 | 2025-07-22 | 2025-07-22 | 0 | INF | For Information | 1 | "Unpriced PO for Non-return Check Valve (Breen International)" | INF
001515 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0004 | 0 | 131242-WSW41-PO-M-0004 | 2025-07-22 | Unpriced PO for Metallic Butterfly Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001515 | 2025-07-22 | 2025-07-22 | 0 | INF | For Information | 1 | "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | INF
001516 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-M-0005 | 2025-07-22 | Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000548&&001516 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for Sludge Pump (Netzsch) " && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" | INF
001517 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-M-0006 | 2025-07-22 | Unpriced PO for SS Auto Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000549&&001517 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for cPVC Pipes (George Fischer)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" | INF
001518 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0025 | 0 | 131242-WSW41-PO-M-0025 | 2025-07-22 | Unpriced PO for Manual Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | 89 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001518 | 2025-07-22 | 2025-07-22 | 0 | INF | For Information | 1 | "Unpriced PO for Manual Ball Valve (OVS Engineering) " | INF
001519 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1005 | 0 | 131242-WSW41-SH-M-1005 | 2025-07-22 | Piping Valve List & Datasheet – Plastic Valve (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-19 | 2025-09-04 | 32 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001519 | 2025-07-22 | 2025-07-22 | 0 | AWC | Approved with Comments | 1 | "Piping Valve List & Datasheet – Plastic Valve (GF)" | AWC
001520 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0041 | 0 | 131242-WST02-QA-I-0041 | 2025-07-22 | Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-19 | 2025-12-09 | 100 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001520 | 2025-07-22 | 2025-07-22 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN)" | AWC
001521 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0038 | 0 | 131242-WST02-QA-E-0038 | 2025-07-22 | Inspection Test Plan for Low Voltage Switchgear | Rev 0: Approved | 2025-08-19 | 2025-08-01 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001521 | 2025-07-22 | 2025-07-22 | 0 | APP | Approved | 1 | "Inspection Test Plan for Low Voltage Switchgear" | APP
001522 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0095 | 0 | 131242-WSW41-QA-M-0095 | 2025-07-23 | Inspection Test Plan for CSEL Pipe Installation | NA | 2025-08-20 | 2025-09-08 | 33 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001522 | 2025-07-23 | 2025-07-23 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for CSEL Pipe Installation" | AWC
001523 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1401 | 0 | 131242-WST02-DS-E-1401 | 2025-07-23 | Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118 | Rev 0: Approved with comments. To revise and resubmit. | 2025-08-20 | 2025-08-01 | 7 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001523 | 2025-07-23 | 2025-07-23 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118" | AWC
001524 | 00 | Htet Nu | Project | NA | 131242 | WST02 | RT | S | 0005 | 0 | 131242-WST02-RT-S-0005 | 2025-07-24 | DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-01 | 6 | Not Approved | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001524 | 2025-07-24 | 2025-07-24 | 0 | NAP | Not Approved | 1 | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" | NAP
001525 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1153 | A | 131242-WST02-DR-S-1153 | 2025-07-24 | SSN Electrical building L2, Column C2A PE Endorsement | For Information | 2025-08-21 | 2025-08-12 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001525 | 2025-07-24 | 2025-07-24 | A | INF | For Information | 1 | "SSN Electrical building L2, Column C2A PE Endorsement" | INF
001526 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7000 | A | 131242-WSD11-DR-BE-7000 | 2025-07-24 | THP 1&2 Building Services DB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-21 | 2025-09-15 | 37 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001526 | 2025-07-24 | 2025-07-24 | A | AWC | Approved with Comments | 1 | "THP 1&2 Building Services DB SLD" | AWC
001526 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7002 | A | 131242-WSD11-DR-BE-7002 | 2025-07-24 | THP 1&2 Building Services DB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-21 | 2025-09-15 | 37 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001526 | 2025-07-24 | 2025-07-24 | A | AWC | Approved with Comments | 1 | "THP 1&2 Building Services DB SLD" | AWC
001527 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0025 | 0 | 131242-WST02-QA-A-0025 | 2025-07-24 | Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-01 | 6 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001527 | 2025-07-24 | 2025-07-24 | 0 | AWC | Approved with Comments | 1 | "Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction)" | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A | 131242-WST02-DR-S-8601 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A | 131242-WST02-DR-S-1004 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A | 131242-WST02-DR-S-1005 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A | 131242-WST02-DR-S-1006 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A | 131242-WST02-DR-S-1007 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A | 131242-WST02-DR-S-1008 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A | 131242-WST02-DR-S-1009 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528&&001733 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A | 131242-WST02-DR-S-1010 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A | 131242-WST02-DR-S-3002 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528&&001912 | 2025-07-24 | 2026-02-09 | A.6 | NAP | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | AWC
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601 | A | 131242-WST02-DR-S-5601 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2025-07-24 | A | NAP | Not Approved | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | NAP
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5602 | A | 131242-WST02-DR-S-5602 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2025-07-24 | A | NAP | Not Approved | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | NAP
001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5603 | A | 131242-WST02-DR-S-5603 | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001153&&001528 | 2025-03-24 | 2025-07-24 | A | NAP | Not Approved | 2 | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | NAP
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A.5 | 131242-WST02-DR-S-1004 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A.5 | 131242-WST02-DR-S-1005 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A.5 | 131242-WST02-DR-S-1006 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A.5 | 131242-WST02-DR-S-1007 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A.5 | 131242-WST02-DR-S-1008 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.5 | 131242-WST02-DR-S-1009 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528&&001733 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A.5 | 131242-WST02-DR-S-1010 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A.5 | 131242-WST02-DR-S-3002 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528&&001912 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3003 | A.5 | 131242-WST02-DR-S-3003 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-11-07 | 2026-02-09 | A.6 | AWC | Approved with Comments | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3004 | A.5 | 131242-WST02-DR-S-3004 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-11-07 | 2026-02-09 | A.6 | AWC | Approved with Comments | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A.5 | 131242-WST02-DR-S-8601 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A.6 | 131242-WST02-DR-S-1004 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A.6 | 131242-WST02-DR-S-1005 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A.6 | 131242-WST02-DR-S-1006 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A.6 | 131242-WST02-DR-S-1007 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A.6 | 131242-WST02-DR-S-1008 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.6 | 131242-WST02-DR-S-1009 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 10 |  |  | 001528&&001733 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A.6 | 131242-WST02-DR-S-1010 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A.6 | 131242-WST02-DR-S-3002 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528&&001912 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3003 | A.6 | 131242-WST02-DR-S-3003 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-11-07 | 2026-02-09 | A.6 | PEN | Approved with Comments | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3004 | A.6 | 131242-WST02-DR-S-3004 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-11-07 | 2026-02-09 | A.6 | PEN | Approved with Comments | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3005 | A.6 | 131242-WST02-DR-S-3005 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2026-02-09 | 2026-02-09 | A.6 | PEN | Awaiting S.O.'s response | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | PEN
001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A.6 | 131242-WST02-DR-S-8601 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 0 |  |  | 001528 | 2025-07-24 | 2026-02-09 | A.6 | PEN | Approved with Comments | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | AWC
001529 | 00 | Aaron | CSA | NA | Fabrication Drawing | NA | NA | NA | NA | NA | Fabrication Drawing-NA-NA-NA-NA | 2025-07-24 | ST603_SWPR01&02 fabrication drawing | R0: Not approved. (Same fabrication drawings with PE endorsement submitted in prolog #1531) Please clarify. | 2025-08-21 | 2026-01-02 | 116 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001529&&001531 | 2025-07-24 | 2025-07-24 | NA | NAP | Not Approved | 2 | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | NAP
001530 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | A | 3017 | A | 131242-WST02-SD-A-3017 | 2025-07-24 | Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-25 | 22 | Not Approved | YES | 2025-09-12 | NO | Resubmitted | 0 |  |  | 001356&&001530 | 2025-06-12 | 2025-08-27 | C | NAP | Approved with Comments | 4 | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | AWC
001531 | 00 | Aaron | CSA | NA | Fabrication Drawing | NA | NA | NA | NA | NA | Fabrication Drawing-NA-NA-NA-NA | 2025-07-24 | ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed) | NA | 2025-08-21 | 2025-09-15 | 37 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001529&&001531 | 2025-07-24 | 2025-07-24 | NA | INF | Not Approved | 2 | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | NAP
001532 | 00 | Bryan | Project | NA | 131242 | WSW41 | MS | Z | 0002 | 0 | 131242-WSW41-MS-Z-0002 | 2025-07-28 | MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works | NA | 2025-08-25 | 2025-09-15 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001532 | 2025-07-28 | 2025-07-28 | 0 | APP | Approved | 1 | "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" | APP
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CL | S | 0002_ST618_BCA | 0 | 131242-WSD11-CL-S-0002_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001533 | 2025-07-29 | 2025-07-29 | 0 | INF | For Information | 1 | "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618_BCA | C | 131242-WSD11-DR-S-0302_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618_BCA | C | 131242-WSD11-DR-S-1300_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618_BCA | C | 131242-WSD11-DR-S-1301_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618_BCA | C | 131242-WSD11-DR-S-1302_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618_BCA | C | 131242-WSD11-DR-S-1303_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618_BCA | C | 131242-WSD11-DR-S-1304_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618_BCA | C | 131242-WSD11-DR-S-1305_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1306_ST618_BCA | C | 131242-WSD11-DR-S-1306_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618_BCA | C | 131242-WSD11-DR-S-2300_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618_BCA | C | 131242-WSD11-DR-S-3300_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618_BCA | C | 131242-WSD11-DR-S-5300_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618_BCA | C | 131242-WSD11-DR-S-5301_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618_BCA | C | 131242-WSD11-DR-S-5302_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618_BCA | C | 131242-WSD11-DR-S-5303_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618_BCA | C | 131242-WSD11-DR-S-5304_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618_BCA | C | 131242-WSD11-DR-S-5305_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618_BCA | C | 131242-WSD11-DR-S-5306_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618_BCA | C | 131242-WSD11-DR-S-5307_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618_BCA | C | 131242-WSD11-DR-S-5308_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618_BCA | C | 131242-WSD11-DR-S-5309_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618_BCA | C | 131242-WSD11-DR-S-5310_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5311_ST618_BCA | C | 131242-WSD11-DR-S-5311_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5312_ST618_BCA | C | 131242-WSD11-DR-S-5312_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5313_ST618_BCA | C | 131242-WSD11-DR-S-5313_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5314_ST618_BCA | C | 131242-WSD11-DR-S-5314_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5315_ST618_BCA | C | 131242-WSD11-DR-S-5315_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5316_ST618_BCA | C | 131242-WSD11-DR-S-5316_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 8001_ST618_BCA | C | 131242-WSD11-DR-S-8001_ST618_BCA | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | 113 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001533 | 2025-07-29 | 2025-07-29 | C | INF | For Information | 1 | "BCA Approval of ST618 (THP Train_Cambi Structures)" | INF
001534 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | E | 0039 | 0 | 131242-WSW41-QA-E-0039 | 2025-07-29 | Material Submission for HV Plug and Transformer Termination Kit | Rev 0: Approved with comments. To revise and resubmit. | 2025-08-26 | 2025-09-03 | 26 | Approved with Comments | YES | 2025-09-23 | NO | Resubmitted | 0 |  |  | 001534 | 2025-07-29 | 2025-07-29 | 0 | AWC | Approved with Comments | 1 | "Material Submission for HV Plug and Transformer Termination Kit " | AWC
001535 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0013 | 0 | 131242-WST02-DS-I-0013 | 2025-07-29 | Datasheet for TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-08-15 | 13 | Approved with Comments | YES | 2025-09-04 | NO | Resubmitted | 0 |  |  | 001535 | 2025-07-29 | 2025-07-29 | 0 | AWC | Approved with Comments | 1 | "Datasheet for TSS Analyser" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1751 | B | 131242-WST02-DR-IP-1751 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1752 | B | 131242-WST02-DR-IP-1752 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1753 | B | 131242-WST02-DR-IP-1753 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1754 | B | 131242-WST02-DR-IP-1754 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1755 | B | 131242-WST02-DR-IP-1755 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1756 | B | 131242-WST02-DR-IP-1756 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1757 | B | 131242-WST02-DR-IP-1757 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1758 | B | 131242-WST02-DR-IP-1758 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1759 | B | 131242-WST02-DR-IP-1759 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1760 | B | 131242-WST02-DR-IP-1760 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1761 | B | 131242-WST02-DR-IP-1761 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1762 | B | 131242-WST02-DR-IP-1762 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1763 | B | 131242-WST02-DR-IP-1763 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1764 | B | 131242-WST02-DR-IP-1764 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1765 | B | 131242-WST02-DR-IP-1765 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1766 | B | 131242-WST02-DR-IP-1766 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1767 | B | 131242-WST02-DR-IP-1767 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1768 | B | 131242-WST02-DR-IP-1768 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1769 | B | 131242-WST02-DR-IP-1769 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1770 | B | 131242-WST02-DR-IP-1770 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1771 | B | 131242-WST02-DR-IP-1771 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1772 | B | 131242-WST02-DR-IP-1772 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1773 | B | 131242-WST02-DR-IP-1773 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1774 | B | 131242-WST02-DR-IP-1774 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1775 | B | 131242-WST02-DR-IP-1775 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1776 | B | 131242-WST02-DR-IP-1776 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1777 | B | 131242-WST02-DR-IP-1777 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1778 | B | 131242-WST02-DR-IP-1778 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1779 | B | 131242-WST02-DR-IP-1779 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1780 | B | 131242-WST02-DR-IP-1780 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1781 | B | 131242-WST02-DR-IP-1781 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1782 | B | 131242-WST02-DR-IP-1782 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1783 | B | 131242-WST02-DR-IP-1783 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1784 | B | 131242-WST02-DR-IP-1784 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1785 | B | 131242-WST02-DR-IP-1785 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1786 | B | 131242-WST02-DR-IP-1786 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1787 | B | 131242-WST02-DR-IP-1787 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1788 | B | 131242-WST02-DR-IP-1788 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1789 | B | 131242-WST02-DR-IP-1789 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1790 | B | 131242-WST02-DR-IP-1790 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1791 | B | 131242-WST02-DR-IP-1791 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1792 | B | 131242-WST02-DR-IP-1792 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1793 | B | 131242-WST02-DR-IP-1793 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1794 | B | 131242-WST02-DR-IP-1794 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1795 | B | 131242-WST02-DR-IP-1795 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1796 | B | 131242-WST02-DR-IP-1796 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1797 | B | 131242-WST02-DR-IP-1797 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1798 | B | 131242-WST02-DR-IP-1798 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1799 | B | 131242-WST02-DR-IP-1799 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1800 | B | 131242-WST02-DR-IP-1800 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1801 | B | 131242-WST02-DR-IP-1801 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1802 | B | 131242-WST02-DR-IP-1802 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1803 | B | 131242-WST02-DR-IP-1803 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1804 | B | 131242-WST02-DR-IP-1804 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1805 | B | 131242-WST02-DR-IP-1805 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1806 | B | 131242-WST02-DR-IP-1806 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1807 | B | 131242-WST02-DR-IP-1807 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1808 | B | 131242-WST02-DR-IP-1808 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1809 | B | 131242-WST02-DR-IP-1809 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1810 | B | 131242-WST02-DR-IP-1810 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1811 | B | 131242-WST02-DR-IP-1811 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1812 | B | 131242-WST02-DR-IP-1812 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1813 | B | 131242-WST02-DR-IP-1813 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1814 | B | 131242-WST02-DR-IP-1814 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1815 | B | 131242-WST02-DR-IP-1815 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1816 | B | 131242-WST02-DR-IP-1816 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1817 | B | 131242-WST02-DR-IP-1817 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1818 | B | 131242-WST02-DR-IP-1818 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1819 | B | 131242-WST02-DR-IP-1819 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1820 | B | 131242-WST02-DR-IP-1820 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1821 | B | 131242-WST02-DR-IP-1821 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1822 | B | 131242-WST02-DR-IP-1822 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1823 | B | 131242-WST02-DR-IP-1823 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1824 | B | 131242-WST02-DR-IP-1824 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1825 | B | 131242-WST02-DR-IP-1825 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1826 | B | 131242-WST02-DR-IP-1826 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1827 | B | 131242-WST02-DR-IP-1827 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1828 | B | 131242-WST02-DR-IP-1828 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1829 | B | 131242-WST02-DR-IP-1829 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1830 | B | 131242-WST02-DR-IP-1830 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1831 | B | 131242-WST02-DR-IP-1831 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1832 | B | 131242-WST02-DR-IP-1832 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1833 | B | 131242-WST02-DR-IP-1833 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1834 | B | 131242-WST02-DR-IP-1834 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1835 | B | 131242-WST02-DR-IP-1835 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1836 | B | 131242-WST02-DR-IP-1836 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1837 | B | 131242-WST02-DR-IP-1837 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1838 | B | 131242-WST02-DR-IP-1838 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1839 | B | 131242-WST02-DR-IP-1839 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1840 | B | 131242-WST02-DR-IP-1840 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1841 | B | 131242-WST02-DR-IP-1841 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1842 | B | 131242-WST02-DR-IP-1842 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1843 | B | 131242-WST02-DR-IP-1843 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1844 | B | 131242-WST02-DR-IP-1844 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1845 | B | 131242-WST02-DR-IP-1845 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1846 | B | 131242-WST02-DR-IP-1846 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1847 | B | 131242-WST02-DR-IP-1847 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1848 | B | 131242-WST02-DR-IP-1848 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1849 | B | 131242-WST02-DR-IP-1849 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1850 | B | 131242-WST02-DR-IP-1850 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1851 | B | 131242-WST02-DR-IP-1851 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1852 | B | 131242-WST02-DR-IP-1852 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1853 | B | 131242-WST02-DR-IP-1853 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1854 | B | 131242-WST02-DR-IP-1854 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1855 | B | 131242-WST02-DR-IP-1855 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1856 | B | 131242-WST02-DR-IP-1856 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1857 | B | 131242-WST02-DR-IP-1857 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1858 | B | 131242-WST02-DR-IP-1858 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1859 | B | 131242-WST02-DR-IP-1859 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1860 | B | 131242-WST02-DR-IP-1860 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1861 | B | 131242-WST02-DR-IP-1861 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1862 | B | 131242-WST02-DR-IP-1862 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1863 | B | 131242-WST02-DR-IP-1863 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1864 | B | 131242-WST02-DR-IP-1864 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1865 | B | 131242-WST02-DR-IP-1865 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1866 | B | 131242-WST02-DR-IP-1866 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1867 | B | 131242-WST02-DR-IP-1867 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1868 | B | 131242-WST02-DR-IP-1868 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1869 | B | 131242-WST02-DR-IP-1869 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1870 | B | 131242-WST02-DR-IP-1870 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1871 | B | 131242-WST02-DR-IP-1871 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1872 | B | 131242-WST02-DR-IP-1872 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1873 | B | 131242-WST02-DR-IP-1873 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1874 | B | 131242-WST02-DR-IP-1874 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1875 | B | 131242-WST02-DR-IP-1875 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1876 | B | 131242-WST02-DR-IP-1876 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1877 | B | 131242-WST02-DR-IP-1877 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1878 | B | 131242-WST02-DR-IP-1878 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1879 | B | 131242-WST02-DR-IP-1879 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1880 | B | 131242-WST02-DR-IP-1880 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1881 | B | 131242-WST02-DR-IP-1881 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1882 | B | 131242-WST02-DR-IP-1882 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1883 | B | 131242-WST02-DR-IP-1883 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1884 | B | 131242-WST02-DR-IP-1884 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1885 | B | 131242-WST02-DR-IP-1885 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1886 | B | 131242-WST02-DR-IP-1886 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1887 | B | 131242-WST02-DR-IP-1887 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1888 | B | 131242-WST02-DR-IP-1888 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1889 | B | 131242-WST02-DR-IP-1889 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1890 | B | 131242-WST02-DR-IP-1890 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1891 | B | 131242-WST02-DR-IP-1891 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1892 | B | 131242-WST02-DR-IP-1892 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1893 | B | 131242-WST02-DR-IP-1893 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1894 | B | 131242-WST02-DR-IP-1894 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1895 | B | 131242-WST02-DR-IP-1895 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1896 | B | 131242-WST02-DR-IP-1896 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1897 | B | 131242-WST02-DR-IP-1897 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1898 | B | 131242-WST02-DR-IP-1898 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1899 | B | 131242-WST02-DR-IP-1899 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1900 | B | 131242-WST02-DR-IP-1900 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001536 | 2025-07-29 | 2025-07-29 | B | AWC | Approved with Comments | 1 | "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916 | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | 77 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | AWC
001537 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0013 | 0 | 131242-WST02-QA-BS-0013 | 2025-07-30 | Factory Acceptance Test Report for Public Address System | NA | 2025-08-27 | 2025-09-23 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001537 | 2025-07-30 | 2025-07-30 | 0 | APP | Approved | 1 | "Factory Acceptance Test Report for Public Address System" | APP
001538 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0042 | 0 | 131242-WST02-QA-I-0042 | 2025-07-30 | Factory Acceptance Test Report for Pressure Transmitters (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | 61 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001538 | 2025-07-30 | 2025-07-30 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Pressure Transmitters (SSN)" | AWC
001539 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0014 | 0 | 131242-WST02-QA-BS-0014 | 2025-07-30 | Factory Acceptance Test Report for Clean Gas System Panel | Approved | 2025-08-27 | 2025-10-27 | 63 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001539 | 2025-07-30 | 2025-07-30 | 0 | APP | Approved | 1 | "Factory Acceptance Test Report for Clean Gas System Panel" | APP
001540 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0043 | 0 | 131242-WST02-QA-I-0043 | 2025-07-30 | Factory Acceptance Test Report for PH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-12-09 | 94 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001540 | 2025-07-30 | 2025-07-30 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for PH Analyser" | AWC
001541 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0103 | 0 | 131242-WST02-QA-M-0103 | 2025-07-30 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) | NA | 2025-08-27 | 2025-09-08 | 28 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001541 | 2025-07-30 | 2025-07-30 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) " | AWC
001542 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0044 | 0 | 131242-WST02-QA-I-0044 | 2025-07-30 | Factory Acceptance Test Report for Dissolved Oxygen Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-12-09 | 94 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001542 | 2025-07-30 | 2025-07-30 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Dissolved Oxygen Analyser" | AWC
001543 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 1402 | 0 | 131242-WST02-QA-BS-1402 | 2025-07-30 | Sample Board Submission for 50x50 SS316 Trunking | NA | 2025-08-27 |  | 173 | Awaiting S.O.'s response | YES | 2025-09-16 | NO | Overdue | 0 |  |  | 001543 | 2025-07-30 | 2025-07-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "Sample Board Submission for 50x50 SS316 Trunking" | PEN
001544 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | C | 0034 | 0 | 131242-WST02-MS-C-0034 | 2025-07-30 | MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-27 | 2025-08-25 | 18 | Approved with Comments | YES | 2025-09-12 | NO | Resubmitted | 0 |  |  | 001544 | 2025-07-30 | 2025-07-30 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation" | AWC
001545 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | IP | 0045 | 0 | 131242-WSW41-QA-IP-0045 | 2025-07-31 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-28 | 2025-12-09 | 93 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001545 | 2025-07-31 | 2026-01-15 | 1 | NAP | Not Approved | 2 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" | NAP
001545 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | IP | 0045 | 1 | 131242-WSW41-QA-IP-0045 | 2026-01-15 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-04 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001545 | 2025-07-31 | 2026-01-15 | 1 | PEN | Not Approved | 2 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" | NAP
001546 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0063 | 0 | 131242-WSW41-LT-PM-0063 | 2025-08-01 | CV of Team Member (QA/QC Manager) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-29 | 2026-01-16 | 120 | Not Approved | YES | 2026-02-05 | NO | Resubmitted | 0 |  |  | 001546 | 2025-08-01 | 2025-08-01 | 0 | NAP | Not Approved | 1 | "CV of Team Member (QA/QC Manager)" | NAP
001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001 | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001333&&001547 | 2025-05-30 | 2025-10-28 | A | NAP | Approved with Comments | 3 | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | AWC
001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-I-7002 | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000646&&001547 | 2024-08-13 | 2025-10-28 | B | NAP | Approved with Comments | 3 | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | AWC
001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7003 | A | 131242-WST02-DR-I-7003 | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001547 | 2025-08-01 | 2025-10-28 | B | NAP | Approved with Comments | 2 | " THP Overall Network Diagrams" | AWC
001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001 | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | 21 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001333&&001547 | 2025-05-30 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | AWC
001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7002 | B | 131242-WST02-DR-I-7002 | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | 21 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 407 |  |  | 000646&&001547 | 2024-08-13 | 2025-10-28 | B | AWC | Approved with Comments | 3 | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | AWC
001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7003 | B | 131242-WST02-DR-I-7003 | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | 21 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 001547 | 2025-08-01 | 2025-10-28 | B | AWC | Approved with Comments | 2 | " THP Overall Network Diagrams" | AWC
001548 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | SSN | 0 | 131242-WST02-SD-S-SSN | 2025-08-01 | Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed | For Information. Please refer to comment sheet. | 2025-08-29 | 2025-10-27 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001548 | 2025-08-01 | 2025-08-01 | 0 | INF | For Information | 1 | "Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed" | INF
001549 | 00 | Mr Low | EICA | NA | 131242 | WST02 | VI | I | 0026 | 0 | 131242-WST02-VI-I-0026 | 2025-08-04 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-01 | 2025-09-11 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001549 | 2025-08-04 | 2025-12-04 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of Building Management System (BMS) (Willowglen)" | AWC
001549 | 01 | Mr Low | EICA | NA | 131242 | WST02 | VI | I | 0026 | 1 | 131242-WST02-VI-I-0026 | 2025-09-29 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-17 | 2025-11-14 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001549 | 2025-08-04 | 2025-12-04 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of Building Management System (BMS) (Willowglen)" | AWC
001549 | 02 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0026 | 2 | 131242-WST02-VI-I-0026 | 2025-12-04 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-24 | 2026-02-09 | 47 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001549 | 2025-08-04 | 2025-12-04 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of Building Management System (BMS) (Willowglen)" | AWC
001550 | 00 | Mr Low | EICA | NA | 131242 | WSW41 | VI | I | 0007 | 0 | 131242-WSW41-VI-I-0007 | 2025-08-04 | Vendor Approval of PMS Network Interface Panel (Vector InfoTech) | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-09-01 | 2025-08-14 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001550 | 2025-08-04 | 2025-08-04 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" | AWC
001551 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0015 | 0 | 131242-WST02-DS-I-0015 | 2025-08-04 | Datasheet for Dissolved Oxygen Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-01 | 2025-10-01 | 42 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001551 | 2025-08-04 | 2025-08-04 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Dissolved Oxygen Analyser " | AWC
001552 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0018 | 0 | 131242-WST02-DS-I-0018 | 2025-08-04 | Datasheet for Pressure Gauge | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-09-01 | 2025-11-05 | 67 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001552 | 2025-08-04 | 2025-08-04 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Pressure Gauge" | AWC
001553 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0105 | 0 | 131242-WSD11-QA-M-0105 | 2025-08-04 | FAT Report for SS Pipe in THP-HS Line (Cyclect) | NA | 2025-09-01 | 2025-09-08 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001553 | 2025-08-04 | 2025-08-04 | 0 | APP | Approved | 1 | "FAT Report for SS Pipe in THP-HS Line (Cyclect)" | APP
001554 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0032 | 0 | 131242-WST02-QA-I-0032 | 2025-08-04 | SAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. | 2025-09-01 | 2025-08-26 | 16 | Approved with Comments | YES | 2025-09-15 | NO | Resubmitted | 0 |  |  | 001481&&001554 | 2025-07-16 | 2025-08-04 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" && "SAT Procedure for LVSG Panels (Sunlight)" | AWC
001555 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0106 | 0 | 131242-WSD11-QA-M-0106 | 2025-08-05 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB) | NA | 2025-09-02 | 2025-09-08 | 24 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001555 | 2025-08-05 | 2025-08-05 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB)" | AWC
001556 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0107 | 0 | 131242-WSD11-QA-M-0107 | 2025-08-05 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB) | NA | 2025-09-02 | 2025-09-08 | 24 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001556 | 2025-08-05 | 2025-08-05 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB)" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3004 | A_To withdraw | 131242-WST02-DR-BE-3004 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0001 SLD, Schematic and GA Drawing" | NAP
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A_To withdraw | 131242-WST02-DR-BE-7010 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A_To withdraw | 131242-WST02-DR-BE-3005 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A_To withdraw | 131242-WST02-DR-BE-7011 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A_To withdraw | 131242-WST02-DR-BE-7012 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A_To withdraw | 131242-WST02-DR-BE-7013 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3000 | A_To withdraw | 131242-WST02-DR-BE-3000 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0001 SLD, Schematic and GA Drawing" | NAP
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A_To withdraw | 131242-WST02-DR-BE-3001 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3002 | A_To withdraw | 131242-WST02-DR-BE-3002 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0001 SLD, Schematic and GA Drawing" | NAP
001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3003 | A_To withdraw | 131242-WST02-DR-BE-3003 | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001557 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0001 SLD, Schematic and GA Drawing" | NAP
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A_To withdraw | 131242-WST02-DR-BE-3010 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A_To withdraw | 131242-WST02-DR-BE-3011 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A_To withdraw | 131242-WST02-DR-BE-7016 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A_To withdraw | 131242-WST02-DR-BE-7015 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A_To withdraw | 131242-WST02-DR-BE-7017 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A_To withdraw | 131242-WST02-DR-BE-7018 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A_To withdraw | 131242-WST02-DR-BE-3006 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3007 | A_To withdraw | 131242-WST02-DR-BE-3007 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0002 SLD, Schematic and GA Drawing" | NAP
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3008 | A_To withdraw | 131242-WST02-DR-BE-3008 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0002 SLD, Schematic and GA Drawing" | NAP
001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3009 | A_To withdraw | 131242-WST02-DR-BE-3009 | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001558 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "LDB-0002 SLD, Schematic and GA Drawing" | NAP
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3015 | A_To withdraw | 131242-WST02-DR-BE-3015 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3017 | A_To withdraw | 131242-WST02-DR-BE-3017 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "SDB-0003 SLD, Schematic and GA Drawing" | NAP
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3016 | A_To withdraw | 131242-WST02-DR-BE-3016 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001808 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7020 | A_To withdraw | 131242-WST02-DR-BE-7020 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3018 | A_To withdraw | 131242-WST02-DR-BE-3018 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "SDB-0003 SLD, Schematic and GA Drawing" | NAP
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7021 | A_To withdraw | 131242-WST02-DR-BE-7021 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7023 | A_To withdraw | 131242-WST02-DR-BE-7023 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7022 | A_To withdraw | 131242-WST02-DR-BE-7022 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3012 | A_To withdraw | 131242-WST02-DR-BE-3012 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "SDB-0003 SLD, Schematic and GA Drawing" | NAP
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3013 | A_To withdraw | 131242-WST02-DR-BE-3013 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "SDB-0003 SLD, Schematic and GA Drawing" | NAP
001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3014 | A_To withdraw | 131242-WST02-DR-BE-3014 | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Not Approved | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001559 | 2025-08-05 | 2025-08-05 | A_To withdraw | NAP | Not Approved | 1 | "SDB-0003 SLD, Schematic and GA Drawing" | NAP
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3141 | A | 131242-WST02-DR-EP-3141 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3142 | A | 131242-WST02-DR-EP-3142 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3143 | A | 131242-WST02-DR-EP-3143 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7240 | A | 131242-WST02-DR-EP-7240 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7242 | A | 131242-WST02-DR-EP-7242 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7241 | A | 131242-WST02-DR-EP-7241 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7340 | A | 131242-WST02-DR-EP-7340 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7342 | A | 131242-WST02-DR-EP-7342 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3140 | A | 131242-WST02-DR-EP-3140 | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3141 | B | 131242-WST02-DR-EP-3141 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3142 | B | 131242-WST02-DR-EP-3142 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3143 | B | 131242-WST02-DR-EP-3143 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7240 | B | 131242-WST02-DR-EP-7240 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7242 | B | 131242-WST02-DR-EP-7242 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7241 | B | 131242-WST02-DR-EP-7241 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7340 | B | 131242-WST02-DR-EP-7340 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7342 | B | 131242-WST02-DR-EP-7342 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3140 | B | 131242-WST02-DR-EP-3140 | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | 102 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001560 | 2025-08-05 | 2025-10-01 | B | AWC | Approved with Comments | 2 | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | AWC
001561 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0041 | 0 | 131242-WST02-QA-E-0041 | 2025-08-05 | Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi) | NA | 2025-09-02 | 2025-09-02 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001561 | 2025-08-05 | 2025-08-05 | 0 | INF | For Information | 1 | "Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi)" | INF
001562 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0042 | 0 | 131242-WST02-QA-E-0042 | 2025-08-05 | Certificate of Proper Installation for LVSG Panels (Sunlight) | NA | 2025-09-02 | 2025-09-02 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001562 | 2025-08-05 | 2025-08-05 | 0 | INF | For Information | 1 | "Certificate of Proper Installation for LVSG Panels (Sunlight)" | INF
001563 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0043 | 0 | 131242-WSD11-QA-E-0043 | 2025-08-05 | Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) | NA | 2025-09-02 | 2025-09-02 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001563 | 2025-08-05 | 2025-08-05 | 0 | INF | For Information | 1 | "Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) " | INF
001564 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0015 | 0 | 131242-WST02-QA-BS-0015 | 2025-08-05 | Factory Acceptance Test Report for Fire Alarm System | R0: Approved with comments. Revise and resubmit. | 2025-09-02 | 2025-10-22 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001564 | 2025-08-05 | 2025-11-27 | 1 | AWC | Approved with Comments | 2 | "Factory Acceptance Test Report for Fire Alarm System " | AWC
001564 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0015 | 1 | 131242-WST02-QA-BS-0015 | 2025-11-27 | Factory Acceptance Test Report for Fire Alarm System | R0: Approved with comments. Revise and resubmit. | 2025-12-17 |  | 87 | Awaiting S.O.'s response | YES | 2026-01-14 | NO | Overdue | 0 |  |  | 001564 | 2025-08-05 | 2025-11-27 | 1 | PEN | Approved with Comments | 2 | "Factory Acceptance Test Report for Fire Alarm System " | AWC
001565 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0040 | 0 | 131242-WST02-QA-E-0040 | 2025-08-05 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-10-01 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001565 | 2025-08-05 | 2026-01-02 | 1 | AWC | Approved with Comments | 2 | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | AWC
001565 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0040 | 1 | 131242-WST02-QA-E-0040 | 2026-01-02 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-22 | 2026-02-02 | 21 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 001565 | 2025-08-05 | 2026-01-02 | 1 | AWC | Approved with Comments | 2 | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | AWC
001566 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0064 | 0 | 131242-WSW41-LT-PM-0064 | 2025-08-06 | Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2) | Rev (0): Rejected. Please refer to S.O. correspondence no. 400 dated 10 Sep 2025. | 2025-09-03 | 2025-09-23 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001566 | 2025-08-06 | 2025-08-06 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2)" | REJ
001567 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0008 | 0 | 131242-WST02-VI-A-0008 | 2025-08-06 | Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd | R0: Approved with comments. Please refer to comment sheet. | 2025-09-03 | 2025-08-26 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001567 | 2025-08-06 | 2025-08-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" | AWC
001568 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0026 | 0 | 131242-WST02-QA-A-0026 | 2025-08-06 | Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636 | R0: Approved with comments. Please refer to comment sheet. Resubmission is not required | 2025-09-03 | 2025-10-06 | 43 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001568 | 2025-08-06 | 2025-08-06 | 0 | AWC | Approved with Comments | 1 | "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | AWC
001569 | 00 | YiHao | Contracts | NA | 131242 | WSW41 | PC | W | 0025 | 0 | 131242-WSW41-PC-W-0025 | 2025-08-07 | Payment Claim No.25 | Rev (0): Approved. Please refer to S.O. correspondence no. 381 dated 17 Aug 2025. | 2025-09-04 | 2025-08-22 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001569 | 2025-08-07 | 2025-08-07 | 0 | APP | Approved | 1 | "Payment Claim No.25" | APP
001570 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0108 | 0 | 131242-WSW41-QA-M-0108 | 2025-08-07 | FAT Report for Manual Knife Gate Valves - Batch 1 (Jash) | NA | 2025-09-04 | 2025-09-02 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001570 | 2025-08-07 | 2025-08-07 | 0 | APP | Approved | 1 | "FAT Report for Manual Knife Gate Valves - Batch 1 (Jash)" | APP
001571 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0109 | 0 | 131242-WSW41-QA-M-0109 | 2025-08-07 | Test Report 2.2 for Manual Plastic Valves | NA | 2025-09-04 | 2025-09-08 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001571&&001579 | 2025-08-07 | 2025-08-12 | 0 | NAP | Approved | 2 | "Test Report 2.2 for Manual Plastic Valves " && "FAT Report for CSEL Piping (3rd Batch) " | APP
001572 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200 | 2025-08-07 | THP Courtyard Sump Design (Updates) | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-04 | 2025-08-25 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | APP
001572 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210 | 2025-08-07 | THP Courtyard Sump Design (Updates) | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-04 | 2025-08-25 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 4 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | APP
001572 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200 | 2025-09-15 | THP Courtyard Sump Design (Updates) | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-24 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | AWC | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | APP
001572 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210 | 2025-09-15 | THP Courtyard Sump Design (Updates) | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-24 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001572 | 2024-11-30 | 2025-12-14 | A | AWC | Approved | 4 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | APP
001572 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200 | 2025-12-14 | THP Courtyard Sump Design (Updates) | Rev2: Approved | 2026-01-01 | 2026-01-08 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | APP | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | APP
001572 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210 | 2025-12-14 | THP Courtyard Sump Design (Updates) | Rev2: Approved | 2026-01-01 | 2026-01-08 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001572 | 2024-11-30 | 2025-12-14 | A | APP | Approved | 4 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | APP
001573 | 00 | Bryan | EICA | NA | 131242 | WST02 | MS | M | 0009 | 0 | 131242-WST02-MS-M-0009 | 2025-08-09 | MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-05 | 2025-12-29 | 100 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001573&&001585 | 2025-08-09 | 2025-08-13 | 0 | AWC | Approved with Comments | 2 | "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" && "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " | AWC
001574 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0062 | 0 | 131242-WSW41-CD-IM-0062 | 2025-08-11 | VCM Submission for 2025-07 | NA | 2025-09-08 | 2025-08-27 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001574 | 2025-08-11 | 2025-08-11 | 0 | INF | For Information | 1 | "VCM Submission for 2025-07" | INF
001575 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0065 | 0 | 131242-WSW41-LT-PM-0065 | 2025-08-11 | Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 398 dated 10 Sep 25. | 2025-09-08 | 2025-09-23 | 31 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001575 | 2025-08-11 | 2025-08-11 | 0 | INF | For Information | 1 | "Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024)" | INF
001576 | 00 | Jun | EICA | NA | 131242 | WSD11 | VI | M | 1018 | 0 | 131242-WSD11-VI-M-1018 | 2025-08-12 | Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-09-09 | 2025-11-24 | 74 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001576 | 2025-08-12 | 2025-08-12 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS" | AWC
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0305_ST621_BCA | A | 131242-WSW41-DR-S-0305_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0306_ST621_BCA | A | 131242-WSW41-DR-S-0306_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0307_ST621_BCA | A | 131242-WSW41-DR-S-0307_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0308_ST621_BCA | A | 131242-WSW41-DR-S-0308_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0309_ST621_BCA | A | 131242-WSW41-DR-S-0309_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST621_BCA | A | 131242-WSW41-DR-S-1000_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1001_ST621_BCA | A | 131242-WSW41-DR-S-1001_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1002_ST621_BCA | A | 131242-WSW41-DR-S-1002_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1003_ST621_BCA | A | 131242-WSW41-DR-S-1003_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST621_BCA | A | 131242-WSW41-DR-S-1004_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST621_BCA | A | 131242-WSW41-DR-S-2000_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST621_BCA | A | 131242-WSW41-DR-S-3000_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST621_BCA | A | 131242-WSW41-DR-S-2001_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST621_BCA | A | 131242-WSW41-DR-S-5000_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST621_BCA | A | 131242-WSW41-DR-S-5001_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST621_BCA | A | 131242-WSW41-DR-S-5003_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST621_BCA | A | 131242-WSW41-DR-S-5002_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST621_BCA | A | 131242-WSW41-DR-S-8001_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST621_BCA | A | 131242-WSW41-DR-S-0300_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST621_BCA | A | 131242-WSW41-DR-S-0301_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0303_ST621_BCA | A | 131242-WSW41-DR-S-0303_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0302_ST621_BCA | A | 131242-WSW41-DR-S-0302_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0304_ST621_BCA | A | 131242-WSW41-DR-S-0304_ST621_BCA | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001577 | 2025-08-12 | 2025-08-12 | A | INF | For Information | 1 | "BCA Approval of ST621 (Site Wide Pipe Rack)" | INF
001578 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5761 | 0 | 131242-WST02-DS-M-5761 | 2025-08-12 | SSN Aeration Line Automatic Condensate Drain Valve | NA | 2025-09-09 |  | 164 | Awaiting S.O.'s response | YES | 2025-09-29 | NO | Overdue | 0 |  |  | 001578 | 2025-08-12 | 2025-08-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "SSN Aeration Line Automatic Condensate Drain Valve" | PEN
001579 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0109 | 0 | 131242-WSW41-QA-M-0109 | 2025-08-12 | FAT Report for CSEL Piping (3rd Batch) | NA | 2025-09-09 | 2025-09-08 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001571&&001579 | 2025-08-07 | 2025-08-12 | 0 | APP | Approved | 2 | "Test Report 2.2 for Manual Plastic Valves " && "FAT Report for CSEL Piping (3rd Batch) " | APP
001580 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0104 | 0 | 131242-WSD11-QA-M-0104 | 2025-08-12 | FAT Report for IA Line from THP to SWPR (SS Spools) | NA | 2025-09-09 | 2025-09-08 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001580 | 2025-08-12 | 2025-08-12 | 0 | APP | Approved | 1 | "FAT Report for IA Line from THP to SWPR (SS Spools)" | APP
001581 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 0 | 131242-WST02-DS-E-1403 | 2025-08-12 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 0: Not approved. To revise and resubmit. | 2025-09-09 | 2025-09-26 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001581 | 2025-08-12 | 2025-10-06 | 2 | NAP | Not Approved | 3 | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | NAP
001581 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 0 | 131242-WST02-DS-E-1403 | 2025-09-30 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 1: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-10-20 | 2025-10-02 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001581 | 2025-08-12 | 2025-10-06 | 2 | REJ | Not Approved | 3 | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | NAP
001581 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 2 | 131242-WST02-DS-E-1403 | 2025-10-06 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 2: Not approved - Revise and Resubmit Refer to attached file for comments. | 2025-10-24 | 2026-02-02 | 85 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 001581 | 2025-08-12 | 2025-10-06 | 2 | NAP | Not Approved | 3 | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | NAP
001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0049 | 0 | 131242-WSW41-MI-C-0049 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001582 | 2025-08-12 | 2025-08-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | INF
001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0050 | 0 | 131242-WSW41-MI-C-0050 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001582 | 2025-08-12 | 2025-08-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | INF
001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0051 | 0 | 131242-WSW41-MI-C-0051 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001582 | 2025-08-12 | 2025-08-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | INF
001583 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0110 | 0 | 131242-WSW41-QA-M-0110 | 2025-08-12 | FAT Report for SWPR Pipe's Guide Supports | NA | 2025-09-09 | 2025-09-08 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001583 | 2025-08-12 | 2025-08-12 | 0 | APP | Approved | 1 | "FAT Report for SWPR Pipe's Guide Supports " | APP
001584 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0066 | 0 | 131242-WSW41-LT-PM-0066 | 2025-08-13 | Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire | Rev (0): Rejected. Please refer to S.O. correspondence no. 408 dated 3 Oct 2025. | 2025-09-10 | 2025-10-15 | 45 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001584 | 2025-08-13 | 2025-08-13 | 0 | REJ | Rejected | 1 | "Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire" | REJ
001585 | 00 | Bryan | BS | NA | 131242 | WST02 | MS | M | 0009 | 0 | 131242-WST02-MS-M-0009 | 2025-08-13 | MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-12-29 | 98 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001573&&001585 | 2025-08-09 | 2025-08-13 | 0 | AWC | Approved with Comments | 2 | "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" && "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " | AWC
001586 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5200 | E | 131242-WSW41-DR-S-5200 | 2025-08-13 | SWPR _Platform A and B- Cat ladders | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-10-14 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001226&&001586 | 2025-04-14 | 2025-08-13 | E | NAP | Not Approved | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "SWPR _Platform A and B- Cat ladders" | NAP
001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8600 | A.3 | 131242-WSW41-DR-S-8600 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001586 | 2025-11-06 | 2025-11-06 | A.3 | APP | Approved | 1 | "SWPR _Platform A and B- Cat ladders" | APP
001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5604 | A.3 | 131242-WSW41-DR-S-5604 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001586 | 2025-11-06 | 2025-11-06 | A.3 | APP | Approved | 1 | "SWPR _Platform A and B- Cat ladders" | APP
001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1011 | A.3 | 131242-WSW41-DR-S-1011 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001586 | 2025-11-06 | 2025-11-06 | A.3 | APP | Approved | 1 | "SWPR _Platform A and B- Cat ladders" | APP
001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1010 | A.3 | 131242-WSW41-DR-S-1010 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001586 | 2025-11-06 | 2025-11-06 | A.3 | APP | Approved | 1 | "SWPR _Platform A and B- Cat ladders" | APP
001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | CL | S | 5200 | B | 131242-WSW41-CL-S-5200 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001586 | 2025-11-06 | 2025-11-06 | B | APP | Approved | 1 | "SWPR _Platform A and B- Cat ladders" | APP
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1101 | A.3 | 131242-WSD11-SD-S-1101 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1102 | A.3 | 131242-WSD11-SD-S-1102 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1103 | A.3 | 131242-WSD11-SD-S-1103 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 2100 | A.3 | 131242-WSD11-SD-S-2100 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 3100 | A.3 | 131242-WSD11-SD-S-3100 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5100 | A.3 | 131242-WSD11-SD-S-5100 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5101 | A.3 | 131242-WSD11-SD-S-5101 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5102 | A.3 | 131242-WSD11-SD-S-5102 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 8002 | A.3 | 131242-WSD11-SD-S-8002 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001587 | 2025-08-13 | 2025-08-13 | A.3 | INF | For Information | 1 | "ST619 THP-PR01 (PE endorsed drawing)" | INF
001588 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | SSN_PLINTH REBAR DETAILS | A | 131242-WST02-DR-S-SSN_PLINTH REBAR DETAILS | 2025-08-13 | SSN Equipment Loading and Equipment Plinth Layout | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-10-06 | 38 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001588 | 2025-08-13 | 2025-08-13 | A | AWC | Approved with Comments | 1 | "SSN Equipment Loading and Equipment Plinth Layout" | AWC
001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5600 | A | 131242-WST02-SD-S-5600 | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | 29 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001589 | 2025-08-13 | 2025-08-13 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Typical Railing Details" | AWC
001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5601 | A | 131242-WST02-SD-S-5601 | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | 29 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001589 | 2025-08-13 | 2025-08-13 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Typical Railing Details" | AWC
001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5602 | A | 131242-WST02-SD-S-5602 | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | 29 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001458&&001589 | 2025-07-11 | 2025-08-13 | A | AWC | Approved with Comments | 2 | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | AWC
001590 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0111 | 0 | 131242-WSW41-QA-M-0111 | 2025-08-13 | Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton) | NA | 2025-09-10 | 2025-09-08 | 18 | Not Approved | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001590 | 2025-08-13 | 2025-08-13 | 0 | NAP | Not Approved | 1 | "Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton)" | NAP
001591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0003 | 0 | 131242-WSD11-RT-Z-0003 | 2025-08-14 | 80% THP ALMOP Report | NA | 2025-09-11 |  | 162 | Awaiting S.O.'s response | YES | 2025-10-01 | NO | Overdue | 0 |  |  | 001591 | 2025-08-14 | 2025-08-14 | 0 | PEN | Awaiting S.O.'s response | 1 | "80% THP ALMOP Report" | PEN
001592 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0046 | 0 | 131242-WST02-QA-I-0046 | 2025-08-14 | Factory Acceptance Test Report for Temperature Transmitters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-10-06 | 37 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001592 | 2025-08-14 | 2025-08-14 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Temperature Transmitters" | AWC
001593 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0047 | 0 | 131242-WST02-QA-I-0047 | 2025-08-14 | Factory Acceptance Test Report for Tuning Fork Level Switches | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-11-05 | 59 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001593 | 2025-08-14 | 2025-08-14 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Tuning Fork Level Switches " | AWC
001594 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0027 | 0 | 131242-WSW41-RT-PM-0027 | 2025-08-15 | C4B Monthly Progress Report Number No.27 (07 25) | NA | 2025-09-12 | 2025-08-30 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001594 | 2025-08-15 | 2025-08-15 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.27 (07 25)" | AWC
001595 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0112 | 0 | 131242-WSW41-QA-M-0112 | 2025-08-15 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch) | NA | 2025-09-12 | 2025-09-08 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001595 | 2025-08-15 | 2025-08-15 | 0 | APP | Approved | 1 | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch)" | APP
001596 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0042 | 0 | 131242-WSW41-QA-C-0042 | 2025-08-15 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025 | NA | 2025-09-12 | 2025-08-26 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001596 | 2025-08-15 | 2025-08-15 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025" | INF
001597 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0067 | 0 | 131242-WSW41-LT-PM-0067 | 2025-08-15 | Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG | Rev (0): Rejected. Please refer to S.O. correspondence no. 409 dated 3 Oct 2025. | 2025-09-12 | 2025-10-15 | 43 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001597 | 2025-08-15 | 2025-08-15 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG" | REJ
001598 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0048 | 0 | 131242-WST02-QA-I-0048 | 2025-08-17 | Factory Acceptance Test Report for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-23 | 48 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001598 | 2025-08-17 | 2025-08-17 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Thermal Flow Switch" | AWC
001599 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0049 | 0 | 131242-WST02-QA-I-0049 | 2025-08-17 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-23 | 48 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001599 | 2025-08-17 | 2025-08-17 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) " | AWC
001600 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0016 | 0 | 131242-WST02-QA-BS-0016 | 2025-08-19 | QA/QC Report for Air Conditioning System | Rev0: Not Approved. Resubmission required. | 2025-09-16 | 2025-10-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001600 | 2025-08-19 | 2025-10-13 | 1 | NAP | Not Approved | 2 | "QA/QC Report for Air Conditioning System" | NAP
001600 | 01 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0016 | 1 | 131242-WST02-QA-BS-0016 | 2025-10-13 | QA/QC Report for Air Conditioning System | Rev0: Not Approved. Resubmission required. | 2025-10-31 |  | 120 | Awaiting S.O.'s response | YES | 2025-11-28 | NO | Overdue | 0 |  |  | 001600 | 2025-08-19 | 2025-10-13 | 1 | PEN | Not Approved | 2 | "QA/QC Report for Air Conditioning System" | NAP
001601 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0017 | 0 | 131242-WST02-QA-BS-0017 | 2025-08-19 | QA/QC Report for Mechanical Ventilation Fan | Rev0: Not Approved. Resubmission required. | 2025-09-16 | 2025-10-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001601 | 2025-08-19 | 2025-10-13 | 1 | NAP | Not Approved | 2 | "QA/QC Report for Mechanical Ventilation Fan" | NAP
001601 | 01 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0017 | 1 | 131242-WST02-QA-BS-0017 | 2025-10-13 | QA/QC Report for Mechanical Ventilation Fan | Rev0: Not Approved. Resubmission required. | 2025-10-31 |  | 120 | Awaiting S.O.'s response | YES | 2025-11-28 | NO | Overdue | 0 |  |  | 001601 | 2025-08-19 | 2025-10-13 | 1 | PEN | Not Approved | 2 | "QA/QC Report for Mechanical Ventilation Fan" | NAP
001602 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0113 | 0 | 131242-WST02-QA-M-0113 | 2025-08-19 | FAT Report for Manual Knife Gate Valves Batch 2 (Jash) | NA | 2025-09-16 | 2025-09-02 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001602 | 2025-08-19 | 2025-08-19 | 0 | APP | Approved | 1 | "FAT Report for Manual Knife Gate Valves Batch 2 (Jash)" | APP
001603 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0002 | 0 | 131242-WST02-QA-S-0002 | 2025-08-19 | ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-16 | 2025-10-27 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001603 | 2025-08-19 | 2025-08-19 | 0 | INF | For Information | 1 | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " | INF
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 2008 | A | 131242-WST02-SD-A-2008 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5300 | A | 131242-WST02-SD-A-5300 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5301 | A | 131242-WST02-SD-A-5301 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5302 | A | 131242-WST02-SD-A-5302 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5303 | A | 131242-WST02-SD-A-5303 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5340 | A | 131242-WST02-SD-A-5340 | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001604 | 2025-08-19 | 2025-08-19 | A | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-A-1000 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | NAP | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 2000 | 0 | 131242-WST02-DR-A-2000 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 321 |  |  | 000809&&001604&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 4 | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 2008 | 1 | 131242-WST02-DR-A-2008 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 1 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5300 | 1 | 131242-WST02-DR-A-5300 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 1 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5301 | 0 | 131242-WST02-DR-A-5301 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 0 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5302 | 0 | 131242-WST02-DR-A-5302 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 0 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5303 | 1 | 131242-WST02-DR-A-5303 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 1 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5340 | 0 | 131242-WST02-DR-A-5340 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 0 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | CL | A | 0005 | 0 | 131242-WST02-CL-A-0005 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | 16 | Not Approved | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 001604 | 2025-11-12 | 2025-11-12 | 0 | NAP | Not Approved | 1 | "Shop Drawing for Louvre Door and Window" | NAP
001605 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0003 | 0 | 131242-WST02-QA-S-0003 | 2025-08-19 | ST609 Inspection Reports | For information | 2025-09-16 | 2025-10-13 | 39 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001605 | 2025-08-19 | 2025-08-19 | 0 | INF | For Information | 1 | "ST609 Inspection Reports" | INF
001606 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 0 | 131242-WSW41-QA-S-0004 | 2025-08-19 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | NA | 2025-09-16 | 2025-09-24 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001606 | 2025-08-19 | 2026-01-07 | 2 | AWC | Approved with Comments | 3 | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | AWC
001606 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 1 | 131242-WSW41-QA-S-0004 | 2025-12-10 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-30 | 2025-12-17 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001606 | 2025-08-19 | 2026-01-07 | 2 | AWC | Approved with Comments | 3 | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | AWC
001606 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 2 | 131242-WSW41-QA-S-0004 | 2026-01-07 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-27 | 2026-01-12 | 3 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001606 | 2025-08-19 | 2026-01-07 | 2 | AWC | Approved with Comments | 3 | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | AWC
001607 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0044 | 0 | 131242-WST02-QA-E-0044 | 2025-08-22 | Inspection Test Plan for Distribution Panels (MDBs) | NA | 2025-09-19 | 2025-09-15 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001607 | 2025-08-22 | 2025-08-22 | 0 | APP | Approved | 1 | " Inspection Test Plan for Distribution Panels (MDBs)" | APP
001608 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0005 | 0 | 131242-WST02-QA-S-0005 | 2025-08-20 | ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For informaiton | 2025-09-17 | 2025-10-27 | 48 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001608 | 2025-08-20 | 2025-08-20 | 0 | INF | For Information | 1 | "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | INF
001609 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | BF | 7001 | A | 131242-WSD11-DR-BF-7001 | 2025-08-22 | THP Fire alarm devices interface with C4A Fire Alarm panel | R0: Approved. | 2025-09-19 | 2025-10-22 | 43 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001609 | 2025-08-22 | 2025-08-22 | A | APP | Approved | 1 | " THP Fire alarm devices interface with C4A Fire Alarm panel" | APP
001610 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0012 | 0 | 131242-WST02-CL-P-0012 | 2025-08-22 | G2D Water Hydraulic Pressure Loss Calculation | NA | 2025-09-19 |  | 156 | Awaiting S.O.'s response | YES | 2025-10-09 | NO | Overdue | 0 |  |  | 001610 | 2025-08-22 | 2025-08-22 | 0 | PEN | Awaiting S.O.'s response | 1 | "G2D Water Hydraulic Pressure Loss Calculation" | PEN
001611 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0013 | 0 | 131242-WSW41-PO-I-0013 | 2025-08-22 | Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001611 | 2025-08-22 | 2025-08-22 | 0 | INF | For Information | 1 | "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | INF
001612 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0014 | 0 | 131242-WSW41-PO-I-0014 | 2025-08-22 | Unpriced PO for Thermal Flow Switch (Endress & Hauser) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001612 | 2025-08-22 | 2025-08-22 | 0 | INF | For Information | 1 | "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | INF
001613 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0015 | 0 | 131242-WSW41-PO-I-0015 | 2025-08-22 | Unpriced PO for Pressure Switch (IFM) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001613 | 2025-08-22 | 2025-08-22 | 0 | INF | For Information | 1 | "Unpriced PO for Pressure Switch (IFM) " | INF
001614 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0016 | 0 | 131242-WSW41-PO-I-0016 | 2025-08-22 | Unpriced PO for Rotameter (Krohne) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001614 | 2025-08-22 | 2025-08-22 | 0 | INF | For Information | 1 | "Unpriced PO for Rotameter (Krohne) " | INF
001615 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0026 | 0 | 131242-WSW41-PO-M-0026 | 2025-08-22 | Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng) | Rev 0: For Information Only. | 2025-09-19 | 2025-11-24 | 66 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001615&&001800 | 2025-08-22 | 2025-10-31 | 0 | INF | For Information | 2 | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | INF
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1004 | A.1 | 131242-WST02-SD-S-1004 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1005 | A.1 | 131242-WST02-SD-S-1005 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1006 | A.1 | 131242-WST02-SD-S-1006 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.1 | 131242-WST02-SD-S-1007 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616&&001698&&001803 | 2025-08-22 | 2026-02-09 | A.5 | VOID | Not Approved | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1008 | A.1 | 131242-WST02-SD-S-1008 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1009 | A.1 | 131242-WST02-SD-S-1009 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616&&001700 | 2025-08-22 | 2025-09-29 | A | VOID | Rejected | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | REJ
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1010 | A.1 | 131242-WST02-SD-S-1010 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3002 | A.1 | 131242-WST02-SD-S-3002 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3003 | A.1 | 131242-WST02-SD-S-3003 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8601 | A.1 | 131242-WST02-SD-S-8601 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001616 | 2025-08-22 | 2025-08-22 | A.1 | VOID | (VOID NOT IN USE) | 1 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | VOID
001617 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5361 | 0 | 131242-WSW41-DR-M-5361 | 2025-08-25 | Piping Special Item - Metallic Strainer (Spirax Sarco) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments | 2025-09-22 | 2025-10-22 | 42 | Not Approved | YES | 2025-11-11 | NO | Resubmitted | 0 |  |  | 001617 | 2025-08-25 | 2025-08-25 | 0 | NAP | Not Approved | 1 | "Piping Special Item - Metallic Strainer (Spirax Sarco)" | NAP
001618 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5371 | 0 | 131242-WSW41-DR-M-5371 | 2025-08-25 | Piping Special Item - Plastic Strainer (Asahi/ Argu) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-10-22 | 42 | Not Approved | YES | 2025-11-11 | NO | Resubmitted | 0 |  |  | 001618 | 2025-08-25 | 2025-08-25 | 0 | NAP | Not Approved | 1 | "Piping Special Item - Plastic Strainer (Asahi/ Argu)" | NAP
001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5465 | A | 131242-WST02-DR-M-5465 | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | 55 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | AWC | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5466 | A | 131242-WST02-DR-M-5466 | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | 55 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | AWC | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5467 | A | 131242-WST02-DR-M-5467 | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | 55 | Approved with Comments | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | D | AWC | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5465 | B | 131242-WST02-DR-M-5465 | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-06 |  | 115 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5466 | B | 131242-WST02-DR-M-5466 | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5467 | B | 131242-WST02-DR-M-5467 | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | D | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5468 | B | 131242-WST02-DR-M-5468 | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 001619&&001974 | 2025-10-18 | 2026-01-22 | D | PEN | Awaiting S.O.'s response | 2 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | PEN
001620 | 00 | Htet Nu | EICA | NA | 131242 | WSW41 | LC | E | 0001 | 0 | 131242-WSW41-LC-E-0001 | 2025-08-25 | C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026) | Rev 0: For Information. | 2025-09-22 | 2025-10-01 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001620 | 2025-08-25 | 2025-08-25 | 0 | INF | For Information | 1 | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" | INF
001621 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403 | 2025-08-25 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-09-26 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001621 | 2025-08-25 | 2025-10-29 | 0 | NAP | Not Approved | 3 | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | NAP
001621 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403 | 2025-10-01 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 1: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2025-10-06 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001621 | 2025-08-25 | 2025-10-29 | 0 | REJ | Not Approved | 3 | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | NAP
001621 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403 | 2025-10-29 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 2: Not approved - Revise and Resubmit Refer to attached file for comments. | 2025-11-18 | 2026-02-24 | 84 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001621 | 2025-08-25 | 2025-10-29 | 0 | NAP | Not Approved | 3 | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | NAP
001622 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0006 | 0 | 131242-WST02-QA-S-0006 | 2025-08-25 | ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-22 | 2025-10-24 | 44 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001622 | 2025-08-25 | 2025-08-25 | 0 | INF | For Information | 1 | "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | INF
001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1602 | A | 131242-WST02-DR-S-1602 | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | 71 | Approved with Comments | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001623 | 2025-08-25 | 2025-08-25 | A | AWC | Approved with Comments | 1 | "SSN Chemical Dosing Platform Design" | AWC
001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1603 | A | 131242-WST02-DR-S-1603 | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | 71 | Approved with Comments | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001623 | 2025-08-25 | 2025-08-25 | A | AWC | Approved with Comments | 1 | "SSN Chemical Dosing Platform Design" | AWC
001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5604 | A | 131242-WST02-DR-S-5604 | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | 71 | Approved with Comments | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001623&&001656 | 2025-08-25 | 2025-09-08 | A.1 | AWC | Not Approved | 2 | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | NAP
001624 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0018 | 0 | 131242-WST02-OM-M-0018 | 2025-08-25 | Operation and Maintenance Manual for Parabolic Screen | NA | 2025-09-22 |  | 155 | Awaiting S.O.'s response | YES | 2025-10-10 | NO | Overdue | 0 |  |  | 001624 | 2025-08-25 | 2025-08-25 | 0 | PEN | Awaiting S.O.'s response | 1 | "Operation and Maintenance Manual for Parabolic Screen" | PEN
001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | 54 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 243 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | 54 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 243 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | 54 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 243 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
001626 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0027 | 0 | 131242-WSW41-QA-A-0027 | 2025-08-26 | Material Submission for Waterproofing (Pro-Werkze Pte Ltd) | R0: Approved | 2025-09-23 | 2025-09-17 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001626 | 2025-08-26 | 2025-08-26 | 0 | APP | Approved | 1 | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" | APP
001627 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0068 | 0 | 131242-WSW41-LT-PM-0068 | 2025-08-26 | CV of Team Member (WSHO) | NA | 2025-09-23 | 2025-09-11 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001627 | 2025-08-26 | 2025-08-26 | 0 | APP | Approved | 1 | "CV of Team Member (WSHO)" | APP
001628 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0045 | 0 | 131242-WST02-QA-EI-0045 | 2025-08-27 | SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-24 | 2025-10-01 | 25 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001628 | 2025-08-27 | 2025-08-27 | 0 | AWC | Approved with Comments | 1 | "SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B" | AWC
001629 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0007 | 0 | 131242-WST02-QA-S-0007 | 2025-08-27 | ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-24 | 2025-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001629 | 2025-08-27 | 2025-08-27 | 0 | INF | For Information | 1 | "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | INF
001630 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | B | 0001 | 0 | 131242-WSW41-PO-B-0001 | 2025-08-27 | Unpriced PO for Building Management System (Willowglen) | NA | 2025-09-24 |  | 153 | Awaiting S.O.'s response | YES | 2025-10-14 | NO | Overdue | 0 |  |  | 001630 | 2025-08-27 | 2025-08-27 | 0 | PEN | Awaiting S.O.'s response | 1 | "Unpriced PO for Building Management System (Willowglen)" | PEN
001631 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0006 | 0 | 131242-WSD11-VI-I-0006 | 2025-08-27 | Vendor Information of BD Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-10-30 | 46 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001631 | 2025-08-27 | 2025-08-27 | 0 | AWC | Approved with Comments | 1 | "Vendor Information of BD Flowmeter " | AWC
001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5390 | A | 131242-WST02-DR-I-5390 | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | 75 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001632 | 2025-08-27 | 2025-08-27 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | AWC
001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5391 | A | 131242-WST02-DR-I-5391 | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | 75 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001632 | 2025-08-27 | 2025-08-27 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | AWC
001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5392 | A | 131242-WST02-DR-I-5392 | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | 75 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001632 | 2025-08-27 | 2025-08-27 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | AWC
001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5393 | A | 131242-WST02-DR-I-5393 | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | 75 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001632 | 2025-08-27 | 2025-08-27 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | AWC
001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5394 | A | 131242-WST02-DR-I-5394 | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | 75 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001632 | 2025-08-27 | 2025-08-27 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | AWC
001633 | 00 | Karthik | EICA | NA | 131242 | WSD11 | BQ | I | 0010 | 0 | 131242-WSD11-BQ-I-0010 | 2025-08-27 | Cable List for RIO-0101 | Rev 0: Rejected. No resubmission required. | 2025-09-24 | 2025-12-10 | 75 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001633 | 2025-08-27 | 2025-08-27 | 0 | REJ | Rejected | 1 | "Cable List for RIO-0101" | REJ
001634 | 00 | Karthik | EICA | NA | 131242 | WSD11 | BQ | I | 0011 | 0 | 131242-WSD11-BQ-I-0011 | 2025-08-27 | Cable List for RIO-002A | Rev 0: Rejected. No resubmission required. | 2025-09-24 | 2025-12-10 | 75 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001634 | 2025-08-27 | 2025-08-27 | 0 | REJ | Rejected | 1 | "Cable List for RIO-002A" | REJ
001635 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0046 | 0 | 131242-WSW41-QA-E-0046 | 2025-08-28 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | Rev 0: Not approved. To revise and resubmit. Refer to attache file for comments. | 2025-09-25 | 2025-10-01 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001635 | 2025-08-28 | 2025-10-02 | 1 | NAP | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" | AWC
001635 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0046 | 1 | 131242-WSW41-QA-E-0046 | 2025-10-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-22 | 2025-10-10 | 6 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001635 | 2025-08-28 | 2025-10-02 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" | AWC
001636 | 00 | Joo Kwan | Process | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-08-29 | Testing Check List (Process) | Approved with comments. | 2025-09-26 | 2025-10-01 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | AWC | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0011 | 0 | 131242-WSW41-QA-N-0011 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0012 | 0 | 131242-WSW41-QA-N-0012 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0013 | 0 | 131242-WSW41-QA-N-0013 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0014 | 0 | 131242-WSW41-QA-N-0014 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0015 | 0 | 131242-WSW41-QA-N-0015 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0016 | 0 | 131242-WSW41-QA-N-0016 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0017 | 0 | 131242-WSW41-QA-N-0017 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 15 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | PEN | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001637 | 00 | Joo Kwan | Process | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-08-29 | Commissioning Plan for EQ Tank and Lamella Clarifier | NA | 2025-09-26 | 2025-09-08 | 6 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | AWC | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001638 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0200 | 0 | 131242-WSD11-QA-N-0200 | 2025-08-29 | Commissioning Plan for THP Train | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-26 | 2025-09-04 | 4 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001638 | 2025-08-29 | 2025-08-29 | 0 | AWC | Approved with Comments | 1 | "Commissioning Plan for THP Train" | AWC
001639 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0050 | 0 | 131242-WST02-QA-I-0050 | 2025-08-29 | Factory Acceptance Test Report for Conductive Probe Level Switches | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-26 | 2025-11-14 | 55 | Approved with Comments | YES | 2025-12-04 | NO | Resubmitted | 0 |  |  | 001639 | 2025-08-29 | 2025-08-29 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Conductive Probe Level Switches" | AWC
001640 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0301 | C | 131242-WSD11-DR-S-0301 | 2025-08-29 | HDG Grating Clamp Details | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-26 | 2025-10-23 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001640 | 2025-08-29 | 2025-08-29 | C | NAP | Not Approved | 1 | "HDG Grating Clamp Details" | NAP
001640 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment sheet | NA | 131242-WSD11-DR-S-comment sheet | 2025-11-05 | HDG Grating Clamp Details | Rev 1: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-25 | 2025-11-13 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001640 | 2025-11-05 | 2025-11-05 | NA | NAP | Not Approved | 1 | "HDG Grating Clamp Details" | NAP
001640 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment sheet.R1 | NA | 131242-WSD11-DR-S-comment sheet.R1 | 2025-11-24 | HDG Grating Clamp Details | Rev 2: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-12 | 2025-12-29 | 25 | Not Approved | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001640 | 2025-11-24 | 2025-11-24 | NA | NAP | Not Approved | 1 | "HDG Grating Clamp Details" | NAP
001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1604 | F | 131242-WSD11-DR-S-1604 | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | 13 | Not Approved | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 001641 | 2025-08-29 | 2025-08-29 | F | NAP | Not Approved | 1 | "THP Silo Crossover Platform Pipe Support" | NAP
001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5603 | E | 131242-WSD11-DR-S-5603 | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | 13 | Not Approved | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 001641 | 2025-08-29 | 2025-08-29 | E | NAP | Not Approved | 1 | "THP Silo Crossover Platform Pipe Support" | NAP
001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5604 | F | 131242-WSD11-DR-S-5604 | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | 13 | Not Approved | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 001641 | 2025-08-29 | 2025-08-29 | F | NAP | Not Approved | 1 | "THP Silo Crossover Platform Pipe Support" | NAP
001642 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5471 | A | 131242-WST02-DR-M-5471 | 2025-09-01 | GA drawing for Sampling Sink | NA | 2025-09-29 |  | 150 | Awaiting S.O.'s response | YES | 2025-10-17 | NO | Overdue | 0 |  |  | 001642 | 2025-09-01 | 2025-09-01 | A | PEN | Awaiting S.O.'s response | 1 | "GA drawing for Sampling Sink" | PEN
001643 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0047 | 0 | 131242-WST02-QA-EI-0047 | 2025-09-01 | SAT Report for WST02-MCC-1001A & WST02-MCC-1001B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-29 | 2025-10-01 | 22 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001643 | 2025-09-01 | 2025-09-01 | 0 | AWC | Approved with Comments | 1 | "SAT Report for WST02-MCC-1001A & WST02-MCC-1001B" | AWC
001644 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | M | 0116 | 0 | 131242-WSW41-QA-M-0116 | 2025-09-01 | Load Test Reports for Top Manway (Aluminium Hatch) | NA | 2025-09-29 |  | 150 | Awaiting S.O.'s response | YES | 2025-10-17 | NO | Overdue | 0 |  |  | 001644 | 2025-09-01 | 2025-09-01 | 0 | PEN | Awaiting S.O.'s response | 1 | "Load Test Reports for Top Manway (Aluminium Hatch)" | PEN
001645 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0069 | 0 | 131242-WSW41-LT-PM-0069 | 2025-09-02 | Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | Rev (0): Rejected. Please refer to S.O. correspondence no. 409 dated 3 Oct 2025. | 2025-09-30 | 2025-10-15 | 31 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001645 | 2025-09-02 | 2025-09-02 | 0 | REJ | Rejected | 1 | "Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | REJ
001646 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CN | E | 0002 | 0 | 131242-WST02-CN-E-0002 | 2025-09-03 | RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-01 | 2025-10-06 | 23 | Not Approved | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001646 | 2025-09-03 | 2025-09-03 | 0 | NAP | Not Approved | 1 | "RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base" | NAP
001647 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0026 | 0 | 131242-WSW41-PC-W-0026 | 2025-09-03 | Payment Claim No.26 | Rev (0): Approved. Please refer S.O. correspondence no. 396 dated 9 Sep 25. | 2025-10-01 | 2025-09-23 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001647 | 2025-09-03 | 2025-09-03 | 0 | APP | Approved | 1 | "Payment Claim No.26" | APP
001648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0046 | 0 | 131242-WSD11-DS-M-0046 | 2025-09-04 | THP G2D Pressure Reducing Valve Data Sheet | Rev 0: Approved | 2025-10-02 | 2025-10-22 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001648 | 2025-09-04 | 2025-09-04 | 0 | APP | Approved | 1 | "THP G2D Pressure Reducing Valve Data Sheet" | APP
001649 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5560 | 0 | 131242-WST02-DS-M-5560 | 2025-09-04 | Solenoid Valve Data Sheet | Rev 0: Approved | 2025-10-02 | 2025-10-22 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001649 | 2025-09-04 | 2026-12-29 | 1 | APP | Approved | 2 | "Solenoid Valve Data Sheet" | APP
001649 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5560 | 1 | 131242-WST02-DS-M-5560 | 2026-12-29 | Solenoid Valve Data Sheet | Rev 0: Approved | 2027-01-18 |  | 0 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 001649 | 2025-09-04 | 2026-12-29 | 1 | PEN | Approved | 2 | "Solenoid Valve Data Sheet" | APP
001650 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0054 | 0 | 131242-WST02-QA-I-0054 | 2025-09-04 | Vendor Manufacturing Inspection Test Plan for Rotameter | Rev 0: Approved with comments. No resubmission required. | 2025-10-02 | 2025-12-10 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001650&&001717 | 2025-09-04 | 2025-10-01 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Rotameter " && "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" | AWC
001651 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0051 | 0 | 131242-WST02-QA-I-0051 | 2025-09-04 | FAT Report for RIO Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-10 | 69 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001651 | 2025-09-04 | 2025-09-04 | 0 | AWC | Approved with Comments | 1 | "FAT Report for RIO Mock Up Panel " | AWC
001652 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0052 | 0 | 131242-WST02-QA-I-0052 | 2025-09-04 | FAT Report for PLC Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-09 | 68 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001652 | 2025-09-04 | 2025-09-04 | 0 | INF | For Information | 1 | "FAT Report for PLC Mock Up Panel " | INF
001653 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0053 | 0 | 131242-WST02-QA-I-0053 | 2025-09-04 | FAT Report for FFOTP Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-09 | 68 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001653 | 2025-09-04 | 2025-09-04 | 0 | AWC | Approved with Comments | 1 | "FAT Report for FFOTP Mock Up Panel" | AWC
001654 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0008 | 0 | 131242-WST02-QA-S-0008 | 2025-09-04 | ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission | For information | 2025-10-02 | 2025-10-29 | 39 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001654 | 2025-09-04 | 2025-09-04 | 0 | INF | For Information | 1 | "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | INF
001655 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | RT | Z | 0002 | 0 | 131242-WSD11-RT-Z-0002 | 2025-09-08 | FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-06 | 2025-10-06 | 20 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001655 | 2025-09-08 | 2025-09-08 | 0 | AWC | Approved with Comments | 1 | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" | AWC
001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A.1 | 131242-WST02-DR-S-8600 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | 33 | Not Approved | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001656&&001733 | 2025-09-08 | 2025-11-06 | A.3 | NAP | Approved with Comments | 3 | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011 | A.1 | 131242-WST02-DR-S-1011 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | 33 | Not Approved | YES | 2025-11-12 | NO | Resubmitted | 52 |  |  | 001284&&001656 | 2025-05-13 | 2025-09-08 | A.1 | NAP | Not Approved | 2 | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | NAP
001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5604 | A.1 | 131242-WST02-DR-S-5604 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | 33 | Not Approved | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001623&&001656 | 2025-08-25 | 2025-09-08 | A.1 | NAP | Not Approved | 2 | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | NAP
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5016 | A | 131242-WST02-DR-M-5016 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5017 | A | 131242-WST02-DR-M-5017 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5018 | A | 131242-WST02-DR-M-5018 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5019 | A | 131242-WST02-DR-M-5019 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5050 | A | 131242-WST02-DR-M-5050 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5051 | A | 131242-WST02-DR-M-5051 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5052 | A | 131242-WST02-DR-M-5052 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5053 | A | 131242-WST02-DR-M-5053 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5054 | A | 131242-WST02-DR-M-5054 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5055 | A | 131242-WST02-DR-M-5055 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5056 | A | 131242-WST02-DR-M-5056 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5057 | A | 131242-WST02-DR-M-5057 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5060 | A | 131242-WST02-DR-M-5060 | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | 145 | Awaiting S.O.'s response | YES | 2025-10-24 | NO | Overdue | 0 |  |  | 001657 | 2025-09-08 | 2025-09-08 | A | PEN | Awaiting S.O.'s response | 1 | "Chemical Cabinet - GA drawing" | PEN
001658 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0114 | 0 | 131242-WSW41-QA-M-0114 | 2025-09-08 | Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-06 | 2025-12-23 | 76 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001658 | 2025-09-08 | 2025-09-08 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe)" | AWC
001659 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0063 | 0 | 131242-WST02-CD-IM-0063 | 2025-09-08 | VCM Submission for 2025-08 | For Information | 2025-10-06 | 2025-10-01 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001659 | 2025-09-08 | 2025-09-08 | 0 | INF | For Information | 1 | "VCM Submission for 2025-08" | INF
001660 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0032 | 0 | 131242-WSW41-SP-C-0032 | 2025-09-09 | Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe) | R0: Not Approved Please refer to comment sheet for resubmission. | 2025-10-07 | 2025-10-24 | 33 | Not Approved | YES | 2025-11-13 | NO | Resubmitted | 25 |  |  | 001436&&001660 | 2025-07-05 | 2025-09-09 | 0 | NAP | Not Approved | 2 | "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" && "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" | NAP
001661 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0043 | 0 | 131242-WSW41-QA-C-0043 | 2025-09-09 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025 | For information | 2025-10-07 | 2025-10-10 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001661 | 2025-09-09 | 2025-09-09 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025" | INF
001662 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0055 | 0 | 131242-WST02-QA-I-0055 | 2025-09-09 | Factory Acceptance Test Report for Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-07 | 2025-12-10 | 66 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001662 | 2025-09-09 | 2025-09-09 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Rotameter" | AWC
001663 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0017 | 0 | 131242-WSW41-PO-I-0017 | 2025-09-09 | Unpriced PO for Raised Floor (Momentum Construction) | Rev 0: Accepted for Information | 2025-10-07 | 2025-12-05 | 63 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001663 | 2025-09-09 | 2025-09-09 | 0 | INF | For Information | 1 | "Unpriced PO for Raised Floor (Momentum Construction)" | INF
001664 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0018 | 0 | 131242-WSW41-PO-I-0018 | 2025-09-09 | Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser) | Rev 0: Accepted for Information | 2025-10-07 | 2025-12-05 | 63 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001664 | 2025-09-09 | 2025-09-09 | 0 | INF | For Information | 1 | "Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser)" | INF
001665 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0019 | 0 | 131242-WSW41-PO-I-0019 | 2025-09-09 | Unpriced PO for Control Panels (Fox Singapore) | Rev 0: Accepted for Information. No resubmission required. Refer attached file for comments. | 2025-10-07 | 2025-10-27 | 34 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001665 | 2025-09-09 | 2025-09-09 | 0 | INF | For Information | 1 | "Unpriced PO for Control Panels (Fox Singapore)" | INF
001666 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0020 | 0 | 131242-WSW41-PO-I-0020 | 2025-09-09 | Unpriced PO for PMS Panel (Vector Infotech) | Rev 0: Accepted for Information. No resubmission required. Refer attached file for comments. | 2025-10-07 | 2025-10-27 | 34 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001666 | 2025-09-09 | 2025-09-09 | 0 | INF | For Information | 1 | "Unpriced PO for PMS Panel (Vector Infotech)" | INF
001667 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0117 | 0 | 131242-WSW41-QA-M-0117 | 2025-09-10 | FAT Report for THP Area Pipe Supports | Rev 0: Approved | 2025-10-08 | 2025-12-23 | 74 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001667 | 2025-09-10 | 2025-09-10 | 0 | APP | Approved | 1 | "FAT Report for THP Area Pipe Supports" | APP
001668 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0005 | 0 | 131242-WSD11-SP-I-0005 | 2025-09-10 | Master Control for THP | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-15 | 68 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001668 | 2025-09-10 | 2025-09-10 | 0 | NAP | Not Approved | 1 | "Master Control for THP" | NAP
001669 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0118 | 0 | 131242-WSW41-QA-M-0118 | 2025-09-10 | FAT Report for SWPR Pipe Guide Supports | Rev 0: Approved | 2025-10-08 | 2025-12-23 | 74 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001669 | 2025-09-10 | 2025-09-10 | 0 | APP | Approved | 1 | "FAT Report for SWPR Pipe Guide Supports" | APP
001670 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0119 | 0 | 131242-WSW41-QA-M-0119 | 2025-09-10 | FAT Report for SWPR SS 316L Pipes | Rev 0: Approved | 2025-10-08 | 2025-12-23 | 74 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001670 | 2025-09-10 | 2025-09-10 | 0 | APP | Approved | 1 | "FAT Report for SWPR SS 316L Pipes" | APP
001671 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0049 | 0 | 131242-WST02-QA-EI-0049 | 2025-09-10 | FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-08 | 2026-02-02 | 103 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 001671 | 2025-09-10 | 2025-09-10 | 0 | AWC | Approved with Comments | 1 | "FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight)" | AWC
001672 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0019 | 0 | 131242-WST02-DS-I-0019 | 2025-09-10 | Datasheet for Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-11-05 | 40 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001672 | 2025-09-10 | 2025-09-10 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Rotameter" | AWC
001673 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0020 | 0 | 131242-WST02-DS-I-0020 | 2025-09-10 | Datasheet for Conductive Level Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-11-13 | 46 | Approved with Comments | YES | 2025-12-03 | NO | Resubmitted | 0 |  |  | 001673 | 2025-09-10 | 2025-09-10 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Conductive Level Switch" | AWC
001674 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5371 | A | 131242-WST02-DR-I-5371 | 2025-09-10 | SSN Instrument Hookup Drawing for Temperature Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | 65 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001674 | 2025-09-10 | 2025-09-10 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Temperature Transmitter" | AWC
001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5340 | A | 131242-WST02-DR-I-5340 | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | 65 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001675 | 2025-09-10 | 2025-09-10 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | AWC
001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5341 | A | 131242-WST02-DR-I-5341 | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | 65 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001675 | 2025-09-10 | 2025-09-10 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | AWC
001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5342 | A | 131242-WST02-DR-I-5342 | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | 65 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001675 | 2025-09-10 | 2025-09-10 | A | AWC | Approved with Comments | 1 | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | AWC
001676 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | Z | 0002 | 0 | 131242-WST02-RT-Z-0002 | 2025-09-11 | 80% SSN ALMOP Report | NA | 2025-10-09 |  | 142 | Awaiting S.O.'s response | YES | 2025-10-29 | NO | Overdue | 0 |  |  | 001676 | 2025-09-11 | 2025-09-11 | 0 | PEN | Awaiting S.O.'s response | 1 | "80% SSN ALMOP Report" | PEN
001677 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1404 | 0 | 131242-WST02-QA-E-1404 | 2025-09-12 | Sample Board Submission for 40W Floodling Lighting | NA | 2025-10-10 | 2025-09-26 | 10 | Not Approved | YES | 2025-10-16 | NO | Resubmitted | 0 |  |  | 001677 | 2025-09-12 | 2025-09-12 | 0 | NAP | Not Approved | 1 | "Sample Board Submission for 40W Floodling Lighting" | NAP
001678 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 0 | 131242-WSW41-QA-M-0120 | 2025-09-12 | FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH) | Rev 0: Approved | 2025-10-10 | 2025-12-15 | 66 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001678&&001684 | 2025-09-12 | 2025-10-21 | 1 | APP | Approved with Comments | 3 | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | AWC
001679 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0009 | 0 | 131242-WST02-QA-S-0009 | 2025-09-15 | ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-10-13 | 2025-10-29 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001679 | 2025-09-15 | 2025-09-15 | 0 | INF | For Information | 1 | "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | INF
001680 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0050 | 0 | 131242-WSD11-QA-E-0050 | 2025-09-16 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B | Rev 0: Approved. | 2025-10-14 | 2025-10-06 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001680 | 2025-09-16 | 2025-09-16 | 0 | APP | Approved | 1 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B" | APP
001681 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0028 | 0 | 131242-WSW41-RT-PM-0028 | 2025-09-16 | C4B Monthly Progress Report Number No.28 (08 25) | NA | 2025-10-14 | 2025-09-26 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001681 | 2025-09-16 | 2025-09-16 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.28 (08 25)" | AWC
001682 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | BCA_INST_ANNEX_E | NA | 131242-NA-NA-NA-BCA_INST_ANNEX_E | 2025-09-17 | Annex E - ST601 & ST602 ERSS | For information | 2025-10-15 | 2025-10-06 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001682 | 2025-09-17 | 2025-09-17 | NA | INF | For Information | 1 | "Annex E - ST601 & ST602 ERSS" | INF
001683 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0051 | 0 | 131242-WST02-QA-E-0051 | 2025-09-18 | FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. | 2025-10-16 | 2025-10-06 | 12 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 001683 | 2025-09-18 | 2025-09-18 | 0 | AWC | Approved with Comments | 1 | "FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight)" | AWC
001684 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 0 | 131242-WSW41-QA-M-0120 | 2025-09-22 | FAT Report for Diffuser System (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-20 | 2025-10-06 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001678&&001684 | 2025-09-12 | 2025-10-21 | 1 | AWC | Approved with Comments | 3 | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | AWC
001684 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 1 | 131242-WSW41-QA-M-0120 | 2025-10-21 | FAT Report for Diffuser System (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-10 |  | 114 | Awaiting S.O.'s response | YES | 2025-12-08 | NO | Overdue | 0 |  |  | 001678&&001684 | 2025-09-12 | 2025-10-21 | 1 | PEN | Approved with Comments | 3 | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | AWC
001685 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0022 | 0 | 131242-WST02-DS-I-0022 | 2025-09-23 | Datasheet for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-10-23 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001685 | 2025-09-23 | 2026-01-15 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Thermal Flow Switch" | AWC
001685 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0022 | 1 | 131242-WST02-DS-I-0022 | 2026-01-15 | Datasheet for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-04 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001685 | 2025-09-23 | 2026-01-15 | 1 | PEN | Approved with Comments | 2 | "Datasheet for Thermal Flow Switch" | AWC
001686 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0071 | 0 | 131242-WSW41-LT-PM-0071 | 2025-09-23 | Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) | Rev (0): Received for information. Please refer to S.O. correspondence no. 407 dated 3 Oct 25. | 2025-10-21 | 2025-10-15 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001686 | 2025-09-23 | 2025-09-23 | 0 | INF | For Information | 1 | "Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) " | INF
001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5490 | A | 131242-WST02-DR-I-5490 | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | 56 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001687 | 2025-09-23 | 2025-09-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Flow Switch" | AWC
001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5491 | A | 131242-WST02-DR-I-5491 | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | 56 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001687 | 2025-09-23 | 2025-09-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Flow Switch" | AWC
001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5492 | A | 131242-WST02-DR-I-5492 | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | 56 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001687 | 2025-09-23 | 2025-09-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Flow Switch" | AWC
001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5493 | A | 131242-WST02-DR-I-5493 | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | 56 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001687 | 2025-09-23 | 2025-09-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Flow Switch" | AWC
001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5494 | A | 131242-WST02-DR-I-5494 | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | 56 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001687 | 2025-09-23 | 2025-09-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Flow Switch" | AWC
001688 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0070 | 0 | 131242-WSW41-LT-PM-0070 | 2025-09-23 | Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays | Rev (0): Rejected. Please refer to S.O. correspondence no. 435 dated 13 Feb 2026. | 2025-10-21 | 2026-02-24 | 110 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001688 | 2025-09-23 | 2025-09-23 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays" | REJ
001689 | 00 | Danny | QAQC | NA | 131242 | WSW41 | QA | M | 0115 | 0 | 131242-WSW41-QA-M-0115 | 2025-09-24 | FAT Report for Manual Knife Gate Valves - Batch 3 (JASH) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-22 | 2026-01-30 | 92 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001689 | 2025-09-24 | 2025-09-24 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Manual Knife Gate Valves - Batch 3 (JASH)" | AWC
001690 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0009 | 0 | 131242-WST02-VI-A-0009 | 2025-09-24 | Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd. | Approved | 2025-10-22 | 2025-10-13 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001690 | 2025-09-24 | 2025-09-24 | 0 | APP | Approved | 1 | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." | APP
001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5480 | A | 131242-WST02-DR-I-5480 | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | 56 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001691 | 2025-09-24 | 2025-09-24 | A | NAP | Not Approved | 1 | "Hookup Drawing - Hydrostatic Level Switch" | NAP
001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5481 | A | 131242-WST02-DR-I-5481 | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | 56 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001691 | 2025-09-24 | 2025-09-24 | A | NAP | Not Approved | 1 | "Hookup Drawing - Hydrostatic Level Switch" | NAP
001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5482 | A | 131242-WST02-DR-I-5482 | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | 56 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001691 | 2025-09-24 | 2025-09-24 | A | NAP | Not Approved | 1 | "Hookup Drawing - Hydrostatic Level Switch" | NAP
001692 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0012 | 0 | 131242-WST02-DS-I-0012 | 2025-09-24 | Datasheet for Pressure Transmitter (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-10-23 | 21 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001692 | 2025-09-24 | 2025-09-24 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Pressure Transmitter (SSN)" | AWC
001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5310 | A | 131242-WST02-DR-I-5310 | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | 55 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001693 | 2025-09-24 | 2025-09-24 | A | AWC | Approved with Comments | 1 | "Hookup Drawing for Pressure Transmitter" | AWC
001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5311 | A | 131242-WST02-DR-I-5311 | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | 55 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001693 | 2025-09-24 | 2025-09-24 | A | AWC | Approved with Comments | 1 | "Hookup Drawing for Pressure Transmitter" | AWC
001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5312 | A | 131242-WST02-DR-I-5312 | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | 55 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001693 | 2025-09-24 | 2025-09-24 | A | AWC | Approved with Comments | 1 | "Hookup Drawing for Pressure Transmitter" | AWC
001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5313 | A | 131242-WST02-DR-I-5313 | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | 55 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001693 | 2025-09-24 | 2025-09-24 | A | AWC | Approved with Comments | 1 | "Hookup Drawing for Pressure Transmitter" | AWC
001694 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0021 | 0 | 131242-WST02-DS-I-0021 | 2025-09-24 | Datasheet for Pressure Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-15 | 58 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001694 | 2025-09-24 | 2025-09-24 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Pressure Switch (SSN)" | AWC
001695 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 0 | 131242-WSW41-QA-M-0121 | 2025-09-25 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-23 | 2026-01-07 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001695&&001696 | 2025-09-25 | 2026-01-27 | 1 | NAP | Not Approved | 3 | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | NAP
001695 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 1 | 131242-WSW41-QA-M-0121 | 2026-01-27 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001695&&001696 | 2025-09-25 | 2026-01-27 | 1 | PEN | Not Approved | 3 | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | NAP
001696 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 0_Withdraw | 131242-WSW41-QA-M-0121 | 2025-09-25 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Contractor request to VOID due to duplication of submission | 2025-10-23 | 2025-10-01 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 001695&&001696 | 2025-09-25 | 2026-01-27 | 1 | VOID | Not Approved | 3 | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | NAP
001697 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0122 | 0 | 131242-WSW41-QA-M-0122 | 2025-09-25 | FAT Report for Actuated Ball Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-23 | 2026-01-07 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001697 | 2025-09-25 | 2026-01-27 | 1 | NAP | Not Approved | 2 | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | NAP
001697 | 01 | Soe Myat | QAQC | NA | 131242 | WSW41 | QA | M | 0122 | 1 | 131242-WSW41-QA-M-0122 | 2026-01-27 | FAT Report for Actuated Ball Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001697 | 2025-09-25 | 2026-01-27 | 1 | PEN | Not Approved | 2 | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | NAP
001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.1 | 131242-WST02-SD-S-8600 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | 31 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 9 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | NAP | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.1 | 131242-WST02-SD-S-1007 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | 31 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001616&&001698&&001803 | 2025-08-22 | 2026-02-09 | A.5 | NAP | Not Approved | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | A.1 | 131242-WST02-SD-S-5003 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | 31 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001498&&001698&&001803 | 2025-07-22 | 2026-02-09 | A.5 | NAP | Not Approved | 3 | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A.1 | 131242-WST02-SD-S-5004 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | 31 | Not Approved | YES | 2025-11-28 | NO | Resubmitted | 0 |  |  | 001698&&001700&&001803 | 2025-09-26 | 2026-02-09 | A.5 | NAP | Rejected | 3 | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | REJ
001699 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0010 | 0 | 131242-WST02-QA-S-0010 | 2025-09-26 | ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-10-24 | 2025-10-13 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001699 | 2025-09-26 | 2025-09-26 | 0 | INF | For Information | 1 | "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | INF
001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1009 | A | 131242-WST02-SD-S-1009 | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | 11 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001616&&001700 | 2025-08-22 | 2025-09-29 | A | REJ | Rejected | 2 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | REJ
001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A | 131242-WST02-SD-S-5004 | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | 11 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001698&&001700&&001803 | 2025-09-26 | 2026-02-09 | A.5 | REJ | Rejected | 3 | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | REJ
001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600 | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | 11 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | REJ | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3030 | A | 131242-WSD11-DR-IC-3030 | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001701 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "THP PMS Panel GA and Wiring Diagram" | AWC
001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3031 | A | 131242-WSD11-DR-IC-3031 | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001701 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "THP PMS Panel GA and Wiring Diagram" | AWC
001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3032 | A | 131242-WSD11-DR-IC-3032 | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001701 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "THP PMS Panel GA and Wiring Diagram" | AWC
001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3033 | A | 131242-WSD11-DR-IC-3033 | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001701 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "THP PMS Panel GA and Wiring Diagram" | AWC
001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3034 | A | 131242-WSD11-DR-IC-3034 | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001701 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "THP PMS Panel GA and Wiring Diagram" | AWC
001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3030 | A | 131242-WST02-DR-IC-3030 | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001702 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "SSN PMS Panel GA and Wiring Diagram" | AWC
001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3031 | A | 131242-WST02-DR-IC-3031 | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001702 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "SSN PMS Panel GA and Wiring Diagram" | AWC
001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3032 | A | 131242-WST02-DR-IC-3032 | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001702 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "SSN PMS Panel GA and Wiring Diagram" | AWC
001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3033 | A | 131242-WST02-DR-IC-3033 | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001702 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "SSN PMS Panel GA and Wiring Diagram" | AWC
001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3034 | A | 131242-WST02-DR-IC-3034 | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | 6 | Approved with Comments | YES | 2025-10-27 | NO | Resubmitted | 0 |  |  | 001702 | 2025-09-29 | 2025-09-29 | A | AWC | Approved with Comments | 1 | "SSN PMS Panel GA and Wiring Diagram" | AWC
001703 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5351 | 0 | 131242-WSW41-DR-M-5351 | 2025-09-29 | SP Item - Flange Adaptor (Synchong Hoe) | NA | 2025-10-27 |  | 130 | Awaiting S.O.'s response | YES | 2025-11-14 | NO | Overdue | 0 |  |  | 001703 | 2025-09-29 | 2025-09-29 | 0 | PEN | Awaiting S.O.'s response | 1 | "SP Item - Flange Adaptor (Synchong Hoe)" | PEN
001704 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0052 | 0 | 131242-WST02-QA-E-0052 | 2025-09-29 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-27 | 2025-10-15 | 12 | Approved with Comments | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 001704 | 2025-09-29 | 2025-09-29 | 0 | AWC | Approved with Comments | 1 | " Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss)" | AWC
001705 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0056 | 0 | 131242-WST02-QA-I-0056 | 2025-09-30 | Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-28 | 2025-12-11 | 52 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001705 | 2025-09-30 | 2025-09-30 | 0 | NAP | Not Approved | 1 | " Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN)" | NAP
001706 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0123 | 0 | 131242-WSW41-QA-M-0123 | 2025-09-30 | FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack | Rev 0: Approved | 2025-10-28 | 2026-01-30 | 88 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001706 | 2025-09-30 | 2025-09-30 | 0 | APP | Approved | 1 | "FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack" | APP
001707 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0124 | 0 | 131242-WSW41-QA-M-0124 | 2025-09-30 | FAT Report for Clamp Shoe Support in Site Wide Pipe Rack | Rev 0: Approved | 2025-10-28 | 2026-01-30 | 88 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001707 | 2025-09-30 | 2025-09-30 | 0 | APP | Approved | 1 | "FAT Report for Clamp Shoe Support in Site Wide Pipe Rack" | APP
001708 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0044 | 0 | 131242-WSW41-QA-C-0044 | 2025-09-30 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025 | For information | 2025-10-28 | 2025-10-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001708 | 2025-09-30 | 2025-09-30 | 0 | INF | For Information | 1 | " Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025" | INF
001709 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0021 | 0 | 131242-WSW41-PO-I-0021 | 2025-09-30 | Unpriced PO for PDB & LCP (GSM) | Rev 0: For Information | 2025-10-28 | 2025-12-11 | 52 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001709 | 2025-09-30 | 2025-09-30 | 0 | INF | For Information | 1 | "Unpriced PO for PDB & LCP (GSM) " | INF
001710 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | E | 0029 | 0 | 131242-WSW41-PO-E-0029 | 2025-09-30 | Unpriced PO for Earthing Material (Heng Hardware) | For Information | 2025-10-28 | 2025-11-05 | 26 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001710 | 2025-09-30 | 2025-09-30 | 0 | INF | For Information | 1 | "Unpriced PO for Earthing Material (Heng Hardware) " | INF
001711 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | E | 0028 | 0 | 131242-WSW41-PO-E-0028 | 2025-09-30 | Unpriced PO for Power and Lighting Material (Hong An Engineering) | For information | 2025-10-28 | 2025-11-10 | 29 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001711 | 2025-09-30 | 2025-09-30 | 0 | INF | For Information | 1 | "Unpriced PO for Power and Lighting Material (Hong An Engineering)" | INF
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0011 | 0 | 131242-WSW41-QA-N-0011 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0012 | 0 | 131242-WSW41-QA-N-0012 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0013 | 0 | 131242-WSW41-QA-N-0013 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0014 | 0 | 131242-WSW41-QA-N-0014 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0015 | 0 | 131242-WSW41-QA-N-0015 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0016 | 0 | 131242-WSW41-QA-N-0016 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0017 | 0 | 131242-WSW41-QA-N-0017 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001636&&001712 | 2025-09-30 | 2026-01-28 | 0 | AWC | Approved with Comments | 2 | "Testing Check List (Process)" && "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0018 | 0 | 131242-WSW41-QA-N-0018 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001712 | 2025-09-30 | 2025-09-30 | 0 | AWC | Approved with Comments | 1 | "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0019 | 0 | 131242-WSW41-QA-N-0019 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001712 | 2025-09-30 | 2025-09-30 | 0 | AWC | Approved with Comments | 1 | "T&C Check List " | AWC
001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0020 | 0 | 131242-WSW41-QA-N-0020 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | 61 | Approved with Comments | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001712 | 2025-09-30 | 2025-09-30 | 0 | AWC | Approved with Comments | 1 | "T&C Check List " | AWC
001713 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5753 | 0 | 131242-WST02-DS-M-5753 | 2025-09-30 | Data Sheet for SSN Sludge Comparment Mixing Nozzle | NA | 2025-10-28 |  | 129 | Awaiting S.O.'s response | YES | 2025-11-17 | NO | Overdue | 0 |  |  | 001713 | 2025-09-30 | 2025-09-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "Data Sheet for SSN Sludge Comparment Mixing Nozzle" | PEN
001714 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0300 | 0 | 131242-WSD11-QA-N-0300 | 2025-09-30 | Commissioning Plan for Steam Line | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-10-28 | 2026-01-06 | 70 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001714 | 2025-09-30 | 2025-09-30 | 0 | NAP | Not Approved | 1 | "Commissioning Plan for Steam Line" | NAP
001715 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0047 | 0 | 131242-WSD11-DS-M-0047 | 2025-09-30 | Data Sheet for THP IA Pressure Reducing Valve | Rev 0: Approved | 2025-10-28 | 2025-10-21 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001715 | 2025-09-30 | 2025-09-30 | 0 | APP | Approved | 1 | "Data Sheet for THP IA Pressure Reducing Valve " | APP
001716 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0072 | 0 | 131242-WSW41-LT-PM-0072 | 2025-09-30 | Extension of Time – CM4 Milestone | NA | 2025-10-28 |  | 129 | Awaiting S.O.'s response | YES | 2025-11-17 | NO | Overdue | 0 |  |  | 001716 | 2025-09-30 | 2025-09-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "Extension of Time – CM4 Milestone " | PEN
001717 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0054 | 0 | 131242-WST02-QA-I-0054 | 2025-10-01 | FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-29 | 2026-02-16 | 98 | Approved with Comments | YES | 2026-03-06 | NO | Resubmitted | 0 |  |  | 001650&&001717 | 2025-09-04 | 2025-10-01 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Rotameter " && "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" | AWC
001718 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0053 | 0 | 131242-WST02-QA-EI-0053 | 2025-10-01 | SAT Procedure for MDB Panels (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-29 | 2025-11-25 | 39 | Approved with Comments | YES | 2025-12-15 | NO | Resubmitted | 0 |  |  | 001718 | 2025-10-01 | 2025-10-01 | 0 | AWC | Approved with Comments | 1 | "SAT Procedure for MDB Panels (Sunlight)" | AWC
001719 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0010 | 0 | 131242-WST02-VI-A-0010 | 2025-10-01 | Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-29 | 2025-10-08 | 5 | Not Approved | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001719 | 2025-10-01 | 2025-10-01 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." | NAP
001720 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0011 | 0 | 131242-WST02-VI-A-0011 | 2025-10-01 | Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-29 | 2025-10-08 | 5 | Not Approved | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001720 | 2025-10-01 | 2025-10-01 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." | NAP
001721 | 00 | NA | Mech | NA | 131242 | WSD11 | CL | M | 1087 | 0 | 131242-WSD11-CL-M-1087 | 2025-10-03 | G2D Line Surge Load Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-31 | 2026-01-30 | 85 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001721 | 2025-10-03 | 2025-10-03 | 0 | AWC | Approved with Comments | 1 | "G2D Line Surge Load Calculation Report " | AWC
001722 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0126 | 0 | 131242-WSW41-QA-M-0126 | 2025-10-06 | FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA) | Rev 0: Approved | 2025-11-03 | 2025-10-22 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001722 | 2025-10-06 | 2025-10-06 | 0 | APP | Approved | 1 | "FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA)" | APP
001723 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0028 | 0 | 131242-WSW41-QA-A-0028 | 2025-10-06 | SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-03 | 2025-10-13 | 5 | Approved with Comments | YES | 2025-10-31 | NO | Resubmitted | 0 |  |  | 001723 | 2025-10-06 | 2025-10-06 | 0 | AWC | Approved with Comments | 1 | "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" | AWC
001724 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | EI | 0055 | 0 | 131242-WSD11-QA-EI-0055 | 2025-10-06 | FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight) | Rev 0: Not approved - Revise and Resubmit | 2025-11-03 | 2026-02-09 | 90 | Not Approved | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001724 | 2025-10-06 | 2025-10-06 | 0 | NAP | Not Approved | 1 | "FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight)" | NAP
001725 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | I | 0058 | 0 | 131242-WSD11-QA-I-0058 | 2025-10-06 | Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-03 | 2025-12-10 | 47 | Not Approved | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001725 | 2025-10-06 | 2025-10-06 | 0 | NAP | Not Approved | 1 | "Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP)" | NAP
001726 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | I | 0057 | 0 | 131242-WSD11-QA-I-0057 | 2025-10-06 | Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-03 | 2025-12-10 | 47 | Approved with Comments | YES | 2025-12-30 | NO | Resubmitted | 0 |  |  | 001726 | 2025-10-06 | 2025-10-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP)" | AWC
001727 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0056 | 0 | 131242-WSD11-QA-E-0056 | 2025-10-06 | SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B | Rev 0: Rejected. Refer to attached file for comments. | 2025-11-03 | 2026-02-09 | 90 | Rejected | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001727 | 2025-10-06 | 2025-10-06 | 0 | REJ | Rejected | 1 | "SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B" | REJ
001728 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | ST617 THP-PF-02 Fab | NA | 131242-WSD11-DR-S-ST617 THP-PF-02 Fab | 2025-10-08 | ST617 THP-PF-02 Fabrication Drawing (PE Endorsed) | For Information | 2025-11-05 | 2025-11-24 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001728 | 2025-10-08 | 2025-10-08 | NA | INF | For Information | 1 | "ST617 THP-PF-02 Fabrication Drawing (PE Endorsed)" | INF
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611 | A | 131242-WST02-DR-S-1600_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | NAP | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611 | A | 131242-WST02-DR-S-1601_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | NAP | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1607_ST611 | A | 131242-WST02-DR-S-1607_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001729 | 2025-10-08 | 2025-10-08 | A | NAP | Not Approved | 1 | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611 | A | 131242-WST02-DR-S-5600_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | NAP | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611 | A | 131242-WST02-DR-S-5601_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001460&&001729 | 2025-07-11 | 2025-10-08 | A | NAP | Not Approved | 2 | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5406_ST611 | A | 131242-WST02-DR-S-5406_ST611 | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001729 | 2025-10-08 | 2025-10-08 | A | NAP | Not Approved | 1 | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | NAP
001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1400 | A | 131242-WST02-DR-S-1400 | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 286 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1401 | A | 131242-WST02-DR-S-1401 | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001730&&001914 | 2025-10-08 | 2025-12-18 | H | NAP | Not Approved | 2 | "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-S-5400 | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | 62 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 286 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001731 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0064 | 0 | 131242-WST02-CD-IM-0064 | 2025-10-08 | VCM Submission for 2025-09 | For Information | 2025-11-05 | 2025-10-29 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001731 | 2025-10-08 | 2025-10-08 | 0 | INF | For Information | 1 | "VCM Submission for 2025-09" | INF
001732 | 00 | Freedomer | EICA | NA | 131242 | WST00 | DS | E | 0001 | 0 | 131242-WST00-DS-E-0001 | 2025-10-08 | SSN and THP Local Control Station (LCS) Components Datasheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-05 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001732 | 2025-10-08 | 2025-10-08 | 0 | AWC | Approved with Comments | 1 | "SSN and THP Local Control Station (LCS) Components Datasheet" | AWC
001733 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A | 131242-WST02-DR-S-8600 | 2025-10-09 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-06 | 2025-10-14 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001656&&001733 | 2025-09-08 | 2025-11-06 | A.3 | NAP | Approved with Comments | 3 | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A.3 | 131242-WST02-DR-S-8600 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | 47 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001656&&001733 | 2025-09-08 | 2025-11-06 | A.3 | AWC | Approved with Comments | 3 | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.3 | 131242-WST02-DR-S-1009 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | 47 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001528&&001733 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5004 | A.3 | 131242-WST02-DR-S-5004 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | 47 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001733 | 2025-11-06 | 2025-11-06 | A.3 | AWC | Approved with Comments | 1 | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5005 | A.3 | 131242-WST02-DR-S-5005 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | 47 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001733 | 2025-11-06 | 2025-11-06 | A.3 | AWC | Approved with Comments | 1 | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | AWC
001734 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | Fabrication Drawing | NA | 131242-WSD11-DR-S-Fabrication Drawing | 2025-10-09 | THP-PF01 Grating Fabrication Drawing | For information | 2025-11-06 | 2025-11-13 | 25 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001734 | 2025-10-09 | 2025-10-09 | NA | INF | For Information | 1 | "THP-PF01 Grating Fabrication Drawing" | INF
001735 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 1019 | 0 | 131242-WSW41-VI-M-1019 | 2025-10-10 | Preliminary Design and Vendor Approval – Hose Point | Rev 0: Approved | 2025-11-07 | 2025-11-24 | 31 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001735 | 2025-10-10 | 2025-10-10 | 0 | APP | Approved | 1 | "Preliminary Design and Vendor Approval – Hose Point" | APP
001736 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0001 | 0 | 131242-WSD11-SH-M-0001 | 2025-10-10 | Line List for Hydrotest (CA system) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-07 | 2025-11-24 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001736 | 2025-10-10 | 2025-10-10 | 0 | AWC | Approved with Comments | 1 | "Line List for Hydrotest (CA system)" | AWC
001737 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0029 | 0 | 131242-WSW41-RT-PM-0029 | 2025-10-11 | C4B Monthly Progress Report Number No. 29 (09 25) | Approved with comments which will be addressed in the next MPR. | 2025-11-07 | 2025-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001737&&001746 | 2025-10-11 | 2025-10-13 | 0_VOID | AWC | Rejected | 2 | "C4B Monthly Progress Report Number No. 29 (09 25)" | REJ
001738 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 01247 | 0 | 131242-WSW41-QA-M-01247 | 2025-10-13 | FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) | NA | 2025-11-10 |  | 120 | Awaiting S.O.'s response | YES | 2025-11-28 | NO | Overdue | 0 |  |  | 001738 | 2025-10-13 | 2025-10-13 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) " | PEN
001739 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0128 | 0 | 131242-WSD11-QA-M-0128 | 2025-10-13 | FAT report for Steam Jet Heater (Steam Sparger) | NA | 2025-11-10 |  | 120 | Awaiting S.O.'s response | YES | 2025-11-28 | NO | Overdue | 0 |  |  | 001739 | 2025-10-13 | 2025-10-13 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT report for Steam Jet Heater (Steam Sparger) " | PEN
001740 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | DS | BH | 0001 | 0 | 131242-WST02-DS-BH-0001 | 2025-10-13 | Datasheet for ACMV Equipment | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-10 | 2025-10-22 | 7 | Not Approved | YES | 2025-11-11 | NO | Resubmitted | 0 |  |  | 001740 | 2025-10-13 | 2025-10-13 | 0 | NAP | Not Approved | 1 | "Datasheet for ACMV Equipment" | NAP
001741 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0129 | 0 | 131242-WST02-QA-M-0129 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-1) | Rev0: Approved | 2025-11-10 | 2025-10-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001741 | 2025-10-13 | 2025-10-13 | 0 | APP | Approved | 1 | "FAT Report for Lamella Clarifier Biomass Separator (ARS-1)" | APP
001742 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0130 | 0 | 131242-WST02-QA-M-0130 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-2) | Rev0: Approved | 2025-11-10 | 2025-10-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001742 | 2025-10-13 | 2025-10-13 | 0 | APP | Approved | 1 | "FAT Report for Lamella Clarifier Biomass Separator (ARS-2)" | APP
001743 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0131 | 0 | 131242-WST02-QA-M-0131 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-3) | Rev0: Approved | 2025-11-10 | 2025-10-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001743 | 2025-10-13 | 2025-10-13 | 0 | APP | Approved | 1 | "FAT Report for Lamella Clarifier Biomass Separator (ARS-3)" | APP
001744 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0132 | 0 | 131242-WST02-QA-M-0132 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-4) | Rev0: Approved | 2025-11-10 | 2025-10-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001744 | 2025-10-13 | 2025-10-13 | 0 | APP | Approved | 1 | "FAT Report for Lamella Clarifier Biomass Separator (ARS-4) " | APP
001745 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0029 | 0 | 131242-WSW41-QA-A-0029 | 2025-10-13 | Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-10 | 2025-10-23 | 8 | Not Approved | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001745 | 2025-10-13 | 2025-10-13 | 0 | NAP | Not Approved | 1 | "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" | NAP
001746 | 00 | Jeline | PMT | NA | 131242 | WSW41 | RT | PM | 0029 | 0_VOID | 131242-WSW41-RT-PM-0029 | 2025-10-13 | C4B Monthly Progress Report Number No. 29 (09 25) | Contractor submit duplication from #1737 | 2025-11-10 | 2025-10-17 | 4 | Rejected | NO | 2025-11-06 | NO | Resubmitted | 0 |  |  | 001737&&001746 | 2025-10-11 | 2025-10-13 | 0_VOID | REJ | Rejected | 2 | "C4B Monthly Progress Report Number No. 29 (09 25)" | REJ
001747 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0057 | 0 | 131242-WSW41-QA-E-0057 | 2025-10-14 | FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-11 | 2025-11-27 | 32 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001747 | 2025-10-14 | 2025-10-14 | 0 | AWC | Approved with Comments | 1 | "FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight)" | AWC
001748 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0027 | 0 | 131242-WSW41-PC-W-0027 | 2025-10-16 | Payment Claim No. 27 | Rev (0): Approved. Please refer to S.O. correspondence no. 411 dated 13 Oct 2025. | 2025-11-13 | 2025-11-13 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001748 | 2025-10-16 | 2025-10-16 | 0 | APP | Approved | 1 | "Payment Claim No. 27" | APP
001749 | 00 | K Balaji | Mech | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-M-0001 | 2025-10-16 | Line List for Hydrotest (Sitewide PipeRack) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000445&&001749 | 2024-04-17 | 2025-10-16 | 0 | AWC | Approved with Comments | 2 | "Sidewide Piperack Line List" && "Line List for Hydrotest (Sitewide PipeRack)" | AWC
001750 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0003 | 0 | 131242-WSD11-SH-M-0003 | 2025-10-16 | Line List for Hydrotest (Biosolid Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | 27 | Approved with Comments | YES | 2025-12-12 | NO | Resubmitted | 0 |  |  | 001750 | 2025-10-16 | 2025-10-16 | 0 | AWC | Approved with Comments | 1 | "Line List for Hydrotest (Biosolid Building)" | AWC
001751 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0004 | 0 | 131242-WSD11-SH-M-0004 | 2025-10-16 | Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001751 | 2025-10-16 | 2025-10-16 | 0 | AWC | Approved with Comments | 1 | "Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack)" | AWC
001752 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0005 | 0 | 131242-WSD11-SH-M-0005 | 2025-10-16 | Line List for Hydrotest (THP Courtyard - Cooler Platforms) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | 27 | Approved with Comments | YES | 2025-12-12 | NO | Resubmitted | 0 |  |  | 001752 | 2025-10-16 | 2025-10-16 | 0 | AWC | Approved with Comments | 1 | "Line List for Hydrotest (THP Courtyard - Cooler Platforms)" | AWC
001753 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0073 | 0 | 131242-WSW41-LT-PM-0073 | 2025-10-16 | Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | NA | 2025-11-13 |  | 117 | Awaiting S.O.'s response | YES | 2025-12-03 | NO | Overdue | 0 |  |  | 001753 | 2025-10-16 | 2025-10-16 | 0 | PEN | Awaiting S.O.'s response | 1 | "Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | PEN
001754 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1001 | 0 | 131242-WST02-CL-M-1001 | 2025-10-18 | Blower Aeration Air Piping Stress Calculation Report | NA | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  | Submitted Docs is 131242-WSD11-CL-M-1001. Typo in Area code | 001754 | 2025-10-18 | 2025-10-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "Blower Aeration Air Piping Stress Calculation Report" | PEN
001755 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0004 | 0 | 131242-WST02-OM-M-0004 | 2025-10-18 | O&M Manual for Hyperbolic Mixer | NA | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  |  | 001755 | 2025-10-18 | 2025-10-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "O&M Manual for Hyperbolic Mixer" | PEN
001756 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0027 | 0 | 131242-WSW41-VI-M-0027 | 2025-10-18 | Preliminary Design And Vendor Approval For Chute | Rev 0: Approved | 2025-11-14 | 2025-11-24 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001756 | 2025-10-18 | 2025-10-18 | 0 | APP | Approved | 1 | "Preliminary Design And Vendor Approval For Chute" | APP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3001 | A | 131242-WSD11-DR-BE-3001 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3005 | A | 131242-WSD11-DR-BE-3005 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7010 | A | 131242-WSD11-DR-BE-7010 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7011 | A | 131242-WSD11-DR-BE-7011 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7012 | A | 131242-WSD11-DR-BE-7012 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7013 | A | 131242-WSD11-DR-BE-7013 | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3001 | B | 131242-WSD11-DR-BE-3001 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3005 | B | 131242-WSD11-DR-BE-3005 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7010 | B | 131242-WSD11-DR-BE-7010 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7011 | B | 131242-WSD11-DR-BE-7011 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7012 | B | 131242-WSD11-DR-BE-7012 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7013 | B | 131242-WSD11-DR-BE-7013 | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001757 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "THP LDB-0001 SLD, Schematic and GA Drawing" | NAP
001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7300 | A | 131242-WSD11-DR-EI-7300 | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3100 | A | 131242-WSD11-DR-EP-3100 | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3101 | A | 131242-WSD11-DR-EP-3101 | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7200 | A | 131242-WSD11-DR-EP-7200 | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7201 | A | 131242-WSD11-DR-EP-7201 | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7300 | B | 131242-WSD11-DR-EI-7300 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3100 | B | 131242-WSD11-DR-EP-3100 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3101 | B | 131242-WSD11-DR-EP-3101 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7200 | B | 131242-WSD11-DR-EP-7200 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7201 | B | 131242-WSD11-DR-EP-7201 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7202 | B | 131242-WSD11-DR-EP-7202 | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001758 | 2026-01-27 | 2026-01-27 | B | AWC | Approved with Comments | 1 | "THP UPSDB-0001A SLD, Schematic and GA Drawing" | AWC
001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7302 | A | 131242-WSD11-DR-EI-7302 | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3102 | A | 131242-WSD11-DR-EP-3102 | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3103 | A | 131242-WSD11-DR-EP-3103 | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7205 | A | 131242-WSD11-DR-EP-7205 | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7206 | A | 131242-WSD11-DR-EP-7206 | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7302 | B | 131242-WSD11-DR-EI-7302 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 48 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3102 | B | 131242-WSD11-DR-EP-3102 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 48 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3103 | B | 131242-WSD11-DR-EP-3103 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 48 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7205 | B | 131242-WSD11-DR-EP-7205 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 48 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7206 | B | 131242-WSD11-DR-EP-7206 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 48 |  |  | 001759 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | NAP
001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7207 | B | 131242-WSD11-DR-EP-7207 | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001759 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | PEN
001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7304 | A | 131242-WSD11-DR-EI-7304 | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3104 | A | 131242-WSD11-DR-EP-3104 | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3105 | A | 131242-WSD11-DR-EP-3105 | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7210 | A | 131242-WSD11-DR-EP-7210 | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7211 | A | 131242-WSD11-DR-EP-7211 | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7304 | B | 131242-WSD11-DR-EI-7304 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 48 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3104 | B | 131242-WSD11-DR-EP-3104 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 48 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3105 | B | 131242-WSD11-DR-EP-3105 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 48 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7210 | B | 131242-WSD11-DR-EP-7210 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 48 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7211 | B | 131242-WSD11-DR-EP-7211 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 48 |  |  | 001760 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7212 | B | 131242-WSD11-DR-EP-7212 | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001760 | 2026-01-27 | 2026-01-27 | B | AWC | Approved with Comments | 1 | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | AWC
001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7308 | A | 131242-WST02-DR-EI-7308 | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3108 | A | 131242-WST02-DR-EP-3108 | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3109 | A | 131242-WST02-DR-EP-3109 | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7220 | A | 131242-WST02-DR-EP-7220 | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7221 | A | 131242-WST02-DR-EP-7221 | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7308 | B | 131242-WST02-DR-EI-7308 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3108 | B | 131242-WST02-DR-EP-3108 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3109 | B | 131242-WST02-DR-EP-3109 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7220 | B | 131242-WST02-DR-EP-7220 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7221 | B | 131242-WST02-DR-EP-7221 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7222 | B | 131242-WST02-DR-EP-7222 | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001761 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | PEN
001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7312 | A | 131242-WST02-DR-EI-7312 | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3112 | A | 131242-WST02-DR-EP-3112 | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3113 | A | 131242-WST02-DR-EP-3113 | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7230 | A | 131242-WST02-DR-EP-7230 | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7231 | A | 131242-WST02-DR-EP-7231 | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7312 | B | 131242-WST02-DR-EI-7312 | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3112 | B | 131242-WST02-DR-EP-3112 | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3113 | B | 131242-WST02-DR-EP-3113 | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7230 | B | 131242-WST02-DR-EP-7230 | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7231 | B | 131242-WST02-DR-EP-7231 | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001762 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 2 | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | NAP
001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7324 | A | 131242-WST02-DR-EI-7324 | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3124 | A | 131242-WST02-DR-EP-3124 | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3125 | A | 131242-WST02-DR-EP-3125 | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7265 | A | 131242-WST02-DR-EP-7265 | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7266 | A | 131242-WST02-DR-EP-7266 | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7324 | B | 131242-WST02-DR-EI-7324 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3124 | B | 131242-WST02-DR-EP-3124 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3125 | B | 131242-WST02-DR-EP-3125 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7265 | B | 131242-WST02-DR-EP-7265 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7266 | B | 131242-WST02-DR-EP-7266 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | AWC
001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7267 | B | 131242-WST02-DR-EP-7267 | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001763 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | PEN
001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7326 | A | 131242-WST02-DR-EI-7326 | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3126 | A | 131242-WST02-DR-EP-3126 | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3127 | A | 131242-WST02-DR-EP-3127 | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7270 | A | 131242-WST02-DR-EP-7270 | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7271 | A | 131242-WST02-DR-EP-7271 | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7326 | B | 131242-WST02-DR-EI-7326 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3126 | B | 131242-WST02-DR-EP-3126 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3127 | B | 131242-WST02-DR-EP-3127 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7270 | B | 131242-WST02-DR-EP-7270 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7271 | B | 131242-WST02-DR-EP-7271 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2025-10-22 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | NAP
001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7272 | B | 131242-WST02-DR-EP-7272 | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001764 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | PEN
001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7316 | A | 131242-WST02-DR-EI-7316 | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3116 | A | 131242-WST02-DR-EP-3116 | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3117 | A | 131242-WST02-DR-EP-3117 | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7245 | A | 131242-WST02-DR-EP-7245 | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7246 | A | 131242-WST02-DR-EP-7246 | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | 21 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7316 | B | 131242-WST02-DR-EI-7316 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 49 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3116 | B | 131242-WST02-DR-EP-3116 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 49 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3117 | B | 131242-WST02-DR-EP-3117 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 49 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7245 | B | 131242-WST02-DR-EP-7245 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 49 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7246 | B | 131242-WST02-DR-EP-7246 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 49 |  |  | 001765 | 2025-10-22 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | NAP
001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7247 | B | 131242-WST02-DR-EP-7247 | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001765 | 2026-01-28 | 2026-01-28 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | PEN
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | A_VOID | 131242-WSD11-DR-BE-3006 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | A_VOID | 131242-WSD11-DR-BE-3010 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | A_VOID | 131242-WSD11-DR-BE-7015 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | A_VOID | 131242-WSD11-DR-BE-7016 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | A_VOID | 131242-WSD11-DR-BE-7017 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | A_VOID | 131242-WSD11-DR-BE-7018 | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | REJ | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7306 | A | 131242-WSD11-DR-EI-7306 | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3106 | A | 131242-WSD11-DR-EP-3106 | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3107 | A | 131242-WSD11-DR-EP-3107 | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7215 | A | 131242-WSD11-DR-EP-7215 | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7216 | A | 131242-WSD11-DR-EP-7216 | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | NAP | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7306 | B | 131242-WSD11-DR-EI-7306 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3106 | B | 131242-WSD11-DR-EP-3106 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3107 | B | 131242-WSD11-DR-EP-3107 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7215 | B | 131242-WSD11-DR-EP-7215 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7216 | B | 131242-WSD11-DR-EP-7216 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7217 | B | 131242-WSD11-DR-EP-7217 | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001767 | 2026-01-27 | 2026-01-27 | B | AWC | Approved with Comments | 1 | "THP UPSDB-0106A SLD, Schematic and GA Drawing" | AWC
001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7308 | A | 131242-WSD11-DR-EI-7308 | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3108 | A | 131242-WSD11-DR-EP-3108 | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3109 | A | 131242-WSD11-DR-EP-3109 | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7220 | A | 131242-WSD11-DR-EP-7220 | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7221 | A | 131242-WSD11-DR-EP-7221 | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7308 | B | 131242-WSD11-DR-EI-7308 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3108 | B | 131242-WSD11-DR-EP-3108 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3109 | B | 131242-WSD11-DR-EP-3109 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7220 | B | 131242-WSD11-DR-EP-7220 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7221 | B | 131242-WSD11-DR-EP-7221 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2025-10-22 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | AWC
001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7222 | B | 131242-WSD11-DR-EP-7222 | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001768 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "THP UPSDB-0107 SLD, Schematic and GA Drawing" | PEN
001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7310 | A | 131242-WST02-DR-EI-7310 | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | 26 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3110 | A | 131242-WST02-DR-EP-3110 | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | 26 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3111 | A | 131242-WST02-DR-EP-3111 | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | 26 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7225 | A | 131242-WST02-DR-EP-7225 | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | 26 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7226 | A | 131242-WST02-DR-EP-7226 | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | 26 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7310 | B | 131242-WST02-DR-EI-7310 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3110 | B | 131242-WST02-DR-EP-3110 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3111 | B | 131242-WST02-DR-EP-3111 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7225 | B | 131242-WST02-DR-EP-7225 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7226 | B | 131242-WST02-DR-EP-7226 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001769 | 2025-10-22 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7227 | B | 131242-WST02-DR-EP-7227 | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001769 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | PEN
001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7314 | A | 131242-WST02-DR-EI-7314 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3114 | A | 131242-WST02-DR-EP-3114 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3115 | A | 131242-WST02-DR-EP-3115 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7235 | A | 131242-WST02-DR-EP-7235 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7236 | A | 131242-WST02-DR-EP-7236 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7314 | B | 131242-WST02-DR-EI-7314 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-12 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3114 | B | 131242-WST02-DR-EP-3114 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3115 | B | 131242-WST02-DR-EP-3115 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7235 | B | 131242-WST02-DR-EP-7235 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7236 | B | 131242-WST02-DR-EP-7236 | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001770 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 2 | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | AWC
001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7304 | A | 131242-WST02-DR-EI-7304 | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3104 | A | 131242-WST02-DR-EP-3104 | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3105 | A | 131242-WST02-DR-EP-3105 | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7210 | A | 131242-WST02-DR-EP-7210 | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7211 | A | 131242-WST02-DR-EP-7211 | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7304 | B | 131242-WST02-DR-EI-7304 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3104 | B | 131242-WST02-DR-EP-3104 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3105 | B | 131242-WST02-DR-EP-3105 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7210 | B | 131242-WST02-DR-EP-7210 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7211 | B | 131242-WST02-DR-EP-7211 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | AWC
001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7212 | B | 131242-WST02-DR-EP-7212 | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001771 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | PEN
001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7306 | A | 131242-WST02-DR-EI-7306 | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3106 | A | 131242-WST02-DR-EP-3106 | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3107 | A | 131242-WST02-DR-EP-3107 | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7215 | A | 131242-WST02-DR-EP-7215 | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7216 | A | 131242-WST02-DR-EP-7216 | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | 25 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7306 | B | 131242-WST02-DR-EI-7306 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3106 | B | 131242-WST02-DR-EP-3106 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3107 | B | 131242-WST02-DR-EP-3107 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7215 | B | 131242-WST02-DR-EP-7215 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7216 | B | 131242-WST02-DR-EP-7216 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 48 |  |  | 001772 | 2025-10-23 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | AWC
001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7217 | B | 131242-WST02-DR-EP-7217 | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001772 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | PEN
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | A | 131242-WSD11-DR-BE-3006 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | A | 131242-WSD11-DR-BE-3010 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | A | 131242-WSD11-DR-BE-7015 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | A | 131242-WSD11-DR-BE-7016 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | A | 131242-WSD11-DR-BE-7017 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | A | 131242-WSD11-DR-BE-7018 | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | NAP | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | B | 131242-WSD11-DR-BE-3006 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | B | 131242-WSD11-DR-BE-3010 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | B | 131242-WSD11-DR-BE-7015 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | B | 131242-WSD11-DR-BE-7016 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | B | 131242-WSD11-DR-BE-7017 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | B | 131242-WSD11-DR-BE-7018 | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001766&&001773 | 2025-10-22 | 2026-02-03 | B | PEN | Not Approved | 3 | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | NAP
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A | 131242-WST02-DR-BE-3001 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A | 131242-WST02-DR-BE-3005 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A | 131242-WST02-DR-BE-7010 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A | 131242-WST02-DR-BE-7011 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A | 131242-WST02-DR-BE-7012 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A | 131242-WST02-DR-BE-7013 | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | 20 | Not Approved | YES | 2025-12-10 | NO | Resubmitted | 44 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | B | 131242-WST02-DR-BE-3001 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | B | 131242-WST02-DR-BE-3005 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | B | 131242-WST02-DR-BE-7010 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | B | 131242-WST02-DR-BE-7011 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | B | 131242-WST02-DR-BE-7012 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | B | 131242-WST02-DR-BE-7013 | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 55 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A_VOID | 131242-WST02-DR-BE-3001 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A_VOID | 131242-WST02-DR-BE-3005 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A_VOID | 131242-WST02-DR-BE-7010 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A_VOID | 131242-WST02-DR-BE-7011 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A_VOID | 131242-WST02-DR-BE-7012 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A_VOID | 131242-WST02-DR-BE-7013 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001557&&001774&&001775 | 2025-08-05 | 2026-02-03 | B | REJ | Approved with Comments | 4 | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A | 131242-WST02-DR-BE-3006 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A | 131242-WST02-DR-BE-3010 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A | 131242-WST02-DR-BE-7015 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A | 131242-WST02-DR-BE-7016 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A | 131242-WST02-DR-BE-7017 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A | 131242-WST02-DR-BE-7018 | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A | 131242-WST02-DR-BE-3006 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A | 131242-WST02-DR-BE-3010 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A | 131242-WST02-DR-BE-7015 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A | 131242-WST02-DR-BE-7016 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A | 131242-WST02-DR-BE-7017 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A | 131242-WST02-DR-BE-7018 | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001558&&001776 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A | 131242-WST02-DR-BE-3011 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001558&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3015 | A | 131242-WST02-DR-BE-3015 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7020 | A | 131242-WST02-DR-BE-7020 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7021 | A | 131242-WST02-DR-BE-7021 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7022 | A | 131242-WST02-DR-BE-7022 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7023 | A | 131242-WST02-DR-BE-7023 | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A | 131242-WST02-DR-BE-3011 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001558&&001777 | 2025-08-05 | 2026-02-03 | A | PEN | Approved with Comments | 3 | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3015 | A | 131242-WST02-DR-BE-3015 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Approved with Comments | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7020 | A | 131242-WST02-DR-BE-7020 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Approved with Comments | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7021 | A | 131242-WST02-DR-BE-7021 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Approved with Comments | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7022 | A | 131242-WST02-DR-BE-7022 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Approved with Comments | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7023 | A | 131242-WST02-DR-BE-7023 | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | 39 | Approved with Comments | YES | 2026-03-23 | NO | Overdue | 147 |  |  | 001559&&001777 | 2025-08-05 | 2026-02-03 | A | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | AWC
001778 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | PS | P | 0001 | 0 | 131242-WST02-PS-P-0001 | 2025-10-23 | SSN Functional Design Specification Workshop | Rev0: The document is submitted for information. However, please see the comments in the comment sheet. | 2025-11-20 | 2026-01-12 | 57 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001778 | 2025-10-23 | 2025-10-23 | 0 | INF | For Information | 1 | "SSN Functional Design Specification Workshop" | INF
001779 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5204 | 0 | 131242-WSD11-DR-M-5204 | 2025-10-23 | GA for Steam Strainer | NA | 2025-11-20 |  | 112 | Awaiting S.O.'s response | YES | 2025-12-10 | NO | Overdue | 0 |  |  | 001779 | 2025-10-23 | 2025-10-23 | 0 | PEN | Awaiting S.O.'s response | 1 | "GA for Steam Strainer" | PEN
001780 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5203 | 0 | 131242-WSD11-DR-M-5203 | 2025-10-23 | GA for Steam Relief Valve | NA | 2025-11-20 |  | 112 | Awaiting S.O.'s response | YES | 2025-12-10 | NO | Overdue | 0 |  |  | 001780 | 2025-10-23 | 2025-10-23 | 0 | PEN | Awaiting S.O.'s response | 1 | "GA for Steam Relief Valve" | PEN
001781 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | ST617 THP-PF-01 TOS 15.875 Grating Fab | NA | 131242-WSD11-DR-S-ST617 THP-PF-01 TOS 15.875 Grating Fab | 2025-10-23 | ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement) | For Information. Drawings shall be submitted individual sheet. | 2025-11-20 | 2025-12-17 | 39 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001781 | 2025-10-23 | 2025-10-23 | NA | INF | For Information | 1 | "ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement)" | INF
001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5450 | A | 131242-WST02-DR-I-5450 | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001782 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Pressure Gauge" | NAP
001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5451 | A | 131242-WST02-DR-I-5451 | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001782 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Pressure Gauge" | NAP
001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5452 | A | 131242-WST02-DR-I-5452 | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001782 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Pressure Gauge" | NAP
001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5453 | A | 131242-WST02-DR-I-5453 | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001782 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Pressure Gauge" | NAP
001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5454 | A | 131242-WST02-DR-I-5454 | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001782 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Pressure Gauge" | NAP
001783 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5460 | A | 131242-WST02-DR-I-5460 | 2025-10-23 | Hookup Drawing - Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001783 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - Rotameter" | AWC
001783 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5461 | A | 131242-WST02-DR-I-5461 | 2025-10-23 | Hookup Drawing - Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001783 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - Rotameter" | AWC
001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5350 | A | 131242-WST02-DR-I-5350 | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001784 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Capacitive Level Switch" | NAP
001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5351 | A | 131242-WST02-DR-I-5351 | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001784 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Capacitive Level Switch" | NAP
001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5352 | A | 131242-WST02-DR-I-5352 | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Not Approved | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001784 | 2025-10-23 | 2025-10-23 | A | NAP | Not Approved | 1 | "Hookup Drawing - Capacitive Level Switch" | NAP
001785 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5410 | A | 131242-WST02-DR-I-5410 | 2025-10-23 | Hookup Drawing - Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001785 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - Conductivity Analyser" | AWC
001785 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5411 | A | 131242-WST02-DR-I-5411 | 2025-10-23 | Hookup Drawing - Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001785 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - Conductivity Analyser" | AWC
001786 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5420 | A | 131242-WST02-DR-I-5420 | 2025-10-23 | Hookup Drawing - DO Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001786 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - DO Analyser" | AWC
001786 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5421 | A | 131242-WST02-DR-I-5421 | 2025-10-23 | Hookup Drawing - DO Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001786 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - DO Analyser" | AWC
001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5320 | A | 131242-WST02-DR-I-5320 | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001787 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - pH Analyser" | AWC
001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5321 | A | 131242-WST02-DR-I-5321 | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001787 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - pH Analyser" | AWC
001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5322 | A | 131242-WST02-DR-I-5322 | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001787 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing - pH Analyser" | AWC
001788 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5400 | A | 131242-WST02-DR-I-5400 | 2025-10-23 | Hookup Drawing -TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001788 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -TSS Analyser" | AWC
001788 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5401 | A | 131242-WST02-DR-I-5401 | 2025-10-23 | Hookup Drawing -TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | 37 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001788 | 2025-10-23 | 2025-10-23 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -TSS Analyser" | AWC
001789 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | ST617 THP-PF-01 | A | 131242-WSD11-SD-S-ST617 THP-PF-01 | 2025-10-24 | ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-21 | 2025-12-19 | 40 | Approved with Comments | YES | 2026-01-08 | NO | Resubmitted | 0 |  |  | 001789 | 2025-10-24 | 2025-10-24 | A | AWC | Approved with Comments | 1 | "ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875" | AWC
001790 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | ST617 THP-PF-01 Platform & Railing | A | 131242-WSD11-SD-S-ST617 THP-PF-01 Platform & Railing | 2025-10-24 | ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed) | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-21 | 2025-12-09 | 32 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001790 | 2025-10-24 | 2025-10-24 | A | AWC | Approved with Comments | 1 | "ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed)" | AWC
001791 | 00 | Yibo | Mech | NA | 131242 | WST11 | DR | M | 5475 | A | 131242-WST11-DR-M-5475 | 2025-10-27 | Rectangular Bellow Drawing | Rev 0: Approved | 2025-11-24 | 2025-11-24 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001791 | 2025-10-27 | 2025-10-27 | A | APP | Approved | 1 | "Rectangular Bellow Drawing" | APP
001792 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0006 | 0 | 131242-WST02-VI-B-0006 | 2025-10-27 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-24 | 2025-12-11 | 33 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001792 | 2025-10-27 | 2025-10-27 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" | AWC
001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1071 | A | 131242-WST02-IP-BM-1071 | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001793 | 2025-10-27 | 2025-10-27 | A | NAP | Not Approved | 1 | "BMS Panel GA & Wiring Drawing " | NAP
001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1001 | A | 131242-WST02-IP-BM-1001 | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001793 | 2025-10-27 | 2025-10-27 | A | NAP | Not Approved | 1 | "BMS Panel GA & Wiring Drawing " | NAP
001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1031 | A | 131242-WST02-IP-BM-1031 | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001793 | 2025-10-27 | 2025-10-27 | A | NAP | Not Approved | 1 | "BMS Panel GA & Wiring Drawing " | NAP
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1001 | A | 131242-WST02-DR-BM-1001 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1002 | A | 131242-WST02-DR-BM-1002 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1003 | A | 131242-WST02-DR-BM-1003 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1004 | A | 131242-WST02-DR-BM-1004 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1005 | A | 131242-WST02-DR-BM-1005 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1006 | A | 131242-WST02-DR-BM-1006 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1007 | A | 131242-WST02-DR-BM-1007 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1008 | A | 131242-WST02-DR-BM-1008 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1009 | A | 131242-WST02-DR-BM-1009 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1010 | A | 131242-WST02-DR-BM-1010 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1011 | A | 131242-WST02-DR-BM-1011 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1012 | A | 131242-WST02-DR-BM-1012 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1013 | A | 131242-WST02-DR-BM-1013 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1014 | A | 131242-WST02-DR-BM-1014 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1015 | A | 131242-WST02-DR-BM-1015 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1016 | A | 131242-WST02-DR-BM-1016 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1017 | A | 131242-WST02-DR-BM-1017 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1018 | A | 131242-WST02-DR-BM-1018 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1019 | A | 131242-WST02-DR-BM-1019 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1020 | A | 131242-WST02-DR-BM-1020 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1021 | A | 131242-WST02-DR-BM-1021 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1022 | A | 131242-WST02-DR-BM-1022 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1023 | A | 131242-WST02-DR-BM-1023 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1024 | A | 131242-WST02-DR-BM-1024 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1025 | A | 131242-WST02-DR-BM-1025 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1026 | A | 131242-WST02-DR-BM-1026 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1027 | A | 131242-WST02-DR-BM-1027 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1028 | A | 131242-WST02-DR-BM-1028 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1031 | A | 131242-WST02-DR-BM-1031 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1032 | A | 131242-WST02-DR-BM-1032 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1033 | A | 131242-WST02-DR-BM-1033 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1034 | A | 131242-WST02-DR-BM-1034 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1035 | A | 131242-WST02-DR-BM-1035 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1036 | A | 131242-WST02-DR-BM-1036 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1037 | A | 131242-WST02-DR-BM-1037 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1038 | A | 131242-WST02-DR-BM-1038 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1039 | A | 131242-WST02-DR-BM-1039 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1040 | A | 131242-WST02-DR-BM-1040 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1041 | A | 131242-WST02-DR-BM-1041 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1042 | A | 131242-WST02-DR-BM-1042 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1043 | A | 131242-WST02-DR-BM-1043 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1044 | A | 131242-WST02-DR-BM-1044 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1045 | A | 131242-WST02-DR-BM-1045 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1046 | A | 131242-WST02-DR-BM-1046 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1047 | A | 131242-WST02-DR-BM-1047 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1048 | A | 131242-WST02-DR-BM-1048 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1049 | A | 131242-WST02-DR-BM-1049 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1050 | A | 131242-WST02-DR-BM-1050 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1051 | A | 131242-WST02-DR-BM-1051 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1052 | A | 131242-WST02-DR-BM-1052 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1053 | A | 131242-WST02-DR-BM-1053 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1054 | A | 131242-WST02-DR-BM-1054 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1055 | A | 131242-WST02-DR-BM-1055 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1056 | A | 131242-WST02-DR-BM-1056 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1057 | A | 131242-WST02-DR-BM-1057 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1058 | A | 131242-WST02-DR-BM-1058 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1059 | A | 131242-WST02-DR-BM-1059 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1060 | A | 131242-WST02-DR-BM-1060 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1061 | A | 131242-WST02-DR-BM-1061 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1062 | A | 131242-WST02-DR-BM-1062 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1063 | A | 131242-WST02-DR-BM-1063 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1064 | A | 131242-WST02-DR-BM-1064 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1065 | A | 131242-WST02-DR-BM-1065 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1066 | A | 131242-WST02-DR-BM-1066 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1067 | A | 131242-WST02-DR-BM-1067 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1068 | A | 131242-WST02-DR-BM-1068 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1071 | A | 131242-WST02-DR-BM-1071 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1072 | A | 131242-WST02-DR-BM-1072 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1073 | A | 131242-WST02-DR-BM-1073 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1074 | A | 131242-WST02-DR-BM-1074 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1075 | A | 131242-WST02-DR-BM-1075 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1076 | A | 131242-WST02-DR-BM-1076 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1077 | A | 131242-WST02-DR-BM-1077 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1078 | A | 131242-WST02-DR-BM-1078 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1079 | A | 131242-WST02-DR-BM-1079 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1080 | A | 131242-WST02-DR-BM-1080 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1081 | A | 131242-WST02-DR-BM-1081 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1082 | A | 131242-WST02-DR-BM-1082 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1083 | A | 131242-WST02-DR-BM-1083 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1084 | A | 131242-WST02-DR-BM-1084 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1085 | A | 131242-WST02-DR-BM-1085 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1086 | A | 131242-WST02-DR-BM-1086 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1087 | A | 131242-WST02-DR-BM-1087 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1088 | A | 131242-WST02-DR-BM-1088 | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001793 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "BMS Panel GA & Wiring Drawing " | PEN
001794 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0058 | 0 | 131242-WSW41-QA-E-0058 | 2025-10-27 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-24 | 2026-02-02 | 70 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 001794 | 2025-10-27 | 2025-10-27 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM)" | AWC
001795 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0003 | 0 | 131242-WST02-CD-I-0003 | 2025-10-28 | SSN Master Blower HMI Graphic List and Graphic Screen | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-12-09 | 30 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001795 | 2025-10-28 | 2025-10-28 | 0 | AWC | Approved with Comments | 1 | "SSN Master Blower HMI Graphic List and Graphic Screen" | AWC
001796 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | BH | 0001 | 0 | 131242-WSW41-MS-BH-0001 | 2025-10-28 | MSRA, SWP for ACMV System works | NA | 2025-11-25 |  | 109 | Awaiting S.O.'s response | YES | 2025-12-15 | NO | Overdue | 0 |  |  | 001796 | 2025-10-28 | 2025-10-28 | 0 | PEN | Awaiting S.O.'s response | 1 | "MSRA, SWP for ACMV System works" | PEN
001797 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | E | 0016 | 0 | 131242-WSW41-MS-E-0016 | 2025-10-28 | MSRA for MCCB Replacement Works | Rev 0: For Information | 2025-11-25 | 2026-02-02 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001797 | 2025-10-28 | 2025-10-28 | 0 | INF | For Information | 1 | "MSRA for MCCB Replacement Works" | INF
001798 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | M | 0016 | 0 | 131242-WSW41-MS-M-0016 | 2025-10-28 | MSRA, SWP for FRP Tanks Defect Repair Lamination Works | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-25 | 2025-12-29 | 44 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 001798 | 2025-10-28 | 2025-10-28 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | AWC
001799 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0059 | 0 | 131242-WSW41-QA-E-0059 | 2025-10-29 | Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM) | Rev 0: Not approved - Revise and Resubmit. Refer to attached file for comments. | 2025-11-26 | 2026-02-20 | 82 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001799 | 2025-10-29 | 2025-10-29 | 0 | NAP | Not Approved | 1 | "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | NAP
001800 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0026 | 0 | 131242-WSW41-PO-M-0026 | 2025-10-31 | Unpriced PO for Valve for Condensate System (Spirax Sarco) | Rev 0: For Information | 2025-11-28 | 2025-11-24 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001615&&001800 | 2025-08-22 | 2025-10-31 | 0 | INF | For Information | 2 | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | INF
001801 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0027 | 0 | 131242-WSW41-PO-M-0027 | 2025-10-31 | Unpriced PO for Manual Lifting Equipment (Growa) | Rev 0: For Information Only. | 2025-11-28 |  | 106 | For Information | NO |  | YES | NO | 0 |  |  | 001801 | 2025-10-31 | 2025-10-31 | 0 | INF | For Information | 1 | "Unpriced PO for Manual Lifting Equipment (Growa)" | INF
001802 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | THP-PF-01 & 02 Cat ladders | A | 131242-WSD11-SD-S-THP-PF-01 & 02 Cat ladders | 2025-10-31 | Shop Drawing for THP-PF-01 & 02 Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2026-01-12 | 51 | Not Approved | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001802 | 2025-10-31 | 2025-10-31 | A | NAP | Not Approved | 1 | "Shop Drawing for THP-PF-01 & 02 Cat ladders " | NAP
001803 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | SSN Area and Electrical Building Cat ladders | A | 131242-WST02-SD-S-SSN Area and Electrical Building Cat ladders | 2025-10-31 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2026-01-12 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001803 | 2025-10-31 | 2025-10-31 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.5 | 131242-WST02-SD-S-1007 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 73 |  |  | 001616&&001698&&001803 | 2025-08-22 | 2026-02-09 | A.5 | PEN | Not Approved | 3 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | A.5 | 131242-WST02-SD-S-5003 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 41 |  |  | 001498&&001698&&001803 | 2025-07-22 | 2026-02-09 | A.5 | PEN | Not Approved | 3 | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | NAP
001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A.5 | 131242-WST02-SD-S-5004 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 73 |  |  | 001698&&001700&&001803 | 2025-09-26 | 2026-02-09 | A.5 | PEN | Rejected | 3 | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | REJ
001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.5 | 131242-WST02-SD-S-8600 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | 35 | Awaiting S.O.'s response | YES | 2026-03-27 | NO | Overdue | 10 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | PEN | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001804 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0002 | 0 | 131242-WSD11-PS-P-0002 | 2025-10-31 | THP Functional Design Specification Workshop | The document is accepted for information only. | 2025-11-28 | 2026-02-09 | 71 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001804 | 2025-10-31 | 2025-10-31 | 0 | INF | For Information | 1 | "THP Functional Design Specification Workshop" | INF
001805 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0076 | 0 | 131242-WSW41-LT-PM-0076 | 2025-10-31 | CV of Team Member (ECO) | Approved | 2025-11-28 | 2025-12-10 | 28 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001805 | 2025-10-31 | 2025-10-31 | 0 | APP | Approved | 1 | "CV of Team Member (ECO)" | APP
001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7300 | A | 131242-WST02-DR-EI-7300 | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3100 | A | 131242-WST02-DR-EP-3100 | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3101 | A | 131242-WST02-DR-EP-3101 | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7200 | A | 131242-WST02-DR-EP-7200 | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7201 | A | 131242-WST02-DR-EP-7201 | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7300 | B | 131242-WST02-DR-EI-7300 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3100 | B | 131242-WST02-DR-EP-3100 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3101 | B | 131242-WST02-DR-EP-3101 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7200 | B | 131242-WST02-DR-EP-7200 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7201 | B | 131242-WST02-DR-EP-7201 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | AWC
001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7202 | B | 131242-WST02-DR-EP-7202 | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001806 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | PEN
001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7302 | A | 131242-WST02-DR-EI-7302 | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3102 | A | 131242-WST02-DR-EP-3102 | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3103 | A | 131242-WST02-DR-EP-3103 | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7205 | A | 131242-WST02-DR-EP-7205 | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7206 | A | 131242-WST02-DR-EP-7206 | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7302 | B | 131242-WST02-DR-EI-7302 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3102 | B | 131242-WST02-DR-EP-3102 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3103 | B | 131242-WST02-DR-EP-3103 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7205 | B | 131242-WST02-DR-EP-7205 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7206 | B | 131242-WST02-DR-EP-7206 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2025-10-31 | 2026-02-03 | B | PEN | Approved with Comments | 2 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7207 | B | 131242-WST02-DR-EP-7207 | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001807 | 2026-02-03 | 2026-02-03 | B | PEN | Awaiting S.O.'s response | 1 | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | PEN
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3016 | A | 131242-WST02-DR-BE-3016 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001559&&001808 | 2025-08-05 | 2026-02-03 | B | NAP | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | A | 131242-WST02-DR-BE-3020 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001808&&001809 | 2025-10-31 | 2026-02-03 | B | NAP | Approved with Comments | 3 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7025 | A | 131242-WST02-DR-BE-7025 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | NAP | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7026 | A | 131242-WST02-DR-BE-7026 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | NAP | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7027 | A | 131242-WST02-DR-BE-7027 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | NAP | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7028 | A | 131242-WST02-DR-BE-7028 | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | NAP | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3016 | B | 131242-WST02-DR-BE-3016 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 147 |  |  | 001559&&001808 | 2025-08-05 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | B | 131242-WST02-DR-BE-3020 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001808&&001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7025 | B | 131242-WST02-DR-BE-7025 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7026 | B | 131242-WST02-DR-BE-7026 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7027 | B | 131242-WST02-DR-BE-7027 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7028 | B | 131242-WST02-DR-BE-7028 | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001808 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | A | 131242-WST02-DR-BE-3020 | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001808&&001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3021 | A | 131242-WST02-DR-BE-3021 | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7030 | A | 131242-WST02-DR-BE-7030 | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7031 | A | 131242-WST02-DR-BE-7031 | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7032 | A | 131242-WST02-DR-BE-7032 | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3021 | B | 131242-WST02-DR-BE-3021 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | B | 131242-WST02-DR-BE-3025 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809&&001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7030 | B | 131242-WST02-DR-BE-7030 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7031 | B | 131242-WST02-DR-BE-7031 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7032 | B | 131242-WST02-DR-BE-7032 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7033 | B | 131242-WST02-DR-BE-7033 | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809 | 2026-02-03 | 2026-02-03 | B | AWC | Approved with Comments | 1 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | A | 131242-WST02-DR-BE-3025 | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001809&&001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3026 | A | 131242-WST02-DR-BE-3026 | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7035 | A | 131242-WST02-DR-BE-7035 | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7036 | A | 131242-WST02-DR-BE-7036 | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7037 | A | 131242-WST02-DR-BE-7037 | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | B | 131242-WST02-DR-BE-3025 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001809&&001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 3 | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3026 | B | 131242-WST02-DR-BE-3026 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7035 | B | 131242-WST02-DR-BE-7035 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7036 | B | 131242-WST02-DR-BE-7036 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7037 | B | 131242-WST02-DR-BE-7037 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001810 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7038 | B | 131242-WST02-DR-BE-7038 | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001810 | 2026-02-03 | 2026-02-03 | B | AWC | Approved with Comments | 1 | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | AWC
001811 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | M | 0017 | 0 | 131242-WSW41-MS-M-0017 | 2025-10-31 | MSRA & Safe Work Procedure For NDT Activities | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-28 | 2025-12-29 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001811 | 2025-10-31 | 2025-10-31 | 0 | AWC | Approved with Comments | 1 | "MSRA & Safe Work Procedure For NDT Activities" | AWC
001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3030 | A | 131242-WST02-DR-BE-3030 | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3031 | A | 131242-WST02-DR-BE-3031 | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7040 | A | 131242-WST02-DR-BE-7040 | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7041 | A | 131242-WST02-DR-BE-7041 | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7042 | A | 131242-WST02-DR-BE-7042 | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3030 | B | 131242-WST02-DR-BE-3030 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3031 | B | 131242-WST02-DR-BE-3031 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7040 | B | 131242-WST02-DR-BE-7040 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7041 | B | 131242-WST02-DR-BE-7041 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7042 | B | 131242-WST02-DR-BE-7042 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7043 | B | 131242-WST02-DR-BE-7043 | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001812 | 2026-02-03 | 2026-02-03 | B | AWC | Approved with Comments | 1 | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3035 | A | 131242-WST02-DR-BE-3035 | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2025-10-31 | A | AWC | Approved with Comments | 1 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3036 | A | 131242-WST02-DR-BE-3036 | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7045 | A | 131242-WST02-DR-BE-7045 | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7046 | A | 131242-WST02-DR-BE-7046 | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7047 | A | 131242-WST02-DR-BE-7047 | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3036 | B | 131242-WST02-DR-BE-3036 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3040 | B | 131242-WST02-DR-BE-3040 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2026-02-03 | 2026-02-03 | B | AWC | Approved with Comments | 1 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7045 | B | 131242-WST02-DR-BE-7045 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7046 | B | 131242-WST02-DR-BE-7046 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7047 | B | 131242-WST02-DR-BE-7047 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2025-10-31 | 2026-02-03 | B | AWC | Approved with Comments | 2 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7048 | B | 131242-WST02-DR-BE-7048 | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001813 | 2026-02-03 | 2026-02-03 | B | AWC | Approved with Comments | 1 | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7320 | A | 131242-WST02-DR-EI-7320 | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3120 | A | 131242-WST02-DR-EP-3120 | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3121 | A | 131242-WST02-DR-EP-3121 | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7255 | A | 131242-WST02-DR-EP-7255 | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7256 | A | 131242-WST02-DR-EP-7256 | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7320 | B | 131242-WST02-DR-EI-7320 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3120 | B | 131242-WST02-DR-EP-3120 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3121 | B | 131242-WST02-DR-EP-3121 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7255 | B | 131242-WST02-DR-EP-7255 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7256 | B | 131242-WST02-DR-EP-7256 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2025-10-31 | 2026-01-27 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | AWC
001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7257 | B | 131242-WST02-DR-EP-7257 | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001814 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | PEN
001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7322 | A | 131242-WST02-DR-EI-7322 | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3122 | A | 131242-WST02-DR-EP-3122 | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3123 | A | 131242-WST02-DR-EP-3123 | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7260 | A | 131242-WST02-DR-EP-7260 | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7261 | A | 131242-WST02-DR-EP-7261 | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | NAP | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7322 | B | 131242-WST02-DR-EI-7322 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3122 | B | 131242-WST02-DR-EP-3122 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3123 | B | 131242-WST02-DR-EP-3123 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7260 | B | 131242-WST02-DR-EP-7260 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7261 | B | 131242-WST02-DR-EP-7261 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2025-10-31 | 2026-01-27 | B | PEN | Not Approved | 2 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | NAP
001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7262 | B | 131242-WST02-DR-EP-7262 | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001815 | 2026-01-27 | 2026-01-27 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | PEN
001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7328 | A | 131242-WST02-DR-EI-7328 | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3128 | A | 131242-WST02-DR-EP-3128 | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3129 | A | 131242-WST02-DR-EP-3129 | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7275 | A | 131242-WST02-DR-EP-7275 | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7276 | A | 131242-WST02-DR-EP-7276 | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7328 | B | 131242-WST02-DR-EI-7328 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3128 | B | 131242-WST02-DR-EP-3128 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3129 | B | 131242-WST02-DR-EP-3129 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7275 | B | 131242-WST02-DR-EP-7275 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7276 | B | 131242-WST02-DR-EP-7276 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001816 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | NAP
001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7277 | B | 131242-WST02-DR-EP-7277 | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001816 | 2026-01-28 | 2026-01-28 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | PEN
001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7330 | A | 131242-WST02-DR-EI-7330 | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3130 | A | 131242-WST02-DR-EP-3130 | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3131 | A | 131242-WST02-DR-EP-3131 | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7280 | A | 131242-WST02-DR-EP-7280 | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7281 | A | 131242-WST02-DR-EP-7281 | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | AWC | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7330 | B | 131242-WST02-DR-EI-7330 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3130 | B | 131242-WST02-DR-EP-3130 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3131 | B | 131242-WST02-DR-EP-3131 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7280 | B | 131242-WST02-DR-EP-7280 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7281 | B | 131242-WST02-DR-EP-7281 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2025-10-31 | 2026-01-28 | B | PEN | Approved with Comments | 2 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | AWC
001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7282 | B | 131242-WST02-DR-EP-7282 | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001817 | 2026-01-28 | 2026-01-28 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | PEN
001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7318 | A | 131242-WST02-DR-EI-7318 | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3118 | A | 131242-WST02-DR-EP-3118 | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3119 | A | 131242-WST02-DR-EP-3119 | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7250 | A | 131242-WST02-DR-EP-7250 | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7251 | A | 131242-WST02-DR-EP-7251 | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | 29 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | NAP | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7318 | B | 131242-WST02-DR-EI-7318 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3118 | B | 131242-WST02-DR-EP-3118 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3119 | B | 131242-WST02-DR-EP-3119 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7250 | B | 131242-WST02-DR-EP-7250 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7251 | B | 131242-WST02-DR-EP-7251 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 28 |  |  | 001818 | 2025-10-31 | 2026-01-28 | B | PEN | Not Approved | 2 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | NAP
001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7252 | B | 131242-WST02-DR-EP-7252 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001818 | 2026-01-28 | 2026-01-28 | B | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | PEN
001819 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0134 | 0 | 131242-WST02-QA-M-0134 | 2025-11-04 | FAT Report for Lamella Clarifier Biomass Separator (ARS-5) | NA | 2025-12-02 |  | 104 | Awaiting S.O.'s response | YES | 2025-12-22 | NO | Overdue | 0 |  |  | 001819 | 2025-11-04 | 2025-11-04 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Lamella Clarifier Biomass Separator (ARS-5)" | PEN
001820 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5752 | 0 | 131242-WST02-DS-M-5752 | 2025-11-05 | Data Sheet for SSN IA Pressure Reducing Valve | NA | 2025-12-03 |  | 103 | Awaiting S.O.'s response | YES | 2025-12-23 | NO | Overdue | 0 |  |  | 001820 | 2025-11-05 | 2025-11-05 | 0 | PEN | Awaiting S.O.'s response | 1 | "Data Sheet for SSN IA Pressure Reducing Valve " | PEN
001821 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0135 | 0 | 131242-WSW41-QA-M-0135 | 2025-11-05 | FAT Report for SS 316L Pipes - 32 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-01-30 | 62 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001821 | 2025-11-05 | 2025-11-05 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS 316L Pipes - 32 Nos" | AWC
001822 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5381 | 0 | 131242-WST02-DR-I-5381 | 2025-11-05 | Hookup Drawing - Autosampler | NA | 2025-12-03 |  | 103 | Awaiting S.O.'s response | YES | 2025-12-23 | NO | Overdue | 0 |  |  | 001822 | 2025-11-05 | 2025-11-05 | 0 | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing - Autosampler" | PEN
001823 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | E | 0060 | 0 | 131242-WSW41-QA-E-0060 | 2025-11-05 | FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-02-09 | 68 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001823 | 2025-11-05 | 2025-11-05 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" | AWC
001824 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0137 | 0 | 131242-WSD11-QA-M-0137 | 2025-11-05 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-01-30 | 62 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001824 | 2025-11-05 | 2026-02-03 | 1 | NAP | Not Approved | 2 | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | NAP
001824 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0137 | 1 | 131242-WSD11-QA-M-0137 | 2026-02-03 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001824 | 2025-11-05 | 2026-02-03 | 1 | PEN | Not Approved | 2 | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | NAP
001825 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0138 | 0 | 131242-WSW41-QA-M-0138 | 2025-11-06 | FAT Report for SS 316L Pipes - 21 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | 61 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001825 | 2025-11-06 | 2025-11-06 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS 316L Pipes - 21 Nos" | AWC
001826 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0139 | 0 | 131242-WSW41-QA-M-0139 | 2025-11-06 | FAT Report for SS 316L Pipes - 40 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | 61 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001826 | 2025-11-06 | 2025-11-06 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS 316L Pipes - 40 Nos" | AWC
001827 | 00 | Aaron | CSA | NA | 131242 | WSW41 | SD | S | FABRICATION DRAWIG | A | 131242-WSW41-SD-S-FABRICATION DRAWIG | 2025-11-06 | Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-04 | 2026-01-02 | 41 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001827 | 2025-11-06 | 2025-11-06 | A | NAP | Not Approved | 1 | "Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed)" | NAP
001828 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0140 | 0 | 131242-WST02-QA-M-0140 | 2025-11-06 | Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+) | NA | 2025-12-04 |  | 102 | Awaiting S.O.'s response | YES | 2025-12-24 | NO | Overdue | 0 |  |  | 001828 | 2025-11-06 | 2025-11-06 | 0 | PEN | Awaiting S.O.'s response | 1 | "Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+)" | PEN
001829 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0133 | 0 | 131242-WSW41-QA-M-0133 | 2025-11-06 | FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | 61 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001829 | 2025-11-06 | 2025-11-06 | 0 | AWC | Approved with Comments | 1 | "FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs" | AWC
001830 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0045 | 0 | 131242-WSW41-QA-C-0045 | 2025-11-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025 | For information | 2025-12-05 | 2025-12-24 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001830 | 2025-11-07 | 2025-11-07 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" | INF
001831 | 00 | Hang Peng | QAQC | NA | 131242 | WSW41 | CD | IM | 0064 | 0 | 131242-WSW41-CD-IM-0064 | 2025-11-10 | VCM Submission for 2025-10 | For Information | 2025-12-08 | 2025-12-02 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001831 | 2025-11-10 | 2025-11-10 | 0 | INF | For Information | 1 | "VCM Submission for 2025-10" | INF
001832 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0141 | 0 | 131242-WST02-QA-M-0141 | 2025-11-10 | FAT Report & Mill Test Certificates for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-08 | 2026-01-30 | 59 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001832&&001833 | 2025-11-10 | 2025-11-10 | 0 | AWC | Approved with Comments | 2 | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | AWC
001833 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0141 | 0 | 131242-WST02-QA-M-0141 | 2025-11-10 | Material & Test Certificates for Blower's Encapsulation | NA | 2025-12-08 |  | 100 | Awaiting S.O.'s response | YES | 2025-12-26 | NO | Overdue | 0 |  |  | 001832&&001833 | 2025-11-10 | 2025-11-10 | 0 | PEN | Approved with Comments | 2 | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | AWC
001834 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0144 | 0 | 131242-WSW41-QA-M-0144 | 2025-11-11 | FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets | NA | 2025-12-09 |  | 99 | Awaiting S.O.'s response | YES | 2025-12-29 | NO | Overdue | 0 |  |  | 001834 | 2025-11-11 | 2025-11-11 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets" | PEN
001835 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0028 | 0 | 131242-WSW41-PC-W-0028 | 2025-11-11 | Payment Claim No.28 | Rev (0): Approved. Please refer to S.O. correspondence no. 417 dated 12 November 2025. | 2025-12-09 | 2025-12-10 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001835 | 2025-11-11 | 2025-11-11 | 0 | APP | Approved | 1 | "Payment Claim No.28" | APP
001836 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0145 | 0 | 131242-WSD11-QA-M-0145 | 2025-11-11 | FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area | NA | 2025-12-09 |  | 99 | Awaiting S.O.'s response | YES | 2025-12-29 | NO | Overdue | 0 |  |  | 001836 | 2025-11-11 | 2025-11-11 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area" | PEN
001837 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0146 | 0 | 131242-WSD11-QA-M-0146 | 2025-11-11 | FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area | NA | 2025-12-09 |  | 99 | Awaiting S.O.'s response | YES | 2025-12-29 | NO | Overdue | 0 |  |  | 001837 | 2025-11-11 | 2025-11-11 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area" | PEN
001838 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0147 | 0 | 131242-WSW41-QA-M-0147 | 2025-11-12 | FAT Report for SS 316L Pipes for streamline-55 pcs | NA | 2025-12-10 |  | 98 | Awaiting S.O.'s response | YES | 2025-12-30 | NO | Overdue | 0 |  |  | 001838 | 2025-11-12 | 2025-11-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for SS 316L Pipes for streamline-55 pcs" | PEN
001839 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0148 | 0 | 131242-WST02-QA-M-0148 | 2025-11-12 | FAT Report for ARI-Armaturen Safety Valve - (OVS) | NA | 2025-12-10 |  | 98 | Awaiting S.O.'s response | YES | 2025-12-30 | NO | Overdue | 0 |  |  | 001839 | 2025-11-12 | 2025-11-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for ARI-Armaturen Safety Valve - (OVS) " | PEN
001840 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | CD | I | 0016 | 0 | 131242-WST02-CD-I-0016 | 2025-11-12 | FAT document for SSN Blower PLC/RIO Panels | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-10 | 2025-12-11 | 21 | Approved with Comments | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001840 | 2025-11-12 | 2025-11-12 | 0 | AWC | Approved with Comments | 1 | "FAT document for SSN Blower PLC/RIO Panels" | AWC
001841 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0149 | 0 | 131242-WSD11-QA-M-0149 | 2025-11-13 | FAT Report for Carbon Steel Pipe Support | NA | 2025-12-11 |  | 97 | Awaiting S.O.'s response | YES | 2025-12-31 | NO | Overdue | 0 |  |  | 001841 | 2025-11-13 | 2025-11-13 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Carbon Steel Pipe Support" | PEN
001842 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0143 | 0 | 131242-WSW41-QA-M-0143 | 2025-11-14 | FAT Report for Motorized Steam Ball Valves (OVS/Rotork) | NA | 2025-12-12 |  | 96 | Awaiting S.O.'s response | YES | 2026-01-01 | NO | Overdue | 0 |  |  | 001842 | 2025-11-14 | 2025-11-14 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Motorized Steam Ball Valves (OVS/Rotork)" | PEN
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5650 | A | 131242-WST02-DR-M-5650 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5651 | A | 131242-WST02-DR-M-5651 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5652 | A | 131242-WST02-DR-M-5652 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5655 | A | 131242-WST02-DR-M-5655 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5656 | A | 131242-WST02-DR-M-5656 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5657 | A | 131242-WST02-DR-M-5657 | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | 74 | Approved with Comments | YES | 2026-03-19 | NO | Resubmitted | 0 |  |  | 001843 | 2025-11-17 | 2025-11-17 | A | AWC | Approved with Comments | 1 | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | AWC
001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5360 | A | 131242-WST02-DR-I-5360 | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | 19 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001844 | 2025-11-18 | 2025-11-18 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Mass Flowmeter" | AWC
001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5631 | A | 131242-WST02-DR-I-5631 | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | 19 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001844 | 2025-11-18 | 2025-11-18 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Mass Flowmeter" | AWC
001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5362 | A | 131242-WST02-DR-I-5362 | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | 19 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001844 | 2025-11-18 | 2025-11-18 | A | AWC | Approved with Comments | 1 | "Hookup Drawing -Thermal Mass Flowmeter" | AWC
001845 | 00 | Kumar | CSA | NA | 131242 | WSW41 | MS | S | 0001 | 0 | 131242-WSW41-MS-S-0001 | 2025-11-18 | Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-16 | 2026-01-02 | 33 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001845 | 2025-11-18 | 2025-11-18 | 0 | NAP | Not Approved | 1 | "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | NAP
001846 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0150 | 0 | 131242-WST02-QA-M-0150 | 2025-11-18 | FAT Procedure for Portable A Frame & T-Davit (Growa) | NA | 2025-12-16 |  | 94 | Awaiting S.O.'s response | YES | 2026-01-05 | NO | Overdue | 0 |  |  | 001846 | 2025-11-18 | 2025-11-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Procedure for Portable A Frame & T-Davit (Growa)" | PEN
001847 | 00 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0004 | 0 | 131242-WST02-MS-M-0004 | 2025-11-18 | Method Statement for the Installation of Fine Bubble Diffuser | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-12-16 | 2025-12-23 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001847 | 2025-11-18 | 2025-11-18 | 0 | AWC | Approved with Comments | 1 | "Method Statement for the Installation of Fine Bubble Diffuser" | AWC
001848 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0077 | 0 | 131242-WSW41-LT-PM-0077 | 2025-11-19 | Notice For Extension Of Time And Cost For Delays For Power Turn On | NA | 2025-12-17 |  | 93 | Awaiting S.O.'s response | YES | 2026-01-06 | NO | Overdue | 0 |  |  | 001848 | 2025-11-19 | 2025-11-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Notice For Extension Of Time And Cost For Delays For Power Turn On" | PEN
001849 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0030 | 0 | 131242-WSW41-RT-PM-0030 | 2025-11-19 | C4B Monthly Progress Report Number No. 30 (10 25) | Approved with comments which will be addressed in the next MPR. | 2025-12-17 | 2026-02-23 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001849 | 2025-11-19 | 2025-11-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No. 30 (10 25)" | AWC
001850 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DS | M | 5345 | 0 | 131242-WSW41-DS-M-5345 | 2025-11-19 | Detailed Design PVC Strainer Data Sheet | NA | 2025-12-17 |  | 93 | Awaiting S.O.'s response | YES | 2026-01-06 | NO | Overdue | 0 |  |  | 001850 | 2025-11-19 | 2025-11-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Detailed Design PVC Strainer Data Sheet" | PEN
001851 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DS | M | 5346 | 0 | 131242-WSW41-DS-M-5346 | 2025-11-19 | Detailed Design SS316 Strainer Data Sheet | NA | 2025-12-17 |  | 93 | Awaiting S.O.'s response | YES | 2026-01-06 | NO | Overdue | 0 |  |  | 001851 | 2025-11-19 | 2025-11-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Detailed Design SS316 Strainer Data Sheet" | PEN
001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5640 | 0 | 131242-WST02-DS-M-5640 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001852 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datat Sheet & Drawing for Portable A-Frame" | PEN
001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5640 | 0 | 131242-WST02-DR-M-5640 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001852 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datat Sheet & Drawing for Portable A-Frame" | PEN
001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5641 | 0 | 131242-WST02-DR-M-5641 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001852 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datat Sheet & Drawing for Portable A-Frame" | PEN
001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5642 | 0 | 131242-WST02-DR-M-5642 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001852 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datat Sheet & Drawing for Portable A-Frame" | PEN
001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5643 | 0 | 131242-WST02-DR-M-5643 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001852 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datat Sheet & Drawing for Portable A-Frame" | PEN
001853 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0151 | 0 | 131242-WSW41-QA-M-0151 | 2025-11-20 | Material & Test Certificates for Flange Adaptors (Synchong Hoe) | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001853 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Material & Test Certificates for Flange Adaptors (Synchong Hoe)" | PEN
001854 | 00 | Balaji | QAQC | NA | 131242 | WST02 | QA | BS | 0018 | 0 | 131242-WST02-QA-BS-0018 | 2025-11-20 | Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng) | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001854 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng)" | PEN
001855 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0028 | 0 | 131242-WSW41-PS-HS-0028 | 2025-11-20 | Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025 | For Information | 2025-12-18 | 2025-12-23 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001855 | 2025-11-20 | 2025-11-20 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025" | INF
001856 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0006 | 0 | 131242-WST02-RT-S-0006 | 2025-11-20 | Safety Review Report for SSN Steel Structures and MEICA Equipment Installation | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001856 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" | PEN
001857 | 00 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0152 | 0 | 131242-WSD11-QA-M-0152 | 2025-11-20 | FAT Report for NON Return Check Valve (Breen) | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001857 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for NON Return Check Valve (Breen)" | PEN
001858 | 00 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0153 | 0 | 131242-WSD11-QA-M-0153 | 2025-11-20 | FAT Report for Sampling Sinks (4 units) | NA | 2025-12-18 |  | 92 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 001858 | 2025-11-20 | 2025-11-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Sampling Sinks (4 units)" | PEN
001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0001 | 0 | 131242-WSD11-MM-M-0001 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001859 | 2025-11-20 | 2025-11-20 | 0 | INF | For Information | 1 | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | INF
001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0002 | 0 | 131242-WSD11-MM-M-0002 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001859 | 2025-11-20 | 2025-11-20 | 0 | INF | For Information | 1 | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | INF
001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0003 | 0 | 131242-WSD11-MM-M-0003 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001859 | 2025-11-20 | 2025-11-20 | 0 | INF | For Information | 1 | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | INF
001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0004 | 0 | 131242-WSD11-MM-M-0004 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001859 | 2025-11-20 | 2025-11-20 | 0 | INF | For Information | 1 | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | INF
001860 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0059 | 0 | 131242-WSW41-QA-I-0059 | 2025-11-24 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-12-22 | 2025-12-16 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001860 | 2025-11-24 | 2025-12-18 | 1 | NAP | Not Approved | 2 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" | NAP
001860 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0059 | 1 | 131242-WSW41-QA-I-0059 | 2025-12-18 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2026-01-07 |  | 72 | Awaiting S.O.'s response | YES | 2026-02-04 | NO | Overdue | 0 |  |  | 001860 | 2025-11-24 | 2025-12-18 | 1 | PEN | Not Approved | 2 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" | NAP
001861 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0060 | 0 | 131242-WSW41-QA-I-0060 | 2025-11-24 | Factory Acceptance Test Report for Pressure Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-12-22 | 2025-12-16 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001861 | 2025-11-24 | 2026-01-13 | 1 | NAP | Not Approved | 2 | "Factory Acceptance Test Report for Pressure Switch" | NAP
001861 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0060 | 1 | 131242-WSW41-QA-I-0060 | 2026-01-13 | Factory Acceptance Test Report for Pressure Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-02 |  | 54 | Awaiting S.O.'s response | YES | 2026-03-02 | NO | Overdue | 0 |  |  | 001861 | 2025-11-24 | 2026-01-13 | 1 | PEN | Not Approved | 2 | "Factory Acceptance Test Report for Pressure Switch" | NAP
001862 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0155 | 0 | 131242-WSD11-QA-M-0155 | 2025-11-24 | FAT Report for THP Courtyard Area Pipe Supports (Less than 2m) | NA | 2025-12-22 |  | 90 | Awaiting S.O.'s response | YES | 2026-01-09 | NO | Overdue | 0 |  |  | 001862 | 2025-11-24 | 2025-11-24 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for THP Courtyard Area Pipe Supports (Less than 2m)" | PEN
001863 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0156 | 0 | 131242-WST02-QA-M-0156 | 2025-11-25 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units | NA | 2025-12-23 |  | 89 | Awaiting S.O.'s response | YES | 2026-01-12 | NO | Overdue | 0 |  |  | 001863 | 2025-11-25 | 2025-11-25 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units" | PEN
001864 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0052 | 0 | 131242-WSW41-MI-C-0052 | 2025-11-26 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001864 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | INF
001864 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0053 | 0 | 131242-WSW41-MI-C-0053 | 2025-11-26 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001864 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | INF
001865 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0054 | 0 | 131242-WSW41-MI-C-0054 | 2025-11-26 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001865 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | INF
001865 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0055 | 0 | 131242-WSW41-MI-C-0055 | 2025-11-26 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001865 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | INF
001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0056 | 0 | 131242-WSW41-MI-C-0056 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001866 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | INF
001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0057 | 0 | 131242-WSW41-MI-C-0057 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001866 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | INF
001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0058 | 0 | 131242-WSW41-MI-C-0058 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001866 | 2025-11-26 | 2025-11-26 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | INF
001867 | 00 | Balaji | EICA | NA | 131242 | WST00 | DR | BM | 1091 | A | 131242-WST00-DR-BM-1091 | 2025-11-26 | SSN BMS Network Architecture Drawing | NA | 2025-12-24 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001867 | 2025-11-26 | 2025-11-26 | A | PEN | Awaiting S.O.'s response | 1 | "SSN BMS Network Architecture Drawing" | PEN
001868 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0154 | 0 | 131242-WSD11-QA-M-0154 | 2025-11-27 | FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15) | NA | 2025-12-25 |  | 87 | Awaiting S.O.'s response | YES | 2026-01-14 | NO | Overdue | 0 |  |  | 001868 | 2025-11-27 | 2025-11-27 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15)" | PEN
001869 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0030 | 0 | 131242-WST02-QA-A-0030 | 2025-11-27 | Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2025-12-24 | 19 | Not Approved | YES | 2026-01-13 | NO | Resubmitted | 0 |  |  | 001869 | 2025-11-27 | 2025-11-27 | 0 | NAP | Not Approved | 1 | "Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd)" | NAP
001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1011 | A | 131242-WST02-SD-S-1011 | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | 55 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001870 | 2025-11-27 | 2025-11-27 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Biomass GI Railing - Rev A" | NAP
001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1012 | A | 131242-WST02-SD-S-1012 | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | 55 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001870 | 2025-11-27 | 2025-11-27 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Biomass GI Railing - Rev A" | NAP
001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1013 | A | 131242-WST02-SD-S-1013 | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | 55 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001870 | 2025-11-27 | 2025-11-27 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Biomass GI Railing - Rev A" | NAP
001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3005 | A | 131242-WST02-SD-S-3005 | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | 55 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001870 | 2025-11-27 | 2025-11-27 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Biomass GI Railing - Rev A" | NAP
001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8602 | A | 131242-WST02-SD-S-8602 | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | 55 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001870 | 2025-11-27 | 2025-11-27 | A | NAP | Not Approved | 1 | "Shop Drawing for SSN Biomass GI Railing - Rev A" | NAP
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1602 | A | 131242-WST02-SD-S-1602 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1603 | A | 131242-WST02-SD-S-1603 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1604 | A | 131242-WST02-SD-S-1604 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1606 | A | 131242-WST02-SD-S-1606 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5403 | A | 131242-WST02-SD-S-5403 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5604 | A | 131242-WST02-SD-S-5604 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001871 | 2025-11-27 | 2025-11-27 | A | AWC | Approved with Comments | 1 | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600 | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | 32 | Approved with Comments | YES | 2026-01-30 | NO | Resubmitted | 0 |  |  | 001458&&001698&&001700&&001803&&001871 | 2025-07-11 | 2026-02-09 | A.5 | AWC | Approved with Comments | 7 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | AWC
001872 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0001 | 0 | 131242-WST02-CD-B-0001 | 2025-11-27 | SSN- I/O List-BIO-0001 | Rev0: Not Approved | 2025-12-25 | 2025-12-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001872 | 2025-11-27 | 2026-01-28 | 0 | NAP | Not Approved | 2 | "SSN- I/O List-BIO-0001 " | NAP
001872 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0001 | 0 | 131242-WST02-CD-B-0001 | 2026-01-28 | SSN- I/O List-BIO-0001 | Rev0: Not Approved | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001872 | 2025-11-27 | 2026-01-28 | 0 | PEN | Not Approved | 2 | "SSN- I/O List-BIO-0001 " | NAP
001873 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0002 | 0 | 131242-WST02-CD-B-0002 | 2025-11-27 | SSN- I/O List-BIO-0002 | Rev0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2025-12-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001873 | 2025-11-27 | 2026-01-28 | 0 | NAP | Not Approved | 2 | "SSN- I/O List-BIO-0002 " | NAP
001873 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0002 | 0 | 131242-WST02-CD-B-0002 | 2026-01-28 | SSN- I/O List-BIO-0002 | Rev0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001873 | 2025-11-27 | 2026-01-28 | 0 | PEN | Not Approved | 2 | "SSN- I/O List-BIO-0002 " | NAP
001874 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0029 | 0 | 131242-WSW41-PS-HS-0029 | 2025-11-28 | Incentive/ Disincentive Audit Scheme for Jul 2025 | Rev 0: Scoring confirmed to be at 95/100 | 2025-12-26 | 2025-12-23 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001874 | 2025-11-28 | 2025-11-28 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jul 2025" | INF
001875 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0030 | 0 | 131242-WSW41-PS-HS-0030 | 2025-11-28 | Incentive/ Disincentive Audit Scheme for Sept 2025 | Rev 0: Scoring confirmed to be at 95/100 | 2025-12-26 | 2025-12-23 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001875 | 2025-11-28 | 2025-11-28 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Sept 2025" | INF
001876 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | QA | N | 0200 | 0 | 131242-WST02-QA-N-0200 | 2025-11-28 | Commissioning Plan for Reactor and Blowers | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-26 | 2026-01-02 | 25 | Not Approved | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 001876 | 2025-11-28 | 2025-11-28 | 0 | NAP | Not Approved | 1 | " Commissioning Plan for Reactor and Blowers" | NAP
001877 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0061 | 0 | 131242-WSW41-QA-I-0061 | 2025-12-02 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN | NA | 2025-12-30 |  | 84 | Awaiting S.O.'s response | YES | 2026-01-19 | NO | Overdue | 0 |  |  | 001877 | 2025-12-02 | 2025-12-02 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN" | PEN
001878 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0157 | 0 | 131242-WSD11-QA-M-0157 | 2025-12-03 | FAT Report for SS316L Pipes - G2D Line | NA | 2025-12-31 |  | 83 | Awaiting S.O.'s response | YES | 2026-01-20 | NO | Overdue | 0 |  |  | 001878 | 2025-12-03 | 2025-12-03 | 0 | PEN | Awaiting S.O.'s response | 1 | " FAT Report for SS316L Pipes - G2D Line" | PEN
001879 | 00 | Franklin | Mech | NA | 131242 | WSD11 | CL | M | 1088 | 0 | 131242-WSD11-CL-M-1088 | 2025-12-04 | Steam Piping Stress Calculation Report | NA | 2026-01-01 |  | 82 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001879 | 2025-12-04 | 2025-12-04 | 0 | PEN | Awaiting S.O.'s response | 1 | "Steam Piping Stress Calculation Report" | PEN
001880 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0029 | 0 | 131242-WSW41-PC-W-0029 | 2025-12-04 | Payment Claim No.29 | NA | 2026-01-01 |  | 82 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001880 | 2025-12-04 | 2025-12-04 | 0 | PEN | Awaiting S.O.'s response | 1 | "Payment Claim No.29" | PEN
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1604 | A | 131242-WST02-DR-S-1604 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1605 | A | 131242-WST02-DR-S-1605 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1610 | A | 131242-WST02-DR-S-1610 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1611 | A | 131242-WST02-DR-S-1611 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1612 | A | 131242-WST02-DR-S-1612 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5402 | A | 131242-WST02-DR-S-5402 | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | 28 | Approved with Comments | YES | 2026-02-03 | NO | Resubmitted | 0 |  |  | 001881 | 2025-12-05 | 2025-12-05 | A | AWC | Approved with Comments | 1 | "Standardize Support Design for Shelter 1" | AWC
001882 | 00 | Balaji | QAQC | NA | 131242 | WST02 | CD | I | 0002 | 0 | 131242-WST02-CD-I-0002 | 2025-12-08 | SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000 | NA | 2026-01-05 |  | 80 | Awaiting S.O.'s response | YES | 2026-01-23 | NO | Overdue | 0 |  |  | 001882 | 2025-12-08 | 2025-12-08 | 0 | PEN | Awaiting S.O.'s response | 1 | "SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000" | PEN
001883 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0016 | 0 | 131242-WST02-DS-I-0016 | 2025-12-08 | Datasheet for NO2 & NO3 (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-05 | 2026-02-12 | 48 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001883 | 2025-12-08 | 2025-12-08 | 0 | AWC | Approved with Comments | 1 | "Datasheet for NO2 & NO3 (SSN)" | AWC
001884 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0017 | 0 | 131242-WST02-DS-I-0017 | 2025-12-08 | Datasheet for Ammonia Analyser (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-05 | 2026-02-12 | 48 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001884 | 2025-12-08 | 2025-12-08 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Ammonia Analyser (SSN)" | AWC
001885 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0061 | 0 | 131242-WST02-QA-E-0061 | 2025-12-08 | SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | 56 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001885 | 2025-12-08 | 2025-12-08 | 0 | AWC | Approved with Comments | 1 | " SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B" | AWC
001886 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0062 | 0 | 131242-WST02-QA-E-0062 | 2025-12-08 | SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | 56 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001886 | 2025-12-08 | 2025-12-08 | 0 | AWC | Approved with Comments | 1 | "SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B" | AWC
001887 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0063 | 0 | 131242-WST02-QA-E-0063 | 2025-12-08 | SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | 56 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001887 | 2025-12-08 | 2025-12-08 | 0 | AWC | Approved with Comments | 1 | " SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B" | AWC
001888 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-IM-NA | 2025-12-08 | VCM Submission for 2025-11 | For information | 2026-01-05 | 2025-12-31 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000879&&001888&&001941&&002009 | 2024-12-09 | 2026-02-09 | 0 | INF | For Information | 4 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | INF
001889 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0063 | 0 | 131242-WST02-QA-I-0063 | 2025-12-09 | FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX) | R0: Approved with comments. Please find attached comment sheet for resubmission. | 2026-01-06 | 2025-12-19 | 8 | Approved with Comments | YES | 2026-01-08 | NO | Resubmitted | 0 |  |  | 001889 | 2025-12-09 | 2025-12-09 | 0 | AWC | Approved with Comments | 1 | "FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX)" | AWC
001890 | 00 | NA | QAQC | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-12-09 | FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-06 | 2025-12-19 | 8 | Approved with Comments | YES | 2026-01-08 | NO | Resubmitted | 74 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | AWC | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001891 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | I | 0023 | 0 | 131242-WST02-QA-I-0023 | 2025-12-09 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | NA | 2026-01-06 |  | 79 | Awaiting S.O.'s response | YES | 2026-01-26 | NO | Overdue | 130 |  |  | 001396&&001891 | 2025-06-23 | 2025-12-09 | 0 | PEN | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | AWC
001892 | 00 | NA | PMT | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-12-12 | Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A” | NA | 2026-01-09 |  | 76 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | PEN | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0001 | A.1 | 131242-WSD11-DR-A-0001 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0002 | A.1 | 131242-WSD11-DR-A-0002 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0003 | A.1 | 131242-WSD11-DR-A-0003 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A.1 | 131242-WSD11-DR-A-1002 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A.1 | 131242-WSD11-DR-A-1003 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1004 | A.1 | 131242-WSD11-DR-A-1004 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | YES | 2026-01-21 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A.1 | 131242-WSD11-DR-A-2000 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A.1 | 131242-WSD11-DR-A-3000 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | 75 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001894 | 00 | Kumar | CSA | NA | 131242 | WSW41 | QA | C | 0046 | 0 | 131242-WSW41-QA-C-0046 | 2025-12-15 | Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025 | For information | 2026-01-12 | 2025-12-29 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001894 | 2025-12-15 | 2025-12-15 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" | INF
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3145 | A | 131242-WSD11-DR-EP-3145 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3146 | A | 131242-WSD11-DR-EP-3146 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7245 | A | 131242-WSD11-DR-EP-7245 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7246 | A | 131242-WSD11-DR-EP-7246 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7345 | A | 131242-WSD11-DR-EP-7345 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7346 | A | 131242-WSD11-DR-EP-7346 | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | 51 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001895 | 2025-12-15 | 2025-12-15 | A | NAP | Not Approved | 1 | "G1 Booster Pump LCP Drawings" | NAP
001896 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | M | 0158 | 0 | 131242-WST02-QA-M-0158 | 2025-12-15 | ITP for Portable A Frame & T-Davit (Growa) | NA | 2026-01-12 |  | 75 | Awaiting S.O.'s response | YES | 2026-01-30 | NO | Overdue | 0 |  |  | 001896 | 2025-12-15 | 2025-12-15 | 0 | PEN | Awaiting S.O.'s response | 1 | "ITP for Portable A Frame & T-Davit (Growa)" | PEN
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1541 | A | 131242-WSD11-DR-IP-1541 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1542 | A | 131242-WSD11-DR-IP-1542 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1543 | A | 131242-WSD11-DR-IP-1543 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1544 | A | 131242-WSD11-DR-IP-1544 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1545 | A | 131242-WSD11-DR-IP-1545 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1546 | A | 131242-WSD11-DR-IP-1546 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1547 | A | 131242-WSD11-DR-IP-1547 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1548 | A | 131242-WSD11-DR-IP-1548 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1549 | A | 131242-WSD11-DR-IP-1549 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1550 | A | 131242-WSD11-DR-IP-1550 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1551 | A | 131242-WSD11-DR-IP-1551 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1552 | A | 131242-WSD11-DR-IP-1552 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1553 | A | 131242-WSD11-DR-IP-1553 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1554 | A | 131242-WSD11-DR-IP-1554 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1555 | A | 131242-WSD11-DR-IP-1555 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1556 | A | 131242-WSD11-DR-IP-1556 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1557 | A | 131242-WSD11-DR-IP-1557 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | AWC
001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1558 | A | 131242-WSD11-DR-IP-1558 | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | 40 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001897 | 2025-12-15 | 2025-12-15 | A | AWC | Approved with Comments | 1 | "THP FOIP-0001 GA & Wiring Drawings" | AWC
001898 | 00 | Joo Kwan | EICA | NA | 131242 | WST02 | SP | I | 0003 | 0 | 131242-WST02-SP-I-0003 | 2025-12-15 | SSNR Master Control | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-16 | 45 | Not Approved | YES | 2026-03-06 | NO | Resubmitted | 0 |  |  | 001898 | 2025-12-15 | 2025-12-15 | 0 | NAP | Not Approved | 1 | "SSNR Master Control" | NAP
001899 | 00 | NA | PMT | NA | 131242 | WSW41 | RT | PM | 0031 | 0 | 131242-WSW41-RT-PM-0031 | 2025-12-16 | C4B Monthly Progress Report Number No.31 (11 25) | NA | 2026-01-13 |  | 74 | Awaiting S.O.'s response | YES | 2026-02-02 | NO | Overdue | 0 |  |  | 001899 | 2025-12-16 | 2025-12-16 | 0 | PEN | Awaiting S.O.'s response | 1 | "C4B Monthly Progress Report Number No.31 (11 25)" | PEN
001900 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0012 | 0 | 131242-WST02-VI-A-0012 | 2025-12-16 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-13 | 2026-01-07 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001900 | 2025-12-16 | 2025-12-16 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | NAP
001900 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | CRS | 1 | 131242-WST02-VI-A-CRS | 2026-01-27 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-09 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001900 | 2026-01-27 | 2026-02-11 | 2 | AWC | Approved with Comments | 2 | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | AWC
001900 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | CRS | 2 | 131242-WST02-VI-A-CRS | 2026-02-11 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-03 | 2026-02-25 | 10 | Approved with Comments | YES | 2026-03-17 | NO | Resubmitted | 0 |  |  | 001900 | 2026-01-27 | 2026-02-11 | 2 | AWC | Approved with Comments | 2 | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | AWC
001901 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 5001 | A | 131242-WSD11-DR-BF-5001 | 2025-12-16 | Typical Fire Alarm Installation Detail (THP) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-13 | 2026-01-07 | 16 | Not Approved | YES | 2026-01-27 | NO | Resubmitted | 0 |  |  | 001901 | 2025-12-16 | 2025-12-16 | A | NAP | Not Approved | 1 | "Typical Fire Alarm Installation Detail (THP)" | NAP
001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 3000 | A1 | 131242-WSD11-DR-BF-3000 | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | 74 | Awaiting S.O.'s response | YES | 2026-02-02 | NO | Overdue | 0 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | PEN | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 5000 | A | 131242-WSD11-DR-BF-5000 | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | 74 | Awaiting S.O.'s response | YES | 2026-02-02 | NO | Overdue | 0 |  |  | 001902 | 2025-12-16 | 2025-12-16 | A | PEN | Awaiting S.O.'s response | 1 | "Dry Riser Installation Details" | PEN
001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A1 | 131242-WSD11-DR-BF-7000 | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | 74 | Awaiting S.O.'s response | YES | 2026-02-02 | NO | Overdue | 246 |  |  | 001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | PEN | Approved with Comments | 2 | "THP-Dry Riser System" && "Dry Riser Installation Details" | AWC
001903 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0023 | 0 | 131242-WST02-DS-I-0023 | 2025-12-16 | Datasheet for Magnetic Level Gauge (SSN) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-01-13 | 2026-02-12 | 42 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001903 | 2025-12-16 | 2025-12-16 | 0 | NAP | Not Approved | 1 | "Datasheet for Magnetic Level Gauge (SSN)" | NAP
001904 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5102 | B | 131242-WSD11-DR-I-5102 | 2025-12-16 | Hook-up drawing for PDSH for CAS (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-13 | 2026-02-12 | 42 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001352&&001904 | 2025-06-10 | 2025-12-16 | B | AWC | Approved with Comments | 2 | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | AWC
001905 | 00 | NA | NA | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2025-12-17 | As Built Drawing for ST619 (THP Cooler Platform) | VOID, NOT IN USE | 2026-01-14 |  | 73 | Rejected | YES | 2026-01-26 | NO | Overdue | 0 |  | To withdraw since duplicate submission with 1906. | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | REJ | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 0306 | X | 131242-WSW41-SD-S-0306 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001906 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | PEN
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1101 | X | 131242-WSW41-SD-S-1101 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1102 | X | 131242-WSW41-SD-S-1102 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1103 | X | 131242-WSW41-SD-S-1103 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2100 | X | 131242-WSW41-SD-S-2100 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 3100 | X | 131242-WSW41-SD-S-3100 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 000581&&001085&&001906 | 2024-07-23 | 2025-12-17 | X | PEN | Not Approved | 3 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5100 | X | 131242-WSW41-SD-S-5100 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5101 | X | 131242-WSW41-SD-S-5101 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5102 | X | 131242-WSW41-SD-S-5102 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 8002 | X | 131242-WSW41-SD-S-8002 | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 173 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | PEN | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | NAP
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 0300 | X | 131242-WSW41-SD-S-0300 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1000 | X | 131242-WSW41-SD-S-1000 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1001 | X | 131242-WSW41-SD-S-1001 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1002 | X | 131242-WSW41-SD-S-1002 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1003 | X | 131242-WSW41-SD-S-1003 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1004 | X | 131242-WSW41-SD-S-1004 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1005 | X | 131242-WSW41-SD-S-1005 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1006 | X | 131242-WSW41-SD-S-1006 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1007 | X | 131242-WSW41-SD-S-1007 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1008 | X | 131242-WSW41-SD-S-1008 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2000 | X | 131242-WSW41-SD-S-2000 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2001 | X | 131242-WSW41-SD-S-2001 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 3000 | X | 131242-WSW41-SD-S-3000 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5000 | X | 131242-WSW41-SD-S-5000 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5001 | X | 131242-WSW41-SD-S-5001 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5002 | X | 131242-WSW41-SD-S-5002 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5003 | X | 131242-WSW41-SD-S-5003 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5004 | X | 131242-WSW41-SD-S-5004 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 8001 | X | 131242-WSW41-SD-S-8001 | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | 73 | Awaiting S.O.'s response | YES | 2026-02-03 | NO | Overdue | 0 |  |  | 001907 | 2025-12-17 | 2025-12-17 | X | PEN | Awaiting S.O.'s response | 1 | "As built drawing for ST621 (SWPR PR 01 & 02)" | PEN
001908 | 00 | Jun | EICA | NA | 131242 | WST02 | RT | E | 0012 | 0 | 131242-WST02-RT-E-0012 | 2025-12-18 | SSN-Transformer Bay Gravel Sieve Analysis Report | Rev 0: Approved | 2026-01-15 | 2026-02-24 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001908 | 2025-12-18 | 2025-12-18 | 0 | APP | Approved | 1 | "SSN-Transformer Bay Gravel Sieve Analysis Report" | APP
001909 | 00 | NA | BS | NA | 131242 | WST02 | QA | BS | 0020 | 0 | 131242-WST02-QA-BS-0020 | 2025-12-18 | SAT Procedure for Public Address System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-01-07 | 14 | Not Approved | YES | 2026-01-27 | NO | Resubmitted | 0 |  |  | 001909 | 2025-12-18 | 2025-12-18 | 0 | NAP | Not Approved | 1 | "SAT Procedure for Public Address System" | NAP
001910 | 00 | NA | CSA | NA | 131242 | WSD11 | SD | S | Fab Drawing | NA | 131242-WSD11-SD-S-Fab Drawing | 2025-12-18 | THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed) | For Information | 2026-01-15 | 2026-01-12 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001910 | 2025-12-18 | 2025-12-18 | NA | INF | For Information | 1 | "THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed)" | INF
001911 | 00 | NA | BS | NA | 131242 | WST02 | QA | BS | 0019 | 0 | 131242-WST02-QA-BS-0019 | 2025-12-18 | Site Acceptance Test Procedure for Clean Gas System Panel | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-01-07 | 14 | Not Approved | YES | 2026-01-27 | NO | Resubmitted | 0 |  |  | 001911 | 2025-12-18 | 2025-12-18 | 0 | NAP | Not Approved | 1 | "Site Acceptance Test Procedure for Clean Gas System Panel" | NAP
001912 | 00 | NA | CSA | NA | 131242 | WST02 | DR | S | 3002 | E | 131242-WST02-DR-S-3002 | 2025-12-18 | ST Updates for SSN Staircase (ST607) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-04 | 34 | Approved with Comments | YES | 2026-02-24 | NO | Resubmitted | 0 |  |  | 001528&&001912 | 2025-07-24 | 2026-02-09 | A.6 | AWC | Approved with Comments | 4 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | AWC
001913 | 00 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0010 | 0 | 131242-WSD11-CD-I-0010 | 2025-12-18 | THP RIO 0201 I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-15 | 2026-02-04 | 34 | Approved with Comments | YES | 2026-02-24 | NO | Resubmitted | 0 |  |  | 001913 | 2025-12-18 | 2025-12-18 | 0 | AWC | Approved with Comments | 1 | "THP RIO 0201 I/O List" | AWC
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1023 | C | 131242-WST02-DR-S-1023 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | C | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1024 | C | 131242-WST02-DR-S-1024 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | C | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1025 | B.1 | 131242-WST02-DR-S-1025 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | B.1 | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1026 | A | 131242-WST02-DR-S-1026 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | A | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1400 | H | 131242-WST02-DR-S-1400 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1401 | H | 131242-WST02-DR-S-1401 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001730&&001914 | 2025-10-08 | 2025-12-18 | H | NAP | Not Approved | 2 | "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1402 | C | 131242-WST02-DR-S-1402 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | C | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1403 | C | 131242-WST02-DR-S-1403 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | C | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1607 | F | 131242-WST02-DR-S-1607 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | F | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 5400 | F | 131242-WST02-DR-S-5400 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 5406 | E | 131242-WST02-DR-S-5406 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | 46 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001914 | 2025-12-18 | 2025-12-18 | E | NAP | Not Approved | 1 | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | NAP
001915 | 00 | Franklin | Mech | NA | 131242 | WST02 | DS | M | 5650 | 0 | 131242-WST02-DS-M-5650 | 2025-12-18 | Data Sheet for Davit Arm and Mount Socket | NA | 2026-01-15 |  | 72 | Awaiting S.O.'s response | YES | 2026-02-04 | NO | Overdue | 0 |  |  | 001915 | 2025-12-18 | 2025-12-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "Data Sheet for Davit Arm and Mount Socket" | PEN
001915 | 00 | Franklin | Mech | NA | 131242 | WST02 | DS | M | 5655 | 0 | 131242-WST02-DS-M-5655 | 2025-12-18 | Data Sheet for Davit Arm and Mount Socket | NA | 2026-01-15 |  | 72 | Awaiting S.O.'s response | YES | 2026-02-04 | NO | Overdue | 0 |  |  | 001915 | 2025-12-18 | 2025-12-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "Data Sheet for Davit Arm and Mount Socket" | PEN
001916 | 00 | NA | Mech | NA | 131242 | WST02 | OM | M | 0017 | 0 | 131242-WST02-OM-M-0017 | 2025-12-18 | O&M Manual for A-Frame and T-Davit | NA | 2026-01-15 |  | 72 | Awaiting S.O.'s response | YES | 2026-02-04 | NO | Overdue | 0 |  |  | 001916 | 2025-12-18 | 2025-12-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "O&M Manual for A-Frame and T-Davit" | PEN
001917 | 00 | NA | Mech | NA | 131242 | WST02 | OM | M | 0019 | 0 | 131242-WST02-OM-M-0019 | 2025-12-18 | Long term storage & Preservation procedure for A-Frame and T-Davit | NA | 2026-01-15 |  | 72 | Awaiting S.O.'s response | YES | 2026-02-04 | NO | Overdue | 0 |  |  | 001917 | 2025-12-18 | 2025-12-18 | 0 | PEN | Awaiting S.O.'s response | 1 | "Long term storage & Preservation procedure for A-Frame and T-Davit" | PEN
001918 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | E | 0064 | 0 | 131242-WST02-QA-E-0064 | 2025-12-18 | SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | 48 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001918 | 2025-12-18 | 2025-12-18 | 0 | AWC | Approved with Comments | 1 | "SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B)" | AWC
001919 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0006 | 0 | 131242-WSD11-QA-E-0006 | 2025-12-18 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | 48 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001919 | 2025-12-18 | 2025-12-18 | 0 | AWC | Approved with Comments | 1 | "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | AWC
001920 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0066 | 0 | 131242-WSD11-QA-E-0066 | 2025-12-18 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | Rev 0: Rejected | 2026-01-15 | 2026-02-23 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001920 | 2025-12-18 | 2025-12-18 | 0 | REJ | Rejected | 1 | "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | REJ
001921 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0065 | 0 | 131242-WSD11-QA-E-0065 | 2025-12-18 | SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | 48 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001921 | 2025-12-18 | 2025-12-18 | 0 | AWC | Approved with Comments | 1 | "SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B" | AWC
001922 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | M | 0159 | 0 | 131242-WSD11-QA-M-0159 | 2025-12-19 | FAT Report for SS 316L (CWP 205) Pipes -149 Nos | NA | 2026-01-16 |  | 71 | Awaiting S.O.'s response | YES | 2026-02-05 | NO | Overdue | 0 |  |  | 001922 | 2025-12-19 | 2025-12-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for SS 316L (CWP 205) Pipes -149 Nos" | PEN
001923 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | I | 0064 | 0 | 131242-WST02-QA-I-0064 | 2025-12-19 | Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN | NA | 2026-01-16 |  | 71 | Awaiting S.O.'s response | YES | 2026-02-05 | NO | Overdue | 0 |  |  | 001923 | 2025-12-19 | 2025-12-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN" | PEN
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1000 | A.2 | 131242-WST02-DR-A-1000 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | NAP | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1001 | A.2 | 131242-WST02-DR-A-1001 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1002 | A.2 | 131242-WST02-DR-A-1002 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1003 | A.2 | 131242-WST02-DR-A-1003 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1004 | A.2 | 131242-WST02-DR-A-1004 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1005 | A | 131242-WST02-DR-A-1005 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A | NAP | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1006 | A.2 | 131242-WST02-DR-A-1006 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | NAP | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1009 | A.2 | 131242-WST02-DR-A-1009 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2000 | A.2 | 131242-WST02-DR-A-2000 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000809&&001604&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 4 | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2001 | A.2 | 131242-WST02-DR-A-2001 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2002 | A.2 | 131242-WST02-DR-A-2002 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2003 | A.2 | 131242-WST02-DR-A-2003 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2007 | A.2 | 131242-WST02-DR-A-2007 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 3000 | A.2 | 131242-WST02-DR-A-3000 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000809&&001924 | 2024-11-13 | 2026-02-03 | A.2 | NAP | Not Approved | 3 | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 9000 | A.2 | 131242-WST02-DR-A-9000 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | NAP | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 9001 | A.2 | 131242-WST02-DR-A-9001 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | NAP | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1000 | A.2 | 131242-WST02-DR-A-1000 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 41 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | PEN | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1001 | A.2 | 131242-WST02-DR-A-1001 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 67 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1002 | A.2 | 131242-WST02-DR-A-1002 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1003 | A.2 | 131242-WST02-DR-A-1003 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1004 | A.2 | 131242-WST02-DR-A-1004 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1005 | A | 131242-WST02-DR-A-1005 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A | PEN | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1006 | A.2 | 131242-WST02-DR-A-1006 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | PEN | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1009 | A.2 | 131242-WST02-DR-A-1009 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2000 | A.2 | 131242-WST02-DR-A-2000 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 41 |  |  | 000809&&001604&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 4 | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2001 | A.2 | 131242-WST02-DR-A-2001 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2002 | A.2 | 131242-WST02-DR-A-2002 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2003 | A.2 | 131242-WST02-DR-A-2003 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2007 | A.2 | 131242-WST02-DR-A-2007 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 3000 | A.2 | 131242-WST02-DR-A-3000 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 404 |  |  | 000809&&001924 | 2024-11-13 | 2026-02-03 | A.2 | PEN | Not Approved | 3 | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 9000 | A.2 | 131242-WST02-DR-A-9000 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | PEN | Not Approved | 2 | "SSN URA Submission" | NAP
001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 9001 | A.2 | 131242-WST02-DR-A-9001 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001924 | 2025-12-22 | 2026-02-03 | A.2 | PEN | Not Approved | 2 | "SSN URA Submission" | NAP
001925 | 00 | NA | Process | NA | 131242 | WST02 | SP | P | 0004 | 0 | 131242-WST02-SP-P-0004 | 2025-12-22 | SSN Blower Plant Control Narrative | Rev0: Approved with comments. Please revise as per the comments and resubmit. | 2026-01-19 | 2026-02-09 | 35 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001925 | 2025-12-22 | 2025-12-22 | 0 | AWC | Approved with Comments | 1 | "SSN Blower Plant Control Narrative" | AWC
001926 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | M | 0160 | 0 | 131242-WST02-QA-M-0160 | 2025-12-23 | FAT Report for Solenoid Valves (Norgren) | NA | 2026-01-20 |  | 69 | Awaiting S.O.'s response | YES | 2026-02-09 | NO | Overdue | 0 |  |  | 001926 | 2025-12-23 | 2025-12-23 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Solenoid Valves (Norgren)" | PEN
001927 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | M | 0161 | 0 | 131242-WSD11-QA-M-0161 | 2025-12-23 | FAT Report for SS 316L Pipes - 77 Nos | NA | 2026-01-20 |  | 69 | Awaiting S.O.'s response | YES | 2026-02-09 | NO | Overdue | 0 |  |  | 001927 | 2025-12-23 | 2025-12-23 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for SS 316L Pipes - 77 Nos" | PEN
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1101 | X | 131242-WSW41-DR-S-1101 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1102 | X | 131242-WSW41-DR-S-1102 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1103 | X | 131242-WSW41-DR-S-1103 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1104 | X | 131242-WSW41-DR-S-1104 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1105 | X | 131242-WSW41-DR-S-1105 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1106 | X | 131242-WSW41-DR-S-1106 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1107 | X | 131242-WSW41-DR-S-1107 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1108 | X | 131242-WSW41-DR-S-1108 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2100 | X | 131242-WSW41-DR-S-2100 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2101 | X | 131242-WSW41-DR-S-2101 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2102 | X | 131242-WSW41-DR-S-2102 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3100 | X | 131242-WSW41-DR-S-3100 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3101 | X | 131242-WSW41-DR-S-3101 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5100 | X | 131242-WSW41-DR-S-5100 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5101 | X | 131242-WSW41-DR-S-5101 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5102 | X | 131242-WSW41-DR-S-5102 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5103 | X | 131242-WSW41-DR-S-5103 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5104 | X | 131242-WSW41-DR-S-5104 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5105 | X | 131242-WSW41-DR-S-5105 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5106 | X | 131242-WSW41-DR-S-5106 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928 | 2025-12-29 | 2025-12-29 | X | NAP | Not Approved | 1 | "As built drawing for ST614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8002 | X | 131242-WSW41-DR-S-8002 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0310 | X | 131242-WSW41-DR-S-0310 | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | 40 | Not Approved | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001929 | 00 | NA | QAQC | NA | 131242 | WSW41 | QA | E | 0067 | 0 | 131242-WSW41-QA-E-0067 | 2025-12-30 | Earthing System Test Report (SSN Electrical Building) | Rev 0: Not approved - Revise and Resubmit | 2026-01-27 | 2026-02-24 | 40 | Not Approved | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001929 | 2025-12-30 | 2025-12-30 | 0 | NAP | Not Approved | 1 | "Earthing System Test Report (SSN Electrical Building)" | NAP
001930 | 00 | NA | PMT | NA | 131242 | WSW41 | LT | PM | 0079 | 0 | 131242-WSW41-LT-PM-0079 | 2025-12-31 | Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities | Rev (0): Received for information. Please refer to S.O. correspondence no. 436 dated 13 Feb 2026. | 2026-01-28 | 2026-02-24 | 39 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001930 | 2025-12-31 | 2025-12-31 | 0 | INF | For Information | 1 | "Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities" | INF
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0001 | A | 131242-WSD11-DR-A-0001 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | YES | 2026-02-20 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0002 | A | 131242-WSD11-DR-A-0002 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | YES | 2026-02-20 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0003 | A | 131242-WSD11-DR-A-0003 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | YES | 2026-02-20 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1000 | A | 131242-WSD11-DR-A-1000 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | YES | 2026-02-20 | NO | Overdue | 0 |  |  | 001931 | 2026-01-05 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 1 | "THP BCA BP Submission" | PEN
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-A-1001 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 2 | "THP Layout, Elevations and Section Details" && "THP BCA BP Submission" | INF
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A | 131242-WSD11-DR-A-1002 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A | 131242-WSD11-DR-A-1003 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1004 | A | 131242-WSD11-DR-A-1004 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | YES | 2026-02-20 | NO | Overdue | 0 |  |  | 001893&&001931 | 2025-12-14 | 2026-01-05 | A | PEN | Awaiting S.O.'s response | 2 | "THP URA Amendment submissions" && "THP BCA BP Submission" | PEN
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A | 131242-WSD11-DR-A-2000 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A | 131242-WSD11-DR-A-3000 | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | 60 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | PEN | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | INF
001932 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | BH | 0002 | 0 | 131242-WSW41-MS-BH-0002 | 2026-01-05 | MSRA, SWP for Testing and Commissioning for ACMV System works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-02 | 2026-01-07 | 2 | Not Approved | YES | 2026-01-27 | NO | Resubmitted | 0 |  |  | 001932 | 2026-01-05 | 2026-01-05 | 0 | NAP | Not Approved | 1 | "MSRA, SWP for Testing and Commissioning for ACMV System works" | NAP
001933 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0065 | 0 | 131242-WSW41-QA-I-0065 | 2026-01-05 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP) | Rev 0. Approved with comments. Revise and resubmit required. Refer to the attached SRC response. | 2026-02-02 | 2026-01-22 | 13 | Approved with Comments | YES | 2026-02-11 | NO | Resubmitted | 0 |  |  | 001933 | 2026-01-05 | 2026-01-05 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP)" | AWC
001934 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | MM | PM | 0002 | 0 | 131242-WSW41-MM-PM-0002 | 2026-01-05 | Memo-Appointment of LEW Representatives_01 Nov 2025 | Rev 0: For Information | 2026-02-02 | 2026-02-09 | 25 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001934 | 2026-01-05 | 2026-01-05 | 0 | INF | For Information | 1 | "Memo-Appointment of LEW Representatives_01 Nov 2025" | INF
001935 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0066 | 0 | 131242-WSW41-QA-I-0066 | 2026-01-07 | Factory Acceptance Test Report for Thermal Flow Switch (THP) | Rev 0. Approved with comments. Revise and resubmit. Refer to attached SRC response | 2026-02-04 | 2026-01-22 | 11 | Approved with Comments | YES | 2026-02-11 | NO | Resubmitted | 0 |  |  | 001935 | 2026-01-07 | 2026-01-07 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Thermal Flow Switch (THP)" | AWC
001936 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DS | E | 0001 | 0 | 131242-WSD11-DS-E-0001 | 2026-01-07 | THP and SSN Cable Ladder/ Tray Data Sheet and Specifications | NA | 2026-02-04 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 001936 | 2026-01-07 | 2026-01-07 | 0 | PEN | Awaiting S.O.'s response | 1 | "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | PEN
001937 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0026 | 0 | 131242-WST02-DS-E-0026 | 2026-01-07 | SSN ACB Lifting Truck Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2026-02-04 | 2026-02-09 | 23 | Not Approved | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001937 | 2026-01-07 | 2026-01-07 | 0 | NAP | Not Approved | 1 | "SSN ACB Lifting Truck Data Sheet" | NAP
001938 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0163 | 0 | 131242-WST02-QA-M-0163 | 2026-01-07 | Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen) | NA | 2026-02-04 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 001938 | 2026-01-07 | 2026-01-07 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen)" | PEN
001939 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0162 | 0 | 131242-WSD11-QA-M-0162 | 2026-01-07 | FAT Report for SS 316L (CWP 205) Pipes - 201 Nos | NA | 2026-02-04 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 001939 | 2026-01-07 | 2026-01-07 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for SS 316L (CWP 205) Pipes - 201 Nos" | PEN
001940 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0031 | 0 | 131242-WSW41-QA-A-0031 | 2026-01-08 | SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team) | R0: Approved | 2026-02-05 | 2026-02-12 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001940 | 2026-01-08 | 2026-01-08 | 0 | APP | Approved | 1 | "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | APP
001941 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-IM-NA | 2026-01-08 | VCM Submission for 2025-12 | NA | 2026-02-05 |  | 57 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000879&&001888&&001941&&002009 | 2024-12-09 | 2026-02-09 | 0 | PEN | For Information | 4 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | INF
001942 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0080 | 0 | 131242-WSW41-LT-PM-0080 | 2026-01-12 | Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001942 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation" | PEN
001943 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0164 | 0 | 131242-WSW41-QA-M-0164 | 2026-01-12 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax) | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001943 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax)" | PEN
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 8002 | C | 131242-WSD11-DR-S-8002 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1100 | C | 131242-WSD11-DR-S-1100 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0306 | C | 131242-WSD11-DR-S-0306 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0307 | C | 131242-WSD11-DR-S-0307 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0308 | C | 131242-WSD11-DR-S-0308 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1101 | C | 131242-WSD11-DR-S-1101 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001944&&001975 | 2026-01-12 | 2026-01-26 | C | NAP | For Information | 2 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "WD for ST622 " | INF
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2100 | C | 131242-WSD11-DR-S-2100 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3100 | C | 131242-WSD11-DR-S-3100 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5100 | C | 131242-WSD11-DR-S-5100 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5101 | C | 131242-WSD11-DR-S-5101 | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Not Approved | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001944 | 2026-01-12 | 2026-01-12 | C | NAP | Not Approved | 1 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | NAP
001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5407 | B | 131242-WSD11-DR-S-5407 | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001945 | 2026-01-12 | 2026-01-12 | B | AWC | Approved with Comments | 1 | "G2D Pipe Support_Report from QPD" | AWC
001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1613 | B | 131242-WSD11-DR-S-1613 | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 0 |  |  | 001945 | 2026-01-12 | 2026-01-12 | B | AWC | Approved with Comments | 1 | "G2D Pipe Support_Report from QPD" | AWC
001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CL | S | 0007 | 1 | 131242-WSD11-CL-S-0007 | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | 23 | Approved with Comments | YES | 2026-03-04 | NO | Resubmitted | 308 |  |  | 000960&&001945 | 2025-01-10 | 2026-01-12 | 1 | AWC | Approved with Comments | 2 | "Support design for compressed Air system >2m" && "G2D Pipe Support_Report from QPD" | AWC
001946 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0166 | 0 | 131242-WSW41-QA-M-0166 | 2026-01-12 | FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001946 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) " | PEN
001947 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0067 | 0 | 131242-WST02-QA-I-0067 | 2026-01-12 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001947 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN" | PEN
001948 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DS | E | 0003 | 0 | 131242-WSD11-DS-E-0003 | 2026-01-12 | THP and SSN Earthing Material Specifications | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001948 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "THP and SSN Earthing Material Specifications" | PEN
001949 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0032 | 0 | 131242-WST02-QA-A-0032 | 2026-01-12 | Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-02 | 15 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 001949 | 2026-01-12 | 2026-01-12 | 0 | NAP | Not Approved | 1 | "Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd)" | NAP
001950 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0033 | 0 | 131242-WST02-QA-A-0033 | 2026-01-12 | Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal) | For Information | 2026-02-09 | 2026-02-20 | 29 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001950 | 2026-01-12 | 2026-01-12 | 0 | INF | For Information | 1 | "Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal)" | INF
001951 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0167 | 0 | 131242-WSD11-QA-M-0167 | 2026-01-12 | FAT Report for Non Return Check Valve - Batch 2 (Breen) | NA | 2026-02-09 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 001951 | 2026-01-12 | 2026-01-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Non Return Check Valve - Batch 2 (Breen)" | PEN
001952 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0168 | 0 | 131242-WSW41-QA-M-0168 | 2026-01-13 | Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax) | NA | 2026-02-10 |  | 54 | Awaiting S.O.'s response | YES | 2026-03-02 | NO | Overdue | 0 |  |  | 001952 | 2026-01-13 | 2026-01-13 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax)" | PEN
001953 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0081 | 0 | 131242-WSW41-LT-PM-0081 | 2026-01-14 | CV of Team Member (MEM) | NA | 2026-02-11 |  | 53 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 001953&&002012 | 2026-01-14 | 2026-02-11 | 0 | PEN | Awaiting S.O.'s response | 2 | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | PEN
001954 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0030 | 0 | 131242-WSW41-PC-W-0030 | 2026-01-14 | Payment Claim No.30 | NA | 2026-02-11 |  | 53 | Awaiting S.O.'s response | YES | 2026-03-03 | NO | Overdue | 0 |  |  | 001954 | 2026-01-14 | 2026-01-14 | 0 | PEN | Awaiting S.O.'s response | 1 | "Payment Claim No.30" | PEN
001955 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0032 | 0 | 131242-WSW41-RT-PM-0032 | 2026-01-15 | C4B Monthly Progress Report Number No.32 (12 25) | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001955 | 2026-01-15 | 2026-01-15 | 0 | PEN | Awaiting S.O.'s response | 1 | "C4B Monthly Progress Report Number No.32 (12 25)" | PEN
001956 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0012 | 0 | 131242-WSD11-DS-I-0012 | 2026-01-15 | Datasheet for Thermal Flow Switch (THP-BOP) | Rev 0. Approved with comments. Revise and resubmit required. Refer to the attached SRC response. | 2026-02-12 | 2026-01-20 | 3 | Approved with Comments | YES | 2026-02-09 | NO | Resubmitted | 0 |  |  | 001956 | 2026-01-15 | 2026-01-15 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Thermal Flow Switch (THP-BOP)" | AWC
001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5430 | A | 131242-WST02-DR-I-5430 | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001957 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NO2 / NO3 Analyser" | PEN
001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5431 | A | 131242-WST02-DR-I-5431 | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001957 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NO2 / NO3 Analyser" | PEN
001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5432 | A | 131242-WST02-DR-I-5432 | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001957 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NO2 / NO3 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5440 | A | 131242-WST02-DR-I-5440 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5441 | A | 131242-WST02-DR-I-5441 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5442 | A | 131242-WST02-DR-I-5442 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5443 | A | 131242-WST02-DR-I-5443 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5444 | A | 131242-WST02-DR-I-5444 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5445 | A | 131242-WST02-DR-I-5445 | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001958 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for NH4 Analyser" | PEN
001959 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0013 | A | 131242-WSD11-DS-I-0013 | 2026-01-15 | Datasheet for Electromagnetic Flow Meter (THP-BOP) | NA | 2026-02-12 |  | 52 | Awaiting S.O.'s response | YES | 2026-03-04 | NO | Overdue | 0 |  |  | 001959 | 2026-01-15 | 2026-01-15 | A | PEN | Awaiting S.O.'s response | 1 | "Datasheet for Electromagnetic Flow Meter (THP-BOP) " | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0001_FSSD BP | A | 131242-WSD11-DR-A-0001_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0002_FSSD BP | A | 131242-WSD11-DR-A-0002_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0003_FSSD BP | A | 131242-WSD11-DR-A-0003_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD BP | A | 131242-WSD11-DR-A-1000_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD BP | A | 131242-WSD11-DR-A-1001_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD BP | A | 131242-WSD11-DR-A-1002_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD BP | A | 131242-WSD11-DR-A-1003_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD BP | A | 131242-WSD11-DR-A-1004_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_FSSD BP | A | 131242-WSD11-DR-A-2000_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_FSSD BP | A | 131242-WSD11-DR-A-3000_FSSD BP | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001960 | 2026-01-19 | 2026-01-19 | A | PEN | Awaiting S.O.'s response | 1 | "THP_FSSD (BP) Submission" | PEN
001961 | 00 | Yuen Fatt | BS | NA | 131242 | WST02 | VI | B | 0007 | 0 | 131242-WST02-VI-B-0007 | 2026-01-19 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001961 | 2026-01-19 | 2026-01-19 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" | PEN
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0310 | E | 131242-WSW41-DR-S-0310 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0311 | E | 131242-WSW41-DR-S-0311 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | E | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0312 | D | 131242-WSW41-DR-S-0312 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | D | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0313 | D | 131242-WSW41-DR-S-0313 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | D | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0314 | D | 131242-WSW41-DR-S-0314 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | D | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0315 | D | 131242-WSW41-DR-S-0315 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | D | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1100 | E | 131242-WSW41-DR-S-1100 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001962 | 2026-01-19 | 2026-01-19 | E | NAP | Not Approved | 1 | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1101 | E | 131242-WSW41-DR-S-1101 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1102 | E | 131242-WSW41-DR-S-1102 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1103 | E | 131242-WSW41-DR-S-1103 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1104 | E | 131242-WSW41-DR-S-1104 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1105 | E | 131242-WSW41-DR-S-1105 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1106 | E | 131242-WSW41-DR-S-1106 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2100 | E | 131242-WSW41-DR-S-2100 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2101 | E | 131242-WSW41-DR-S-2101 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3100 | E | 131242-WSW41-DR-S-3100 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5100 | E | 131242-WSW41-DR-S-5100 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5101 | E | 131242-WSW41-DR-S-5101 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5102 | E | 131242-WSW41-DR-S-5102 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5103 | E | 131242-WSW41-DR-S-5103 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8002 | E | 131242-WSW41-DR-S-8002 | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | 24 | Not Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001928&&001962 | 2025-12-29 | 2026-01-19 | E | NAP | Not Approved | 2 | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | NAP
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0300 | F | 131242-WSW41-DR-S-0300 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0301 | F | 131242-WSW41-DR-S-0301 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0302 | F | 131242-WSW41-DR-S-0302 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0303 | F | 131242-WSW41-DR-S-0303 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0304 | F | 131242-WSW41-DR-S-0304 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0305 | F | 131242-WSW41-DR-S-0305 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0306 | F | 131242-WSW41-DR-S-0306 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0307 | F | 131242-WSW41-DR-S-0307 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | F | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0308 | NA | 131242-WSW41-DR-S-0308 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0309 | NA | 131242-WSW41-DR-S-0309 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1000 | NA | 131242-WSW41-DR-S-1000 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1001 | NA | 131242-WSW41-DR-S-1001 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1002 | NA | 131242-WSW41-DR-S-1002 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1003 | NA | 131242-WSW41-DR-S-1003 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1004 | NA | 131242-WSW41-DR-S-1004 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2000 | NA | 131242-WSW41-DR-S-2000 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2001 | NA | 131242-WSW41-DR-S-2001 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3000 | NA | 131242-WSW41-DR-S-3000 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5000 | NA | 131242-WSW41-DR-S-5000 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5001 | E | 131242-WSW41-DR-S-5001 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | E | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5002 | E | 131242-WSW41-DR-S-5002 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | E | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5003 | NA | 131242-WSW41-DR-S-5003 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8001 | NA | 131242-WSW41-DR-S-8001 | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 001963 | 2026-01-19 | 2026-01-19 | NA | PEN | Awaiting S.O.'s response | 1 | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | PEN
001964 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2026-01-19 | Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | PEN | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001965 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2026-01-19 | Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed) | NA | 2026-02-16 |  | 50 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | PEN | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
001966 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BF | 1003 | NA | 131242-WSD11-DR-BF-1003 | 2026-01-20 | THP Fire Alarm System Layout Plan | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001966 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "THP Fire Alarm System Layout Plan" | PEN
001967 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0014 | 0 | 131242-WSD11-DS-I-0014 | 2026-01-20 | Datasheet for Pressure Gauge (THP-BOP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-17 | 2026-02-24 | 25 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001967 | 2026-01-20 | 2026-01-20 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Pressure Gauge (THP-BOP)" | AWC
001968 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5330 | NA | 131242-WST02-DR-I-5330 | 2026-01-20 | Hookup Drawing -Tuning Fork Level Switch | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001968 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing -Tuning Fork Level Switch" | PEN
001968 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5331 | NA | 131242-WST02-DR-I-5331 | 2026-01-20 | Hookup Drawing -Tuning Fork Level Switch | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001968 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing -Tuning Fork Level Switch" | PEN
001969 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5500 | NA | 131242-WST02-DR-I-5500 | 2026-01-20 | Hookup Drawing for Magnetic Level Gauge | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001969 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for Magnetic Level Gauge" | PEN
001969 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5501 | NA | 131242-WST02-DR-I-5501 | 2026-01-20 | Hookup Drawing for Magnetic Level Gauge | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001969 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for Magnetic Level Gauge" | PEN
001970 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5470 | NA | 131242-WST02-DR-I-5470 | 2026-01-20 | Hookup Drawing for Conductive Probe Level Switch | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001970 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for Conductive Probe Level Switch" | PEN
001970 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5471 | NA | 131242-WST02-DR-I-5471 | 2026-01-20 | Hookup Drawing for Conductive Probe Level Switch | NA | 2026-02-17 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001970 | 2026-01-20 | 2026-01-20 | NA | PEN | Awaiting S.O.'s response | 1 | "Hookup Drawing for Conductive Probe Level Switch" | PEN
001971 | 00 | Kyi Kyi | EICA | NA | 131242 | WST02 | DS | E | 0027 | 0 | 131242-WST02-DS-E-0027 | 2026-01-21 | Data Sheet for Lamp Pole | Rev 0: Not approved - Revise and Resubmit. | 2026-02-18 | 2026-02-09 | 13 | Not Approved | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001971 | 2026-01-21 | 2026-01-21 | 0 | NAP | Not Approved | 1 | "Data Sheet for Lamp Pole" | NAP
001972 | 00 | NA | NA | NA | 131242 | WSD11 | QA | M | 0171 | 0 | 131242-WSD11-QA-M-0171 | 2026-01-21 | FAT Report for G2D Booster Pumps (KSB) | NA | 2026-02-18 |  | 48 | Awaiting S.O.'s response | YES | 2026-03-10 | NO | Overdue | 0 |  |  | 001972 | 2026-01-21 | 2026-01-21 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for G2D Booster Pumps (KSB)" | PEN
001973 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | 0170 | 0 | 131242-WSW41-QA-M-0170 | 2026-01-22 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch | NA | 2026-02-19 |  | 47 | Awaiting S.O.'s response | YES | 2026-03-11 | NO | Overdue | 0 |  |  | 001973 | 2026-01-22 | 2026-01-22 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch" | PEN
001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5465 | C | 131242-WST02-DR-M-5465 | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | 47 | Awaiting S.O.'s response | YES | 2026-03-11 | NO | Overdue | 55 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5466 | C | 131242-WST02-DR-M-5466 | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | 47 | Awaiting S.O.'s response | YES | 2026-03-11 | NO | Overdue | 55 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | C | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5467 | D | 131242-WST02-DR-M-5467 | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | 47 | Awaiting S.O.'s response | YES | 2026-03-11 | NO | Overdue | 55 |  |  | 001619&&001974 | 2025-08-25 | 2026-01-22 | D | PEN | Approved with Comments | 3 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | AWC
001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5468 | D | 131242-WST02-DR-M-5468 | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | 47 | Awaiting S.O.'s response | YES | 2026-03-11 | NO | Overdue | 57 |  |  | 001619&&001974 | 2025-10-18 | 2026-01-22 | D | PEN | Awaiting S.O.'s response | 2 | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | PEN
001975 | 00 | NA | NA | NA | 131242 | WSD11 | DR | S | 1101 | C | 131242-WSD11-DR-S-1101 | 2026-01-26 | WD for ST622 | For Information. Please provide reaction loadings onto existing structures for review. | 2026-02-23 | 2026-02-12 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001944&&001975 | 2026-01-12 | 2026-01-26 | C | INF | For Information | 2 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "WD for ST622 " | INF
001976 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0068 | 0 | 131242-WSD11-QA-I-0068 | 2026-01-26 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-16 | 15 | Approved with Comments | YES | 2026-03-06 | NO | Resubmitted | 0 |  |  | 001976&&001980 | 2026-01-26 | 2026-01-26 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | AWC
001977 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0069 | 0 | 131242-WSD11-QA-I-0069 | 2026-01-26 | Factory Acceptance Test Report for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-24 | 21 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001977 | 2026-01-26 | 2026-01-26 | 0 | AWC | Approved with Comments | 1 | "Factory Acceptance Test Report for Pressure Gauges (THP)" | AWC
001978 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0070 | 0 | 131242-WST02-QA-I-0070 | 2026-01-26 | Factory Acceptance Test Report for Magnetic Level Gauge | NA | 2026-02-23 |  | 45 | Awaiting S.O.'s response | YES | 2026-03-13 | NO | Overdue | 0 |  |  | 001978&&001979 | 2026-01-26 | 2026-01-26 | 0 | PEN | Awaiting S.O.'s response | 2 | "Factory Acceptance Test Report for Magnetic Level Gauge" | PEN
001979 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0070 | 0 | 131242-WST02-QA-I-0070 | 2026-01-26 | Factory Acceptance Test Report for Magnetic Level Gauge | NA | 2026-02-23 |  | 45 | Awaiting S.O.'s response | YES | 2026-03-13 | NO | Overdue | 0 |  |  | 001978&&001979 | 2026-01-26 | 2026-01-26 | 0 | PEN | Awaiting S.O.'s response | 2 | "Factory Acceptance Test Report for Magnetic Level Gauge" | PEN
001980 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0068 | 0 | 131242-WSD11-QA-I-0068 | 2026-01-26 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-24 | 21 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001976&&001980 | 2026-01-26 | 2026-01-26 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | AWC
001981 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0173 | 0 | 131242-WST02-QA-M-0173 | 2026-01-26 | FAT Report for Splitter Box | NA | 2026-02-23 |  | 45 | Awaiting S.O.'s response | YES | 2026-03-13 | NO | Overdue | 0 |  |  | 001981 | 2026-01-26 | 2026-01-26 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Splitter Box" | PEN
001982 | 00 | NA | NA | NA | 131242 | WSD11 | QA | M | 0172 | 0 | 131242-WSD11-QA-M-0172 | 2026-01-26 | FAT Report for G1 Booster Pumps (KSB) | NA | 2026-02-23 |  | 45 | Awaiting S.O.'s response | YES | 2026-03-13 | NO | Overdue | 0 |  |  | 001982 | 2026-01-26 | 2026-01-26 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for G1 Booster Pumps (KSB)" | PEN
001983 | 00 | NA | NA | NA | 131242 | WST02 | DS | E | 0028 | 0 | 131242-WST02-DS-E-0028 | 2026-01-27 | Data Sheet of Isolator for Motorized Valves | Rev 0: Not approved - Revise and Resubmit | 2026-02-24 | 2026-02-13 | 13 | Not Approved | YES | 2026-03-05 | NO | Resubmitted | 0 |  |  | 001983 | 2026-01-27 | 2026-01-27 | 0 | NAP | Not Approved | 1 | "Data Sheet of Isolator for Motorized Valves" | NAP
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3144 | A | 131242-WST02-DR-EP-3144 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3145 | A | 131242-WST02-DR-EP-3145 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7305 | A | 131242-WST02-DR-EP-7305 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7306 | A | 131242-WST02-DR-EP-7306 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7307 | A | 131242-WST02-DR-EP-7307 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7344 | A | 131242-WST02-DR-EI-7344 | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001984 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3138 | A | 131242-WST02-DR-EP-3138 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3139 | A | 131242-WST02-DR-EP-3139 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7300 | A | 131242-WST02-DR-EP-7300 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7301 | A | 131242-WST02-DR-EP-7301 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7302 | A | 131242-WST02-DR-EP-7302 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7338 | A | 131242-WST02-DR-EI-7338 | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001985 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3136 | A | 131242-WST02-DR-EP-3136 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3137 | A | 131242-WST02-DR-EP-3137 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7295 | A | 131242-WST02-DR-EP-7295 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7296 | A | 131242-WST02-DR-EP-7296 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7297 | A | 131242-WST02-DR-EP-7297 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7336 | A | 131242-WST02-DR-EI-7336 | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001986 | 2026-01-27 | 2026-01-27 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | PEN
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3111 | A | 131242-WSD11-DR-EP-3111 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3310 | A | 131242-WSD11-DR-EP-3310 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7225 | A | 131242-WSD11-DR-EP-7225 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7226 | A | 131242-WSD11-DR-EP-7226 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7227 | A | 131242-WSD11-DR-EP-7227 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7310 | A | 131242-WSD11-DR-EI-7310 | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001987 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3113 | A | 131242-WSD11-DR-EP-3113 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3312 | A | 131242-WSD11-DR-EP-3312 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7230 | A | 131242-WSD11-DR-EP-7230 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7231 | A | 131242-WSD11-DR-EP-7231 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7232 | A | 131242-WSD11-DR-EP-7232 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7312 | A | 131242-WSD11-DR-EI-7312 | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | 22 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 001988 | 2026-01-27 | 2026-01-27 | A | AWC | Approved with Comments | 1 | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | AWC
001989 | 00 | Soe Myat | QAQC | NA | 131242 | WST02 | QA | M | 0174 | 0 | 131242-WST02-QA-M-0174 | 2026-01-27 | Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001989 | 2026-01-27 | 2026-01-27 | 0 | PEN | Awaiting S.O.'s response | 1 | "Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures" | PEN
001990 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0169 | 0 | 131242-WST02-QA-M-0169 | 2026-01-27 | Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box | NA | 2026-02-24 |  | 44 | Awaiting S.O.'s response | YES | 2026-03-16 | NO | Overdue | 0 |  |  | 001990 | 2026-01-27 | 2026-01-27 | 0 | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box" | PEN
001991 | 00 | NA | NA | NA | 131242 | WSD11 | DS | M | 0048 | 0 | 131242-WSD11-DS-M-0048 | 2026-01-28 | Steam Trap Data Sheet | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001991 | 2026-01-28 | 2026-01-28 | 0 | PEN | Awaiting S.O.'s response | 1 | "Steam Trap Data Sheet" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3146 | A | 131242-WST02-DR-EP-3146 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3147 | A | 131242-WST02-DR-EP-3147 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7310 | A | 131242-WST02-DR-EP-7310 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7311 | A | 131242-WST02-DR-EP-7311 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7312 | A | 131242-WST02-DR-EP-7312 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7346 | A | 131242-WST02-DR-EI-7346 | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001992 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3132 | A | 131242-WST02-DR-EP-3132 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3133 | A | 131242-WST02-DR-EP-3133 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7285 | A | 131242-WST02-DR-EP-7285 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7286 | A | 131242-WST02-DR-EP-7286 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7287 | A | 131242-WST02-DR-EP-7287 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7332 | A | 131242-WST02-DR-EI-7332 | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001993 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3134 | A | 131242-WST02-DR-EP-3134 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3135 | A | 131242-WST02-DR-EP-3135 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7290 | A | 131242-WST02-DR-EP-7290 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7291 | A | 131242-WST02-DR-EP-7291 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7292 | A | 131242-WST02-DR-EP-7292 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7334 | A | 131242-WST02-DR-EI-7334 | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 0 |  |  | 001994 | 2026-01-28 | 2026-01-28 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | PEN
001995 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0015 | 0 | 131242-WSD11-DS-I-0015 | 2026-01-29 | Datasheet for Pressure Switch (THP-BOP) | NA | 2026-02-26 |  | 42 | Awaiting S.O.'s response | YES | 2026-03-18 | NO | Overdue | 0 |  |  | 001995 | 2026-01-29 | 2026-01-29 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datasheet for Pressure Switch (THP-BOP)" | PEN
001996 | 00 | NA | NA | NA | 131242 | WSW41 | QA | I | 0071 | 0 | 131242-WSW41-QA-I-0071 | 2026-01-30 | FAT Report for FFOTP Panel SSN & THP (FOX) | NA | 2026-02-27 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001996 | 2026-01-30 | 2026-01-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for FFOTP Panel SSN & THP (FOX)" | PEN
001997 | 00 | NA | NA | NA | 131242 | WSW41 | QA | I | 0072 | 0 | 131242-WSW41-QA-I-0072 | 2026-01-30 | FAT Report for FOIP Panel SSN & THP (FOX) | NA | 2026-02-27 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001997 | 2026-01-30 | 2026-01-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for FOIP Panel SSN & THP (FOX)" | PEN
001998 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0073 | 0 | 131242-WST02-QA-I-0073 | 2026-01-30 | FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN | NA | 2026-02-27 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001998 | 2026-01-30 | 2026-01-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN" | PEN
001999 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0016 | 0 | 131242-WSD11-DS-I-0016 | 2026-01-30 | Datasheet for Pressure Transmitter (THP-BOP) | NA | 2026-02-27 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001999 | 2026-01-30 | 2026-01-30 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datasheet for Pressure Transmitter (THP-BOP) " | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3011 | A | 131242-WSD11-DR-BE-3011 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3015 | A | 131242-WSD11-DR-BE-3015 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7020 | A | 131242-WSD11-DR-BE-7020 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7021 | A | 131242-WSD11-DR-BE-7021 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7022 | A | 131242-WSD11-DR-BE-7022 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7023 | A | 131242-WSD11-DR-BE-7023 | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002000 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0001B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3016 | A | 131242-WSD11-DR-BE-3016 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3020 | A | 131242-WSD11-DR-BE-3020 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7025 | A | 131242-WSD11-DR-BE-7025 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7026 | A | 131242-WSD11-DR-BE-7026 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7027 | A | 131242-WSD11-DR-BE-7027 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7028 | A | 131242-WSD11-DR-BE-7028 | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002001 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "THP LDB-0002B SLD, Schematic and GA Drawing" | PEN
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3041 | A | 131242-WST02-DR-BE-3041 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3045 | A | 131242-WST02-DR-BE-3045 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7050 | A | 131242-WST02-DR-BE-7050 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7051 | A | 131242-WST02-DR-BE-7051 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7052 | A | 131242-WST02-DR-BE-7052 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7053 | A | 131242-WST02-DR-BE-7053 | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002002 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0001B SLD, Schematic and GA Drawing " | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3046 | A | 131242-WST02-DR-BE-3046 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3050 | A | 131242-WST02-DR-BE-3050 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7055 | A | 131242-WST02-DR-BE-7055 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7056 | A | 131242-WST02-DR-BE-7056 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7057 | A | 131242-WST02-DR-BE-7057 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7058 | A | 131242-WST02-DR-BE-7058 | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002003 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0002B SLD, Schematic and GA Drawing" | AWC
002004 | 00 | NA | NA | NA | 131242 | NA | NA | NA | NA | VOID | 131242-NA-NA-NA-NA | 2026-02-03 | Unpriced PO for Magnetic Level Gauge (Pipeline Process) | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30 | 2026-02-03 | VOID | PEN | Rejected | 9 | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | REJ
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3051 | A | 131242-WST02-DR-BE-3051 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3055 | A | 131242-WST02-DR-BE-3055 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7060 | A | 131242-WST02-DR-BE-7060 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7061 | A | 131242-WST02-DR-BE-7061 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7062 | A | 131242-WST02-DR-BE-7062 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7063 | A | 131242-WST02-DR-BE-7063 | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | 39 | Awaiting S.O.'s response | YES | 2026-03-23 | NO | Overdue | 0 |  |  | 002005 | 2026-02-03 | 2026-02-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN SDB-0003B SLD, Schematic and GA Drawing" | PEN
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3056 | A | 131242-WST02-DR-BE-3056 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3060 | A | 131242-WST02-DR-BE-3060 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7065 | A | 131242-WST02-DR-BE-7065 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7066 | A | 131242-WST02-DR-BE-7066 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7067 | A | 131242-WST02-DR-BE-7067 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7068 | A | 131242-WST02-DR-BE-7068 | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | 17 | Approved with Comments | YES | 2026-03-18 | NO | Resubmitted | 0 |  |  | 002006 | 2026-02-03 | 2026-02-03 | A | AWC | Approved with Comments | 1 | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | AWC
002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3020 | A | 131242-WST02-DR-A-3020 | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 0 |  |  | 002007 | 2026-02-04 | 2026-02-04 | A | PEN | Awaiting S.O.'s response | 1 | "Staircase 1 Block Wall Shop Drawing" | PEN
002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3021 | A | 131242-WST02-DR-A-3021 | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 0 |  |  | 002007 | 2026-02-04 | 2026-02-04 | A | PEN | Awaiting S.O.'s response | 1 | "Staircase 1 Block Wall Shop Drawing" | PEN
002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3022 | A | 131242-WST02-DR-A-3022 | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 0 |  |  | 002007 | 2026-02-04 | 2026-02-04 | A | PEN | Awaiting S.O.'s response | 1 | "Staircase 1 Block Wall Shop Drawing" | PEN
002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3023 | A | 131242-WST02-DR-A-3023 | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | 38 | Awaiting S.O.'s response | YES | 2026-03-24 | NO | Overdue | 0 |  |  | 002007 | 2026-02-04 | 2026-02-04 | A | PEN | Awaiting S.O.'s response | 1 | "Staircase 1 Block Wall Shop Drawing" | PEN
002008 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | NA | NA | 131242-WSW41-QA-M-NA | 2026-02-06 | Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve | NA | 2026-03-06 |  | 36 | Awaiting S.O.'s response | YES | 2026-03-26 | NO | Overdue | 0 |  |  | 002008 | 2026-02-06 | 2026-02-06 | NA | PEN | Awaiting S.O.'s response | 1 | "Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve " | PEN
002009 | 00 | NA | NA | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-IM-NA | 2026-02-09 | VCM Submission for 2026-01 | NA | 2026-03-09 |  | 35 | Awaiting S.O.'s response | NO |  | YES | NO | 0 |  |  | 000879&&001888&&001941&&002009 | 2024-12-09 | 2026-02-09 | 0 | PEN | For Information | 4 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | INF
002010 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | 0176 | 0 | 131242-WSW41-QA-M-0176 | 2026-02-10 | FAT Report for SS316L Pipe (CWP 323) 117 Nos | NA | 2026-03-10 |  | 34 | Awaiting S.O.'s response | YES | 2026-03-30 | NO | NO | 0 |  |  | 002010 | 2026-02-10 | 2026-02-10 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for SS316L Pipe (CWP 323) 117 Nos" | PEN
002011 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PC | W | 0031 | 0 | 131242-WSW41-PC-W-0031 | 2026-02-11 | Payment Claim No.31 | Rev (0): Approved. Please refer to S.O. correspondence no. 433 dated 10 Feb 2026. | 2026-03-11 | 2026-02-24 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 002011 | 2026-02-11 | 2026-02-11 | 0 | APP | Approved | 1 | "Payment Claim No.31" | APP
002012 | 00 | NA | NA | NA | 131242 | WSW41 | LT | PM | 0081 | 0 | 131242-WSW41-LT-PM-0081 | 2026-02-11 | Purchase Of Spare Parts Under SOP 10 | NA | 2026-03-11 |  | 33 | Awaiting S.O.'s response | YES | 2026-03-31 | NO | NO | 0 |  |  | 001953&&002012 | 2026-01-14 | 2026-02-11 | 0 | PEN | Awaiting S.O.'s response | 2 | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | PEN
002013 | 00 | NA | NA | NA | 131242 | WSW41 | LT | PM | 0082 | 0 | 131242-WSW41-LT-PM-0082 | 2026-02-12 | Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards | NA | 2026-03-12 |  | 32 | Awaiting S.O.'s response | YES | 2026-04-01 | NO | NO | 0 |  |  | 002013 | 2026-02-12 | 2026-02-12 | 0 | PEN | Awaiting S.O.'s response | 1 | "Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards " | PEN
002014 | 00 | NA | NA | NA | 131242 | WSW41 | RT | PM | 0033 | 0 | 131242-WSW41-RT-PM-0033 | 2026-02-20 | C4B Monthly Progress Report Number No.33 (01 26) | NA | 2026-03-20 |  | 26 | Awaiting S.O.'s response | YES | 2026-04-09 | NO | NO | 0 |  |  | 002014 | 2026-02-20 | 2026-02-20 | 0 | PEN | Awaiting S.O.'s response | 1 | "C4B Monthly Progress Report Number No.33 (01 26)" | PEN
002015 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0177 | 0 | 131242-WST02-QA-M-0177 | 2026-02-24 | ITP and Test Procedure for Chemical Dosing Cabinets | NA | 2026-03-24 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 002015 | 2026-02-24 | 2026-02-24 | 0 | PEN | Awaiting S.O.'s response | 1 | "ITP and Test Procedure for Chemical Dosing Cabinets" | PEN
002016 | 00 | NA | NA | NA | 131242 | WSW41 | CN | S | 0003 | 0 | 131242-WSW41-CN-S-0003 | 2026-02-24 | RFC for Electrical Building Chequer Plate | NA | 2026-03-24 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 002016 | 2026-02-24 | 2026-02-24 | 0 | PEN | Awaiting S.O.'s response | 1 | "RFC for Electrical Building Chequer Plate" | PEN
002017 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0178 | 0 | 131242-WST02-QA-M-0178 | 2026-02-24 | FAT Report for Chemical Dosing Cabinets | NA | 2026-03-24 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 002017 | 2026-02-24 | 2026-02-24 | 0 | PEN | Awaiting S.O.'s response | 1 | "FAT Report for Chemical Dosing Cabinets " | PEN
002018 | 00 | NA | NA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-C-1025 | 2026-02-24 | C4B SSN Drain Hydraulic Calculation | NA | 2026-03-24 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 425 |  |  | 000835&&002018 | 2024-11-22 | 2026-02-24 | A | PEN | Approved with Comments | 2 | "SSN Pavement Plan" && "C4B SSN Drain Hydraulic Calculation" | AWC
002018 | 00 | NA | NA | NA | 131242 | WST02 | CL | C | 1000 | 0 | 131242-WST02-CL-C-1000 | 2026-02-24 | C4B SSN Drain Hydraulic Calculation | NA | 2026-03-24 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 002018 | 2026-02-24 | 2026-02-24 | 0 | PEN | Awaiting S.O.'s response | 1 | "C4B SSN Drain Hydraulic Calculation" | PEN
002019 | 00 | NA | NA | NA | 131242 | WST02 | QA | E | 0068 | 0 | 131242-WST02-QA-E-0068 | 2026-02-25 | SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | NA | 2026-03-25 |  | 23 | Awaiting S.O.'s response | YES | 2026-04-14 | NO | NO | 0 |  |  | 002019 | 2026-02-25 | 2026-02-25 | 0 | PEN | Awaiting S.O.'s response | 1 | "SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) " | PEN
002020 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0017 | 0 | 131242-WSD11-DS-I-0017 | 2026-03-02 | Datasheet for Temperature Sensor (THP-BOP) | NA | 2026-03-30 |  | 20 | Awaiting S.O.'s response | YES | 2026-04-17 | NO | NO | 0 |  |  | 002020 | 2026-03-02 | 2026-03-02 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datasheet for Temperature Sensor (THP-BOP) " | PEN
002021 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0018 | 0 | 131242-WSD11-DS-I-0018 | 2026-03-02 | Datasheet for Differential Pressure Flowmeter (THP-BOP) | NA | 2026-03-30 |  | 20 | Awaiting S.O.'s response | YES | 2026-04-17 | NO | NO | 0 |  |  | 002021 | 2026-03-02 | 2026-03-02 | 0 | PEN | Awaiting S.O.'s response | 1 | "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | PEN
002022 | 00 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA-NA-NA-NA-NA |  |  | NA |  |  |  | Awaiting S.O.'s response | YES |  | NO | NO | 0 |  |  | 001418&&002022&&002023&&002024 | 2025-07-01 | 2025-07-01 | NA | PEN | Not Approved | 4 | "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | NAP
002023 | 00 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA-NA-NA-NA-NA |  |  | NA |  |  |  | Awaiting S.O.'s response | YES |  | NO | NO | 0 |  |  | 001418&&002022&&002023&&002024 | 2025-07-01 | 2025-07-01 | NA | PEN | Not Approved | 4 | "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | NAP
002024 | 00 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA-NA-NA-NA-NA |  |  | NA |  |  |  | Awaiting S.O.'s response | YES |  | NO | NO | 0 |  |  | 001418&&002022&&002023&&002024 | 2025-07-01 | 2025-07-01 | NA | PEN | Not Approved | 4 | "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | NAP
002025 | 00 | Mabele | Contracts | NA | 131242 | WSW41 | LT | PM | 0083 | 0 | 131242-WSW41-LT-PM-0083 | 2026-03-05 | Notice For Extension Of Time And Cost For Delays For Power Turn On | NA |  |  | 17 | Awaiting S.O.'s response | YES | 2026-04-22 | NO | NO | 0 |  |  | 002025 | 2026-03-05 | 2026-03-05 | 0 | PEN | Awaiting S.O.'s response | 1 | "Notice For Extension Of Time And Cost For Delays For Power Turn On " | PEN