## Sheet1
Submission_Session | Submission_Session_Revision | Submission_Session_Subject | Submission_Date | Review_Status | Submitted_By
000189 | 03 | SSN Plumbing and Sanitary | 2025-07-15 | Awaiting S.O.'s response | Kyaw Myo
000191 | 03 | Milestone 3 SSN Electrical Building | 2026-01-16 | Awaiting S.O.'s response | Heng Peng/ Muthu
000192 | 03 | Milestone 3 SSN Chemical Dosing Area | 2026-01-16 | Awaiting S.O.'s response | Heng Peng/ Muthu
000227 | 03 | SSN Power Layout Plan | 2026-01-19 | Awaiting S.O.'s response | Freedomer
000292 | 03 | Milestone 3 THP Overall & Equipment Layout | 2025-11-28 | Awaiting S.O.'s response | Heng Peng/ Muthu
000338 | 08 | PUB DC Drainage Submission | 2026-01-12 | Awaiting S.O.'s response | Aaron/HP
000396 | 07 | LTA & Nparks submission Set | 2026-01-09 | Awaiting S.O.'s response | Aaron
000397 | 05 | NEA DC submission Set | 2026-01-06 | Awaiting S.O.'s response | Zora/HP
000402 | 08 | SSN_FSSD (BP) Submission | 2026-01-07 | Awaiting S.O.'s response | Aaron
000618 | 02 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | 2025-05-13 | Awaiting S.O.'s response | Yibo
000651 | 01 | THP PC Pump GA Drawings | 2025-06-12 | Awaiting S.O.'s response | Joo Kwan
000670 | 01 | Monthly Concrete Cube Records for Structural works for May 2024 | 2024-08-27 | Awaiting S.O.'s response | Boopathi
000697 | 01 | Data Sheet for Pre Cooler Cooling Water Control Valve | 2025-05-05 | Awaiting S.O.'s response | Joo Kwan
000709 | 02 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | 2025-10-09 | Awaiting S.O.'s response | Dhanapal
000731 | 03 | P&ID for SSN | 2026-02-24 | Awaiting S.O.'s response | Qili
000798 | 01 | GA Drawing for Centrifugal Pump | 2025-04-17 | Awaiting S.O.'s response | David
000907 | 01 | SSN Harmonics Study Report | 2026-01-20 | Awaiting S.O.'s response | Freedomer
000917 | 01 | GA Drawing for Dosing Pump | 2025-06-15 | Awaiting S.O.'s response | Yibo
000931 | 01 | Screen General Arrangement Drawing | 2025-05-26 | Awaiting S.O.'s response | Yibo
000962 | 03 | FAT report for THP Train 1 (Part-1) | 2026-01-06 | Awaiting S.O.'s response | Soe Myat
000976 | 02 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | 2026-01-06 | Awaiting S.O.'s response | Soe Myat
000989 | 03 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | 2025-08-25 | Awaiting S.O.'s response | Joo Kwan
000993 | 03 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | 2026-01-28 | Awaiting S.O.'s response | Joo Kwan
001080 | 01 | C4B SSN Pressure Reducing Valve Datasheet | 2025-07-07 | Awaiting S.O.'s response | Prachi
001108 | 01 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | 2025-08-22 | Awaiting S.O.'s response | Karthikeyan
001113 | 02 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | 2026-02-05 | Awaiting S.O.'s response | K. Balaji
001139 | 01 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | 2025-05-05 | Awaiting S.O.'s response | Qili
001170 | 01 | SSN FCV Calculation and Datasheet | 2025-07-07 | Awaiting S.O.'s response | Qili
001172 | 01 | Datasheet & GA drawing for sampling pump | 2025-10-18 | Awaiting S.O.'s response | David
001173 | 02 | Datasheet for Temperature Transmitter | 2026-01-21 | Awaiting S.O.'s response | Yean Yee
001181 | 02 | Datasheet for Pressure Switch | 2026-01-30 | Awaiting S.O.'s response | Yean Yee
001186 | 03 | SSN BCA BP Submission | 2026-01-20 | Awaiting S.O.'s response | Aaron
001195 | 02 | Manual Butterfly Valve | 2025-11-26 | Awaiting S.O.'s response | Joo Kwan
001262 | 01 | Inspection and test Plan and Factory Acceptance Test for Public Address System | 2025-07-05 | Awaiting S.O.'s response | Danapal
001308 | 01 | G1 Booster Pump Hydraulics Calculation | 2025-08-25 | Awaiting S.O.'s response | Joo Kwan
001309 | 01 | G2D Booster Pump Hydraulics Calculation | 2025-07-28 | Awaiting S.O.'s response | Joo Kwan
001310 | 01 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | 2025-07-15 | Awaiting S.O.'s response | Joo Kwan
001314 | 01 | Preliminary Design and Vendor Approval for Solenoid Valve | 2025-07-28 | Awaiting S.O.'s response | Joo Kwan
001318 | 00 | O&M Manual for Aeration Blower | 2025-05-26 | Awaiting S.O.'s response | Yibo
001319 | 01 | Data Sheet and Drawing for Davit Crane | 2025-11-26 | Awaiting S.O.'s response | Yibo
001320 | 01 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | 2025-10-01 | Awaiting S.O.'s response | Radha
001345 | 00 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | 2025-06-06 | Awaiting S.O.'s response | Yibo
001347 | 01 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | 2025-09-29 | Awaiting S.O.'s response | Yibo
001350 | 00 | Electrical Signal List for MCC - TYPICAL | 2025-06-10 | Awaiting S.O.'s response | Freedomer
001370 | 00 | General Arrangement for TCI Flow Control valve | 2025-06-12 | Awaiting S.O.'s response | Joo Kwan
001371 | 00 | General Arrangement for DC Partial Bypass Line Flow Control Valve | 2025-06-12 | Awaiting S.O.'s response | Joo Kwan
001372 | 00 | General Arrangement for Lamella Clarifier Flow Control Valve | 2025-06-12 | Awaiting S.O.'s response | Joo Kwan
001373 | 00 | General Arrangement for IRIS Diaphragm Flow Control Valve | 2025-06-12 | Awaiting S.O.'s response | Joo Kwan
001374 | 00 | GA Drawing for Static Screen - Plinth Opening & Seal plate | 2025-06-16 | Awaiting S.O.'s response | Joo Kwan
001376 | 00 | GA for SSN G2D PRV | 2025-06-16 | Awaiting S.O.'s response | Joo Kwan
001383 | 00 | GA for Bypass Control Valve 1 | 2025-06-16 | Awaiting S.O.'s response | Joo Kwan
001384 | 00 | GA for Bypass Control Valve 2 | 2025-06-16 | Awaiting S.O.'s response | Joo Kwan
001392 | 00 | Laser Scanning Method of Statement | 2025-06-19 | Awaiting S.O.'s response | Muthu
001398 | 02 | MSRA, SWP for fire protection services | 2026-02-13 | Awaiting S.O.'s response | Bryan
001402 | 03 | ACMV LCP GA & Wiring Drawing | 2026-02-04 | Awaiting S.O.'s response | Yuen Fatt
001428 | 00 | Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik | 2025-07-02 | Awaiting S.O.'s response | Yuen Fatt
001431 | 00 | Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik | 2025-07-03 | Awaiting S.O.'s response | Yuen Fatt
001438 | 02 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | 2026-02-24 | Awaiting S.O.'s response | Freedomer
001445 | 00 | GA for G2D Booster Pump | 2025-07-07 | Awaiting S.O.'s response | Joo Kwan
001473 | 00 | GA for G1 Booster Pump | 2025-07-14 | Awaiting S.O.'s response | Joo Kwan
001528 | 02 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | 2026-02-09 | Awaiting S.O.'s response | Aaron
001543 | 00 | Sample Board Submission for 50x50 SS316 Trunking | 2025-07-30 | Awaiting S.O.'s response | Mohan
001545 | 01 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | 2026-01-15 | Awaiting S.O.'s response | Dhanapal
001564 | 01 | Factory Acceptance Test Report for Fire Alarm System | 2025-11-27 | Awaiting S.O.'s response | Dhanapal
001578 | 00 | SSN Aeration Line Automatic Condensate Drain Valve | 2025-08-12 | Awaiting S.O.'s response | Joo Kwan
001591 | 00 | 80% THP ALMOP Report | 2025-08-14 | Awaiting S.O.'s response | Joo Kwan
001600 | 01 | QA/QC Report for Air Conditioning System | 2025-10-13 | Awaiting S.O.'s response | Mohan
001601 | 01 | QA/QC Report for Mechanical Ventilation Fan | 2025-10-13 | Awaiting S.O.'s response | Mohan
001610 | 00 | G2D Water Hydraulic Pressure Loss Calculation | 2025-08-22 | Awaiting S.O.'s response | Qili
001619 | 01 | GA drawing for Splitter Box | 2025-10-18 | Awaiting S.O.'s response | David Li
001624 | 00 | Operation and Maintenance Manual for Parabolic Screen | 2025-08-25 | Awaiting S.O.'s response | Yibo
001630 | 00 | Unpriced PO for Building Management System (Willowglen) | 2025-08-27 | Awaiting S.O.'s response | Caeden
001636 | 01 | Testing Check List (Process) | 2026-01-28 | Awaiting S.O.'s response | Joo Kwan
001642 | 00 | GA drawing for Sampling Sink | 2025-09-01 | Awaiting S.O.'s response | David
001644 | 00 | Load Test Reports for Top Manway (Aluminium Hatch) | 2025-09-01 | Awaiting S.O.'s response | Kumar
001657 | 00 | Chemical Cabinet - GA drawing | 2025-09-08 | Awaiting S.O.'s response | David
001676 | 00 | 80% SSN ALMOP Report | 2025-09-11 | Awaiting S.O.'s response | Joo Kwan
001684 | 01 | FAT Report for Diffuser System (Xylem) | 2025-10-21 | Awaiting S.O.'s response | Mohan
001685 | 01 | Datasheet for Thermal Flow Switch | 2026-01-15 | Awaiting S.O.'s response | Yean Yee
001695 | 01 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | 2026-01-27 | Awaiting S.O.'s response | Mohan
001697 | 01 | FAT Report for Actuated Ball Valves (OVS/Rotork) | 2026-01-27 | Awaiting S.O.'s response | Soe Myat
001703 | 00 | SP Item - Flange Adaptor (Synchong Hoe) | 2025-09-29 | Awaiting S.O.'s response | Liying
001713 | 00 | Data Sheet for SSN Sludge Comparment Mixing Nozzle | 2025-09-30 | Awaiting S.O.'s response | Joo Kwan
001716 | 00 | Extension of Time – CM4 Milestone | 2025-09-30 | Awaiting S.O.'s response | Vincent
001738 | 00 | FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) | 2025-10-13 | Awaiting S.O.'s response | Mohan
001739 | 00 | FAT report for Steam Jet Heater (Steam Sparger) | 2025-10-13 | Awaiting S.O.'s response | Mohan
001753 | 00 | Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | 2025-10-16 | Awaiting S.O.'s response | Vincent
001754 | 00 | Blower Aeration Air Piping Stress Calculation Report | 2025-10-18 | Awaiting S.O.'s response | David
001755 | 00 | O&M Manual for Hyperbolic Mixer | 2025-10-18 | Awaiting S.O.'s response | Yibo
001757 | 01 | THP LDB-0001 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001759 | 01 | THP UPSDB-0001B SLD, Schematic and GA Drawing | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001761 | 01 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001762 | 01 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001763 | 01 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001764 | 01 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001765 | 01 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | 2026-01-28 | Awaiting S.O.'s response | Freedomer
001768 | 01 | THP UPSDB-0107 SLD, Schematic and GA Drawing | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001769 | 01 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001771 | 01 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001772 | 01 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001773 | 01 | THP LDB-0002 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001777 | 01 | SSN SDB-0003 SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001779 | 00 | GA for Steam Strainer | 2025-10-23 | Awaiting S.O.'s response | Joo Kwan
001780 | 00 | GA for Steam Relief Valve | 2025-10-23 | Awaiting S.O.'s response | Joo Kwan
001793 | 01 | BMS Panel GA & Wiring Drawing | 2026-01-28 | Awaiting S.O.'s response | M Balaji
001796 | 00 | MSRA, SWP for ACMV System works | 2025-10-28 | Awaiting S.O.'s response | Bryan
001803 | 01 | Shop Drawing for SSN Area and Electrical Building Cat ladders | 2026-02-09 | Awaiting S.O.'s response | Aaron
001806 | 01 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001807 | 01 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | 2026-02-03 | Awaiting S.O.'s response | Freedomer
001814 | 01 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001815 | 01 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001816 | 01 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | 2026-01-28 | Awaiting S.O.'s response | Freedomer
001817 | 01 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | 2026-01-28 | Awaiting S.O.'s response | Freedomer
001818 | 01 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | 2026-01-28 | Awaiting S.O.'s response | Freedomer
001819 | 00 | FAT Report for Lamella Clarifier Biomass Separator (ARS-5) | 2025-11-04 | Awaiting S.O.'s response | Mohan
001820 | 00 | Data Sheet for SSN IA Pressure Reducing Valve | 2025-11-05 | Awaiting S.O.'s response | Joo Kwan
001822 | 00 | Hookup Drawing - Autosampler | 2025-11-05 | Awaiting S.O.'s response | Yean Yee
001824 | 01 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | 2026-02-03 | Awaiting S.O.'s response | Mohan
001828 | 00 | Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+) | 2025-11-06 | Awaiting S.O.'s response | Mohan
001833 | 00 | Material & Test Certificates for Blower's Encapsulation | 2025-11-10 | Awaiting S.O.'s response | Mohan
001834 | 00 | FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets | 2025-11-11 | Awaiting S.O.'s response | Mohan
001836 | 00 | FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area | 2025-11-11 | Awaiting S.O.'s response | Mohan
001837 | 00 | FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area | 2025-11-11 | Awaiting S.O.'s response | Mohan
001838 | 00 | FAT Report for SS 316L Pipes for streamline-55 pcs | 2025-11-12 | Awaiting S.O.'s response | Mohan
001839 | 00 | FAT Report for ARI-Armaturen Safety Valve - (OVS) | 2025-11-12 | Awaiting S.O.'s response | Mohan
001841 | 00 | FAT Report for Carbon Steel Pipe Support | 2025-11-13 | Awaiting S.O.'s response | Mohan
001842 | 00 | FAT Report for Motorized Steam Ball Valves (OVS/Rotork) | 2025-11-14 | Awaiting S.O.'s response | Mohan
001846 | 00 | FAT Procedure for Portable A Frame & T-Davit (Growa) | 2025-11-18 | Awaiting S.O.'s response | Mohan
001848 | 00 | Notice For Extension Of Time And Cost For Delays For Power Turn On | 2025-11-19 | Awaiting S.O.'s response | Vincent
001850 | 00 | Detailed Design PVC Strainer Data Sheet | 2025-11-19 | Awaiting S.O.'s response | Joo Kwan
001851 | 00 | Detailed Design SS316 Strainer Data Sheet | 2025-11-19 | Awaiting S.O.'s response | Joo Kwan
001852 | 00 | Datat Sheet & Drawing for Portable A-Frame | 2025-11-20 | Awaiting S.O.'s response | Yibo
001853 | 00 | Material & Test Certificates for Flange Adaptors (Synchong Hoe) | 2025-11-20 | Awaiting S.O.'s response | Mohan
001854 | 00 | Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng) | 2025-11-20 | Awaiting S.O.'s response | Balaji
001856 | 00 | Safety Review Report for SSN Steel Structures and MEICA Equipment Installation | 2025-11-20 | Awaiting S.O.'s response | Max
001857 | 00 | FAT Report for NON Return Check Valve (Breen) | 2025-11-20 | Awaiting S.O.'s response | Soe Myat
001858 | 00 | FAT Report for Sampling Sinks (4 units) | 2025-11-20 | Awaiting S.O.'s response | Soe Myat
001860 | 01 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | 2025-12-18 | Awaiting S.O.'s response | Dhanapal
001861 | 01 | Factory Acceptance Test Report for Pressure Switch | 2026-01-13 | Awaiting S.O.'s response | Dhanapal
001862 | 00 | FAT Report for THP Courtyard Area Pipe Supports (Less than 2m) | 2025-11-24 | Awaiting S.O.'s response | Mohan
001863 | 00 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units | 2025-11-25 | Awaiting S.O.'s response | Mohan
001867 | 00 | SSN BMS Network Architecture Drawing | 2025-11-26 | Awaiting S.O.'s response | Balaji
001868 | 00 | FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15) | 2025-11-27 | Awaiting S.O.'s response | Mohan
001872 | 01 | SSN- I/O List-BIO-0001 | 2026-01-28 | Awaiting S.O.'s response | Balaji
001873 | 01 | SSN- I/O List-BIO-0002 | 2026-01-28 | Awaiting S.O.'s response | Balaji
001877 | 00 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN | 2025-12-02 | Awaiting S.O.'s response | Dhanapal
001878 | 00 | FAT Report for SS316L Pipes - G2D Line | 2025-12-03 | Awaiting S.O.'s response | Mohan
001879 | 00 | Steam Piping Stress Calculation Report | 2025-12-04 | Awaiting S.O.'s response | Franklin
001880 | 00 | Payment Claim No.29 | 2025-12-04 | Awaiting S.O.'s response | Yi Hao
001882 | 00 | SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000 | 2025-12-08 | Awaiting S.O.'s response | Balaji
001891 | 00 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | 2025-12-09 | Awaiting S.O.'s response | NA
001892 | 00 | Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A” | 2025-12-12 | Awaiting S.O.'s response | NA
001893 | 00 | THP URA Amendment submissions | 2025-12-14 | Awaiting S.O.'s response | NA
001896 | 00 | ITP for Portable A Frame & T-Davit (Growa) | 2025-12-15 | Awaiting S.O.'s response | NA
001899 | 00 | C4B Monthly Progress Report Number No.31 (11 25) | 2025-12-16 | Awaiting S.O.'s response | NA
001902 | 00 | Dry Riser Installation Details | 2025-12-16 | Awaiting S.O.'s response | NA
001906 | 00 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | 2025-12-17 | Awaiting S.O.'s response | NA
001907 | 00 | As built drawing for ST621 (SWPR PR 01 & 02) | 2025-12-17 | Awaiting S.O.'s response | NA
001915 | 00 | Data Sheet for Davit Arm and Mount Socket | 2025-12-18 | Awaiting S.O.'s response | Franklin
001916 | 00 | O&M Manual for A-Frame and T-Davit | 2025-12-18 | Awaiting S.O.'s response | NA
001917 | 00 | Long term storage & Preservation procedure for A-Frame and T-Davit | 2025-12-18 | Awaiting S.O.'s response | NA
001922 | 00 | FAT Report for SS 316L (CWP 205) Pipes -149 Nos | 2025-12-19 | Awaiting S.O.'s response | NA
001923 | 00 | Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN | 2025-12-19 | Awaiting S.O.'s response | NA
001924 | 01 | SSN URA Submission | 2026-02-03 | Awaiting S.O.'s response | NA
001926 | 00 | FAT Report for Solenoid Valves (Norgren) | 2025-12-23 | Awaiting S.O.'s response | NA
001927 | 00 | FAT Report for SS 316L Pipes - 77 Nos | 2025-12-23 | Awaiting S.O.'s response | NA
001931 | 00 | THP BCA BP Submission | 2026-01-05 | Awaiting S.O.'s response | NA
001936 | 00 | THP and SSN Cable Ladder/ Tray Data Sheet and Specifications | 2026-01-07 | Awaiting S.O.'s response | Freedomer
001938 | 00 | Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen) | 2026-01-07 | Awaiting S.O.'s response | Mohan
001939 | 00 | FAT Report for SS 316L (CWP 205) Pipes - 201 Nos | 2026-01-07 | Awaiting S.O.'s response | Mohan
001941 | 00 | VCM Submission for 2025-12 | 2026-01-08 | Awaiting S.O.'s response | Heng Peng
001942 | 00 | Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation | 2026-01-12 | Awaiting S.O.'s response | Vincent
001943 | 00 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax) | 2026-01-12 | Awaiting S.O.'s response | Mohan
001946 | 00 | FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) | 2026-01-12 | Awaiting S.O.'s response | Mohan
001947 | 00 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN | 2026-01-12 | Awaiting S.O.'s response | Dhanapal
001948 | 00 | THP and SSN Earthing Material Specifications | 2026-01-12 | Awaiting S.O.'s response | Freedomer
001951 | 00 | FAT Report for Non Return Check Valve - Batch 2 (Breen) | 2026-01-12 | Awaiting S.O.'s response | Mohan
001952 | 00 | Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax) | 2026-01-13 | Awaiting S.O.'s response | Mohan
001953 | 00 | CV of Team Member (MEM) | 2026-01-14 | Awaiting S.O.'s response | Htet Nu
001954 | 00 | Payment Claim No.30 | 2026-01-14 | Awaiting S.O.'s response | Yi Hao
001955 | 00 | C4B Monthly Progress Report Number No.32 (12 25) | 2026-01-15 | Awaiting S.O.'s response | Htet Nu
001957 | 00 | Hookup Drawing for NO2 / NO3 Analyser | 2026-01-15 | Awaiting S.O.'s response | Yean Yee
001958 | 00 | Hookup Drawing for NH4 Analyser | 2026-01-15 | Awaiting S.O.'s response | Yean Yee
001959 | 00 | Datasheet for Electromagnetic Flow Meter (THP-BOP) | 2026-01-15 | Awaiting S.O.'s response | Yean Yee
001960 | 00 | THP_FSSD (BP) Submission | 2026-01-19 | Awaiting S.O.'s response | Aaron
001961 | 00 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron) | 2026-01-19 | Awaiting S.O.'s response | Yuen Fatt
001963 | 00 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | 2026-01-19 | Awaiting S.O.'s response | Aaron
001964 | 00 | Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed) | 2026-01-19 | Awaiting S.O.'s response | Aaron
001965 | 00 | Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed) | 2026-01-19 | Awaiting S.O.'s response | Aaron
001966 | 00 | THP Fire Alarm System Layout Plan | 2026-01-20 | Awaiting S.O.'s response | NA
001968 | 00 | Hookup Drawing -Tuning Fork Level Switch | 2026-01-20 | Awaiting S.O.'s response | NA
001969 | 00 | Hookup Drawing for Magnetic Level Gauge | 2026-01-20 | Awaiting S.O.'s response | NA
001970 | 00 | Hookup Drawing for Conductive Probe Level Switch | 2026-01-20 | Awaiting S.O.'s response | NA
001972 | 00 | FAT Report for G2D Booster Pumps (KSB) | 2026-01-21 | Awaiting S.O.'s response | NA
001973 | 00 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch | 2026-01-22 | Awaiting S.O.'s response | NA
001974 | 00 | Splitter Box Structural Supports | 2026-01-22 | Awaiting S.O.'s response | Salahudin
001978 | 00 | Factory Acceptance Test Report for Magnetic Level Gauge | 2026-01-26 | Awaiting S.O.'s response | NA
001979 | 00 | Factory Acceptance Test Report for Magnetic Level Gauge | 2026-01-26 | Awaiting S.O.'s response | NA
001981 | 00 | FAT Report for Splitter Box | 2026-01-26 | Awaiting S.O.'s response | NA
001982 | 00 | FAT Report for G1 Booster Pumps (KSB) | 2026-01-26 | Awaiting S.O.'s response | NA
001984 | 00 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001985 | 00 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001986 | 00 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | 2026-01-27 | Awaiting S.O.'s response | Freedomer
001989 | 00 | Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures | 2026-01-27 | Awaiting S.O.'s response | Soe Myat
001990 | 00 | Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box | 2026-01-27 | Awaiting S.O.'s response | Mohan
001991 | 00 | Steam Trap Data Sheet | 2026-01-28 | Awaiting S.O.'s response | NA
001992 | 00 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | 2026-01-28 | Awaiting S.O.'s response | NA
001993 | 00 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | 2026-01-28 | Awaiting S.O.'s response | NA
001994 | 00 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | 2026-01-28 | Awaiting S.O.'s response | NA
001995 | 00 | Datasheet for Pressure Switch (THP-BOP) | 2026-01-29 | Awaiting S.O.'s response | NA
001996 | 00 | FAT Report for FFOTP Panel SSN & THP (FOX) | 2026-01-30 | Awaiting S.O.'s response | NA
001997 | 00 | FAT Report for FOIP Panel SSN & THP (FOX) | 2026-01-30 | Awaiting S.O.'s response | NA
001998 | 00 | FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN | 2026-01-30 | Awaiting S.O.'s response | NA
001999 | 00 | Datasheet for Pressure Transmitter (THP-BOP) | 2026-01-30 | Awaiting S.O.'s response | NA
002000 | 00 | THP LDB-0001B SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | NA
002001 | 00 | THP LDB-0002B SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | NA
002004 | 00 | Unpriced PO for Magnetic Level Gauge (Pipeline Process) | 2026-02-03 | Awaiting S.O.'s response | NA
002005 | 00 | SSN SDB-0003B SLD, Schematic and GA Drawing | 2026-02-03 | Awaiting S.O.'s response | NA
002007 | 00 | Staircase 1 Block Wall Shop Drawing | 2026-02-04 | Awaiting S.O.'s response | NA
002008 | 00 | Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve | 2026-02-06 | Awaiting S.O.'s response | NA
002009 | 00 | VCM Submission for 2026-01 | 2026-02-09 | Awaiting S.O.'s response | NA
002010 | 00 | FAT Report for SS316L Pipe (CWP 323) 117 Nos | 2026-02-10 | Awaiting S.O.'s response | NA
002012 | 00 | Purchase Of Spare Parts Under SOP 10 | 2026-02-11 | Awaiting S.O.'s response | NA
002013 | 00 | Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards | 2026-02-12 | Awaiting S.O.'s response | NA
002014 | 00 | C4B Monthly Progress Report Number No.33 (01 26) | 2026-02-20 | Awaiting S.O.'s response | NA
002015 | 00 | ITP and Test Procedure for Chemical Dosing Cabinets | 2026-02-24 | Awaiting S.O.'s response | NA
002016 | 00 | RFC for Electrical Building Chequer Plate | 2026-02-24 | Awaiting S.O.'s response | NA
002017 | 00 | FAT Report for Chemical Dosing Cabinets | 2026-02-24 | Awaiting S.O.'s response | NA
002018 | 00 | C4B SSN Drain Hydraulic Calculation | 2026-02-24 | Awaiting S.O.'s response | NA
002019 | 00 | SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | 2026-02-25 | Awaiting S.O.'s response | NA